## Progress Report Phase-I (2)
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE
SHDP - PHASE - I PACKAGES
2021-11-30
Sl. No. | Admini- strative approval No. | Pkg No | Details of packages | SH No. | Estimate Amount as per Administrative approval (Rs. in lakhs) | Contract Amount (Rs. in lakhs) | Variation Amount (Rs. in lakhs) | Revised Contract Amount including VO (Rs. in lakhs) | Name of the Contractor | Date |  |  | Length As per DPR in km |  |  | Length after VO in km |  |  | Physical Progress |  |  |  | Balance Length |  |  | Financial Progress |  | Remarks
[10 empty] | Commencement | Completion | Revised | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Renewal (km) | Improvements (km) | Total Length Completed (in km) | % Progress | Renewal (km) | Improvements(km) | Total Length (in km) | Total (Rs. In Lakhs) | Financial Progress To Be Achived (Rs. In lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
NORTH ZONE
DHARWAD DIVISION
1 | PWD/ 45/EAP/01 | 1 | Improvements to Padubidri -Chikkalgudda SH - 01 from km 318.50 to km 356.96 (In selected reaches) (Tabakadahonnahalli, Devalingikoppa of Kalaghatagi Taluk) | 1 | 1926.67 | 1609.73 | 215.09 | 1824.82 | M/s N.S.Nayak & Sons | 02.11.2012 | 02.10.2013 | 26.12.2013 | 0 | 35.25 | 35.25 | 0 | 35.25 | 35.25 | 0 | 35.25 | 35.25 | 100% | 0 | 0 | 0 | 1890.98 | 0 | Completed
2 | PWD/ 45/EAP/02 | 2a | Improvements to Kalmala Shiggaon SH - 23 from km 273.61 to km 284.51(In selected reaches) (Railway Gate to Savanur, Taluka Border of Kundagol Taluk) | 23 | 2134.94 | 1929.66 | 53.5 | 1983.16 | N.S.Nayak | 02.11.2012 | 02.10.2013 | 13.11.2013 | 7.9 | 3 | 10.9 | 0 | 2.91 | 2.91 | 0 | 2.91 | 2.91 | 100% | 0 | 0 | 0 | 2058.88 | 0 | Completed
|  | 2b | Improvements to Navalgund - Banavasi SH - 137 from km 4.90 to km 18.30(In selected reaches) (Navalgunda to Annigeri of Navalgunda Taluk) | 137 | [8 empty] | 0 | 13.4 | 13.4 | 0 | 13.8 | 13.8 | 0 | 13.8 | 13.8 | 100% | 0 | 0 | 0
|  | 2c | Improvements to Supa - Annigeri SH - 28from km 41.31 to km 68.42(In selected reaches) (Mavinkoppa Checkpost to Dharwad via Nigadi of Dharwad Taluk) | 28 | [8 empty] | 10.82 | 16.29 | 27.11 | 9.68 | 16.47 | 26.15 | 9.68 | 16.47 | 26.15 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4061.61 | 3539.39 | 268.59 | 3807.98 |  |  |  |  | 18.72 | 67.94 | 86.66 | 9.68 | 68.43 | 78.11 | 9.68 | 68.43 | 78.11 | 100% | 0 | 0 | 0 | 3949.86 | 0
GADAG DIVISION
3 | PWD/ 45/EAP/03 | 3 | Improvements to Karwar - Ilkal SH - 06 from km 199.73 to km 271.60(In selected reaches) (Laxmeshwar, Magadi, Gadag of Gadag Taluk) | 6 | 3066.49 | 2915.69 | 164.69 | 3080.38 | P.R.Nayak | 18.10.2012 | 18.09.2013 | 26.06.2013 | 23.59 | 47.07 | 70.66 | 23.59 | 47.27 | 70.86 | 23.59 | 47.27 | 70.86 | 100% | 0 | 0 | 0 | 3050.1 | 30.28 | Completed
4 | PWD/ 45/EAP/04 | 4 | Improvements to Karwar - Ilkal SH-06 from km 271.60 to km 310.81(In selected reaches) (Naregal, Gajendraghada of Ron Taluk) | 6 | 1806.23 | 1875.02 | 94.14 | 1969.16 | B.S.Gaonkar | 10.01.2013 | 10.12.2013 | 28.02.2014 | 6.65 | 30.67 | 37.32 | 8.4 | 24.6 | 33 | 8.4 | 24.6 | 33 | 100% | 0 | 0 | 0 | 1977.29 | 0 | Completed
5 | PWD/ 45/EAP/05 | 5a | Improvements to Sindhnur - Hemmadga SH - 30 from km 117.80 to km149.00 (In selected reaches) (Belavanaki,Yavagal in Naragund & Ron Taluk) | 30 | 1748.83 | 1978.15 | 242.4 | 2220.55 | B.Thirupathi.Reddy | 20.10.2012 | 20.09.2013 | 29.07.2013 | 17.2 | 14 | 31.2 | 17.2 | 11.6 | 28.8 | 17.2 | 11.6 | 28.8 | 100% | 0 | 0 | 0 | 2251.55 | 0 | Completed
|  | 5b | Improvements to Raravi - Belur SH - 63 from km 160.20 to km185.70 (In selected reaches) (Mushigeri in Ron Taluk) | 63 | [8 empty] | 17.05 | 6 | 23.05 | 17.7 | 5.6 | 23.3 | 17.7 | 5.6 | 23.3 | 100% | 0 | 0 | 0
6 | PWD/ 45/EAP/06 | 6 | Improvements to Munavalli - Kotamuchagi SH-83 from km 63.14 to km104.50 (In selected reaches) (Mensigi, Holehalur of Naragund & Ron Taluk) | 83 | 2144.97 | 2347.41 | 348.23 | 2695.64 | N.B.Hiremath | 26.02.2013 | 25.01.2014 | 24.01.2014 | 6 | 35.36 | 41.36 | 6 | 35.36 | 41.36 | 6 | 35.36 | 41.36 | 100% | 0 | 0 | 0 | 2706.84 | 0 | Completed
7 | PWD/ 45/EAP/07 | 7 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 126.51 to km 167.89 (In selected reaches) (Shirahatti, Belatti of Shirahatti Taluk) | 57 | 2168 | 2499.41 | 372.65 | 2872.06 | N.S.Nayak | 13.03.2013 | 12.02.2014 | 12.02.2014 | 0 | 41.38 | 41.38 | 0.3 | 41.08 | 41.38 | 0.3 | 41.08 | 41.38 | 100% | 0 | 0 | 0 | 2900.44 | 0 | Completed
8 | PWD/ 45/EAP/08 | 8 | Improvements to Bagalkote - Biligiriranganbetta SH-57 from km 72.27 to km 126.51 (In selected reaches) (Betageri , Beladatti of Ron & Gadag Taluks) | 57 | 2249.1 | 2449.94 | 509.75 | 2959.69 | N.B.Hiremath | 01.03.2013 | 01.02.2014 | 13.12.2014 | 0 | 44.51 | 44.51 | 0 | 42.55 | 42.55 | 0 | 42.55 | 42.55 | 100% | 0 | 0 | 0 | 2939.45 | 20.24 | Completed
DIVISION TOTAL |  |  |  |  | 13183.62 | 14065.62 | 1731.86 | 15797.48 |  |  |  |  | 70.49 | 218.99 | 289.48 | 73.19 | 208.06 | 281.25 | 73.19 | 208.06 | 281.25 | 100% | 0 | 0 | 0 | 15825.67 | 50.52
HAVERI DIVISION
9 | PWD/ 45/EAP/09 | 9a | Improvements to Ekkumbi - MolkalmurSH-02 from km 8.20 to km 88.49 (In selected reaches) (From Dasanakoppa cross to Hangal crosss & Agadi, Basapur up to Guttal of Hangal & Haveri Taluk | 2 | 2161.68 | 2542.44 | 220.68 | 2763.12 | A.V.Patil | 28.02.2013 | 27.01.2014 | 25.01.2014 | 23.83 | 10.47 | 34.3 | 22.65 | 10.92 | 33.57 | 22.65 | 10.92 | 33.57 | 100% | 0 | 0 | 0 | 2725.45 | 37.67 | Completed
|  | 9b | Improvements to Haveri - Sagar SH - 62 from km 9.63 to km 57.20 (In selected reaches) (Kagineli, Hamsabhavi of Byadagi & Hirekerur Taluk) | 62 | [8 empty] | 4.8 | 17.86 | 22.66 | 0 | 15.26 | 15.26 | 0 | 15.26 | 15.26 | 100% | 0 | 0 | 0
10 | PWD/ 45/EAP/10 | 10 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 196.72 to km 236.83 (In selected reaches) (Ranebennur, Haligeri of Ranebennur Taluk) | 57 | 1434.02 | 1609.55 | 144.25 | 1753.8 | S.R.Bellary | 17.10.2012 | 17.09.2013 | 03.11.2013 | 0 | 25.83 | 25.83 | 0 | 26.06 | 26.06 | 0 | 26.06 | 26.06 | 100% | 0 | 0 | 0 | 1750.33 | 3.47 | Completed
11 | PWD/ 45/EAP/11 | 11 | Improvements to Birur - Sammasagi SH-76 from km 125.01 to km 189.00 (In selected reaches) (Haligeri, koda of Ranebennuru & Hirekerur Taluk) | 76 | 1452.21 | 1616.25 | 98.97 | 1715.22 | S.R.Bellary | 17.10.2012 | 17.09.2013 | 16.11.2013 | 6.14 | 24.95 | 31.09 | 6.12 | 24.98 | 31.1 | 6.12 | 24.98 | 31.1 | 100% | 0 | 0 | 0 | 1666.76 | 48.46 | Completed
DIVISION TOTAL |  |  |  |  | 5047.91 | 5768.24 | 463.9 | 6232.14 |  |  |  |  | 34.77 | 79.11 | 113.88 | 28.77 | 77.22 | 105.99 | 28.77 | 77.22 | 105.99 | 100% | 0 | 0 | 0 | 6142.54 | 89.6
SIRSI DIVISION
12 | PWD/ 45/EAP/12 | 12a | Improvements to Kumta - Tadas SH - 69 from km 0.00 to km 27.15(In selected reaches)(from kumta to Sirsi Taluk Border via Alkod of Karwar Taluk) | 69 | 1207.5 | 1075.97 | 183.74 | 1259.71 | Ramashree Global Construction | 16.10.2012 | 16.09.2013 | 30.04.2014 | 16.4 | 1.6 | 18 | 16.4 | 1.6 | 18 | 16.4 | 1.6 | 18 | 100% | 0 | 0 | 0 | 1259.94 | -0.23 | Completed
|  | 12b | Improvements to Karwar Kaiga Ilkal SH-06 from km 0.50 to km 69.40(In selected reaches)(Shirwadi, Wailwadi of Karwar Taluk) | 6 | [8 empty] | 41.25 | 0 | 41.25 | 25.95 | 15.15 | 41.1 | 25.95 | 15.15 | 41.1 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1207.5 | 1075.97 | 183.74 | 1259.71 |  |  |  |  | 57.65 | 1.6 | 59.25 | 42.35 | 16.75 | 59.1 | 42.35 | 16.75 | 59.1 | 100% | 0 | 0 | 0 | 1259.94
KARWAR DIVISION | [18 empty] | 0 | 0
13 | PWD/ 45/EAP/13 | 13a | Improvements to Kumta Tadas SH-69 from km 40.00 to km 83.70 (In selected reaches) (Sirsi,Isloor of Sirsi Taluk) | 69 | 1717.28 | 1494.82 | 0 | 1494.82 | N.S.Nayak | 16.10.2012 | 17.06.2013 | 17.06.2013 | 22 | 6.54 | 28.54 | 24.59 | 2.47 | 27.06 | 24.59 | 2.47 | 27.06 | 100% | 0 | 0 | 0 | 1390.06 | 104.76 | Completed
|  | 13b | Improvements to Karwar - Kaiga - Ilkal SH-06 from km 69.40 to km125.80 (In selected reaches) (Idagundi, Yellapur Taluk) | 6 | [8 empty] | 29.64 | 17.86 | 47.5 | 29.64 | 18.13 | 47.77 | 29.64 | 18.132 | 47.772 | 100% | 0 | -0.002 | -0.002
DIVISION TOTAL |  |  |  |  | 1717.28 | 1494.82 | 0 | 1494.82 |  |  |  |  | 51.64 | 24.4 | 76.04 | 54.23 | 20.6 | 74.83 | 54.23 | 20.602 | 74.832 | 100% | 0 | -0.002 | -0.002 | 1390.06 | 104.76
DHARWAD CIRCLE TOTAL |  |  |  |  | 25217.92 | 25944.04 | 2648.09 | 28592.13 |  |  |  |  | 233.27 | 392.04 | 625.31 | 208.22 | 391.06 | 599.28 | 208.22 | 391.062 | 599.282 | 100% | 0 | -0.002 | -0.002 | 28568.07 | 244.88
BELAGAVI CIRCLE
BELAGAVI DIVISION
14 | PWD/ 45/EAP/14 | 14a | Improvements to Khanapur - Talaguppa SH - 93 from km 0.00 to km 34.58 (In selected reaches) (Khanapur of Kahanapur Taluk) | 93 | 2266.02 | 2212.08 | -7.17 | 2204.91 | M/s. P.R. Nayak. Hubli | 2012-10-12 | 2013-09-11 | 24.05.2013 | 31.57 | 1.456 | 33.026 | 33.03 | 0 | 33.03 | 33.03 | 0 | 33.03 | 100% | 0 | 0 | 0 | 2220.59 | 0 | Completed
|  | 14b | Improvements to Yargatti - Babaleshwar SH-55 from km 7.50 to km 28.46(In selected reaches) (Yaragalli, Sattigeri,Savadatti, Itnal, Hulkund of Ramadurga Taluk) | 55 | [8 empty] | 0 | 20.96 | 20.96 | 0 | 20.96 | 20.96 | 0 | 20.96 | 20.96 | 100% | 0 | 0 | 0
|  | 14c | Improvements to of Jamboti - Rabkavi SH - 54 from km 29.74 to km 54.28.(In selected reaches) (Belgaum, Kanbargi, Muchhandi, Suldhal, Tumarguddi, Hudli of Belgaum Taluk) | 54 | [8 empty] | 7.2 | 7.85 | 15.05 | 9.857 | 8.884 | 18.741 | 9.857 | 8.884 | 18.741 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2266.02 | 2212.08 | -7.17 | 2204.91 |  |  |  |  | 38.77 | 30.266 | 69.036 | 42.887 | 29.844 | 72.731 | 42.887 | 29.844 | 72.731 | 100% | 0 | 0 | 0 | 2220.59 | 0
CHIKKODI DIVISION
15 | PWD/ 45/EAP/15 | 15a | Improvements to Padubidri - Chikklagudda SH-01 from km 478.77 to km 497.35 (In selected reaches) (Hosur, Yaragatti, Badkundri cross, Kurni Chikkalgudda of Hukkeri Taluk) | 1 | 2144.97 | 2464.85 | 174.28 | 2639.13 | R.S.Patil | 06.02.2013 | 05.01.2014 | 30.04.2014 | 12 | 4 | 16 | 12 | 4 | 16 | 12 | 4 | 16 | 100% | 0 | 0 | 0 | 2646.71 | -7.58 | Completed
|  | 15b | Improvements to Jath - Jamboti SH-31 from km 0.00 to km 116.82 (In selected reaches) (Anantpur, Malabad, Parthanalli & Gokak cross, Kolavi, Vannur of Athani Taluk) | 31 | [8 empty] | 20 | 0 | 20 | 20 | 10 | 30 | 20 | 10 | 30 | 100% | 0 | 0 | 0
|  | 15c | Improvements to Kagawad Kaladagi SH-53 from km0.00 to km15.70(In selected reaches) (Kagwad, Shedbal, UgarBK, Ughar Kurd of Athani Taluk) | 53 | [8 empty] | 9.85 | 0 | 9.85 | 9.78 | 0 | 9.78 | 9.78 | 0 | 9.78 | 100% | 0 | 0 | 0
|  | 15d | Improvements to Mangasuli Laxmeshwar SH-73 from km 79.03 to km114.80 (In selected reaches) (Ghataprabha, Konnur, Mavanur, Godchinmalki, Pachhapur, Akkatangerhal of Gokak Taluk) | 73 | [8 empty] | 16.98 | 9.11 | 26.09 | 15.56 | 11.12 | 26.68 | 15.56 | 11.12 | 26.68 | 100% | 0 | 0 | 0
16 | PWD/ 45/EAP/16 | 16 | 16(a)Improvements to Nippani - Kottalagi SH-72 from km 0.00 to km 67.45 (Excluding from km 57.20 to km 58.18 ) (In selected reaches) (Madalga, Shippur & Nippani, Galataga, Nej ,Nandi,Examba, Kallol, Manjri, Shriguppi of Athani Taluk) | 72 | 1628.29 | 1876.92 | -0.236 | 1876.684 | P.Wantamutte | 22.02.2013 | 01.01.2014 | 31.12.2013 | 49.85 | 14.847 | 64.697 | 28.43 | 30.772 | 59.202 | 28.43 | 30.77 | 59.2 | 100% | 0 | 0.002 | 0.002 | 1873.21 | 3.474 | Completed
|  |  | 16(b)Improvements to Madalaga - ShippurSH-72 from km 0.00 to km 12.00 (In selected reaches) | [19 empty] | 0 | 0
17 | PWD/ 45/EAP/17 | 17 | Improvements to Nippani - Kottalagi SH-72 from km 57.20 to km 58.18 & km 67.45 to km 151.81 (In selected reaches) (Shriguppi, Molwad, Kusnal, Ugar BK, UgarKH of Athani Taluk) | 72 | 2201.28 | 2678.34 | 441.77 | 3120.11 | S.S.Alur | 06.10.2012 | 05.10.2013 | 31.12.2013 | 47.99 | 22 | 69.99 | 42.98 | 27.04 | 70.02 | 42.98 | 27.04 | 70.02 | 100% | 0 | 0 | 0 | 2916.01 | 0 | Completed
DIVISION TOTAL |  |  |  |  | 5974.54 | 7020.11 | 615.814 | 7635.924 |  |  |  |  | 156.67 | 49.957 | 206.627 | 128.75 | 82.932 | 211.682 | 128.75 | 82.93 | 211.68 | 100% | 0 | 0.002 | 0.002 | 7435.93 | -4.106
BAGALKOT DIVISION
18 | PWD/ 45/EAP/18 | 18a | Improvements to Bagalkot - Biligiriranganabetta SH-57 from km0.00 to km 29.38 (In selected reaches)(Bagalkote , Sulekere, Katageri, Badami of Badami Taluk) | 57 | 2342.33 | 2478.84 | 246.18 | 2725.02 | Haigreevea Construction | 08.10.2012 | 07.10.2013 | 30.4.2014 | 9.14 | 20.24 | 29.38 | 0 | 29.38 | 29.38 | 0 | 29.38 | 29.38 | 100% | 0 | 0 | 0 | 2705.56 | 19.46 | Completed
|  | 18b | Improvements to Yaragatti - Babaleshwar S.H.55 from km 42.41 to km 44.91 km 78.79 (In selected reaches) (Mudhol, Amalzari, Balgali of Badami Taluk) | 55 | [8 empty] | 0 | 17 | 17 | 0 | 17.81 | 17.81 | 0 | 17.81 | 17.81 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2342.33 | 2478.84 | 246.18 | 2725.02 |  |  |  |  | 9.14 | 37.24 | 46.38 | 0 | 47.19 | 47.19 | 0 | 47.19 | 47.19 | 100% | 0 | 0 | 0 | 2705.56 | 19.46
BIJAPUR DIVISION
19 | PWD/ 45/EAP/19 | 19a | Improvements to Shiradan - Lingasur SH-41from km 0.00 to km 71.43 (In selected reaches) (Shirdon, Chadchan, Zalki, Indi of Indi Taluk) | 41 | 2814 | 2736.37 | 139.88 | 2876.25 | S.M.Authade | 26.10.2012 | 25.10.2013 | 18.05.2013 | 0.61 | 26.23 | 26.84 | 0 | 30.04 | 30.04 | 0 | 30.04 | 30.04 | 100% | 0 | 0 | 0 | 2882.39 | -6.14 | Completed
|  | 19b | Improvements to Shiradan - Lingasur SH-41 from km 71.43 to km 100.73(In selected reaches) (Roog, Devaripurgi of Indi Taluk) | 41 | [8 empty] | 0 | 26.15 | 26.15 | 0 | 26.15 | 26.15 | 0 | 26.15 | 26.15 | 100% | 0 | 0 | 0
20 | PWD/ 45/EAP/20 | 20a | Improvements to Shiradan - Lingasur SH-41 from km 100.73 to km131.18 (In selected reaches) (Shirdon, Basavanbagewadi cross, of Muddebihal Taluk) | 41 | 2404 | 2577.82 | 227.56 | 2805.38 | S.S.Alur | 19.10.2012 | 18.10.2013 | 06.05.2013 | 0 | 24.45 | 24.45 | 0 | 24.115 | 24.115 | 0 | 24.115 | 24.115 | 100% | 0 | 0 | 0 | 2826.62 | 0 | Completed
|  | 20b | Improvements to Shiradan - Lingasur SH-41 from km131.18 to km 176.78 (In selected reaches) (Nalatwad, Muddebihal of Muddebihal Taluk) | 41 | [8 empty] | 21.88 | 16.29 | 38.17 | 6.25 | 35.57 | 41.82 | 6.25 | 35.57 | 41.82 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 5218 | 5314.19 | 367.44 | 5681.63 |  |  |  |  | 22.49 | 93.12 | 115.61 | 6.25 | 115.875 | 122.125 | 6.25 | 115.875 | 122.125 | 100% | 0 | 0 | 0 | 5709.01 | -6.14
BELAGAVI CIRCLE TOTAL |  |  |  |  | 15800.89 | 17025.22 | 1222.264 | 18247.484 |  |  |  |  | 227.07 | 210.583 | 437.653 | 177.887 | 275.841 | 453.728 | 177.887 | 275.839 | 453.726 | 100% | 0 | 0.002 | 0.002 | 18071.09 | 9.214
BELLARY CIRCLE
BELLARY DIVISION
21 | PWD/ 45/EAP/21 | 21 | Improvements to Kampli - Bellary SH-132 from km 0.00 to km 69.20 (In selected reaches) (Kampli town, Nilludi Kottayal, Emmiganur of Hospet Taluk & Kurugodu, Siddammanahalli, Badanhatti, Kudutini, Hariginadoni, Belagal& Bellary city limit of Bellary Taluk) | 132 | 2766 | 3042.53 | 135.88 | 3178.41 | Prabhakar Reddy | 12.03.13 | 11.02.14 | 30.06.2014 | 25.3 | 43.79 | 69.09 | 16.384 | 45.22 | 61.604 | 16.384 | 45.22 | 61.604 | 100% | 0 | 0 | 0 | 3114.94 | 63.47 | Completed
22 | PWD/ 45/EAP/22 | 22a | Improvements to Shiraguppa - Sandur SH-49 from km 27.00 to kmb 73.73 & SH-25 from km 0.00 to km 2.60 (In selected reaches) (Mallappana Gudi, Kamalapur, Bukka Sagara, Ramasagara, Kampli, Sanapura in Hospet Taluk) | 49 & 25 | 2414.1 | 2653.24 | 260.4 | 2913.64 | Rajshekhar (Swamy Constructions) | 31.10.2013 | 2016-01-25 | 2016-01-25 | 3.4 | 23.63 | 27.03 | 0 | 21.32 | 21.32 | 0 | 21.32 | 21.32 | 100% | 0 | 0 | 0 | 2921.45 | -7.81 | Completed
|  | 22b | Improvements to Shirguppa - Sandur SH-49 from km 73.73 to km 106.23 (In selected reaches) (Manur Sugur, Nadivi in Siraguppa Taluk) | 49 | [8 empty] | 0 | 14.76 | 14.76 | 0 | 9.17 | 9.17 | 0 | 9.17 | 9.17 | 100% | 0 | 0 | 0
23 | PWD/ 45/EAP/23 | 23a | Improvements to Hampi - Hagaribommanahalli SH-131 from km 0.00 to km 22.70 (In selected reaches) (Hampi, Kamalapura, Kakubal in Hospet Taluk) | 131 | 2937 | 2951.09 | 259.64 | 3210.73 | P.R.Nayak | 25.10.12 | 24.09.13 | 31.05.2014 | 6.2 | 12.9 | 19.1 | 1.904 | 14.365 | 16.269 | 1.904 | 14.365 | 16.269 | 100% | 0 | 0 | 0 | 3168.9 | 41.83 | Completed
|  | 23b | Improvements to Hampi - Hagaribommanahalli SH-131from km 22.70 to km 73.20 (In selected reaches) (Talur, Ubbalagundi, Rajapur, Metriki in Sandur Taluk) | 131 | [8 empty] | 9 | 35.93 | 44.93 | 5.172 | 39.544 | 44.716 | 5.172 | 39.544 | 44.716 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 8117.1 | 8646.86 | 655.92 | 9302.78 |  |  |  |  | 43.9 | 131.01 | 174.91 | 23.46 | 129.619 | 153.079 | 23.46 | 129.619 | 153.079 | 100% | 0 | 0 | 0 | 9205.29 | 97.49
HADAGALI DIVISION
24 | PWD/ 45/EAP/24 | 24a | Improvements to Mylar - Toranagal SH-40 from km 0.0 to km 97.33 (In selected reaches) (Holallu, Badanuru, Giriyapura, Hirehadagali, Haganuru, Thippapura, Huvinahadagali of Hadagali Taluk & Hampa sagara, Basapura, H.B.Halli, Anekallu, Basapura Thanda, Hosakere, Hansi in H.B.Halli Taluk) | 40 | 1878 | 1995.25 | 195.25 | 2190.5 | Rammohan Reddy | 19.12.2013 | 18.11-2014 | 2016-03-31 | 30.25 | 23.47 | 53.72 | 27 | 25.12 | 52.12 | 27 | 25.12 | 52.12 | 100% | 0 | 0 | 0 | 2191.54 | -1.04 | Completed
|  | 24b | Improvements to Mylar - Torangal SH-40 from km 104.00 to km 109.00 (In selected reaches) (Kudligi Town inKudligi Taluk) | 40 | [8 empty] | 0 | 3.85 | 3.85 | 0 | 2.95 | 2.95 | 0 | 2.95 | 2.95 | 100% | 0 | 0 | 0
25 | PWD/ 45/EAP/25 | 25a | Improvements to Hampi - Hagaribommanhalli SH-131from km 96.45 to km 137.00(In selected reaches)(Appena Halli, Appena Hall Thanda, Mahadevapura, Gudekote, Ramadurga Cross, C.J.Halli in Kudligi Taluk) | 131 | 2298 | 2393.23 | 128.1 | 2521.33 | K.Krishna | 18.10.12 | 17.09.13 | 30.07.2014 | 0 | 26.61 | 26.61 | 0 | 26.7 | 26.7 | 0 | 26.7 | 26.7 | 100% | 0 | 0 | 0 | 2469.97 | 51.36 | Completed
|  | 25b | Improvements to Hampi -Hagaribommanhalli SH-131 from km 187.92 to km 198.75 (In selected reaches) (H.B.Halli, Chintara palli in H.B.Halli Taluk) | 131 | [8 empty] | 2.1 | 4.09 | 6.19 | 2.35 | 3.95 | 6.3 | 2.35 | 3.95 | 6.3 | 100% | 0 | 0 | 0
|  | 25c | Improvements to Arabhavi - Challakere SH-45 from km 239.00 to km 261.02 (In Selected reaches) (Kottur, Kaalapur, Ujjini, Lakkampura in Kudligi Taluk) | 45 | [8 empty] | 0 | 13.42 | 13.42 | 0 | 13.52 | 13.52 | 0 | 13.52 | 13.52 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4176 | 4388.48 | 323.35 | 4711.83 |  |  |  |  | 32.35 | 71.44 | 103.79 | 29.35 | 72.24 | 101.59 | 29.35 | 72.24 | 101.59 | 100% | 0 | 0 | 0 | 4661.51 | 50.32
RAICHUR DIVISION
26 | PWD/ 45/EAP/26 | 26a | Improvements to Mudhol - Yeragera SH-127 from km 134.91 to km 177.24 (In selected reaches) (Attunur, Kudri, Aroli, Purtipalli in Manvi Taluk) | 127 | 2114 | 2005.47 | 184.96 | 2190.43 | Shankar Kotarki | 05.11.12 | 04.10.13 | 30.06.2014 | 14.82 | 16.07 | 30.89 | 10.664 | 20.092 | 30.756 | 10.664 | 20.092 | 30.756 | 100% | 0 | 0 | 0 | 2117.51 | 72.92 | Completed
|  | 26b | Improvements to Mudhol - Yeragera SH - 127 from km 177.24 to km 207.96 (In selected reaches) (Gujhali, Yeragera, Jambaladinni in Raichur Taluk) | 127 | [8 empty] | 15.3 | 11.31 | 26.61 | 10.265 | 14.096 | 24.361 | 10.265 | 14.096 | 24.361 | 100% | 0 | 0 | 0
27 | PWD/ 45/EAP/27 | 27a | Improvements to Deodurg - Bellary SH - 128 from km 21.00 to km 76.24 (In selected reaches) (Chinchirki, K Thimmapura, Hussain pura, Hire Hanagi, Bhogavathi, Bagalvada, Hirekottankal, Chikkotnakalin Manvi Taluk) | 128 | 2374 | 2305.32 | 200.92 | 2506.24 | Jagadeeswarudu Chilukuri (M/s Haigreeva Infratech Pvt. Ltd) | 05.11.12 | 30.09.2014 | 31.03.2015 | 18.64 | 29.57 | 48.21 | 16.548 | 23.317 | 39.865 | 16.548 | 23.317 | 39.865 | 100% | 0 | 0 | 0 | 2512.42 | -6.18 | Completed
|  | 27b | Improvements to Deodurg - Bellary SH - 128 from km 0.00 to km 21.00 (In selected reaches)(Mundargi, Galag in Deodurga Taluk) | 128 | [8 empty] | 9.9 | 6.6 | 16.5 | 6.7 | 8.21 | 14.91 | 6.7 | 8.21 | 14.91 | 100% | 0 | 0 | 0
28 | PWD/ 45/EAP/28 | 28a | Improvements to Wanmarpalli - Raichur SH-15 from km 332.05 to km 346.29 (In selected reaches) (Raichur town limit, Singanodi in Raichur Taluk) | 15 | 1770.4 | 1951.97 | 292.13 | 2244.1 | P.Ramarao (Patel Engineering) | 19.10.12 | 18.09.13 | 31.10.2014 | 6.25 | 7.99 | 14.24 | 5.527 | 8.548 | 14.075 | 5.527 | 8.548 | 14.075 | 100% | 0 | 0 | 0 | 2202.56 | 41.54 | Completed
|  | 28b | Improvements to Managuli - Bichal SH - 61from km 161.00 to km 191.87 (In selected reaches) (Kottadoddi, Arkera, Jagir Jadaladinni, of Deodurga Taluk & Siravara inManvi Taluk) | 61 | [8 empty] | 13.07 | 17.8 | 30.87 | 9.55 | 21.325 | 30.875 | 9.55 | 21.325 | 30.875 | 100% | 0 | 0 | 0
29 | PWD/ 45/EAP/29 | 29a | Improvements to Raravi- Belur SH - 63 from km 32.50 to km 44.98 (In selected reaches)(Salgunda, Gorebal in Sindanur Taluk) | 63 | 1925.5 | 2140.59 | 64.25 | 2204.84 | P.Ramarao (Patel Engineering) | 12.03.13 | 11.02.14 | 30.11.2014 | 0 | 12.48 | 12.48 | 0 | 12.48 | 12.48 | 0 | 12.48 | 12.48 | 100% | 0 | 0 | 0 | 2071 | 133.84 | Completed
|  | 29b | Srirangapatna Jewargi SH -19 from km 477.00 to km 505.00 (In selected reaches)(Lingasugur, Gurugunta in Lingasugur Taluk) | 19 | [8 empty] | 28 | 0 | 28 | 28 | 0 | 28 | 28 | 0 | 28 | 100% | 0 | 0 | 0
|  | 29c | Improvements to Managuli -Bichal SH -61 from km 239.03 to km 251.05 (In selected reaches) (Gillesuguru in Raichur Taluk) | 61 | [8 empty] | 0 | 12.03 | 12.03 | 0 | 11.975 | 11.975 | 0 | 11.975 | 11.975 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 8183.9 | 8403.35 | 742.26 | 9145.61 |  |  |  |  | 105.98 | 113.85 | 219.83 | 87.254 | 120.043 | 207.297 | 87.254 | 120.043 | 207.297 | 100% | 0 | 0 | 0 | 8903.49 | 242.12
KOPPAL DIVISION
30 | PWD/ 45/EAP/30 | 30 | Improvements to Kalmala - Shiggaon SH -23 from km 162.45 to km 203.58 & Ginigera - Gondabal MDR from km 4.57 to km 20.90 (In selected reaches) (Ginigera, Basavapura, koppal town limit, Chikkasindagi, Hiresindagi, Hatti, Billi Gatta in Koppal Taluk) | 23 & MD R | 2258 | 2464.93 | 244.04 | 2708.97 | Sai Constructions | 16.10.12 | 15.09.13 | 31.03.2014 | 26.04 | 29.09 | 55.13 | 16.98 | 36.46 | 53.44 | 16.98 | 36.46 | 53.44 | 100% | 0 | 0 | 0 | 2710.98 | 0 | Completed
DIVISION TOTAL |  |  |  |  | 2258 | 2464.93 | 244.04 | 2708.97 |  |  |  |  | 26.04 | 29.09 | 55.13 | 16.98 | 36.46 | 53.44 | 16.98 | 36.46 | 53.44 | 100% | 0 | 0 | 0 | 2710.98 | 0
BELLARY CIRCLE TOTAL |  |  |  |  | 22735 | 23903.62 | 1965.57 | 25869.19 |  |  |  |  | 208.27 | 345.39 | 553.66 | 157.044 | 358.362 | 515.406 | 157.044 | 358.362 | 515.406 | 100% | 0 | 0 | 0 | 25481.27 | 389.93
GULBARGA CIRCLE
GULBARGA DIVISION
31 | PWD/ 45/EAP/31 | 31 | Improvements to Mahagaon - Sulepeth SH - 32 from km 70.42 to km 118.00 (In selected reaches) (Mahagaon of Gulbarga Taluk& Ratkal,Kodli, Sulepet of Chincholli Taluk) | 32 | 2486 | 2904.53 | 725.44 | 3629.97 | M/s Shankar Kotarki | 2012-10-30 | 2013-09-29 | 30.06.2015 | 0 | 47.58 | 47.58 | 0 | 47.58 | 47.58 | 0 | 47.58 | 47.58 | 100% | 0 | 0 | 0 | 3568.71 | 61.26 | Completed
32 | PWD/ 45/EAP/32 | 32a | Improvements to Gulbarga - Jewargi - Sindagi MDR via Chigaralli cross joining Yadrami from km 0.00 to km 52.00 (In selected reaches)(Chigaralli , Yedrami of Jewargi Taluk) | MDR | 3144 | 3158.78 | 271.22 | 3430 | M/sKPC Projects . Ltd | 2012-10-26 | 2013-09-25 | 24.10.2014 | 22 | 30 | 52 | 0 | 39 | 39 | 0 | 39 | 39 | 100% | 0 | 0 | 0 | 3465.91 | 0 | Completed
|  | 32b | Improvements to Srirangapatna - JewargiSH-19 from km 573.00 to km 592.00 (In selected reaches)(Kallur &Jewargi of Jewargi Taluk) | 19 | [8 empty] | 19 | 0 | 19 | 19 | 0 | 19 | 19 | 0 | 19 | 100% | 0 | 0 | 0
|  | 32c | Improvements to Mudhol -Yeragera SH-127 from km 0.00 to km 24.50 (In selected reaches)(Mudhol & Itkal of Sedam Taluk) | 127 | [8 empty] | 18.94 | 5.56 | 24.5 | 18.7 | 5.8 | 24.5 | 18.7 | 5.8 | 24.5 | 100% | 0 | 0 | 0
33 | PWD/ 45/EAP/33 | 33 | Improvements to Aurad - Sadashivgad SH - 34 from km 138.67 to km 206.40 (In selected reaches) (Kinni sultan , Jidga of Aland Taluk) | 34 | 1988 | 2372.65 | 229.49 | 2602.14 | M/s SRK Constructions | 2013-11-23 | 2013-10-22 | 2016-03-31 | 33 | 29.7 | 62.7 | 0 | 26.76 | 26.76 | 0 | 26.76 | 26.76 | 100% | 0 | 0 | 0 | 2514.75 | 87.39 | Completed
DIVISION TOTAL |  |  |  |  | 7618 | 8435.96 | 1226.15 | 9662.11 |  |  |  |  | 92.94 | 112.84 | 205.78 | 37.7 | 119.14 | 156.84 | 37.7 | 119.14 | 156.84 | 100% | 0 | 0 | 0 | 9549.37 | 148.65
YADAGIRI DIVISION
34 | PWD/ 45/EAP/34 | 34a | Improvements to Mudhol - Yeragera SH-127 from km 40.73 to km 83.64(In selected reaches) (Anpur,Saidapur, Kondapur of Yadagir Taluk) | 127 | 1751 | 2009.24 | 196.29 | 2205.53 | M/s RMN Infrastructures | 2012-12-13 | 2013-11-12 | 31.03.2014 | 26.98 | 12.64 | 39.62 | 25.18 | 14.44 | 39.62 | 25.18 | 14.44 | 39.62 | 100% | 0 | 0 | 0 | 2121.38 | 84.15 | Completed
|  | 34b | Improvements to Basavakalyan - Raichur SH-51 from km 171.42 to km 192.30 (In selected reaches) (Ramasamudra, Halgeri, Ballichakra, Killankeri of Yadagir Taluk) | 51 | [8 empty] | 17.38 | 3.5 | 20.88 | 17.12 | 3.76 | 20.88 | 17.12 | 3.76 | 20.88 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1751 | 2009.24 | 196.29 | 2205.53 |  |  |  |  | 44.36 | 16.14 | 60.5 | 42.3 | 18.2 | 60.5 | 42.3 | 18.2 | 60.5 | 100% | 0 | 0 | 0 | 2121.38 | 84.15
BIDAR DIVISION
35 | PWD/ 45/EAP/35 | 35 | Improvements to Humnabad - Bidar SH-105 from km 0.00 to km 45.40 (In selected reaches) (Humnabad, Halkhed, Sindbandgi of Humnabad Taluk& Bylhalli, Halhalli of Bhalki Taluk& Andur , Naubad Bidar of Bidar Taluk) | 105 | 1307 | 1206.13 | 98.35 | 1298.4 | M/s Mehul Constructions | 2012-10-16 | 2013-09-19 | 31.01.2014 | 36.7 | 0 | 36.7 | 38.75 | 0 | 38.75 | 38.75 | 0 | 38.75 | 100% | 0 | 0 | 0 | 1303.24 | -4.84 | Completed
36 | PWD/ 45/EAP/ 36 | 36 | Impts.to Wanmarpalli - Raichur SH-15 from km 0.00 to km 90.60 (In selected reaches) (Wanmarpalli,Aurad, Ballur,Kautha B of Aurad Taluk& Chikpet, Bidar,Manalli of Bidar Taluk & Meenkera, Jangalera& Changlera of Humnabad Taluk) | 15 | 2271.01 | 2438.29 | 605.85 | 3044.14 | Gurunath Kollur | 2012-09-29 | 2013-08-29 | 03.05.2014 | 57.7 | 22.3 | 80 | 22.6 | 24.83 | 47.43 | 22.6 | 24.83 | 47.43 | 100% | 0 | 0 | 0 | 3075.68 | 0 | Completed
37 | PWD/ 45/EAP/ 37 | 37 | Improvements to Aurad - Sadashivgad SH-34 from km 0.00 to km 138.67 (In selected reaches) (Aurad,Mugnal,Nittur of Aurad Taluk & Kotgal, Amdabad, Halbarga of Bhalki Taluk & Basavkalyan,Morkhandi, Mannalli, Ekamba, Batagera,Hattaraga of Basavakalyan Taluk) | 34 | 2664.83 | 2736.98 | 409.42 | 3146.4 | M/s KPC Projects . Ltd | 2012-10-16 | 2013-10-08 | 30.10.2014 | 27 | 42.51 | 69.51 | 20.59 | 48.26 | 68.85 | 20.586 | 48.264 | 68.85 | 100% | 0.004 | -0.004 | -3.5527e-15 | 3064.7 | 81.7 | Completed
DIVISION TOTAL |  |  |  |  | 6242.84 | 6381.4 | 1113.62 | 7488.94 |  |  |  |  | 121.4 | 64.81 | 186.21 | 81.94 | 73.09 | 155.03 | 81.936 | 73.094 | 155.03 | 100% | 0.004 | -0.004 | -3.5527e-15 | 7443.62 | 76.86
GULBARGA CIRCLE TOTAL |  |  |  |  | 15611.84 | 16826.6 | 2536.06 | 19356.58 |  |  |  |  | 258.7 | 193.79 | 452.49 | 161.94 | 210.43 | 372.37 | 161.936 | 210.434 | 372.37 | 100% | 0.004 | -0.004 | -3.5527e-15 | 19114.37 | 309.66
NORTH ZONE TOTAL |  |  |  |  | 79365.65 | 83699.48 | 8371.984 | 92065.384 |  |  |  |  | 927.31 | 1141.803 | 2069.113 | 705.091 | 1235.693 | 1940.784 | 705.087 | 1235.697 | 1940.784 | 100% | 0.004 | -0.004 | -7.1054e-15 | 91234.8 | 953.684
SOUTH ZONE
RAMANAGARA DIVISION
38 | PWD/45/EAP/ 38 | 38 | Improvements to Hunasanhalli - Chikkahalli SH-03 from km 0.00 (TN border) to km 83.67 (In selected reaches) (Hunasanahalli, Kodihalli, Tippaya, Aralalu, Kanakapura, Hosakote, Ganulu, Arehalli of Thavarekere, of Kanakapura Taluk & Ramanagara, Kudihalli, Padara halli, Lakshmi pura, Gollarahatti of Ramanagara Taluk) | 3 | 1870 | 2000.13 | 54.98 | 2055.11 | S.R.Ravishanker | 2012-11-07 | 06.10.12 | 06.10.2013 | 34.82 | 15.2 | 50.02 | 29.5 | 13.89 | 43.39 | 29.5 | 13.89 | 43.39 | 100% | 0 | 0 | 0 | 2068.46 | 0 | Completed
|  |  | DIVISION TOTAL |  | 1870 | 2000.13 | 54.98 | 2055.11 |  |  |  |  | 34.82 | 15.2 | 50.02 | 29.5 | 13.89 | 43.39 | 29.5 | 13.89 | 43.39 | 100% | 0 | 0 | 0 | 2068.46 | 0
KOLAR DIVISION
39 | PWD/45/EAP/ 39 | 39 | Improvements to Kothapalli - Masti SH-99 from km 0.00 (AP border) to km 103.40 ( TN border) (In selected reaches) (Kottaoalli, Kappli, Seegehalli, Byrapalli, Srinivaspura, Hosahalli of Srinivasapura Taluk & Muduvadi, Veerapura, Kolara,Muduvathi ofKolar Taluk & Lakshmi sagara, Hanasikote, K.G.Halli, Dinnahalli, Nagadenahalli, Masthi of Malur Taluk) | 99 | 2758.33 | 2843.77 | 310.65 | 3154.42 | M. Venkataramareddy | 2013-01-24 | 2013-11-23 | 2015-03-30 | 9.1 | 46.75 | 55.85 | 10.262 | 30.92 | 41.182 | 10.262 | 30.92 | 41.182 | 100% | 0 | 0 | 0 | 2972.56 | 181.86 | Completed
DIVISION TOTAL |  |  |  |  | 2758.33 | 2843.77 | 310.65 | 3154.42 |  |  |  |  | 9.1 | 46.75 | 55.85 | 10.262 | 30.92 | 41.182 | 10.262 | 30.92 | 41.182 | 100% | 0 | 0 | 0 | 2972.56 | 181.86
TUMKUR DIVISION
40 | PWD/45/EAP/ 40 | 40a | Improvements to Sira - Nanjangud SH-84 from km 13.75 to km 49.25 (In selected reaches) (Devanahalli, Ankasandra, Anthapura, Chellur, Somalapura, Ammanaghatta of Gubbi Taluk | 84 | 1842.96 | 2156.2 | 263.1 | 2419.3 | BSR infratec Ltd | 2012-10-17 | 2013-09-16 |  | 11.4 | 23.98 | 35.38 | 3.58 | 22.79 | 26.37 | 3.58 | 22.79 | 26.37 | 100% | 0 | 0 | 0 | 2390.57 | 28.73 | Completed
|  | 40b | Improvement to Hunasanahalli - Chikkanahalli SH-03 from km 165.88 to km 170.08 (In selected reaches) ( Koratagere town limit of Koratagere Taluk) | 3 | [8 empty] | 2.2 | 2 | 4.2 | 1.88 | 2.32 | 4.2 | 1.88 | 2.32 | 4.2 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1842.96 | 2156.2 | 263.1 | 2419.3 |  |  |  |  | 13.6 | 25.98 | 39.58 | 5.46 | 25.11 | 30.57 | 5.46 | 25.11 | 30.57 | 100% | 0 | 0 | 0 | 2390.57 | 28.73
BANGALORE CIRCLE |  |  |  |  | 6471.29 | 7000.1 | 628.73 | 7628.83 |  |  |  |  | 57.52 | 87.93 | 145.45 | 45.222 | 69.92 | 115.142 | 45.222 | 69.92 | 115.142 | 300% | 0 | 0 | 0 | 7431.59 | 210.59
MYSORE DIVISION
41 | PWD/45/EAP/ 41 | 41 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 610.30 to km 656.50 (In selected reaches) (Maddur Kallali, Maddur, Maddur hundi of Mysore Taluk& Hampapura, Madanahalli, JP Hundi, Hullahalli of H.D.Kote Taluk& Mobbahalli, Gandi Grama, Byluru, Deburu Nanjanagud Town of Nanjanagudu Taluk) | 57 | 1470 | 1578.88 | 364.11 | 1942.99 | Bapuji Cons. | 2012-10-17 | 2013-10-16 | 30.12.2013 | 4.96 | 18 | 22.96 | 4.39 | 20.34 | 24.73 | 4.39 | 20.34 | 24.73 | 100% | 0 | 0 | 0 | 1934.88 | 8.11 | Completed
42 | PWD/45/EAP/ 42 | 42a | Improvements to Ramanathapura - Therakanambi SH-86 from km 107.35 to km 118.40 (In selected reaches) ( Parvatipura, Beere Gowdanapura, Indiranagar ofNanjanagudu Taluk) | 86 | 1447 | 1572.6 | 391.93 | 1964.53 | K.T Ravi | 2012-11-09 | 2013-10-08 | 15.06.2014 | 0 | 8.35 | 8.35 | 0 | 8.425 | 8.425 | 0 | 8.425 | 8.425 | 100% | 0 | 0 | 0 | 1893.91 | 70.62 | Completed
|  | 42b | Improvements to Sira - Nanjanagud SH-84 from km 198.54 to km 243.01 (In selected reaches) (Kalkuli, Bommanahalli, Sosle, T.N.Pura, Alasri katte Hundi of T.N.Pura Taluk & Biligere, Kupperavalli, Nagarle, Alamburu, HosavaralWadi Geekali Hundi of Nanjanagudu Taluk) | 84 | [8 empty] | 3.8 | 16.2 | 20 | 0 | 6.83 | 6.83 | 0 | 6.83 | 6.83 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2917 | 3151.48 | 756.04 | 3907.52 |  |  |  |  | 8.76 | 42.55 | 51.31 | 4.39 | 35.595 | 39.985 | 4.39 | 35.595 | 39.985 | 100% | 0 | 0 | 0 | 3828.79 | 78.73
HUNSUR DIVISION | [18 empty] | 0 | 0
43 | PWD/45/EAP/ 43 | 43 | Improvements to Ramanathapura - Therakanambi SH-86 from km 7.80 to km 107.35(In selected reaches) (Ansoge, Koluru, Mayagowdanahalli, Housuru, Keturu, Malalihalli, Mavahuru, Madanahalli of K.R.Nagar Taluk& Honnenahalli, Kalkuli, Hunsur, Hanchya, Kurubara hosalli, BBH Colony, Gurupura of Hunsur Taluk & Bhimanahalli, Hunnuru, Yedthore, Tiger Block, Shantipura, H.D.Kote, Jakkali, Devalapura, Saraguru of H.D.Kote Taluk) | 86 | 3256.77 | 3390.71 | 475.23 | 3865.94 | SVS Mookambika Cons. | 2012-11-09 | 2013-10-08 | 30.09..2014 | 5.44 | 52.49 | 57.93 | 5.3 | 52.27 | 57.57 | 5.3 | 52.27 | 57.57 | 100% | 0 | 0 | 0 | 3620.23 | 245.71 | Completed
DIVISION TOTAL |  |  |  |  | 3256.77 | 3390.71 | 475.23 | 3865.94 |  |  |  |  | 5.44 | 52.49 | 57.93 | 5.3 | 52.27 | 57.57 | 5.3 | 52.27 | 57.57 | 100% | 0 | 0 | 0 | 3620.23 | 245.71
MANDYA DIVISION
44 | PWD/45/EAP/ 44 | 44a | Improvements to Bangalore - Jalsur SH-85 from km 112.40 to km 153.30 (In selected reaches) (Nagamangala, Mallenahalli, Kanthapura, Bhogadhi, TV Kaloni of Nagamangala Taluk)(Dugnahall, Kotgenehali, Valgere, Mensa, K.R.Pet of K.R.Pet Taluk) | 85 | 2061.5 | 2312.73 | 210.79 | 2523.52 | Govinde gowda | 2012-10-30 | 2013-07-29 | 12.07.2013 | 9.83 | 20.67 | 30.5 | 8.775 | 21.955 | 30.73 | 8.775 | 21.955 | 30.73 | 100% | 0 | 0 | 0 | 2532.02 | 0 | Completed
|  | 44b | Improvements to Mandya - Hadagali SH-47 from km 22.95 to km 55.40 (In selected reaches) (Sangapura, Jakkanahalli, Kadalgere, Valagere of Pandavapura Taluk) Hindasahalli of Nagamangala Taluk) | 47 | [8 empty] | 22.25 | 7.74 | 29.99 | 18.86 | 11.1 | 29.96 | 18.86 | 11.1 | 29.96 | 100% | 0 | 0 | 0
45 | PWD/45/EAP/ 45 | 45a | Improvements to Mandya - Hadagali SH-47 from km 0.69 to km 22.95(In selected reaches) (Mandya, Shivalli, Dudda, Bevakullu, Atna Javanahalli of Mandya Taluk ) | 47 | 1669.1 | 1603.6 | 158.58 | 1762.18 | Govinde gowda | 2012-10-30 | 2013-07-29 | 22.06.2013 | 4.2 | 11.21 | 15.41 | 1.2 | 14.21 | 15.41 | 1.2 | 14.21 | 15.41 | 100% | 0 | 0 | 0 | 1732.06 | 30.12 | Completed
|  | 45b | Improvements to Sira - Nanjanagud SH-84 from km 171.16 to km 198.54 (In selected reaches) (Mangala Thittu of Mandya Taluk & Virajpura, Ramanduru, Mkagepura, Mikkere of Malavalli Taluk) | 84 | [8 empty] | 5.5 | 16.11 | 21.61 | 0 | 21.548 | 21.548 | 0 | 21.548 | 21.548 | 100% | 0 | 0 | 0
46 | PWD/45/EAP/ 46 | 46 | Improvements to Srirangapatna - Arasikere SH-7 from km 4.50 to km 60.42 (In selected reaches) (Pandavapura Village, Shettahalli, Hulikere of Pandavapura Taluk & Murakanahalli, K.R.Pete, Krishnapura , Kikere, Lakshmipura , Angola of KR Pete Taluk) | 7 | 2143.3 | 2340.56 | 273.12 | 2613.68 | Bapuji Cons. | 2012-10-25 | 2013-07-24 | 30.03.2013 | 19.56 | 34.22 | 53.78 | 16.967 | 38.878 | 55.845 | 16.967 | 38.878 | 55.845 | 100% | 0 | 0 | 0 | 2640.6 | 0 | Completed
|  |  | DIVISION TOTAL |  | 5873.9 | 6256.89 | 642.49 | 6899.38 |  |  |  |  | 61.34 | 89.95 | 151.29 | 45.802 | 107.691 | 153.493 | 45.802 | 107.691 | 153.493 | 100% | 0 | 0 | 0 | 6904.68 | 30.12
MYSORE CIRCLE TOTAL |  |  |  |  | 12047.67 | 12799.08 | 1873.76 | 14672.84 |  |  |  |  | 75.54 | 184.99 | 260.53 | 55.492 | 195.556 | 251.048 | 55.492 | 195.556 | 251.048 | 300% | 0 | 0 | 0 | 14353.7 | 354.56
HASSAN DIVISION
47 | PWD/45/EAP/ 47 | 47a | Improvements to Huliyar - Keralapura SH-102 from km 75.28 to km 99.08 (In selected reaches) (Dudda RS, ShantiGrama Village, Devihalli of Hasan Taluk) | 102 | 3257 | 3508.78 | 468.24 | 3977.02 | Rayeegowda | 2012-11-16 | 2013-10-15 | 30.09.2015 | 2.3 | 56.91 | 59.21 | 0.19 | 18.6 | 18.79 | 0.19 | 18.6 | 18.79 | 100% | 0 | 0 | 0 | 3970.78 | 6.24 | Completed
|  | 47b | Improvements to Huliyar - Keralapura SH-102 from km 99.08 to km 144.39 (In selected reaches) (Malali Village, Taranya, Hariharapura, Jakkanahalli, Bidrakka, Nerale of Holenarasipura Taluk) | 102 | [10 empty] | 0 | 0 | 40.92 | 40.92 | 0 | 40.921 | 40.921 | 100% | 0 | -0.001 | -0.001
48 | PWD/45/EAP/ 48 | 48a | Improvements to Hirisave - Chattahalli SH -8 from km 0.00 to km 41.835 (In selected reaches) (Sorekkayipura, Hosahalli, Baralu, CRPatna of Channarayapattana Taluk) | 8 | 2045.5 | 2235.48 | 126.54 | 2362.02 | H.N Ramegowda | 2012-11-16 | 2013-10-15 | 15.10.2013 | 5.25 | 8.3 | 13.55 | 4.45 | 8.36 | 12.81 | 4.45 | 8.36 | 12.81 | 100% | 0 | 0 | 0 | 2321.33 | 40.69 | Completed
|  | 48b | Improvements to Srirangapatna - Arasikere SH -7 from km 61.48 to km 91.27 (In selected reaches) (CRPatna, Moodanahalli, CR patna Taluk border (Yaranahalli) of Channarayapattana Taluk) | 7 | [8 empty] | 17.75 | 7.48 | 25.23 | 17.75 | 7.03 | 24.78 | 17.75 | 7.03 | 24.78 | 100% | 0 | 0 | 0
|  | 48c | Improvements to Srirangapatna - Arasikere SH -7 from km 91.27 to km 117.52(In selected reaches) (Gandsi Handpost, Mududi, Arasikere town of Arasikere Taluk) | 7 | [8 empty] | 17.75 | 8.5 | 26.25 | 17.75 | 8.5 | 26.25 | 17.75 | 8.5 | 26.25 | 100% | 0 | 0 | 0
49 | PWD/45/EAP/ 49 | 49 | Improvements to Huliyar - Keralapura SH-102 from km 15.00 to km 75.28 (In selected reaches) (Kaimara, Modalu, JCPura , Haranahalli, Bageshpura, Dudda Junction of Hassan & Arasikere Taluk) | 102 | 2393.35 | 2459.42 | 363.65 | 2823.07 | Rayeegowda | 2013-03-16 | 2014-02-15 | 30.06.2016 | 11 | 43.58 | 54.58 | 0 | 54.58 | 54.58 | 0 | 54.58 | 54.58 | 100% | 0 | 0 | 0 | 2660.51 | 162.56 | Completed
50 | PWD/45/EAP/ 50 | 50a | Improvements to Belur - Kodlipet SH-110 from km 0.00 to km 20.20 (In selected reaches) (Bikkodu, Madaghatta, Devarajpura of Belur Taluk) | 110 | 1587 | 1596.07 | 200.36 | 1796.43 | CHVN Reddy | 2012-11-16 | 2013-10-15 | 15.10.2013 | 6.25 | 13.95 | 20.2 | 0 | 20.2 | 20.2 | 0 | 20.2 | 20.2 | 100% | 0 | 0 | 0 | 1739.28 | 57.15 | Completed
|  | 50b | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 452.50 to km 475.84 (In selected reaches) (Belur, Hagare, Kalkere gadi of Belur Taluk) | 57 | [8 empty] | 20.19 | 3.15 | 23.34 | 19.69 | 3.65 | 23.34 | 19.69 | 3.65 | 23.34 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 9282.85 | 9799.75 | 1158.79 | 10958.54 |  |  |  |  | 80.49 | 141.87 | 222.36 | 59.83 | 161.84 | 221.67 | 59.83 | 161.841 | 221.671 | 100% | 0 | -0.001 | -0.001 | 10691.9 | 266.64
HASSAN SPECIAL DIVISION
51 | PWD/45/EAP/ 51 | 51a | Improvements to Hirisave - Chattahalli SH-8 from km 80.80 to km 94.20 km (In selected reaches) (Bobbegalale, Chowrgal, Mallipatna of Arakalagudu Taluk) | 8 | 2057 | 2260.59 | 225.67 | 2486.26 | S M Abdul Hafeez | 2012-11-15 | 2013-10-14 | 20.03.2014 | 0 | 13.4 | 13.4 | 0 | 13 | 13 | 0 | 13 | 13 | 100% | 0 | 0 | 0 | 2473.43 | 12.83 | Completed
|  | 51b | Improvements to Hirisave - Chattahalli SH-8 from km 105.55 to km129.97 (In selected reaches) (Changadihalli, Huchchangi, Mageri of Sakaleshpura Taluk) | 8 | [8 empty] | 0 | 19.67 | 19.42 | 0 | 19.42 | 19.42 | 0 | 19.42 | 19.42 | 100% | 0 | 0 | 0
|  | 51c | Improvements to Huliyar - Keralapura SH-102 from km 144.39 to km 150.252 (In selected reaches)(Bombe Koppalu, Boodihal, Keralapura, Karthal of Arakalagudu Taluk) | 102 | [8 empty] | 0 | 5.13 | 5.13 | 0 | 5.13 | 5.13 | 0 | 5.13 | 5.13 | 100% | 0 | 0 | 0
52 | PWD/45/EAP/ 52 | 52 | Improvements to Belur - Kodlipet SH-110 from km 20.20 to km 68.70 (In selected reaches) (Kamathi kudige, Alur, Bairapura Handpost, Magghe, Rayarakoppalu of Sakaleshpura Taluk) | 110 | 2325 | 2583.35 | 182.25 | 2765.6 | H.N Ramegowda | 2012-12-14 | 2013-11-13 | 15.02.2014 | 1.9 | 44.6 | 46.5 | 0 | 43.6 | 43.6 | 0 | 43.6 | 43.6 | 100% | 0 | 0 | 0 | 2711.86 | 53.74 | Completed
DIVISION TOTAL |  |  |  |  | 4382 | 4843.94 | 407.92 | 5251.86 |  |  |  |  | 1.9 | 82.8 | 84.45 | 0 | 81.15 | 81.15 | 0 | 81.15 | 81.15 | 100% | 0 | 0 | 0 | 5185.29 | 66.57
CHICKMAGALUR DIVISION
53 | PWD/45/EAP/ 53 | 53a | Improvements to Malpe - Molakalmur SH-65 from km 91.50 to km 114.50 km (In selected reaches) (Koppa & Shringere, Kudregundi, N.R.Pura(Badra Back down) | 65 | 1150.96 | 1286.28 | 127.83 | 1414.11 | S. Sheshagiri | 2012-10-18 | 2013-09-17 | 20.02.2014 | 14 | 2.95 | 16.95 | 12.5 | 6.35 | 18.85 | 12.5 | 6.35 | 18.85 | 100% | 0 | 0 | 0 | 1385 | 29.11 | Completed
|  | 53b | Improvements to Virajpet - Byndoor SH-27 from km 167.45 to km 187.45 (In selected reaches) (Moodigere, Mudigere Taluk Border) | 27 | [8 empty] | 15 | 5 | 20 | 7 | 13 | 20 | 7 | 13 | 20 | 100% | 0 | 0 | 0
54 | PWD/45/EAP/ 54 | 54 | Improvements to Gangamula - Kotigehara SH-66 from km 0.00 to km 89.95 (In selected reaches)(Kudremukha, Kalsa, Magundi, Niduvale, Kotigehra of Mudugere Taluk) | 66 | 2362.36 | 2777.14 | 261.81 | 3038.95 | Amrutha construction | 2013-03-19 | 2014-02-18 | 15.02.2015 | 65.31 | 22.68 | 87.99 | 66.56 | 24.64 | 91.2 | 66.56 | 24.64 | 91.2 | 100% | 0 | 0 | 0 | 2917.62 | 121.33 | Completed
DIVISION TOTAL |  |  |  |  | 3513.32 | 4063.42 | 389.64 | 4453.06 |  |  |  |  | 94.31 | 30.63 | 124.94 | 86.06 | 43.99 | 130.05 | 86.06 | 43.99 | 130.05 | 100% | 0 | 0 | 0 | 4302.62 | 150.44
HASSAN CIRCLE TOTAL |  |  |  |  | 17178.17 | 18707.11 | 1956.35 | 20663.46 |  |  |  |  | 176.7 | 255.3 | 431.75 | 145.89 | 286.98 | 432.87 | 145.89 | 286.981 | 432.871 | 300% | 0 | -0.001 | -0.001 | 20179.81 | 483.65
SHIMOGA SPECIAL DIVISION
55 | PWD/45/EAP/ 55 | 55 | Improvements to Padubidre - Chikkalgudu SH-1 from km 76.80 to km 138.00 (In selected reaches)(Agumbe, Hosuru, Megaravalli, Kalmane, Kaimara, Thirthahalli Town Hosanagara - Thirthahalli Taluk Border) | 1 | 2489.2 | 2930.36 | 191.04 | 3121.4 | Ibrahim Sherieff | 2012-12-25 | 2013-09-24 | 31.05.2013 | 5 | 45.5 | 50.5 | 5.24 | 43.17 | 48.41 | 5.24 | 43.17 | 48.41 | 100% | 0 | 0 | 0 | 3065.32 | 56.08 | Completed
DIVISION TOTAL |  |  |  |  | 2489.2 | 2930.36 | 191.04 | 3121.4 |  |  |  |  | 5 | 45.5 | 50.5 | 5.24 | 43.17 | 48.41 | 5.24 | 43.17 | 48.41 | 100% | 0 | 0 | 0 | 3065.32 | 56.08
SHIMOGA DIVISION
56 | PWD/45/EAP/ 56 | 56 | Improvements to Sirsi - Hosanagar SH-77 from km 28.50 to km 59.16 & km 59.16 to km 87.20 (In selected reaches)(Sampgodu, Sorabatown, Hosbale of Soraba Taluk & Chikkanelluru, Masuru, Sagara town of Sagara Taluk) | 77 | 2375.59 | 2763.25 | 0 | 2763.25 | A.V Patil | 2012-11-08 | 2013-10-07 | 28.02.2014 | 9.6 | 43.78 | 53.38 | 7.76 | 43.72 | 51.48 | 7.76 | 43.72 | 51.48 | 100% | 0 | 0 | 0 | 2718.94 | 44.31 | Completed
57 | PWD/45/EAP/ 57 | 57a | Improvements to Padubidre - Chikkalgudu SH-1 from km 138.00 to km 169.16(In selected reaches) (Billeshwara, Humcha, Rippenpete Belluru, Nouturu of Hosanagara Taluk & Yedehalli of Sagara Taluk) | 1 | 2481.72 | 2917.71 | 169.55 | 3087.26 | G.D Thimappa Sheregar | 2012-11-07 | 2013-10-06 | 31.05.2013 | 0 | 29.16 | 29.16 | 0 | 29.16 | 29.16 | 0 | 29.16 | 29.16 | 100% | 0 | 0 | 0 | 3168.69 | 0 | Completed
|  | 57b | Improvements to Sirsi - Hosanagar SH-77 from km 87.20 to km 115.30 (In selected reaches) (Battemallapa, Maruthipura, Mavinakoppa of Hosanagara Taluk) | 77 | [8 empty] | 7.14 | 16.02 | 23.16 | 7.76 | 16.96 | 24.72 | 7.76 | 16.96 | 24.72 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4857.31 | 5680.96 | 169.55 | 5850.51 |  |  |  |  | 16.74 | 88.96 | 105.7 | 15.52 | 89.84 | 105.36 | 15.52 | 89.84 | 105.36 | 100% | 0 | 0 | 0 | 5887.63 | 44.31
CHITRADURGA DIVISION
58 | PWD/45/EAP/ 58 | 58a | Improvements to Mandya - Hadagali SH-47 from km 207.70 to km 267.30 (In selected reaches) (Yelakoppanahatti, Moduru, Devigenne, Mavinakatte of Hosadurga Taluk & Kelaganakottige, Havinahatti, Holalkere town Chjikjaur Salsu, Sasuluhalli of Holalkere Taluk) | 47 | 2905 | 3173.57 | 302.33 | 3475.9 | A. Balaram reddy | 2012-11-02 | 2013-10-01 | 30.11.2013 | 0 | 40.24 | 40.24 | 0 | 38.562 | 38.562 | 0 | 38.562 | 38.562 | 100% | 0 | 0 | 0 | 3472.55 | 0 | Completed
|  | 58b | Improvements to Kumata - Kadamadagi SH-48 from km 227.20 to km 246.76(In selected reaches) (Vishwanathanahalli, Kutigehalli, B.Durga, Hirekandavadi of Holalkere Taluk) | 48 | [8 empty] | 0 | 15.76 | 15.76 | 0 | 15.941 | 15.941 | 0 | 15.941 | 15.941 | 100% | 0 | 0 | 0
59 | PWD/45/EAP/ 59 | 59 | Improvements to Kumata - Kadamadagi SH-48 from km 246.76 to km348.91 km (In selected reaches) (Bheemasamudra, Haliyuru, Malappanahatti, Chitradurga town, Appajiudyana of Chitradurga Taluk & Belanahalli, Challakere town, Doddari, Purnalli, Naganahalli Challakere - Pavagada Taluk border of Challakere Taluk) | 48 | 3544.5 | 3572.64 | 855.15 | 4427.79 | K. Krishna | 2012-12-27 | 2013-11-26 | 2016-07-31 | 17.73 | 57.86 | 75.59 | 17.78 | 53.86 | 71.64 | 17.78 | 53.86 | 71.64 | 100% | 0 | 0 | 0 | 4256.46 | 171.33 | Completed
60 | PWD/45/EAP/ 60 | 60 | Improvements to Malpe - Molakalmur SH-65 from km 337.95 to km 381.45 (In selected reaches) (Jagaluru, Abhinahalli, Masthihalagummi of Challakere Taluk & Mutigarahalli, Bekuru, Kolasagar, Molakalmuru of Molakalmur Taluk) | 65 | 1429.42 | 1467.52 | 137.73 | 1605.25 | RMN infrastructure Pvt. ltd | 2012-11-14 | 2013-08-13 | 10.09.20145 | 7.1 | 25.32 | 32.42 | 7.1 | 24.464 | 31.564 | 7.1 | 24.464 | 31.564 | 100% | 0 | 0 | 0 | 1488.02 | 117.23 | Completed
DIVISION TOTAL |  |  |  |  | 7878.92 | 8213.73 | 1295.21 | 9508.94 |  |  |  |  | 24.83 | 139.18 | 164.01 | 24.88 | 132.827 | 157.707 | 24.88 | 132.827 | 157.707 | 100% | 0 | 0 | 0 | 9217.03 | 288.56
DAVANAGERE DIVISION
61 | PWD/45/EAP/ 61 | 61a | Improvements to Malpe - Molakalmur SH-65 from km 186.35 to km 338.00 (In selected reaches) (Joladal, Gopanal, Erehalli ,Kashipura camp of Chennagiri Taluk & Karignoor, Adhadi, 7ne Maili Kallu, 6ne Maili kallu, Siramgondanahalli, Davangere town of Davangere Taluk & Mutsur, Siddihalli, Mallapura of Jagalur Taluk) | 65 | 3257.75 | 3492.5 | 868 | 4360.5 | Sharan D Bandi | 2013-03-20 | 2014-02-19 | 31.12.2014 | 7.89 | 43.65 | 51.54 | 0 | 67.29 | 67.29 | 0 | 67.29 | 67.29 | 100% | 0 | 0 | 0 | 4379.99 | 0 | Completed
|  | 61b | Improvements to Mandya - Hadagali SH-47 from km 261.25 to km 278.50 (In selected reaches) (Holalkere-Davangere Taluk Border, Dindanahalli of Davanagere Taluk) | 47 | [8 empty] | 0 | 14.38 | 14.38 | 0 | 14.38 | 14.38 | 0 | 14.38 | 14.38 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 3257.75 | 3492.5 | 868 | 4360.5 |  |  |  |  | 7.89 | 58.03 | 65.92 | 0 | 81.67 | 81.67 | 0 | 81.67 | 81.67 | 100% | 0 | 0 | 0 | 4379.99 | 0
SHIMOGA CIRCLE TOTAL |  |  |  |  | 20109.18 | 22100.21 | 2627.92 | 24728.13 |  |  |  |  | 54.46 | 345.77 | 400.23 | 45.64 | 361.607 | 407.247 | 45.64 | 361.607 | 407.247 | 500% | 0 | 0 | 0 | 24394.76 | 430.94
MANGALORE DIVISION
62 | PWD/45/EAP/ 62 | 62a | Improvements to Mangalore - Athradi SH-67 from km 23.42 to km 36.42 (In selected reaches) (Maravoor, Bajpe, Yekkaru, Kateel, Damaskatte, Elinje, of Mangalore Sub Division) | 67 | 3365.7 | 3902.12 | 584.82 | 4486.94 | Jagadeep D Suvarna | 2013-03-19 | 2014-02-18 | 30.11.2014 | 10.65 | 2.35 | 13 | 10.1 | 2.9 | 13 | 10.1 | 2.9 | 13 | 100% | 0 | 0 | 0 | 4435.08 | 51.86 | Completed
|  | 62b | Improvements to Subramanya - Udupi SH-37 from km 0.00 to km 36.40 (In selected reaches) (Karikamba, Nettana, Maranda, Kokkada of Sullia & Puttur Sub Division) | 37 | [8 empty] | 12.56 | 10.14 | 22.7 | 10.96 | 10.14 | 21.1 | 10.96 | 10.14 | 21.1 | 100% | 0 | 0 | 0
|  | 62c | Improvements to Subramanya - Manjeswara SH-100 from km 28.80 to km 92.92 (In selected reaches) (Karimajalu, Doddadka, Punacha, Kanyana, Vijayadka of Puttur sub division) | 100 | [8 empty] | 18.51 | 35.76 | 54.27 | 15.51 | 35.76 | 51.27 | 15.51 | 35.76 | 51.27 | 100% | 0 | 0 | 0
[5 empty] | 3365.7 | 3902.12 | 584.82 | 4486.94 |  |  |  |  | 41.72 | 48.25 | 89.97 | 36.57 | 48.8 | 85.37 | 36.57 | 48.8 | 85.37 | 100% | 0 | 0 | 0 | 4435.08 | 51.86
63 | PWD/45/EAP/ 63 | 63 | Improvements to Bangalore - Jalsoor SH-85 from km 291.51 to km 335.71 (In selected reaches) (Bisale, Elimale, Doddathota, Sonangiri, Jalsoor of Sulia Sub division) | 85 | 2013 | 2204.99 | 515 | 2719.99 | M/s Iqbal Ahmed Infraproject Pvt Ltd | 2012-11-15 | 2013-10-14 | 31.03.2014 | 9.22 | 33.28 | 42.5 | 9.22 | 33.28 | 42.5 | 9.22 | 33.28 | 42.5 | 100% | 0 | 0 | 0 | 2697.03 | 22.96 | Completed
DIVISION TOTAL |  |  |  |  | 5378.7 | 6107.11 | 1099.82 | 7206.93 |  |  |  |  | 50.94 | 81.53 | 132.47 | 45.79 | 82.08 | 127.87 | 45.79 | 82.08 | 127.87 | 100% | 0 | 0 | 0 | 7132.11 | 74.82
UDUPI DIVISION
64 | PWD/45/EAP/ 64 | 64a | Improvements to Mangalore - Athradi SH-67 from km 36.48 to km 71.01 (In selected reaches) (Sankalkari, Mundkoor, Jantata, Moodbilli of Udupi sub division) | 67 | 1667.68 | 1838.38 | 170.98 | 2009.36 | M/s Iqbal Ahmed Infraproject Pvt Ltd | 2012-11-15 | 2013-10-14 | 14.10.2013 | 14.54 | 8.14 | 22.68 | 11.95 | 9.1 | 21.05 | 11.95 | 9.1 | 21.05 | 100% | 0 | 0 | 0 | 1935.7 | 73.66 | Completed
|  | 64b | Improvements to Subramanya - Udupi SH-37 from km 105.70 to km 150.40 (In selected reaches) (Eedu, Nellikaru, Bajegoli, Kondadi, Palli, Edamaru, Aleyoor, Kaup cross of Karkala sub Division) | 37 | [8 empty] | 22.03 | 10.57 | 32.6 | 18 | 14.9 | 32.9 | 18 | 14.9 | 32.9 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1667.68 | 1838.38 | 170.98 | 2009.36 |  |  |  |  | 36.57 | 18.71 | 55.28 | 29.95 | 24 | 53.95 | 29.95 | 24 | 53.95 | 100% | 0 | 0 | 0 | 1935.7 | 73.66
KODAGU DIVISION
65 | PWD/45/EAP/ 65 | 65a | Improvements to Hunsur - Talacauvery SH-90 from km 61.00 to km 117.50 (In selected reaches) (Kadanga, Nariyandada, Kakkambe, Napoklu, Bhagamandala of Madikeri sub Division) | 90 | 1706.47 | 1926.93 | 192.16 | 2119.09 | M/s Concord Construction | 2012-12-22 | 2013-11-22 | 2014-03-31 | 36.39 | 5 | 41.39 | 29.88 | 12.13 | 42.01 | 29.88 | 12.13 | 42.01 | 100% | 0 | 0 | 0 | 1916.19 | 202.9 | Copmleted
|  | 65b | Improvements to Virajpet - Byndoor SH-27 from km 0.00 to km 100.19(In selected reaches) (Kodalipete, Bydagota, Kumbur, Makkandur, Madikeri, Virajendra pete) | 27 | [8 empty] | 31.54 | 2 | 33.54 | 31.227 | 1.735 | 32.962 | 31.227 | 1.735 | 32.962 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1706.47 | 1926.93 | 192.16 | 2119.09 |  |  |  |  | 67.93 | 7 | 74.93 | 61.107 | 13.865 | 74.972 | 61.107 | 13.865 | 74.972 | 100% | 0 | 0 | 0 | 1916.19 | 202.9
MANGALORE CIRCLE TOTAL |  |  |  |  | 8752.85 | 9872.42 | 1462.96 | 11335.38 |  |  |  |  | 155.44 | 107.24 | 262.68 | 136.847 | 119.945 | 256.792 | 136.847 | 119.945 | 256.792 | 400% | 0 | 0 | 0 | 10984 | 351.38
DAVANAGERE DIVISION
66 | GO No: PWD/121/ EAP/2012 Bangalore, Dt: 19.11.2012 | 66 | Improvements to Kudligere - Kammaragatte Road SH-115 from km 20.00 to km 36.00 (In selected reaches) (Lingapura Holle, Hosahalli camp-1, Vijayapura, Benekanahalli of Honnali Taluk) | 115 | 1626 | 1782.66 | 104.12 | 1886.78 | Manjushri Cons. | 2013-03-20 | 2014-02-19 | 15.02.2015 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 100% | 0 | 0 | 0 | 1844.79 | 41.99 | Completed
|  |  | DIVISION TOTAL |  | 1626 | 1782.66 | 104.12 | 1886.78 |  |  |  |  | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 100% | 0 | 0 | 0 | 1844.79 | 41.99
|  |  | SOUTH ZONE TOTAL |  | 64559.16 | 70478.92 | 8549.72 | 79028.64 |  |  |  |  | 519.66 | 981.23 | 1500.64 | 429.091 | 1034.008 | 1463.099 | 429.091 | 1034.009 | 1463.1 | 1800% | 0 | -0.001 | -0.001 | 77343.86 | 1831.12
|  |  | NORTH & SOUTH ZONE TOTAL |  | 143924.81 | 154178.4 | 16921.704 | 171094.024 |  |  |  |  | 1446.97 | 2123.033 | 3569.753 | 1134.182 | 2269.701 | 3403.883 | 1134.178 | 2269.706 | 3403.884 | 1900% | 0.004 | 0 | -0.001 | 168578.66 | 2784.804
168.8
1185.8
-231.91

## District wise
Phase I Progress District Wise
Sl No | District | No Of Packages | No Of Packages Completed | Improvement in Km | Financial Progress in Lakhs
1 | Kalburgi | 3 | 3 | 156.84 | 9549.37
2 | Bidar | 3 | 3 | 155.03 | 7443.62
3 | Yadgir | 1 | 1 | 60.5 | 2121.38
4 | Bellary | 5 | 5 | 254.669 | 13866.8
5 | Raichur | 4 | 4 | 207.297 | 8903.49
6 | Koppal | 1 | 1 | 53.44 | 2710.98
7 | Dharwad | 2 | 2 | 78.11 | 3949.86
8 | Gadag | 6 | 6 | 281.25 | 15825.67
9 | Haveri | 3 | 3 | 105.99 | 6142.54
10 | Uttar Kannada | 2 | 2 | 133.932 | 2650
11 | Belgaum | 4 | 4 | 284.411 | 9656.52
12 | Vijayapura | 2 | 2 | 122.125 | 5709.01
13 | Bagalkote | 1 | 1 | 47.19 | 2705.56
14 | Davanagere | 2 | 2 | 95.77 | 6224.78
15 | Chitradurga | 3 | 3 | 157.707 | 9217.03
16 | Shimoga | 3 | 3 | 153.77 | 8952.95
17 | Bangalore | 0 | 0 | 0 | 0
18 | C B pura | 0 | 0 | 0 | 0
19 | Ramanagara | 1 | 1 | 43.39 | 2068.46
20 | Kolar | 1 | 1 | 41.182 | 2972.56
21 | Tumkur | 1 | 1 | 30.57 | 2390.57
22 | Mandya | 3 | 3 | 153.493 | 6904.68
23 | Mysore | 3 | 3 | 97.555 | 7449.02
24 | Chamarajnagar | 0 | 0 | 0 | 0
25 | Udupi | 1 | 1 | 53.95 | 1935.7
26 | Kodagu | 1 | 1 | 74.972 | 1916.19
27 | Dakishna Kannada | 2 | 2 | 127.87 | 7132.11
28 | Chickmagaluru | 2 | 2 | 130.05 | 4302.62
29 | Hassan | 6 | 6 | 302.821 | 15877.19
TOTAL |  | 66 | 66 | 3403.884 | 168578.66

## Progress Report Phase-I (3)
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE
SHDP - PHASE - I PACKAGES
2021-12-30
Sl. No. | Admini- strative approval No. | Pkg No | Details of packages | SH No. | Estimate Amount as per Administrative approval (Rs. in lakhs) | Contract Amount (Rs. in lakhs) | Variation Amount (Rs. in lakhs) | Revised Contract Amount including VO (Rs. in lakhs) | Name of the Contractor | Date |  |  | Length As per DPR in km |  |  | Length after VO in km |  |  | Physical Progress |  |  |  | Balance Length |  |  | Financial Progress |  | Remarks
[10 empty] | Commencement | Completion | Revised | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Renewal (km) | Improvements (km) | Total Length Completed (in km) | % Progress | Renewal (km) | Improvements(km) | Total Length (in km) | Total (Rs. In Lakhs) | Financial Progress To Be Achived (Rs. In lakhs)
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 10 | 11 | 12 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
NORTH ZONE
DHARWAD DIVISION
1 | PWD/ 45/EAP/01 | 1 | Improvements to Padubidri -Chikkalgudda SH - 01 from km 318.50 to km 356.96 (In selected reaches) (Tabakadahonnahalli, Devalingikoppa of Kalaghatagi Taluk) | 1 | 1926.67 | 1609.73 | 215.09 | 1824.82 | M/s N.S.Nayak & Sons | 02.11.2012 | 02.10.2013 | 26.12.2013 | 0 | 35.25 | 35.25 | 0 | 35.25 | 35.25 | 0 | 35.25 | 35.25 | 100% | 0 | 0 | 0 | 1890.98 | 0 | Completed
2 | PWD/ 45/EAP/02 | 2a | Improvements to Kalmala Shiggaon SH - 23 from km 273.61 to km 284.51(In selected reaches) (Railway Gate to Savanur, Taluka Border of Kundagol Taluk) | 23 | 2134.94 | 1929.66 | 53.5 | 1983.16 | N.S.Nayak | 02.11.2012 | 02.10.2013 | 13.11.2013 | 7.9 | 3 | 10.9 | 0 | 2.91 | 2.91 | 0 | 2.91 | 2.91 | 100% | 0 | 0 | 0 | 2058.88 | 0 | Completed
|  | 2b | Improvements to Navalgund - Banavasi SH - 137 from km 4.90 to km 18.30(In selected reaches) (Navalgunda to Annigeri of Navalgunda Taluk) | 137 | [8 empty] | 0 | 13.4 | 13.4 | 0 | 13.8 | 13.8 | 0 | 13.8 | 13.8 | 100% | 0 | 0 | 0
|  | 2c | Improvements to Supa - Annigeri SH - 28from km 41.31 to km 68.42(In selected reaches) (Mavinkoppa Checkpost to Dharwad via Nigadi of Dharwad Taluk) | 28 | [8 empty] | 10.82 | 16.29 | 27.11 | 9.68 | 16.47 | 26.15 | 9.68 | 16.47 | 26.15 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4061.61 | 3539.39 | 268.59 | 3807.98 |  |  |  |  | 18.72 | 67.94 | 86.66 | 9.68 | 68.43 | 78.11 | 9.68 | 68.43 | 78.11 | 100% | 0 | 0 | 0 | 3949.86 | 0
GADAG DIVISION
3 | PWD/ 45/EAP/03 | 3 | Improvements to Karwar - Ilkal SH - 06 from km 199.73 to km 271.60(In selected reaches) (Laxmeshwar, Magadi, Gadag of Gadag Taluk) | 6 | 3066.49 | 2915.69 | 164.69 | 3080.38 | P.R.Nayak | 18.10.2012 | 18.09.2013 | 26.06.2013 | 23.59 | 47.07 | 70.66 | 23.59 | 47.27 | 70.86 | 23.59 | 47.27 | 70.86 | 100% | 0 | 0 | 0 | 3050.1 | 30.28 | Completed
4 | PWD/ 45/EAP/04 | 4 | Improvements to Karwar - Ilkal SH-06 from km 271.60 to km 310.81(In selected reaches) (Naregal, Gajendraghada of Ron Taluk) | 6 | 1806.23 | 1875.02 | 94.14 | 1969.16 | B.S.Gaonkar | 10.01.2013 | 10.12.2013 | 28.02.2014 | 6.65 | 30.67 | 37.32 | 8.4 | 24.6 | 33 | 8.4 | 24.6 | 33 | 100% | 0 | 0 | 0 | 1977.29 | 0 | Completed
5 | PWD/ 45/EAP/05 | 5a | Improvements to Sindhnur - Hemmadga SH - 30 from km 117.80 to km149.00 (In selected reaches) (Belavanaki,Yavagal in Naragund & Ron Taluk) | 30 | 1748.83 | 1978.15 | 242.4 | 2220.55 | B.Thirupathi.Reddy | 20.10.2012 | 20.09.2013 | 29.07.2013 | 17.2 | 14 | 31.2 | 17.2 | 11.6 | 28.8 | 17.2 | 11.6 | 28.8 | 100% | 0 | 0 | 0 | 2251.55 | 0 | Completed
|  | 5b | Improvements to Raravi - Belur SH - 63 from km 160.20 to km185.70 (In selected reaches) (Mushigeri in Ron Taluk) | 63 | [8 empty] | 17.05 | 6 | 23.05 | 17.7 | 5.6 | 23.3 | 17.7 | 5.6 | 23.3 | 100% | 0 | 0 | 0
6 | PWD/ 45/EAP/06 | 6 | Improvements to Munavalli - Kotamuchagi SH-83 from km 63.14 to km104.50 (In selected reaches) (Mensigi, Holehalur of Naragund & Ron Taluk) | 83 | 2144.97 | 2347.41 | 348.23 | 2695.64 | N.B.Hiremath | 26.02.2013 | 25.01.2014 | 24.01.2014 | 6 | 35.36 | 41.36 | 6 | 35.36 | 41.36 | 6 | 35.36 | 41.36 | 100% | 0 | 0 | 0 | 2706.84 | 0 | Completed
7 | PWD/ 45/EAP/07 | 7 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 126.51 to km 167.89 (In selected reaches) (Shirahatti, Belatti of Shirahatti Taluk) | 57 | 2168 | 2499.41 | 372.65 | 2872.06 | N.S.Nayak | 13.03.2013 | 12.02.2014 | 12.02.2014 | 0 | 41.38 | 41.38 | 0.3 | 41.08 | 41.38 | 0.3 | 41.08 | 41.38 | 100% | 0 | 0 | 0 | 2900.44 | 0 | Completed
8 | PWD/ 45/EAP/08 | 8 | Improvements to Bagalkote - Biligiriranganbetta SH-57 from km 72.27 to km 126.51 (In selected reaches) (Betageri , Beladatti of Ron & Gadag Taluks) | 57 | 2249.1 | 2449.94 | 509.75 | 2959.69 | N.B.Hiremath | 01.03.2013 | 01.02.2014 | 13.12.2014 | 0 | 44.51 | 44.51 | 0 | 42.55 | 42.55 | 0 | 42.55 | 42.55 | 100% | 0 | 0 | 0 | 2939.45 | 20.24 | Completed
DIVISION TOTAL |  |  |  |  | 13183.62 | 14065.62 | 1731.86 | 15797.48 |  |  |  |  | 70.49 | 218.99 | 289.48 | 73.19 | 208.06 | 281.25 | 73.19 | 208.06 | 281.25 | 100% | 0 | 0 | 0 | 15825.67 | 50.52
HAVERI DIVISION
9 | PWD/ 45/EAP/09 | 9a | Improvements to Ekkumbi - MolkalmurSH-02 from km 8.20 to km 88.49 (In selected reaches) (From Dasanakoppa cross to Hangal crosss & Agadi, Basapur up to Guttal of Hangal & Haveri Taluk | 2 | 2161.68 | 2542.44 | 220.68 | 2763.12 | A.V.Patil | 28.02.2013 | 27.01.2014 | 25.01.2014 | 23.83 | 10.47 | 34.3 | 22.65 | 10.92 | 33.57 | 22.65 | 10.92 | 33.57 | 100% | 0 | 0 | 0 | 2725.45 | 37.67 | Completed
|  | 9b | Improvements to Haveri - Sagar SH - 62 from km 9.63 to km 57.20 (In selected reaches) (Kagineli, Hamsabhavi of Byadagi & Hirekerur Taluk) | 62 | [8 empty] | 4.8 | 17.86 | 22.66 | 0 | 15.26 | 15.26 | 0 | 15.26 | 15.26 | 100% | 0 | 0 | 0
10 | PWD/ 45/EAP/10 | 10 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 196.72 to km 236.83 (In selected reaches) (Ranebennur, Haligeri of Ranebennur Taluk) | 57 | 1434.02 | 1609.55 | 144.25 | 1753.8 | S.R.Bellary | 17.10.2012 | 17.09.2013 | 03.11.2013 | 0 | 25.83 | 25.83 | 0 | 26.06 | 26.06 | 0 | 26.06 | 26.06 | 100% | 0 | 0 | 0 | 1750.33 | 3.47 | Completed
11 | PWD/ 45/EAP/11 | 11 | Improvements to Birur - Sammasagi SH-76 from km 125.01 to km 189.00 (In selected reaches) (Haligeri, koda of Ranebennuru & Hirekerur Taluk) | 76 | 1452.21 | 1616.25 | 98.97 | 1715.22 | S.R.Bellary | 17.10.2012 | 17.09.2013 | 16.11.2013 | 6.14 | 24.95 | 31.09 | 6.12 | 24.98 | 31.1 | 6.12 | 24.98 | 31.1 | 100% | 0 | 0 | 0 | 1666.76 | 48.46 | Completed
DIVISION TOTAL |  |  |  |  | 5047.91 | 5768.24 | 463.9 | 6232.14 |  |  |  |  | 34.77 | 79.11 | 113.88 | 28.77 | 77.22 | 105.99 | 28.77 | 77.22 | 105.99 | 100% | 0 | 0 | 0 | 6142.54 | 89.6
SIRSI DIVISION
12 | PWD/ 45/EAP/12 | 12a | Improvements to Kumta - Tadas SH - 69 from km 0.00 to km 27.15(In selected reaches)(from kumta to Sirsi Taluk Border via Alkod of Karwar Taluk) | 69 | 1207.5 | 1075.97 | 183.74 | 1259.71 | Ramashree Global Construction | 16.10.2012 | 16.09.2013 | 30.04.2014 | 16.4 | 1.6 | 18 | 16.4 | 1.6 | 18 | 16.4 | 1.6 | 18 | 100% | 0 | 0 | 0 | 1259.94 | -0.23 | Completed
|  | 12b | Improvements to Karwar Kaiga Ilkal SH-06 from km 0.50 to km 69.40(In selected reaches)(Shirwadi, Wailwadi of Karwar Taluk) | 6 | [8 empty] | 41.25 | 0 | 41.25 | 25.95 | 15.15 | 41.1 | 25.95 | 15.15 | 41.1 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1207.5 | 1075.97 | 183.74 | 1259.71 |  |  |  |  | 57.65 | 1.6 | 59.25 | 42.35 | 16.75 | 59.1 | 42.35 | 16.75 | 59.1 | 100% | 0 | 0 | 0 | 1259.94
KARWAR DIVISION | [18 empty] | 0 | 0
13 | PWD/ 45/EAP/13 | 13a | Improvements to Kumta Tadas SH-69 from km 40.00 to km 83.70 (In selected reaches) (Sirsi,Isloor of Sirsi Taluk) | 69 | 1717.28 | 1494.82 | 0 | 1494.82 | N.S.Nayak | 16.10.2012 | 17.06.2013 | 17.06.2013 | 22 | 6.54 | 28.54 | 24.59 | 2.47 | 27.06 | 24.59 | 2.47 | 27.06 | 100% | 0 | 0 | 0 | 1390.06 | 104.76 | Completed
|  | 13b | Improvements to Karwar - Kaiga - Ilkal SH-06 from km 69.40 to km125.80 (In selected reaches) (Idagundi, Yellapur Taluk) | 6 | [8 empty] | 29.64 | 17.86 | 47.5 | 29.64 | 18.13 | 47.77 | 29.64 | 18.132 | 47.772 | 100% | 0 | -0.002 | -0.002
DIVISION TOTAL |  |  |  |  | 1717.28 | 1494.82 | 0 | 1494.82 |  |  |  |  | 51.64 | 24.4 | 76.04 | 54.23 | 20.6 | 74.83 | 54.23 | 20.602 | 74.832 | 100% | 0 | -0.002 | -0.002 | 1390.06 | 104.76
DHARWAD CIRCLE TOTAL |  |  |  |  | 25217.92 | 25944.04 | 2648.09 | 28592.13 |  |  |  |  | 233.27 | 392.04 | 625.31 | 208.22 | 391.06 | 599.28 | 208.22 | 391.062 | 599.282 | 100% | 0 | -0.002 | -0.002 | 28568.07 | 244.88
BELAGAVI CIRCLE
BELAGAVI DIVISION
14 | PWD/ 45/EAP/14 | 14a | Improvements to Khanapur - Talaguppa SH - 93 from km 0.00 to km 34.58 (In selected reaches) (Khanapur of Kahanapur Taluk) | 93 | 2266.02 | 2212.08 | -7.17 | 2204.91 | M/s. P.R. Nayak. Hubli | 2012-10-12 | 2013-09-11 | 24.05.2013 | 31.57 | 1.456 | 33.026 | 33.03 | 0 | 33.03 | 33.03 | 0 | 33.03 | 100% | 0 | 0 | 0 | 2220.59 | 0 | Completed
|  | 14b | Improvements to Yargatti - Babaleshwar SH-55 from km 7.50 to km 28.46(In selected reaches) (Yaragalli, Sattigeri,Savadatti, Itnal, Hulkund of Ramadurga Taluk) | 55 | [8 empty] | 0 | 20.96 | 20.96 | 0 | 20.96 | 20.96 | 0 | 20.96 | 20.96 | 100% | 0 | 0 | 0
|  | 14c | Improvements to of Jamboti - Rabkavi SH - 54 from km 29.74 to km 54.28.(In selected reaches) (Belgaum, Kanbargi, Muchhandi, Suldhal, Tumarguddi, Hudli of Belgaum Taluk) | 54 | [8 empty] | 7.2 | 7.85 | 15.05 | 9.857 | 8.884 | 18.741 | 9.857 | 8.884 | 18.741 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2266.02 | 2212.08 | -7.17 | 2204.91 |  |  |  |  | 38.77 | 30.266 | 69.036 | 42.887 | 29.844 | 72.731 | 42.887 | 29.844 | 72.731 | 100% | 0 | 0 | 0 | 2220.59 | 0
CHIKKODI DIVISION
15 | PWD/ 45/EAP/15 | 15a | Improvements to Padubidri - Chikklagudda SH-01 from km 478.77 to km 497.35 (In selected reaches) (Hosur, Yaragatti, Badkundri cross, Kurni Chikkalgudda of Hukkeri Taluk) | 1 | 2144.97 | 2464.85 | 174.28 | 2639.13 | R.S.Patil | 06.02.2013 | 05.01.2014 | 30.04.2014 | 12 | 4 | 16 | 12 | 4 | 16 | 12 | 4 | 16 | 100% | 0 | 0 | 0 | 2646.71 | -7.58 | Completed
|  | 15b | Improvements to Jath - Jamboti SH-31 from km 0.00 to km 116.82 (In selected reaches) (Anantpur, Malabad, Parthanalli & Gokak cross, Kolavi, Vannur of Athani Taluk) | 31 | [8 empty] | 20 | 0 | 20 | 20 | 10 | 30 | 20 | 10 | 30 | 100% | 0 | 0 | 0
|  | 15c | Improvements to Kagawad Kaladagi SH-53 from km0.00 to km15.70(In selected reaches) (Kagwad, Shedbal, UgarBK, Ughar Kurd of Athani Taluk) | 53 | [8 empty] | 9.85 | 0 | 9.85 | 9.78 | 0 | 9.78 | 9.78 | 0 | 9.78 | 100% | 0 | 0 | 0
|  | 15d | Improvements to Mangasuli Laxmeshwar SH-73 from km 79.03 to km114.80 (In selected reaches) (Ghataprabha, Konnur, Mavanur, Godchinmalki, Pachhapur, Akkatangerhal of Gokak Taluk) | 73 | [8 empty] | 16.98 | 9.11 | 26.09 | 15.56 | 11.12 | 26.68 | 15.56 | 11.12 | 26.68 | 100% | 0 | 0 | 0
16 | PWD/ 45/EAP/16 | 16 | 16(a)Improvements to Nippani - Kottalagi SH-72 from km 0.00 to km 67.45 (Excluding from km 57.20 to km 58.18 ) (In selected reaches) (Madalga, Shippur & Nippani, Galataga, Nej ,Nandi,Examba, Kallol, Manjri, Shriguppi of Athani Taluk) | 72 | 1628.29 | 1876.92 | -0.236 | 1876.684 | P.Wantamutte | 22.02.2013 | 01.01.2014 | 31.12.2013 | 49.85 | 14.847 | 64.697 | 28.43 | 30.772 | 59.202 | 28.43 | 30.77 | 59.2 | 100% | 0 | 0.002 | 0.002 | 1873.21 | 3.474 | Completed
|  |  | 16(b)Improvements to Madalaga - ShippurSH-72 from km 0.00 to km 12.00 (In selected reaches) | [19 empty] | 0 | 0
17 | PWD/ 45/EAP/17 | 17 | Improvements to Nippani - Kottalagi SH-72 from km 57.20 to km 58.18 & km 67.45 to km 151.81 (In selected reaches) (Shriguppi, Molwad, Kusnal, Ugar BK, UgarKH of Athani Taluk) | 72 | 2201.28 | 2678.34 | 441.77 | 3120.11 | S.S.Alur | 06.10.2012 | 05.10.2013 | 31.12.2013 | 47.99 | 22 | 69.99 | 42.98 | 27.04 | 70.02 | 42.98 | 27.04 | 70.02 | 100% | 0 | 0 | 0 | 2916.01 | 0 | Completed
DIVISION TOTAL |  |  |  |  | 5974.54 | 7020.11 | 615.814 | 7635.924 |  |  |  |  | 156.67 | 49.957 | 206.627 | 128.75 | 82.932 | 211.682 | 128.75 | 82.93 | 211.68 | 100% | 0 | 0.002 | 0.002 | 7435.93 | -4.106
BAGALKOT DIVISION
18 | PWD/ 45/EAP/18 | 18a | Improvements to Bagalkot - Biligiriranganabetta SH-57 from km0.00 to km 29.38 (In selected reaches)(Bagalkote , Sulekere, Katageri, Badami of Badami Taluk) | 57 | 2342.33 | 2478.84 | 246.18 | 2725.02 | Haigreevea Construction | 08.10.2012 | 07.10.2013 | 30.4.2014 | 9.14 | 20.24 | 29.38 | 0 | 29.38 | 29.38 | 0 | 29.38 | 29.38 | 100% | 0 | 0 | 0 | 2705.56 | 19.46 | Completed
|  | 18b | Improvements to Yaragatti - Babaleshwar S.H.55 from km 42.41 to km 44.91 km 78.79 (In selected reaches) (Mudhol, Amalzari, Balgali of Badami Taluk) | 55 | [8 empty] | 0 | 17 | 17 | 0 | 17.81 | 17.81 | 0 | 17.81 | 17.81 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2342.33 | 2478.84 | 246.18 | 2725.02 |  |  |  |  | 9.14 | 37.24 | 46.38 | 0 | 47.19 | 47.19 | 0 | 47.19 | 47.19 | 100% | 0 | 0 | 0 | 2705.56 | 19.46
BIJAPUR DIVISION
19 | PWD/ 45/EAP/19 | 19a | Improvements to Shiradan - Lingasur SH-41from km 0.00 to km 71.43 (In selected reaches) (Shirdon, Chadchan, Zalki, Indi of Indi Taluk) | 41 | 2814 | 2736.37 | 139.88 | 2876.25 | S.M.Authade | 26.10.2012 | 25.10.2013 | 18.05.2013 | 0.61 | 26.23 | 26.84 | 0 | 30.04 | 30.04 | 0 | 30.04 | 30.04 | 100% | 0 | 0 | 0 | 2882.39 | -6.14 | Completed
|  | 19b | Improvements to Shiradan - Lingasur SH-41 from km 71.43 to km 100.73(In selected reaches) (Roog, Devaripurgi of Indi Taluk) | 41 | [8 empty] | 0 | 26.15 | 26.15 | 0 | 26.15 | 26.15 | 0 | 26.15 | 26.15 | 100% | 0 | 0 | 0
20 | PWD/ 45/EAP/20 | 20a | Improvements to Shiradan - Lingasur SH-41 from km 100.73 to km131.18 (In selected reaches) (Shirdon, Basavanbagewadi cross, of Muddebihal Taluk) | 41 | 2404 | 2577.82 | 227.56 | 2805.38 | S.S.Alur | 19.10.2012 | 18.10.2013 | 06.05.2013 | 0 | 24.45 | 24.45 | 0 | 24.115 | 24.115 | 0 | 24.115 | 24.115 | 100% | 0 | 0 | 0 | 2826.62 | 0 | Completed
|  | 20b | Improvements to Shiradan - Lingasur SH-41 from km131.18 to km 176.78 (In selected reaches) (Nalatwad, Muddebihal of Muddebihal Taluk) | 41 | [8 empty] | 21.88 | 16.29 | 38.17 | 6.25 | 35.57 | 41.82 | 6.25 | 35.57 | 41.82 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 5218 | 5314.19 | 367.44 | 5681.63 |  |  |  |  | 22.49 | 93.12 | 115.61 | 6.25 | 115.875 | 122.125 | 6.25 | 115.875 | 122.125 | 100% | 0 | 0 | 0 | 5709.01 | -6.14
BELAGAVI CIRCLE TOTAL |  |  |  |  | 15800.89 | 17025.22 | 1222.264 | 18247.484 |  |  |  |  | 227.07 | 210.583 | 437.653 | 177.887 | 275.841 | 453.728 | 177.887 | 275.839 | 453.726 | 100% | 0 | 0.002 | 0.002 | 18071.09 | 9.214
BELLARY CIRCLE
BELLARY DIVISION
21 | PWD/ 45/EAP/21 | 21 | Improvements to Kampli - Bellary SH-132 from km 0.00 to km 69.20 (In selected reaches) (Kampli town, Nilludi Kottayal, Emmiganur of Hospet Taluk & Kurugodu, Siddammanahalli, Badanhatti, Kudutini, Hariginadoni, Belagal& Bellary city limit of Bellary Taluk) | 132 | 2766 | 3042.53 | 135.88 | 3178.41 | Prabhakar Reddy | 12.03.13 | 11.02.14 | 30.06.2014 | 25.3 | 43.79 | 69.09 | 16.384 | 45.22 | 61.604 | 16.384 | 45.22 | 61.604 | 100% | 0 | 0 | 0 | 3114.94 | 63.47 | Completed
22 | PWD/ 45/EAP/22 | 22a | Improvements to Shiraguppa - Sandur SH-49 from km 27.00 to kmb 73.73 & SH-25 from km 0.00 to km 2.60 (In selected reaches) (Mallappana Gudi, Kamalapur, Bukka Sagara, Ramasagara, Kampli, Sanapura in Hospet Taluk) | 49 & 25 | 2414.1 | 2653.24 | 260.4 | 2913.64 | Rajshekhar (Swamy Constructions) | 31.10.2013 | 2016-01-25 | 2016-01-25 | 3.4 | 23.63 | 27.03 | 0 | 21.32 | 21.32 | 0 | 21.32 | 21.32 | 100% | 0 | 0 | 0 | 2921.45 | -7.81 | Completed
|  | 22b | Improvements to Shirguppa - Sandur SH-49 from km 73.73 to km 106.23 (In selected reaches) (Manur Sugur, Nadivi in Siraguppa Taluk) | 49 | [8 empty] | 0 | 14.76 | 14.76 | 0 | 9.17 | 9.17 | 0 | 9.17 | 9.17 | 100% | 0 | 0 | 0
23 | PWD/ 45/EAP/23 | 23a | Improvements to Hampi - Hagaribommanahalli SH-131 from km 0.00 to km 22.70 (In selected reaches) (Hampi, Kamalapura, Kakubal in Hospet Taluk) | 131 | 2937 | 2951.09 | 259.64 | 3210.73 | P.R.Nayak | 25.10.12 | 24.09.13 | 31.05.2014 | 6.2 | 12.9 | 19.1 | 1.904 | 14.365 | 16.269 | 1.904 | 14.365 | 16.269 | 100% | 0 | 0 | 0 | 3168.9 | 41.83 | Completed
|  | 23b | Improvements to Hampi - Hagaribommanahalli SH-131from km 22.70 to km 73.20 (In selected reaches) (Talur, Ubbalagundi, Rajapur, Metriki in Sandur Taluk) | 131 | [8 empty] | 9 | 35.93 | 44.93 | 5.172 | 39.544 | 44.716 | 5.172 | 39.544 | 44.716 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 8117.1 | 8646.86 | 655.92 | 9302.78 |  |  |  |  | 43.9 | 131.01 | 174.91 | 23.46 | 129.619 | 153.079 | 23.46 | 129.619 | 153.079 | 100% | 0 | 0 | 0 | 9205.29 | 97.49
HADAGALI DIVISION
24 | PWD/ 45/EAP/24 | 24a | Improvements to Mylar - Toranagal SH-40 from km 0.0 to km 97.33 (In selected reaches) (Holallu, Badanuru, Giriyapura, Hirehadagali, Haganuru, Thippapura, Huvinahadagali of Hadagali Taluk & Hampa sagara, Basapura, H.B.Halli, Anekallu, Basapura Thanda, Hosakere, Hansi in H.B.Halli Taluk) | 40 | 1878 | 1995.25 | 195.25 | 2190.5 | Rammohan Reddy | 19.12.2013 | 18.11-2014 | 2016-03-31 | 30.25 | 23.47 | 53.72 | 27 | 25.12 | 52.12 | 27 | 25.12 | 52.12 | 100% | 0 | 0 | 0 | 2191.54 | -1.04 | Completed
|  | 24b | Improvements to Mylar - Torangal SH-40 from km 104.00 to km 109.00 (In selected reaches) (Kudligi Town inKudligi Taluk) | 40 | [8 empty] | 0 | 3.85 | 3.85 | 0 | 2.95 | 2.95 | 0 | 2.95 | 2.95 | 100% | 0 | 0 | 0
25 | PWD/ 45/EAP/25 | 25a | Improvements to Hampi - Hagaribommanhalli SH-131from km 96.45 to km 137.00(In selected reaches)(Appena Halli, Appena Hall Thanda, Mahadevapura, Gudekote, Ramadurga Cross, C.J.Halli in Kudligi Taluk) | 131 | 2298 | 2393.23 | 128.1 | 2521.33 | K.Krishna | 18.10.12 | 17.09.13 | 30.07.2014 | 0 | 26.61 | 26.61 | 0 | 26.7 | 26.7 | 0 | 26.7 | 26.7 | 100% | 0 | 0 | 0 | 2469.97 | 51.36 | Completed
|  | 25b | Improvements to Hampi -Hagaribommanhalli SH-131 from km 187.92 to km 198.75 (In selected reaches) (H.B.Halli, Chintara palli in H.B.Halli Taluk) | 131 | [8 empty] | 2.1 | 4.09 | 6.19 | 2.35 | 3.95 | 6.3 | 2.35 | 3.95 | 6.3 | 100% | 0 | 0 | 0
|  | 25c | Improvements to Arabhavi - Challakere SH-45 from km 239.00 to km 261.02 (In Selected reaches) (Kottur, Kaalapur, Ujjini, Lakkampura in Kudligi Taluk) | 45 | [8 empty] | 0 | 13.42 | 13.42 | 0 | 13.52 | 13.52 | 0 | 13.52 | 13.52 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4176 | 4388.48 | 323.35 | 4711.83 |  |  |  |  | 32.35 | 71.44 | 103.79 | 29.35 | 72.24 | 101.59 | 29.35 | 72.24 | 101.59 | 100% | 0 | 0 | 0 | 4661.51 | 50.32
RAICHUR DIVISION
26 | PWD/ 45/EAP/26 | 26a | Improvements to Mudhol - Yeragera SH-127 from km 134.91 to km 177.24 (In selected reaches) (Attunur, Kudri, Aroli, Purtipalli in Manvi Taluk) | 127 | 2114 | 2005.47 | 184.96 | 2190.43 | Shankar Kotarki | 05.11.12 | 04.10.13 | 30.06.2014 | 14.82 | 16.07 | 30.89 | 10.664 | 20.092 | 30.756 | 10.664 | 20.092 | 30.756 | 100% | 0 | 0 | 0 | 2117.51 | 72.92 | Completed
|  | 26b | Improvements to Mudhol - Yeragera SH - 127 from km 177.24 to km 207.96 (In selected reaches) (Gujhali, Yeragera, Jambaladinni in Raichur Taluk) | 127 | [8 empty] | 15.3 | 11.31 | 26.61 | 10.265 | 14.096 | 24.361 | 10.265 | 14.096 | 24.361 | 100% | 0 | 0 | 0
27 | PWD/ 45/EAP/27 | 27a | Improvements to Deodurg - Bellary SH - 128 from km 21.00 to km 76.24 (In selected reaches) (Chinchirki, K Thimmapura, Hussain pura, Hire Hanagi, Bhogavathi, Bagalvada, Hirekottankal, Chikkotnakalin Manvi Taluk) | 128 | 2374 | 2305.32 | 200.92 | 2506.24 | Jagadeeswarudu Chilukuri (M/s Haigreeva Infratech Pvt. Ltd) | 05.11.12 | 30.09.2014 | 31.03.2015 | 18.64 | 29.57 | 48.21 | 16.548 | 23.317 | 39.865 | 16.548 | 23.317 | 39.865 | 100% | 0 | 0 | 0 | 2512.42 | -6.18 | Completed
|  | 27b | Improvements to Deodurg - Bellary SH - 128 from km 0.00 to km 21.00 (In selected reaches)(Mundargi, Galag in Deodurga Taluk) | 128 | [8 empty] | 9.9 | 6.6 | 16.5 | 6.7 | 8.21 | 14.91 | 6.7 | 8.21 | 14.91 | 100% | 0 | 0 | 0
28 | PWD/ 45/EAP/28 | 28a | Improvements to Wanmarpalli - Raichur SH-15 from km 332.05 to km 346.29 (In selected reaches) (Raichur town limit, Singanodi in Raichur Taluk) | 15 | 1770.4 | 1951.97 | 292.13 | 2244.1 | P.Ramarao (Patel Engineering) | 19.10.12 | 18.09.13 | 31.10.2014 | 6.25 | 7.99 | 14.24 | 5.527 | 8.548 | 14.075 | 5.527 | 8.548 | 14.075 | 100% | 0 | 0 | 0 | 2202.56 | 41.54 | Completed
|  | 28b | Improvements to Managuli - Bichal SH - 61from km 161.00 to km 191.87 (In selected reaches) (Kottadoddi, Arkera, Jagir Jadaladinni, of Deodurga Taluk & Siravara inManvi Taluk) | 61 | [8 empty] | 13.07 | 17.8 | 30.87 | 9.55 | 21.325 | 30.875 | 9.55 | 21.325 | 30.875 | 100% | 0 | 0 | 0
29 | PWD/ 45/EAP/29 | 29a | Improvements to Raravi- Belur SH - 63 from km 32.50 to km 44.98 (In selected reaches)(Salgunda, Gorebal in Sindanur Taluk) | 63 | 1925.5 | 2140.59 | 64.25 | 2204.84 | P.Ramarao (Patel Engineering) | 12.03.13 | 11.02.14 | 30.11.2014 | 0 | 12.48 | 12.48 | 0 | 12.48 | 12.48 | 0 | 12.48 | 12.48 | 100% | 0 | 0 | 0 | 2071 | 133.84 | Completed
|  | 29b | Srirangapatna Jewargi SH -19 from km 477.00 to km 505.00 (In selected reaches)(Lingasugur, Gurugunta in Lingasugur Taluk) | 19 | [8 empty] | 28 | 0 | 28 | 28 | 0 | 28 | 28 | 0 | 28 | 100% | 0 | 0 | 0
|  | 29c | Improvements to Managuli -Bichal SH -61 from km 239.03 to km 251.05 (In selected reaches) (Gillesuguru in Raichur Taluk) | 61 | [8 empty] | 0 | 12.03 | 12.03 | 0 | 11.975 | 11.975 | 0 | 11.975 | 11.975 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 8183.9 | 8403.35 | 742.26 | 9145.61 |  |  |  |  | 105.98 | 113.85 | 219.83 | 87.254 | 120.043 | 207.297 | 87.254 | 120.043 | 207.297 | 100% | 0 | 0 | 0 | 8903.49 | 242.12
KOPPAL DIVISION
30 | PWD/ 45/EAP/30 | 30 | Improvements to Kalmala - Shiggaon SH -23 from km 162.45 to km 203.58 & Ginigera - Gondabal MDR from km 4.57 to km 20.90 (In selected reaches) (Ginigera, Basavapura, koppal town limit, Chikkasindagi, Hiresindagi, Hatti, Billi Gatta in Koppal Taluk) | 23 & MD R | 2258 | 2464.93 | 244.04 | 2708.97 | Sai Constructions | 16.10.12 | 15.09.13 | 31.03.2014 | 26.04 | 29.09 | 55.13 | 16.98 | 36.46 | 53.44 | 16.98 | 36.46 | 53.44 | 100% | 0 | 0 | 0 | 2710.98 | 0 | Completed
DIVISION TOTAL |  |  |  |  | 2258 | 2464.93 | 244.04 | 2708.97 |  |  |  |  | 26.04 | 29.09 | 55.13 | 16.98 | 36.46 | 53.44 | 16.98 | 36.46 | 53.44 | 100% | 0 | 0 | 0 | 2710.98 | 0
BELLARY CIRCLE TOTAL |  |  |  |  | 22735 | 23903.62 | 1965.57 | 25869.19 |  |  |  |  | 208.27 | 345.39 | 553.66 | 157.044 | 358.362 | 515.406 | 157.044 | 358.362 | 515.406 | 100% | 0 | 0 | 0 | 25481.27 | 389.93
GULBARGA CIRCLE
GULBARGA DIVISION
31 | PWD/ 45/EAP/31 | 31 | Improvements to Mahagaon - Sulepeth SH - 32 from km 70.42 to km 118.00 (In selected reaches) (Mahagaon of Gulbarga Taluk& Ratkal,Kodli, Sulepet of Chincholli Taluk) | 32 | 2486 | 2904.53 | 725.44 | 3629.97 | M/s Shankar Kotarki | 2012-10-30 | 2013-09-29 | 30.06.2015 | 0 | 47.58 | 47.58 | 0 | 47.58 | 47.58 | 0 | 47.58 | 47.58 | 100% | 0 | 0 | 0 | 3568.71 | 61.26 | Completed
32 | PWD/ 45/EAP/32 | 32a | Improvements to Gulbarga - Jewargi - Sindagi MDR via Chigaralli cross joining Yadrami from km 0.00 to km 52.00 (In selected reaches)(Chigaralli , Yedrami of Jewargi Taluk) | MDR | 3144 | 3158.78 | 271.22 | 3430 | M/sKPC Projects . Ltd | 2012-10-26 | 2013-09-25 | 24.10.2014 | 22 | 30 | 52 | 0 | 39 | 39 | 0 | 39 | 39 | 100% | 0 | 0 | 0 | 3465.91 | 0 | Completed
|  | 32b | Improvements to Srirangapatna - JewargiSH-19 from km 573.00 to km 592.00 (In selected reaches)(Kallur &Jewargi of Jewargi Taluk) | 19 | [8 empty] | 19 | 0 | 19 | 19 | 0 | 19 | 19 | 0 | 19 | 100% | 0 | 0 | 0
|  | 32c | Improvements to Mudhol -Yeragera SH-127 from km 0.00 to km 24.50 (In selected reaches)(Mudhol & Itkal of Sedam Taluk) | 127 | [8 empty] | 18.94 | 5.56 | 24.5 | 18.7 | 5.8 | 24.5 | 18.7 | 5.8 | 24.5 | 100% | 0 | 0 | 0
33 | PWD/ 45/EAP/33 | 33 | Improvements to Aurad - Sadashivgad SH - 34 from km 138.67 to km 206.40 (In selected reaches) (Kinni sultan , Jidga of Aland Taluk) | 34 | 1988 | 2372.65 | 229.49 | 2602.14 | M/s SRK Constructions | 2013-11-23 | 2013-10-22 | 2016-03-31 | 33 | 29.7 | 62.7 | 0 | 26.76 | 26.76 | 0 | 26.76 | 26.76 | 100% | 0 | 0 | 0 | 2514.75 | 87.39 | Completed
DIVISION TOTAL |  |  |  |  | 7618 | 8435.96 | 1226.15 | 9662.11 |  |  |  |  | 92.94 | 112.84 | 205.78 | 37.7 | 119.14 | 156.84 | 37.7 | 119.14 | 156.84 | 100% | 0 | 0 | 0 | 9549.37 | 148.65
YADAGIRI DIVISION
34 | PWD/ 45/EAP/34 | 34a | Improvements to Mudhol - Yeragera SH-127 from km 40.73 to km 83.64(In selected reaches) (Anpur,Saidapur, Kondapur of Yadagir Taluk) | 127 | 1751 | 2009.24 | 196.29 | 2205.53 | M/s RMN Infrastructures | 2012-12-13 | 2013-11-12 | 31.03.2014 | 26.98 | 12.64 | 39.62 | 25.18 | 14.44 | 39.62 | 25.18 | 14.44 | 39.62 | 100% | 0 | 0 | 0 | 2121.38 | 84.15 | Completed
|  | 34b | Improvements to Basavakalyan - Raichur SH-51 from km 171.42 to km 192.30 (In selected reaches) (Ramasamudra, Halgeri, Ballichakra, Killankeri of Yadagir Taluk) | 51 | [8 empty] | 17.38 | 3.5 | 20.88 | 17.12 | 3.76 | 20.88 | 17.12 | 3.76 | 20.88 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1751 | 2009.24 | 196.29 | 2205.53 |  |  |  |  | 44.36 | 16.14 | 60.5 | 42.3 | 18.2 | 60.5 | 42.3 | 18.2 | 60.5 | 100% | 0 | 0 | 0 | 2121.38 | 84.15
BIDAR DIVISION
35 | PWD/ 45/EAP/35 | 35 | Improvements to Humnabad - Bidar SH-105 from km 0.00 to km 45.40 (In selected reaches) (Humnabad, Halkhed, Sindbandgi of Humnabad Taluk& Bylhalli, Halhalli of Bhalki Taluk& Andur , Naubad Bidar of Bidar Taluk) | 105 | 1307 | 1206.13 | 98.35 | 1298.4 | M/s Mehul Constructions | 2012-10-16 | 2013-09-19 | 31.01.2014 | 36.7 | 0 | 36.7 | 38.75 | 0 | 38.75 | 38.75 | 0 | 38.75 | 100% | 0 | 0 | 0 | 1303.24 | -4.84 | Completed
36 | PWD/ 45/EAP/ 36 | 36 | Impts.to Wanmarpalli - Raichur SH-15 from km 0.00 to km 90.60 (In selected reaches) (Wanmarpalli,Aurad, Ballur,Kautha B of Aurad Taluk& Chikpet, Bidar,Manalli of Bidar Taluk & Meenkera, Jangalera& Changlera of Humnabad Taluk) | 15 | 2271.01 | 2438.29 | 605.85 | 3044.14 | Gurunath Kollur | 2012-09-29 | 2013-08-29 | 03.05.2014 | 57.7 | 22.3 | 80 | 22.6 | 24.83 | 47.43 | 22.6 | 24.83 | 47.43 | 100% | 0 | 0 | 0 | 3075.68 | 0 | Completed
37 | PWD/ 45/EAP/ 37 | 37 | Improvements to Aurad - Sadashivgad SH-34 from km 0.00 to km 138.67 (In selected reaches) (Aurad,Mugnal,Nittur of Aurad Taluk & Kotgal, Amdabad, Halbarga of Bhalki Taluk & Basavkalyan,Morkhandi, Mannalli, Ekamba, Batagera,Hattaraga of Basavakalyan Taluk) | 34 | 2664.83 | 2736.98 | 409.42 | 3146.4 | M/s KPC Projects . Ltd | 2012-10-16 | 2013-10-08 | 30.10.2014 | 27 | 42.51 | 69.51 | 20.59 | 48.26 | 68.85 | 20.586 | 48.264 | 68.85 | 100% | 0.004 | -0.004 | -3.5527e-15 | 3064.7 | 81.7 | Completed
DIVISION TOTAL |  |  |  |  | 6242.84 | 6381.4 | 1113.62 | 7488.94 |  |  |  |  | 121.4 | 64.81 | 186.21 | 81.94 | 73.09 | 155.03 | 81.936 | 73.094 | 155.03 | 100% | 0.004 | -0.004 | -3.5527e-15 | 7443.62 | 76.86
GULBARGA CIRCLE TOTAL |  |  |  |  | 15611.84 | 16826.6 | 2536.06 | 19356.58 |  |  |  |  | 258.7 | 193.79 | 452.49 | 161.94 | 210.43 | 372.37 | 161.936 | 210.434 | 372.37 | 100% | 0.004 | -0.004 | -3.5527e-15 | 19114.37 | 309.66
NORTH ZONE TOTAL |  |  |  |  | 79365.65 | 83699.48 | 8371.984 | 92065.384 |  |  |  |  | 927.31 | 1141.803 | 2069.113 | 705.091 | 1235.693 | 1940.784 | 705.087 | 1235.697 | 1940.784 | 100% | 0.004 | -0.004 | -7.1054e-15 | 91234.8 | 953.684
SOUTH ZONE
RAMANAGARA DIVISION
38 | PWD/45/EAP/ 38 | 38 | Improvements to Hunasanhalli - Chikkahalli SH-03 from km 0.00 (TN border) to km 83.67 (In selected reaches) (Hunasanahalli, Kodihalli, Tippaya, Aralalu, Kanakapura, Hosakote, Ganulu, Arehalli of Thavarekere, of Kanakapura Taluk & Ramanagara, Kudihalli, Padara halli, Lakshmi pura, Gollarahatti of Ramanagara Taluk) | 3 | 1870 | 2000.13 | 54.98 | 2055.11 | S.R.Ravishanker | 2012-11-07 | 06.10.12 | 06.10.2013 | 34.82 | 15.2 | 50.02 | 29.5 | 13.89 | 43.39 | 29.5 | 13.89 | 43.39 | 100% | 0 | 0 | 0 | 2068.46 | 0 | Completed
|  |  | DIVISION TOTAL |  | 1870 | 2000.13 | 54.98 | 2055.11 |  |  |  |  | 34.82 | 15.2 | 50.02 | 29.5 | 13.89 | 43.39 | 29.5 | 13.89 | 43.39 | 100% | 0 | 0 | 0 | 2068.46 | 0
KOLAR DIVISION
39 | PWD/45/EAP/ 39 | 39 | Improvements to Kothapalli - Masti SH-99 from km 0.00 (AP border) to km 103.40 ( TN border) (In selected reaches) (Kottaoalli, Kappli, Seegehalli, Byrapalli, Srinivaspura, Hosahalli of Srinivasapura Taluk & Muduvadi, Veerapura, Kolara,Muduvathi ofKolar Taluk & Lakshmi sagara, Hanasikote, K.G.Halli, Dinnahalli, Nagadenahalli, Masthi of Malur Taluk) | 99 | 2758.33 | 2843.77 | 310.65 | 3154.42 | M. Venkataramareddy | 2013-01-24 | 2013-11-23 | 2015-03-30 | 9.1 | 46.75 | 55.85 | 10.262 | 30.92 | 41.182 | 10.262 | 30.92 | 41.182 | 100% | 0 | 0 | 0 | 2972.56 | 181.86 | Completed
DIVISION TOTAL |  |  |  |  | 2758.33 | 2843.77 | 310.65 | 3154.42 |  |  |  |  | 9.1 | 46.75 | 55.85 | 10.262 | 30.92 | 41.182 | 10.262 | 30.92 | 41.182 | 100% | 0 | 0 | 0 | 2972.56 | 181.86
TUMKUR DIVISION
40 | PWD/45/EAP/ 40 | 40a | Improvements to Sira - Nanjangud SH-84 from km 13.75 to km 49.25 (In selected reaches) (Devanahalli, Ankasandra, Anthapura, Chellur, Somalapura, Ammanaghatta of Gubbi Taluk | 84 | 1842.96 | 2156.2 | 263.1 | 2419.3 | BSR infratec Ltd | 2012-10-17 | 2013-09-16 |  | 11.4 | 23.98 | 35.38 | 3.58 | 22.79 | 26.37 | 3.58 | 22.79 | 26.37 | 100% | 0 | 0 | 0 | 2390.57 | 28.73 | Completed
|  | 40b | Improvement to Hunasanahalli - Chikkanahalli SH-03 from km 165.88 to km 170.08 (In selected reaches) ( Koratagere town limit of Koratagere Taluk) | 3 | [8 empty] | 2.2 | 2 | 4.2 | 1.88 | 2.32 | 4.2 | 1.88 | 2.32 | 4.2 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1842.96 | 2156.2 | 263.1 | 2419.3 |  |  |  |  | 13.6 | 25.98 | 39.58 | 5.46 | 25.11 | 30.57 | 5.46 | 25.11 | 30.57 | 100% | 0 | 0 | 0 | 2390.57 | 28.73
BANGALORE CIRCLE |  |  |  |  | 6471.29 | 7000.1 | 628.73 | 7628.83 |  |  |  |  | 57.52 | 87.93 | 145.45 | 45.222 | 69.92 | 115.142 | 45.222 | 69.92 | 115.142 | 300% | 0 | 0 | 0 | 7431.59 | 210.59
MYSORE DIVISION
41 | PWD/45/EAP/ 41 | 41 | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 610.30 to km 656.50 (In selected reaches) (Maddur Kallali, Maddur, Maddur hundi of Mysore Taluk& Hampapura, Madanahalli, JP Hundi, Hullahalli of H.D.Kote Taluk& Mobbahalli, Gandi Grama, Byluru, Deburu Nanjanagud Town of Nanjanagudu Taluk) | 57 | 1470 | 1578.88 | 364.11 | 1942.99 | Bapuji Cons. | 2012-10-17 | 2013-10-16 | 30.12.2013 | 4.96 | 18 | 22.96 | 4.39 | 20.34 | 24.73 | 4.39 | 20.34 | 24.73 | 100% | 0 | 0 | 0 | 1934.88 | 8.11 | Completed
42 | PWD/45/EAP/ 42 | 42a | Improvements to Ramanathapura - Therakanambi SH-86 from km 107.35 to km 118.40 (In selected reaches) ( Parvatipura, Beere Gowdanapura, Indiranagar ofNanjanagudu Taluk) | 86 | 1447 | 1572.6 | 391.93 | 1964.53 | K.T Ravi | 2012-11-09 | 2013-10-08 | 15.06.2014 | 0 | 8.35 | 8.35 | 0 | 8.425 | 8.425 | 0 | 8.425 | 8.425 | 100% | 0 | 0 | 0 | 1893.91 | 70.62 | Completed
|  | 42b | Improvements to Sira - Nanjanagud SH-84 from km 198.54 to km 243.01 (In selected reaches) (Kalkuli, Bommanahalli, Sosle, T.N.Pura, Alasri katte Hundi of T.N.Pura Taluk & Biligere, Kupperavalli, Nagarle, Alamburu, HosavaralWadi Geekali Hundi of Nanjanagudu Taluk) | 84 | [8 empty] | 3.8 | 16.2 | 20 | 0 | 6.83 | 6.83 | 0 | 6.83 | 6.83 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 2917 | 3151.48 | 756.04 | 3907.52 |  |  |  |  | 8.76 | 42.55 | 51.31 | 4.39 | 35.595 | 39.985 | 4.39 | 35.595 | 39.985 | 100% | 0 | 0 | 0 | 3828.79 | 78.73
HUNSUR DIVISION | [18 empty] | 0 | 0
43 | PWD/45/EAP/ 43 | 43 | Improvements to Ramanathapura - Therakanambi SH-86 from km 7.80 to km 107.35(In selected reaches) (Ansoge, Koluru, Mayagowdanahalli, Housuru, Keturu, Malalihalli, Mavahuru, Madanahalli of K.R.Nagar Taluk& Honnenahalli, Kalkuli, Hunsur, Hanchya, Kurubara hosalli, BBH Colony, Gurupura of Hunsur Taluk & Bhimanahalli, Hunnuru, Yedthore, Tiger Block, Shantipura, H.D.Kote, Jakkali, Devalapura, Saraguru of H.D.Kote Taluk) | 86 | 3256.77 | 3390.71 | 475.23 | 3865.94 | SVS Mookambika Cons. | 2012-11-09 | 2013-10-08 | 30.09..2014 | 5.44 | 52.49 | 57.93 | 5.3 | 52.27 | 57.57 | 5.3 | 52.27 | 57.57 | 100% | 0 | 0 | 0 | 3620.23 | 245.71 | Completed
DIVISION TOTAL |  |  |  |  | 3256.77 | 3390.71 | 475.23 | 3865.94 |  |  |  |  | 5.44 | 52.49 | 57.93 | 5.3 | 52.27 | 57.57 | 5.3 | 52.27 | 57.57 | 100% | 0 | 0 | 0 | 3620.23 | 245.71
MANDYA DIVISION
44 | PWD/45/EAP/ 44 | 44a | Improvements to Bangalore - Jalsur SH-85 from km 112.40 to km 153.30 (In selected reaches) (Nagamangala, Mallenahalli, Kanthapura, Bhogadhi, TV Kaloni of Nagamangala Taluk)(Dugnahall, Kotgenehali, Valgere, Mensa, K.R.Pet of K.R.Pet Taluk) | 85 | 2061.5 | 2312.73 | 210.79 | 2523.52 | Govinde gowda | 2012-10-30 | 2013-07-29 | 12.07.2013 | 9.83 | 20.67 | 30.5 | 8.775 | 21.955 | 30.73 | 8.775 | 21.955 | 30.73 | 100% | 0 | 0 | 0 | 2532.02 | 0 | Completed
|  | 44b | Improvements to Mandya - Hadagali SH-47 from km 22.95 to km 55.40 (In selected reaches) (Sangapura, Jakkanahalli, Kadalgere, Valagere of Pandavapura Taluk) Hindasahalli of Nagamangala Taluk) | 47 | [8 empty] | 22.25 | 7.74 | 29.99 | 18.86 | 11.1 | 29.96 | 18.86 | 11.1 | 29.96 | 100% | 0 | 0 | 0
45 | PWD/45/EAP/ 45 | 45a | Improvements to Mandya - Hadagali SH-47 from km 0.69 to km 22.95(In selected reaches) (Mandya, Shivalli, Dudda, Bevakullu, Atna Javanahalli of Mandya Taluk ) | 47 | 1669.1 | 1603.6 | 158.58 | 1762.18 | Govinde gowda | 2012-10-30 | 2013-07-29 | 22.06.2013 | 4.2 | 11.21 | 15.41 | 1.2 | 14.21 | 15.41 | 1.2 | 14.21 | 15.41 | 100% | 0 | 0 | 0 | 1732.06 | 30.12 | Completed
|  | 45b | Improvements to Sira - Nanjanagud SH-84 from km 171.16 to km 198.54 (In selected reaches) (Mangala Thittu of Mandya Taluk & Virajpura, Ramanduru, Mkagepura, Mikkere of Malavalli Taluk) | 84 | [8 empty] | 5.5 | 16.11 | 21.61 | 0 | 21.548 | 21.548 | 0 | 21.548 | 21.548 | 100% | 0 | 0 | 0
46 | PWD/45/EAP/ 46 | 46 | Improvements to Srirangapatna - Arasikere SH-7 from km 4.50 to km 60.42 (In selected reaches) (Pandavapura Village, Shettahalli, Hulikere of Pandavapura Taluk & Murakanahalli, K.R.Pete, Krishnapura , Kikere, Lakshmipura , Angola of KR Pete Taluk) | 7 | 2143.3 | 2340.56 | 273.12 | 2613.68 | Bapuji Cons. | 2012-10-25 | 2013-07-24 | 30.03.2013 | 19.56 | 34.22 | 53.78 | 16.967 | 38.878 | 55.845 | 16.967 | 38.878 | 55.845 | 100% | 0 | 0 | 0 | 2640.6 | 0 | Completed
|  |  | DIVISION TOTAL |  | 5873.9 | 6256.89 | 642.49 | 6899.38 |  |  |  |  | 61.34 | 89.95 | 151.29 | 45.802 | 107.691 | 153.493 | 45.802 | 107.691 | 153.493 | 100% | 0 | 0 | 0 | 6904.68 | 30.12
MYSORE CIRCLE TOTAL |  |  |  |  | 12047.67 | 12799.08 | 1873.76 | 14672.84 |  |  |  |  | 75.54 | 184.99 | 260.53 | 55.492 | 195.556 | 251.048 | 55.492 | 195.556 | 251.048 | 300% | 0 | 0 | 0 | 14353.7 | 354.56
HASSAN DIVISION
47 | PWD/45/EAP/ 47 | 47a | Improvements to Huliyar - Keralapura SH-102 from km 75.28 to km 99.08 (In selected reaches) (Dudda RS, ShantiGrama Village, Devihalli of Hasan Taluk) | 102 | 3257 | 3508.78 | 468.24 | 3977.02 | Rayeegowda | 2012-11-16 | 2013-10-15 | 30.09.2015 | 2.3 | 56.91 | 59.21 | 0.19 | 18.6 | 18.79 | 0.19 | 18.6 | 18.79 | 100% | 0 | 0 | 0 | 3970.78 | 6.24 | Completed
|  | 47b | Improvements to Huliyar - Keralapura SH-102 from km 99.08 to km 144.39 (In selected reaches) (Malali Village, Taranya, Hariharapura, Jakkanahalli, Bidrakka, Nerale of Holenarasipura Taluk) | 102 | [10 empty] | 0 | 0 | 40.92 | 40.92 | 0 | 40.921 | 40.921 | 100% | 0 | -0.001 | -0.001
48 | PWD/45/EAP/ 48 | 48a | Improvements to Hirisave - Chattahalli SH -8 from km 0.00 to km 41.835 (In selected reaches) (Sorekkayipura, Hosahalli, Baralu, CRPatna of Channarayapattana Taluk) | 8 | 2045.5 | 2235.48 | 126.54 | 2362.02 | H.N Ramegowda | 2012-11-16 | 2013-10-15 | 15.10.2013 | 5.25 | 8.3 | 13.55 | 4.45 | 8.36 | 12.81 | 4.45 | 8.36 | 12.81 | 100% | 0 | 0 | 0 | 2321.33 | 40.69 | Completed
|  | 48b | Improvements to Srirangapatna - Arasikere SH -7 from km 61.48 to km 91.27 (In selected reaches) (CRPatna, Moodanahalli, CR patna Taluk border (Yaranahalli) of Channarayapattana Taluk) | 7 | [8 empty] | 17.75 | 7.48 | 25.23 | 17.75 | 7.03 | 24.78 | 17.75 | 7.03 | 24.78 | 100% | 0 | 0 | 0
|  | 48c | Improvements to Srirangapatna - Arasikere SH -7 from km 91.27 to km 117.52(In selected reaches) (Gandsi Handpost, Mududi, Arasikere town of Arasikere Taluk) | 7 | [8 empty] | 17.75 | 8.5 | 26.25 | 17.75 | 8.5 | 26.25 | 17.75 | 8.5 | 26.25 | 100% | 0 | 0 | 0
49 | PWD/45/EAP/ 49 | 49 | Improvements to Huliyar - Keralapura SH-102 from km 15.00 to km 75.28 (In selected reaches) (Kaimara, Modalu, JCPura , Haranahalli, Bageshpura, Dudda Junction of Hassan & Arasikere Taluk) | 102 | 2393.35 | 2459.42 | 363.65 | 2823.07 | Rayeegowda | 2013-03-16 | 2014-02-15 | 30.06.2016 | 11 | 43.58 | 54.58 | 0 | 54.58 | 54.58 | 0 | 54.58 | 54.58 | 100% | 0 | 0 | 0 | 2660.51 | 162.56 | Completed
50 | PWD/45/EAP/ 50 | 50a | Improvements to Belur - Kodlipet SH-110 from km 0.00 to km 20.20 (In selected reaches) (Bikkodu, Madaghatta, Devarajpura of Belur Taluk) | 110 | 1587 | 1596.07 | 200.36 | 1796.43 | CHVN Reddy | 2012-11-16 | 2013-10-15 | 15.10.2013 | 6.25 | 13.95 | 20.2 | 0 | 20.2 | 20.2 | 0 | 20.2 | 20.2 | 100% | 0 | 0 | 0 | 1739.28 | 57.15 | Completed
|  | 50b | Improvements to Bagalkote - Biligiriranganabetta SH-57 from km 452.50 to km 475.84 (In selected reaches) (Belur, Hagare, Kalkere gadi of Belur Taluk) | 57 | [8 empty] | 20.19 | 3.15 | 23.34 | 19.69 | 3.65 | 23.34 | 19.69 | 3.65 | 23.34 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 9282.85 | 9799.75 | 1158.79 | 10958.54 |  |  |  |  | 80.49 | 141.87 | 222.36 | 59.83 | 161.84 | 221.67 | 59.83 | 161.841 | 221.671 | 100% | 0 | -0.001 | -0.001 | 10691.9 | 266.64
HASSAN SPECIAL DIVISION
51 | PWD/45/EAP/ 51 | 51a | Improvements to Hirisave - Chattahalli SH-8 from km 80.80 to km 94.20 km (In selected reaches) (Bobbegalale, Chowrgal, Mallipatna of Arakalagudu Taluk) | 8 | 2057 | 2260.59 | 225.67 | 2486.26 | S M Abdul Hafeez | 2012-11-15 | 2013-10-14 | 20.03.2014 | 0 | 13.4 | 13.4 | 0 | 13 | 13 | 0 | 13 | 13 | 100% | 0 | 0 | 0 | 2473.43 | 12.83 | Completed
|  | 51b | Improvements to Hirisave - Chattahalli SH-8 from km 105.55 to km129.97 (In selected reaches) (Changadihalli, Huchchangi, Mageri of Sakaleshpura Taluk) | 8 | [8 empty] | 0 | 19.67 | 19.42 | 0 | 19.42 | 19.42 | 0 | 19.42 | 19.42 | 100% | 0 | 0 | 0
|  | 51c | Improvements to Huliyar - Keralapura SH-102 from km 144.39 to km 150.252 (In selected reaches)(Bombe Koppalu, Boodihal, Keralapura, Karthal of Arakalagudu Taluk) | 102 | [8 empty] | 0 | 5.13 | 5.13 | 0 | 5.13 | 5.13 | 0 | 5.13 | 5.13 | 100% | 0 | 0 | 0
52 | PWD/45/EAP/ 52 | 52 | Improvements to Belur - Kodlipet SH-110 from km 20.20 to km 68.70 (In selected reaches) (Kamathi kudige, Alur, Bairapura Handpost, Magghe, Rayarakoppalu of Sakaleshpura Taluk) | 110 | 2325 | 2583.35 | 182.25 | 2765.6 | H.N Ramegowda | 2012-12-14 | 2013-11-13 | 15.02.2014 | 1.9 | 44.6 | 46.5 | 0 | 43.6 | 43.6 | 0 | 43.6 | 43.6 | 100% | 0 | 0 | 0 | 2711.86 | 53.74 | Completed
DIVISION TOTAL |  |  |  |  | 4382 | 4843.94 | 407.92 | 5251.86 |  |  |  |  | 1.9 | 82.8 | 84.45 | 0 | 81.15 | 81.15 | 0 | 81.15 | 81.15 | 100% | 0 | 0 | 0 | 5185.29 | 66.57
CHICKMAGALUR DIVISION
53 | PWD/45/EAP/ 53 | 53a | Improvements to Malpe - Molakalmur SH-65 from km 91.50 to km 114.50 km (In selected reaches) (Koppa & Shringere, Kudregundi, N.R.Pura(Badra Back down) | 65 | 1150.96 | 1286.28 | 127.83 | 1414.11 | S. Sheshagiri | 2012-10-18 | 2013-09-17 | 20.02.2014 | 14 | 2.95 | 16.95 | 12.5 | 6.35 | 18.85 | 12.5 | 6.35 | 18.85 | 100% | 0 | 0 | 0 | 1385 | 29.11 | Completed
|  | 53b | Improvements to Virajpet - Byndoor SH-27 from km 167.45 to km 187.45 (In selected reaches) (Moodigere, Mudigere Taluk Border) | 27 | [8 empty] | 15 | 5 | 20 | 7 | 13 | 20 | 7 | 13 | 20 | 100% | 0 | 0 | 0
54 | PWD/45/EAP/ 54 | 54 | Improvements to Gangamula - Kotigehara SH-66 from km 0.00 to km 89.95 (In selected reaches)(Kudremukha, Kalsa, Magundi, Niduvale, Kotigehra of Mudugere Taluk) | 66 | 2362.36 | 2777.14 | 261.81 | 3038.95 | Amrutha construction | 2013-03-19 | 2014-02-18 | 15.02.2015 | 65.31 | 22.68 | 87.99 | 66.56 | 24.64 | 91.2 | 66.56 | 24.64 | 91.2 | 100% | 0 | 0 | 0 | 2917.62 | 121.33 | Completed
DIVISION TOTAL |  |  |  |  | 3513.32 | 4063.42 | 389.64 | 4453.06 |  |  |  |  | 94.31 | 30.63 | 124.94 | 86.06 | 43.99 | 130.05 | 86.06 | 43.99 | 130.05 | 100% | 0 | 0 | 0 | 4302.62 | 150.44
HASSAN CIRCLE TOTAL |  |  |  |  | 17178.17 | 18707.11 | 1956.35 | 20663.46 |  |  |  |  | 176.7 | 255.3 | 431.75 | 145.89 | 286.98 | 432.87 | 145.89 | 286.981 | 432.871 | 300% | 0 | -0.001 | -0.001 | 20179.81 | 483.65
SHIMOGA SPECIAL DIVISION
55 | PWD/45/EAP/ 55 | 55 | Improvements to Padubidre - Chikkalgudu SH-1 from km 76.80 to km 138.00 (In selected reaches)(Agumbe, Hosuru, Megaravalli, Kalmane, Kaimara, Thirthahalli Town Hosanagara - Thirthahalli Taluk Border) | 1 | 2489.2 | 2930.36 | 191.04 | 3121.4 | Ibrahim Sherieff | 2012-12-25 | 2013-09-24 | 31.05.2013 | 5 | 45.5 | 50.5 | 5.24 | 43.17 | 48.41 | 5.24 | 43.17 | 48.41 | 100% | 0 | 0 | 0 | 3065.32 | 56.08 | Completed
DIVISION TOTAL |  |  |  |  | 2489.2 | 2930.36 | 191.04 | 3121.4 |  |  |  |  | 5 | 45.5 | 50.5 | 5.24 | 43.17 | 48.41 | 5.24 | 43.17 | 48.41 | 100% | 0 | 0 | 0 | 3065.32 | 56.08
SHIMOGA DIVISION
56 | PWD/45/EAP/ 56 | 56 | Improvements to Sirsi - Hosanagar SH-77 from km 28.50 to km 59.16 & km 59.16 to km 87.20 (In selected reaches)(Sampgodu, Sorabatown, Hosbale of Soraba Taluk & Chikkanelluru, Masuru, Sagara town of Sagara Taluk) | 77 | 2375.59 | 2763.25 | 0 | 2763.25 | A.V Patil | 2012-11-08 | 2013-10-07 | 28.02.2014 | 9.6 | 43.78 | 53.38 | 7.76 | 43.72 | 51.48 | 7.76 | 43.72 | 51.48 | 100% | 0 | 0 | 0 | 2718.94 | 44.31 | Completed
57 | PWD/45/EAP/ 57 | 57a | Improvements to Padubidre - Chikkalgudu SH-1 from km 138.00 to km 169.16(In selected reaches) (Billeshwara, Humcha, Rippenpete Belluru, Nouturu of Hosanagara Taluk & Yedehalli of Sagara Taluk) | 1 | 2481.72 | 2917.71 | 169.55 | 3087.26 | G.D Thimappa Sheregar | 2012-11-07 | 2013-10-06 | 31.05.2013 | 0 | 29.16 | 29.16 | 0 | 29.16 | 29.16 | 0 | 29.16 | 29.16 | 100% | 0 | 0 | 0 | 3168.69 | 0 | Completed
|  | 57b | Improvements to Sirsi - Hosanagar SH-77 from km 87.20 to km 115.30 (In selected reaches) (Battemallapa, Maruthipura, Mavinakoppa of Hosanagara Taluk) | 77 | [8 empty] | 7.14 | 16.02 | 23.16 | 7.76 | 16.96 | 24.72 | 7.76 | 16.96 | 24.72 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4857.31 | 5680.96 | 169.55 | 5850.51 |  |  |  |  | 16.74 | 88.96 | 105.7 | 15.52 | 89.84 | 105.36 | 15.52 | 89.84 | 105.36 | 100% | 0 | 0 | 0 | 5887.63 | 44.31
CHITRADURGA DIVISION
58 | PWD/45/EAP/ 58 | 58a | Improvements to Mandya - Hadagali SH-47 from km 207.70 to km 267.30 (In selected reaches) (Yelakoppanahatti, Moduru, Devigenne, Mavinakatte of Hosadurga Taluk & Kelaganakottige, Havinahatti, Holalkere town Chjikjaur Salsu, Sasuluhalli of Holalkere Taluk) | 47 | 2905 | 3173.57 | 302.33 | 3475.9 | A. Balaram reddy | 2012-11-02 | 2013-10-01 | 30.11.2013 | 0 | 40.24 | 40.24 | 0 | 38.562 | 38.562 | 0 | 38.562 | 38.562 | 100% | 0 | 0 | 0 | 3472.55 | 0 | Completed
|  | 58b | Improvements to Kumata - Kadamadagi SH-48 from km 227.20 to km 246.76(In selected reaches) (Vishwanathanahalli, Kutigehalli, B.Durga, Hirekandavadi of Holalkere Taluk) | 48 | [8 empty] | 0 | 15.76 | 15.76 | 0 | 15.941 | 15.941 | 0 | 15.941 | 15.941 | 100% | 0 | 0 | 0
59 | PWD/45/EAP/ 59 | 59 | Improvements to Kumata - Kadamadagi SH-48 from km 246.76 to km348.91 km (In selected reaches) (Bheemasamudra, Haliyuru, Malappanahatti, Chitradurga town, Appajiudyana of Chitradurga Taluk & Belanahalli, Challakere town, Doddari, Purnalli, Naganahalli Challakere - Pavagada Taluk border of Challakere Taluk) | 48 | 3544.5 | 3572.64 | 855.15 | 4427.79 | K. Krishna | 2012-12-27 | 2013-11-26 | 2016-07-31 | 17.73 | 57.86 | 75.59 | 17.78 | 53.86 | 71.64 | 17.78 | 53.86 | 71.64 | 100% | 0 | 0 | 0 | 4256.46 | 171.33 | Completed
60 | PWD/45/EAP/ 60 | 60 | Improvements to Malpe - Molakalmur SH-65 from km 337.95 to km 381.45 (In selected reaches) (Jagaluru, Abhinahalli, Masthihalagummi of Challakere Taluk & Mutigarahalli, Bekuru, Kolasagar, Molakalmuru of Molakalmur Taluk) | 65 | 1429.42 | 1467.52 | 137.73 | 1605.25 | RMN infrastructure Pvt. ltd | 2012-11-14 | 2013-08-13 | 10.09.20145 | 7.1 | 25.32 | 32.42 | 7.1 | 24.464 | 31.564 | 7.1 | 24.464 | 31.564 | 100% | 0 | 0 | 0 | 1488.02 | 117.23 | Completed
DIVISION TOTAL |  |  |  |  | 7878.92 | 8213.73 | 1295.21 | 9508.94 |  |  |  |  | 24.83 | 139.18 | 164.01 | 24.88 | 132.827 | 157.707 | 24.88 | 132.827 | 157.707 | 100% | 0 | 0 | 0 | 9217.03 | 288.56
DAVANAGERE DIVISION
61 | PWD/45/EAP/ 61 | 61a | Improvements to Malpe - Molakalmur SH-65 from km 186.35 to km 338.00 (In selected reaches) (Joladal, Gopanal, Erehalli ,Kashipura camp of Chennagiri Taluk & Karignoor, Adhadi, 7ne Maili Kallu, 6ne Maili kallu, Siramgondanahalli, Davangere town of Davangere Taluk & Mutsur, Siddihalli, Mallapura of Jagalur Taluk) | 65 | 3257.75 | 3492.5 | 868 | 4360.5 | Sharan D Bandi | 2013-03-20 | 2014-02-19 | 31.12.2014 | 7.89 | 43.65 | 51.54 | 0 | 67.29 | 67.29 | 0 | 67.29 | 67.29 | 100% | 0 | 0 | 0 | 4379.99 | 0 | Completed
|  | 61b | Improvements to Mandya - Hadagali SH-47 from km 261.25 to km 278.50 (In selected reaches) (Holalkere-Davangere Taluk Border, Dindanahalli of Davanagere Taluk) | 47 | [8 empty] | 0 | 14.38 | 14.38 | 0 | 14.38 | 14.38 | 0 | 14.38 | 14.38 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 3257.75 | 3492.5 | 868 | 4360.5 |  |  |  |  | 7.89 | 58.03 | 65.92 | 0 | 81.67 | 81.67 | 0 | 81.67 | 81.67 | 100% | 0 | 0 | 0 | 4379.99 | 0
SHIMOGA CIRCLE TOTAL |  |  |  |  | 20109.18 | 22100.21 | 2627.92 | 24728.13 |  |  |  |  | 54.46 | 345.77 | 400.23 | 45.64 | 361.607 | 407.247 | 45.64 | 361.607 | 407.247 | 500% | 0 | 0 | 0 | 24394.76 | 430.94
MANGALORE DIVISION
62 | PWD/45/EAP/ 62 | 62a | Improvements to Mangalore - Athradi SH-67 from km 23.42 to km 36.42 (In selected reaches) (Maravoor, Bajpe, Yekkaru, Kateel, Damaskatte, Elinje, of Mangalore Sub Division) | 67 | 3365.7 | 3902.12 | 584.82 | 4486.94 | Jagadeep D Suvarna | 2013-03-19 | 2014-02-18 | 30.11.2014 | 10.65 | 2.35 | 13 | 10.1 | 2.9 | 13 | 10.1 | 2.9 | 13 | 100% | 0 | 0 | 0 | 4435.08 | 51.86 | Completed
|  | 62b | Improvements to Subramanya - Udupi SH-37 from km 0.00 to km 36.40 (In selected reaches) (Karikamba, Nettana, Maranda, Kokkada of Sullia & Puttur Sub Division) | 37 | [8 empty] | 12.56 | 10.14 | 22.7 | 10.96 | 10.14 | 21.1 | 10.96 | 10.14 | 21.1 | 100% | 0 | 0 | 0
|  | 62c | Improvements to Subramanya - Manjeswara SH-100 from km 28.80 to km 92.92 (In selected reaches) (Karimajalu, Doddadka, Punacha, Kanyana, Vijayadka of Puttur sub division) | 100 | [8 empty] | 18.51 | 35.76 | 54.27 | 15.51 | 35.76 | 51.27 | 15.51 | 35.76 | 51.27 | 100% | 0 | 0 | 0
[5 empty] | 3365.7 | 3902.12 | 584.82 | 4486.94 |  |  |  |  | 41.72 | 48.25 | 89.97 | 36.57 | 48.8 | 85.37 | 36.57 | 48.8 | 85.37 | 100% | 0 | 0 | 0 | 4435.08 | 51.86
63 | PWD/45/EAP/ 63 | 63 | Improvements to Bangalore - Jalsoor SH-85 from km 291.51 to km 335.71 (In selected reaches) (Bisale, Elimale, Doddathota, Sonangiri, Jalsoor of Sulia Sub division) | 85 | 2013 | 2204.99 | 515 | 2719.99 | M/s Iqbal Ahmed Infraproject Pvt Ltd | 2012-11-15 | 2013-10-14 | 31.03.2014 | 9.22 | 33.28 | 42.5 | 9.22 | 33.28 | 42.5 | 9.22 | 33.28 | 42.5 | 100% | 0 | 0 | 0 | 2697.03 | 22.96 | Completed
DIVISION TOTAL |  |  |  |  | 5378.7 | 6107.11 | 1099.82 | 7206.93 |  |  |  |  | 50.94 | 81.53 | 132.47 | 45.79 | 82.08 | 127.87 | 45.79 | 82.08 | 127.87 | 100% | 0 | 0 | 0 | 7132.11 | 74.82
UDUPI DIVISION
64 | PWD/45/EAP/ 64 | 64a | Improvements to Mangalore - Athradi SH-67 from km 36.48 to km 71.01 (In selected reaches) (Sankalkari, Mundkoor, Jantata, Moodbilli of Udupi sub division) | 67 | 1667.68 | 1838.38 | 170.98 | 2009.36 | M/s Iqbal Ahmed Infraproject Pvt Ltd | 2012-11-15 | 2013-10-14 | 14.10.2013 | 14.54 | 8.14 | 22.68 | 11.95 | 9.1 | 21.05 | 11.95 | 9.1 | 21.05 | 100% | 0 | 0 | 0 | 1935.7 | 73.66 | Completed
|  | 64b | Improvements to Subramanya - Udupi SH-37 from km 105.70 to km 150.40 (In selected reaches) (Eedu, Nellikaru, Bajegoli, Kondadi, Palli, Edamaru, Aleyoor, Kaup cross of Karkala sub Division) | 37 | [8 empty] | 22.03 | 10.57 | 32.6 | 18 | 14.9 | 32.9 | 18 | 14.9 | 32.9 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1667.68 | 1838.38 | 170.98 | 2009.36 |  |  |  |  | 36.57 | 18.71 | 55.28 | 29.95 | 24 | 53.95 | 29.95 | 24 | 53.95 | 100% | 0 | 0 | 0 | 1935.7 | 73.66
KODAGU DIVISION
65 | PWD/45/EAP/ 65 | 65a | Improvements to Hunsur - Talacauvery SH-90 from km 61.00 to km 117.50 (In selected reaches) (Kadanga, Nariyandada, Kakkambe, Napoklu, Bhagamandala of Madikeri sub Division) | 90 | 1706.47 | 1926.93 | 192.16 | 2119.09 | M/s Concord Construction | 2012-12-22 | 2013-11-22 | 2014-03-31 | 36.39 | 5 | 41.39 | 29.88 | 12.13 | 42.01 | 29.88 | 12.13 | 42.01 | 100% | 0 | 0 | 0 | 1916.19 | 202.9 | Copmleted
|  | 65b | Improvements to Virajpet - Byndoor SH-27 from km 0.00 to km 100.19(In selected reaches) (Kodalipete, Bydagota, Kumbur, Makkandur, Madikeri, Virajendra pete) | 27 | [8 empty] | 31.54 | 2 | 33.54 | 31.227 | 1.735 | 32.962 | 31.227 | 1.735 | 32.962 | 100% | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 1706.47 | 1926.93 | 192.16 | 2119.09 |  |  |  |  | 67.93 | 7 | 74.93 | 61.107 | 13.865 | 74.972 | 61.107 | 13.865 | 74.972 | 100% | 0 | 0 | 0 | 1916.19 | 202.9
MANGALORE CIRCLE TOTAL |  |  |  |  | 8752.85 | 9872.42 | 1462.96 | 11335.38 |  |  |  |  | 155.44 | 107.24 | 262.68 | 136.847 | 119.945 | 256.792 | 136.847 | 119.945 | 256.792 | 400% | 0 | 0 | 0 | 10984 | 351.38
DAVANAGERE DIVISION
66 | GO No: PWD/121/ EAP/2012 Bangalore, Dt: 19.11.2012 | 66 | Improvements to Kudligere - Kammaragatte Road SH-115 from km 20.00 to km 36.00 (In selected reaches) (Lingapura Holle, Hosahalli camp-1, Vijayapura, Benekanahalli of Honnali Taluk) | 115 | 1626 | 1782.66 | 104.12 | 1886.78 | Manjushri Cons. | 2013-03-20 | 2014-02-19 | 15.02.2015 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 100% | 0 | 0 | 0 | 1844.79 | 41.99 | Completed
|  |  | DIVISION TOTAL |  | 1626 | 1782.66 | 104.12 | 1886.78 |  |  |  |  | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 0 | 14.1 | 14.1 | 100% | 0 | 0 | 0 | 1844.79 | 41.99
|  |  | SOUTH ZONE TOTAL |  | 64559.16 | 70478.92 | 8549.72 | 79028.64 |  |  |  |  | 519.66 | 981.23 | 1500.64 | 429.091 | 1034.008 | 1463.099 | 429.091 | 1034.009 | 1463.1 | 1800% | 0 | -0.001 | -0.001 | 77343.86 | 1831.12
|  |  | NORTH & SOUTH ZONE TOTAL |  | 143924.81 | 154178.4 | 16921.704 | 171094.024 |  |  |  |  | 1446.97 | 2123.033 | 3569.753 | 1134.182 | 2269.701 | 3403.883 | 1134.178 | 2269.706 | 3403.884 | 1900% | 0.004 | 0 | -0.001 | 168578.66 | 2784.804
168.8
1185.8
-231.91