## Phase II
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE
SHDP - PHASE - II PROGRESS REPORT
2021-11-30
Sl No | Package No. |  | Name of Work | SH No. | Administrative Approved Amount (Rs. in lakhs) | Technical sanctioned Amount (Rs. in lakhs) | CER No. | Contract Amount (Rs. in lakhs) | Variation Amount (Rs. in lakhs) | Revised Contract Amount (Rs. in lakhs) | Name of Contractor | Date Of Completion |  |  | Length Proposed as per DPR in Km |  |  | Length Proposed as per VO in Km |  |  | Physical Progress |  |  |  | Financial Progress |  | Balance Length ( Km ) |  |  | Balance (Financial amount) Rs. In Lakhs | Remarks
[12 empty] | Commencement | Completion | Revised | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Length (in km) Renewal | Length (in km) Improvements | Total Length (in km) | Renewal (km) | Improvements (km) | Total Length Completed (in km) | % Progress | Total (Rs. In Lakhs) | % Progress | Renewal (km) | Improvements (km) | Total Balance Length (in km)
1 | 2 |  | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
GULBARGA CIRCLE
BIDAR DIVISION
1 | Pkg 67 | 67a | Improvements to Bhalki-Chincholi road SH-75 from km 0.00 to 51.00 (in selected Reaches)in Bidar Dist. | 75 | 1989.24 | 1929.99 | CER No.: 50/2013-14 | 2311.59 | 220.33 | 2531.92 | Sri.Gurunath Kollur | 22.01.2014 | 21.12.2014 | 31.03.2015 | 11.3 | 13.1 | 24.4 | 2.5 | 7.572 | 10.072 | 2.5 | 7.572 | 10.072 | 100% | 2547.38 | 110.2% | 0 | 0 | 0 | -15.46 | Completed
|  | 67b | 3: Improvements to Basavakalyan-Raichur road SH-51 from km 0.00 to 33.00 (in selected reaches) in Basavakalyan Tq.of Bidar Dist.; 4: 51; 15: 18.3; 16: 14.7; 17: 33; 18: 0; 19: 31; 20: 31; 21: 0; 22: 31; 23: 31; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 1989.24 | 1929.99 |  | 2311.59 | 220.33 | 2531.92 |  |  |  |  | 29.6 | 27.8 | 57.4 | 2.5 | 38.572 | 41.072 | 2.5 | 38.572 | 41.072 | 100% | 2547.38 |  | 0 | 0 | 0 | -15.46
GULBARGA DIVISION
2 | Pkg 68 | 68 | Improvements to Gulbarga - Hosur road SH-22 from km 58.15 to 99.80 (in selected reaches) in Gulbarga Dist. | 22 | 2193.5 | 2124.59 | CER No.: 21/2013-14 | 2534.94 | -147.6 | 2387.34 | M/s SRK construction | 26.12.2013 | 25.11.2014 | 2016-03-31 | 0 | 19.8 | 19.8 | 0 | 19.8 | 19.8 | 0 | 19.8 | 19.8 | 100% | 2288.62 | 90.28% | 0 | 0 | 0 | 98.72 | Completed
3 | Pkg 69 | 69a | Improvements to Basavakalyan - Raichur road SH-51 from km.32.85 to 115.00 (in selected reaches) in Gulbarga Dist. | 51 | 3251 | 3138.72 | CER No.: 23/2013-14 | 3750.42 | 367.46 | 4117.88 | M/S Haigreeva infratech projects ltd | 26.12.2013 | 25.11.2014 | 2016-03-31 | 12.6 | 39.3 | 51.9 | 0 | 25.3 | 25.3 | 0 | 25.3 | 25.3 | 100% | 4029.72 | 107.4% | 0 | 0 | 0 | 88.16 | Completed
|  | 69b | 3: Improvements to Bhalki - Chincholi road SH-75 from km.57.60 to 92.20 (in selected reaches) in Gulbarga Dist.; 4: 75; 15: 3; 16: 19; 17: 22; 18: 0; 19: 16.5; 20: 16.5; 21: 0; 22: 16.5; 23: 16.5; 24: 100%; 27: 0; 28: 0; 29: 0
4 | Pkg 70 | 70 | Improvements to Shahapur - Shivarampur road SH-149 from km.22.61 to 125.44 (in selected reaches)in Gulbarga Dist. | 149 | 2649 | 2564.76 | CER No.: 20/2013-14 | 2985.07 | 295.71 | 3280.78 | M/s S.M.Autade | 26.12.2013 | 25.11.2014 | 2015-10-31 | 7.94 | 49.69 | 57.63 | 0 | 33.99 | 33.99 | 0 | 33.99 | 33.99 | 100% | 3257.76 | 109.1% | 0 | 0 | 0 | 23.02 | Completed
5 | Pkg 71 | 71 | Improvements to Shahapur - Shivarampur road SH-149 from km.132.35 to 197.80 (in selected reaches) in Gulbarga Dist. | 149 | 2359 | 2273.03 | CER No.: 19/2013-14 | 2711.75 | 268.1 | 2979.85 | M/s S.M.Autade | 26.12.2013 | 25.11.2014 | 2015-10-31 | 19.09 | 40.57 | 59.66 | 3 | 22.01 | 25.01 | 3 | 22.01 | 25.01 | 100% | 2964.49 | 109.3% | 0 | 0 | 0 | 15.36 | Completed
DIVISION TOTAL |  |  |  |  | 10452.5 | 10101.1 |  | 11982.18 | 783.67 | 12765.85 |  |  |  |  | 42.63 | 168.36 | 210.99 | 3 | 117.6 | 120.6 | 3 | 117.6 | 120.6 | 100% | 12540.59 |  | 0 | 0 | 0 | 225.26
YADGIR DIVISION
6 | Pkg 72 | 72 | Improvements to Srirangapatna - Jewargi road SH-19 from km 505.500 to 542.00 (in selected reaches) in Yadgir Dist. | 19 | 2105 | 1951.24 | CER No.: 17/2013-14 | 2389.62 | 232.42 | 2622.04 | M/s H.P.Madhukar | 26.12.2013 | 25.11.2014 | 31.03.2015 | 0 | 37.2 | 37.2 | 12.5 | 38.2 | 50.7 | 12.5 | 38.2 | 50.7 | 100% | 2631.68 | 100.4% | 0 | 0 | 0 | -9.64 | Completed
7 | Pkg 73 | 73 | Improvements to Sindagi - Kodangal road SH-16 from km 40.00 to 73.30 (in selected reaches) in Yadgir Dist. | 16 | 1540.42 | 1408.33 | CER No.: 22/2013-14 | 1688.24 | 165.49 | 1853.73 | M/S Haigreeva infratech projects ltd | 26.12.2013 | 25.11.2014 | 2015-10-30 | 5 | 27.9 | 32.9 | 0 | 27.73 | 27.73 | 0 | 27.73 | 27.73 | 100% | 1847.34 | 99.66% | 0 | 0 | 0 | 6.39 | Completed
DIVISION TOTAL |  |  |  |  | 3645.42 | 3359.57 |  | 4077.86 | 397.91 | 4475.77 |  |  |  |  | 5 | 65.1 | 70.1 | 12.5 | 65.93 | 78.43 | 12.5 | 65.93 | 78.43 | 100% | 4479.02 | 100.1% | 0 | 0 | 0 | -3.25
GULBARGA CIRCLE TOTAL |  |  |  |  | 16087.16 | 15390.66 |  | 18371.63 | 1401.91 | 19773.54 |  |  |  |  | 77.23 | 261.26 | 338.49 | 18 | 222.102 | 240.102 | 18 | 222.102 | 240.102 | 100% | 19566.99 | 98.96% | 0 | 0 | 0 | 206.55
BELLARY CIRCLE
RAICHUR DIVISION
1 | 74 |  | Improvements to Managuli - Yeragera State Highway -127 frorn Krn 94.64 to Krn 134.91(selected reaches) in Devadurga Taluka of Raichur District. | 127 | 1968 | 1920.22 | CER No.: 14/2013-14 | 2252.9 | 222.1 | 2475 | M/S Haigreeva infratech projects ltd | 2013-12-28 | 2014-11-27 | 2016-03-31 | 4.72 | 35.1 | 39.82 | 0 | 36.4 | 36.4 | 0 | 36.4 | 36.4 | 100% | 2408.89 | 106.9% | 0 | 0 | 0 | 66.11 | Completed
2 | 75 | a | (a)Irnprovements to Managuli - Bichal State Highway - 61 from Km 194.34 to Krn 239.03 (selectecl reaches) in Manvi Taluka of Raichur District. | 61 | 3864.2 | 3675.138 | CER No.: 44/2013-14 | 4540.58 | 1117 | 5657.58 | M/s KBR Infratech Ltd | 2014-07-09 | 2015-06-08 | 2016-04-30 | 24.43 | 16.835 | 41.265 | 0 | 20.671 | 20.671 | 0 | 20.671 | 20.671 | 100% | 5155.69 | 113.5% | 0 | 0 | 0 | 501.89 | Completed
|  | b | 3: (b)Improvements to Deodurg - Bellary State Highway-128 from Km76.24 to Km 108.16 (selected reaches) in Sindanur Taluka of Raichur District.; 4: 128; 15: 9.66; 16: 18.3; 17: 27.96; 18: 0; 19: 21.46; 20: 21.46; 21: 0; 22: 21.46; 23: 21.46; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: (c )Improvements to Chikkesaruru - Mundargi State Highway-129 from Km 0.00 to Km 5l.63 (Selected reaches) in Lingasugur Taluka of Raichur District; 4: 129; 15: 32.76; 16: 8.57; 17: 41.33; 18: 0; 19: 19.53; 20: 19.53; 21: 0; 22: 19.53; 23: 19.53; 24: 100%; 27: 0; 28: 0; 29: 0
Division Total |  |  |  |  | 5832.2 | 5595.358 |  | 6793.48 | 1339.1 | 8132.58 |  |  |  |  | 71.57 | 78.805 | 150.375 | 0 | 98.061 | 98.061 | 0 | 98.061 | 98.061 | 100% | 7564.58 | 93.02% | 0 | 0 | 0 | 568
BELLARY DIVISION
3 | 76 | a | Improvements to Raravi - Belur State Highway-63 from Km 13.00 to Km 23.54 (selected reaches) in Siraguppa Taluka of Bellary District. | 63 | 2616 | 2558.56 | CER No.:16/2013-14 | 2829.39 | 703.3 | 3532.69 | Sri.Srinivasa Constructions (India) Pvt.Ltd | 2013-12-28 | 2014-11-27 | 2016-03-31 | 0 | 10.538 | 10.538 | 0 | 2.22 | 2.22 | 0 | 2.22 | 2.22 | 100% | 3443.41 | 121.7% | 0 | 0 | 0 | 89.28 | Completed
|  | b | 3: lmprovements to Deodurg - Bellary State Highway-128 from Km 117.11 to Km 180.44 (selected reaches) in Siraguppa Taluka of Bellary District.; 4: 128; 15: 27.19; 16: 29.65; 17: 56.84; 18: 0.3; 19: 56.22; 20: 56.52; 21: 0.3; 22: 56.22; 23: 56.52; 24: 100%; 27: 0; 28: 0; 29: 0
4 | 77 |  | lmprovements to Deodurg - Bellary State Highway-128 from 180.44 Km to Km266.26 (selected reaches) in Bellary Taluka of Bellary District. | 128 | 2497 | 2429.72 | CER NO:15/2013-14 | 2699.59 | 260.75 | 2960.34 | Sri.Srinivasa Constructions (India) Pvt.Ltd | 2013-12-28 | 2014-11-27 | 30.05.2015 | 46.68 | 24.63 | 71.31 | 20.76 | 33.81 | 54.57 | 20.76 | 33.81 | 54.57 | 100% | 2594.84 | 96.12% | 0 | 0 | 0 | 365.5 | Completed
DIVISION TOTAL |  |  |  |  | 5113 | 4988.28 |  | 5528.98 | 964.05 | 6493.03 |  |  |  |  | 73.87 | 64.818 | 138.688 | 21.06 | 92.25 | 113.31 | 21.06 | 92.25 | 113.31 | 100% | 6038.25 | 93% | 0 | 0 | 0 | 454.78
HADAGALI DIVISION
5 | 78 | a | Improvements to Ekkumbi - Molakalmur State Highway-02 from Km 166.00 to Km 205.80 (in selected reaches) in Kudlgi Taluka of Bellary District. | 2 | 1214 | 1176.69 | CER NO:18/2013-14 | 1396.15 | 136.36 | 1532.51 | Sali Basavaraj | 2013-12-28 | 2014-11-27 | 27.11.2014 | 0 | 7.8 | 7.8 | 0 | 7.8 | 7.8 | 0 | 7.8 | 7.8 | 100% | 1507.93 | 98.4% | 0 | 0 | 0 | 24.58 | Completed
|  | b | 3: lmprovements to Arabhavi - Challakere State Highway-45 from Km 199.52 to Km 234.10 (selected reaches) in Hadagali Taluka of Bellary District; 4: 45; 15: 0; 16: 16.085; 17: 16.085; 18: 0; 19: 16.3; 20: 16.3; 21: 0; 22: 16.3; 23: 16.3; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 1214 | 1176.69 | 0 | 1396.15 | 136.36 | 1532.51 |  | 41636 |  |  | 0 | 23.885 | 23.885 | 0 | 24.1 | 24.1 | 0 | 24.1 | 24.1 | 100% | 1507.93 | 98.4% | 0 | 0 | 0 | 24.58
KOPPAL DIVISION
6 | 79 | a | lmprovements to Sindhanoor - Hemmadga StateHighway-30 from Km 64.20 to Km 80.14 (selected reaches) in Kustagi Taluka of Koppal District | 30 | 2013 | 1973.39 | CER No:45/2013-14 | 2317.36 | 229.94 | 2547.3 | Sri.Sai Constructions | 2013-12-26 | 2014-11-25 | 31.03.2015 | 15.94 | 0 | 15.94 | 6.19 | 1.6 | 7.79 | 6.19 | 1.6 | 7.79 | 100% | 2435.39 | 95.61% | 0 | 0 | 0 | 111.91 | Completed
|  | b | 3: lmprovements to Chickhesaruru - Mundargi State Highway-129 from Km 144.40 to Km 183.00 (selected reaches) in Koppal Taluka of Koppal District; 4: 129; 15: 27.78; 16: 10.82; 17: 38.6; 18: 0; 19: 34.7; 20: 34.7; 21: 0; 22: 34.7; 23: 34.7; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Chickhesaruru - Mundargi State Highway-129 fiom Km 52.62 to Km 144.40 (selected reaches) in Kustagi Taluka of Koppal District; 4: 129; 15: 8.56; 16: 13; 17: 21.56; 18: 8.53; 19: 13.11; 20: 21.64; 21: 8.53; 22: 13.11; 23: 21.64; 24: 100%; 27: 0; 28: 0; 29: 0
7 | 80 |  | Improvements to Raravi - Belur State Highway-63 from Km 58.22 to Km 159.48 (selected reaches) in Gangavati, Koppal & Yalaburga Talukas of Koppal District | 63 | 2218 | 2150.52 | CER No:43/2013-14 | 2395.8 | 238.03 | 2633.83 | Sri.Saranappa R Alur | 2013-12-28 | 2014-11-27 | 27.11.2014 | 61.81 | 21.02 | 82.83 | 0 | 53.07 | 53.07 | 0 | 53.07 | 53.07 | 100% | 2586.77 | 98.21% | 0 | 0 | 0 | 47.06 | Completed
Division Total |  |  |  |  | 4231 | 4123.91 |  | 4713.16 | 467.97 | 5181.13 |  |  |  |  | 114.09 | 44.84 | 158.93 | 14.72 | 102.48 | 117.2 | 14.72 | 102.48 | 117.2 | 100% | 5022.16 | 96.93% | 0 | 0 | 0 | 158.97
BELLARY CIRCLE TOTAL |  |  |  |  | 16390.2 | 15884.238 |  | 18431.77 | 2907.48 | 21339.25 |  |  |  |  | 259.53 | 212.348 | 471.878 | 35.78 | 316.891 | 352.671 | 35.78 | 316.891 | 352.671 | 100% | 20132.92 | 94.35% | 0 | 0 | 0 | 1206.33
DHARWAD CIRCLE
GADAG DIVISION
1 | 81 | a | Improvements to Kalmala - Shiggaon State Highway-23 Km 203.75 to Km 273.61 (selected reaches) in Mundargi & Shirahatti Taluk of Gadag Dist. | 23 | 3355.59 | 3285.07 | CER No.: 05/2013-14 | 3804.44 | 377.85 | 4182.29 | M/S P R Nayak Associates | 26.12.13 | 25.11.14 | 31.03.2015 | 10 | 46.34 | 56.34 | 0 | 55.95 | 55.95 | 0 | 55.95 | 55.95 | 100% | 4161.58 | 99.5% | 0 | 0 | 0 | 20.71 | Completed
|  | b | 3: Improvements to Arabhavi - Challakere State Highway-45 Km 174.00 to Km 185.60 (selected reaches) in Mundargi Taluk of Gadag Dist.; 4: 45; 15: 0; 16: 11.6; 17: 11.6; 18: 1.28; 19: 0; 20: 1.28; 21: 1.28; 22: 0; 23: 1.28; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 3355.59 | 3285.07 |  | 3804.44 | 377.85 | 4182.29 |  |  |  |  | 10 | 57.94 | 67.94 | 1.28 | 55.95 | 57.23 | 1.28 | 55.95 | 57.23 | 100% | 4161.58 | 99.5% | 0 | 0 | 0 | 20.71
HAVERI DIVISION
2 | 82 | a | Improvement to Bagalkote-Biligiriranganabetta State Highway-57 from Km 167.89 to Km 196.72 (selected reaches) in Haveri Taluk of Haveri Dist | 57 | 2108.18 | 1997.7 | CER No.: 06/2013-14 | 2474.16 | 245.76 | 2719.92 | S R Ballary | 26.12.13 | 25.11.14 | 25.11.2014 | 0 | 18.18 | 18.18 | 0 | 15.595 | 15.595 | 0 | 15.6 | 15.6 | 100% | 2733.33 | 100.5% | 0 | -0.005 | -0.005 | -13.41 | Completed
|  | b | 3: Improvements to Bagalkote-Biligiriranganabetta State Highway-57 from Km 236.83 to Km 258.03 (selected reaches) in Hirekerur Taluk of Haveri Dist; 4: 57; 15: 0; 16: 19.27; 17: 19.27; 18: 0; 19: 13.204; 20: 13.204; 21: 0; 22: 13.2; 23: 13.2; 24: 99.97%; 27: 0; 28: 0.004; 29: 0.004
3 | 83 | a | Improvements to Birur-Sammasagi State Highway-76 from Km 176.30 to 181.35 & Km 185.70 to 188.00 (selected reaches) in Byadagi Tq &Km 189.00 to 217.19 (selected reaches) in Hangal Taluk of Haveri Dist | 76 | 2374.84 | 2300.73 | CER No.: /2013-14 | 2863.65 | 714.63 | 3578.28 | A V Patil | 21.12.2013 | 20.11.2014 | 25.02.2015 | 21.01 | 10.05 | 31.06 | 18.765 | 11.996 | 30.761 | 18.765 | 11.996 | 30.761 | 100% | 3581.08 | 100.1% | 0 | 0 | 0 | -2.8 | Completed
|  | b | 3: Improvements to Kumata-Tadas State Highway-69 from Km 126.10 to Km 142.00 (selected reaches) in Shiggaon Taluk of Haveri Dist.; 4: 69; 15: 8.9; 16: 1; 17: 9.9; 18: 0.49; 19: 6.82; 20: 7.31; 21: 0.49; 22: 6.82; 23: 7.31; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Kalmala - Shiggaon State Highway-23 from Km 284.51 to Km 304.48 (selected reaches) in Shiggon Taluk of Haveri Dist.; 4: 23; 15: 13.97; 16: 1; 17: 14.97; 18: 4.5; 19: 0.95; 20: 5.45; 21: 4.5; 22: 0.95; 23: 5.45; 24: 100%; 27: 5.6843e-14; 28: 0; 29: 5.6843e-14
|  | d | 3: Improvements to Karwar-Ilkal State Highway-06 from Km 170.00 to Km 194.02 (selected reaches) in Savanur Taluk of Haveri Dist.; 4: 6; 15: 0; 16: 17.47; 17: 17.47; 18: 0; 19: 12.35; 20: 12.35; 21: 0; 22: 12.35; 23: 12.35; 24: 100%; 27: 0; 28: 0; 29: 0
4 | 84 |  | Improvements to Hanagal - Hirekeruru via Hosaaladakatti and Honkana road from Km 4.33 to Km 23.80 & Km 22.64 to Km 31.00 (Selected reaches) in Hanagal & Hirekerur of Haveri Dist | MDR | 1700 | 1632.86 | CER NO: 62/2013-14 | 1983.09 | 194.86 | 2177.95 | S R Ballary | 26.12.13 | 25.11.14 | 25.02.2015 | 0 | 18.5 | 18.5 | 0 | 18.33 | 18.33 | 0 | 18.33 | 18.33 | 100% | 2116.97 | 97.2% | 0 | 0 | 0 | 60.98 | Completed
DIVISION TOTAL |  |  |  |  | 6183.02 | 5931.29 |  | 7320.9 | 1155.25 | 8476.15 |  |  |  |  | 43.88 | 85.47 | 129.35 | 23.755 | 79.245 | 103 | 23.755 | 79.246 | 103.001 | 100% | 8431.38 | 99.47% | 5.6843e-14 | -0.001 | -0.001 | 44.77
SIRSI DIVISION
5 | 85 | a | Improvements to Khanapur - Talaguppa State Highway-93 from Km 131.99 to Km 150.00 (selected reaches) in Sirsi Taluk of Uttarakannada Dist. | 93 | 2459.35 | 2360.43 | CER NO: 24/2013-14 | 2772.35 | 276.17 | 3048.52 | H P Madhukar | 26.12.13 | 25.11.14 | 06.06.2014 | 19.01 | 0 | 19.01 | 17.65 | 0 | 17.65 | 17.65 | 0 | 17.65 | 100% | 3029.98 | 99.39% | 0 | 0 | 0 | 18.54 | Completed
|  | b | 3: Improvements to Khanapur - Talaguppa State Highway-93 from Km 179.60 to Km 184.80 & Km 188.82 to 201.00 (selected reaches) in Siddapur Taluk of Uttarakannada Dist.; 4: 93; 15: 17.4; 16: 0; 17: 17.4; 18: 14.54; 19: 2.86; 20: 17.4; 21: 14.54; 22: 2.86; 23: 17.4; 24: 100%; 27: 0; 28: 0; 29: 0
|  | C | 3: Improvements to Khanapur - Talaguppa State Highway-93 from Km 86.85 to Km 93.01 & Km 98.56 to Km 130.99 (selected reaches) in Yellapur Taluk of Uttarakannada Dist.; 4: 93; 15: 32.94; 16: 5.65; 17: 38.59; 18: 32.64; 19: 5.95; 20: 38.59; 21: 32.64; 22: 5.95; 23: 38.59; 24: 100%; 27: 0; 28: 0; 29: 0
|  | d | 3: Improvements to Khanapur - Talaguppa State Highway-93 from Km 35.42 to Km 81.85 (selected reaches) in Haliyal Taluk of Uttarakannada Dist.; 4: 93; 15: 43.33; 16: 0; 17: 43.33; 18: 35.43; 19: 7.9; 20: 43.33; 21: 35.43; 22: 7.9; 23: 43.33; 24: 100%; 27: 0; 28: 0; 29: 0
6 | 86 | a | Improvements to Karwar - Ilkal State Highway-06 from Km 125.00 to Km 154.40 (selected reaches) in Mundagod Taluk of Uttarakannada Dist. | 6 | 2215.22 | 2100.43 | CER No: 08/2013-14 | 2498.14 | 619.38 | 3117.52 | M/S N S Nayak & Sons | 26.12.13 | 25.11.14 | 25.03.2015 | 23.6 | 4.8 | 28.4 | 17 | 11.4 | 28.4 | 17 | 11.4 | 28.4 | 100% | 3111.69 | 99.81% | 0 | 0 | 0 | 5.83 | Completed
|  | b | 3: Improvements to Supa - Annigeri State Highway-28 from Km 33.85 to Km 41.31 (selected reaches) in Haliyal Taluk of Uttarakannada Dist.; 4: 28; 15: 0; 16: 7.46; 17: 7.46; 18: 0; 19: 7.46; 20: 7.46; 21: 0; 22: 7.46; 23: 7.46; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Supa - Annigeri State Highway-28 from Km 12.30 to 29.51 (selected reaches) in Haliyal Taluk of Uttarakannada Dist.; 4: 28; 15: 14.71; 16: 2.5; 17: 17.21; 18: 8.73; 19: 7.19; 20: 15.92; 21: 8.73; 22: 7.19; 23: 15.92; 24: 100%; 27: 0; 28: 0; 29: 0
|  | d | 3: Improvements to Sidhanur -Hemmadaga State Highway-30 from Km 309.07 to 318.57 (selected reaches) in Joida Taluk of Uttarakannada Dist.; 4: 30; 15: 0; 16: 9.38; 17: 9.38; 18: 0; 19: 9.5; 20: 9.5; 21: 0; 22: 9.5; 23: 9.5; 24: 100%; 27: 0; 28: 0; 29: 0
7 | 87 | a | Improvements to Kumta - Tadas State Highway-69 from Km 92.00 to Km 95.00 & Km 98.00 to Km 107.00 & Km 115.00 to Km 117.00 & Km 122.00 to Km 123.00 (selected reaches) in Mundagod Taluk of Uttarakannada Dist. | 69 | 1398.2 | 1345.03 | CER No: 25/2013-14 | 1361.21 | 135.68 | 1496.89 | H.P.Madhukar | 01.02.14 | 31.12.14 | 25.03.2015 | 15 | 0 | 15 | 6.635 | 8.465 | 15.1 | 6.635 | 8.465 | 15.1 | 100% | 1496.72 | 99.99% | 0 | 0 | 0 | 0.17 | Completed
|  | b | 3: Improvements to Kumta - Tadas State Highway-69 from Km 83.70 to Km 92.00 & Km 95.00 to Km 98.00 & Km 107.00 to Km 115.00 & Km 117.00 to Km 122.00 & Km 123.00 to Km 126.0 (selected reaches) in Mundagod Taluk of Uttarakannada Dist.; 4: 69; 15: 0; 16: 27.3; 17: 27.3; 18: 15.1; 19: 12.2; 20: 27.3; 21: 15.1; 22: 12.2; 23: 27.3; 24: 100%; 27: 0; 28: 0; 29: 0
8 | 88 | a | Improvements to Aurad - Sadashivagad State Highway-34 from Km 661.02 to Km 661.77 & Km 668.87 to Km 684.17 (selected reaches) in Joida Taluk of Uttarakannada Dist. | 34 | 2220.94 | 2156.6 | CER No: 26/2013-14 | 2199.88 | 216.41 | 2416.29 | M/S N S Nayak & Sons | 18.01.13 | 17.12.14 | 25.11.2014 | 0 | 16.05 | 16.05 | 3.14 | 12.91 | 16.05 | 3.14 | 12.91 | 16.05 | 100% | 2383.41 | 98.64% | 0 | 0 | 0 | 32.88 | Completed
|  | b | 3: Improvements to Aurad - Sadashivagad State Highway-34 from Km 604.17 to Km 661.02 & Km 661.77 to Km 668.87 & Km 684.17 to Km 687.56 (selected reaches) in Joida Taluk of Uttarakannada Dist.; 4: 34; 15: 67.34; 16: 0; 17: 67.34; 18: 47.39; 19: 19.95; 20: 67.34; 21: 47.39; 22: 19.95; 23: 67.34; 24: 100%; 27: 0; 28: 6.7502e-14; 29: 6.7502e-14
DIVISION TOTAL |  |  |  |  | 8293.71 | 7962.49 |  | 8831.58 | 1247.64 | 10079.22 |  |  |  |  | 233.33 | 73.14 | 306.47 | 198.255 | 105.785 | 304.04 | 198.255 | 105.785 | 304.04 | 100% | 10021.8 | 99.43% | 0 | 6.7502e-14 | 6.7502e-14 | 57.42
KARWAR DIVISION
9 | 89 |  | Improvements to Aurad - Sadashivagad State Highway-34 from Km 687.56 to 725.34 (selected reaches) in Karwar Taluk of Uttarakannada dist. | 34 | 757 | 735.59 | CER No: 27/2013-14 | 695.09 | 68.48 | 763.57 | M/S Ramasree Globle Consrtution Pvt. Ltd. | 26.12.13 | 25.11.14 | 25.11.2014 | 34.48 | 0.3 | 34.78 | 31.79 | 2.99 | 34.78 | 31.79 | 2.99 | 34.78 | 100% | 761.94 | 99.79% | 0 | 0 | 0 | 1.63 | Completed
DIVISION TOTAL |  |  |  |  | 757 | 735.59 |  | 695.09 | 68.48 | 763.57 |  |  |  |  | 34.48 | 0.3 | 34.78 | 31.79 | 2.99 | 34.78 | 31.79 | 2.99 | 34.78 | 100% | 761.94 | 99.79% | 0 | 0 | 0 | 1.63
DHARWAD DIVISION
10 | 90 | a | Improvements to Padubidri - Chikkalgudda State Highway-01 from Km 356.96 to Km 393.08 (selected reaches) in Dharwad Taluk of Dharwad Dist | 1 | 1678.69 | 1641.16 | CER No: 29/2013-14 | 1640.59 | 163.18 | 1803.77 | B S Gaonkar | 26.12.13 | 25.11.14 | 20.02.2015 | 0 | 27.64 | 27.64 | 2.3 | 24.44 | 26.74 | 2.3 | 24.44 | 26.74 | 100% | 1830.62 | 101.5% | 0 | 0 | 0 | -26.85 | Completed
|  | b | 3: Improvements to Padubidri - Chikkalgudda State Highway-01 from Km 364.50 to Km 367.38 (selected reaches) in Kalagatagi Taluk of Dharwad Dist; 4: 1; 15: 2.48; 16: 1; 17: 3.48; 18: 0.38; 19: 2.5; 20: 2.88; 21: 0.38; 22: 2.5; 23: 2.88; 24: 100%; 27: 4.5519e-15; 28: 0; 29: 4.5519e-15
11 | 91 | a | Improvements to Mangasuli - Laxmeshwar State Highway-73 from Km 204.16 to Km 229.20 & Km 248.42 to Km 253.30 (selected reaches)in Dharwad & Hubli Taluk of Dharwad Dist | 73 | 1999.41 | 1958.27 | CER No: 30/2013-14 | 2126.75 | 210.66 | 2337.41 | M/S N S Nayak & Sons | 26.12.13 | 25.11.14 | 31.05.2014 | 0 | 15.77 | 15.77 | 4 | 9.03 | 13.03 | 4 | 9.03 | 13.03 | 100% | 2349.42 | 100.5% | 0 | 0 | 0 | -12.01 | Completed
|  | b | 3: Improvements to Arabhavi - Challakere State Highway-45 from Km 93.25 to Km 107.25 (selected reaches)in Navalgund Taluk of Dharwad Dist; 4: 45; 15: 0; 16: 14; 17: 14; 18: 0; 19: 11.98; 20: 11.98; 21: 0; 22: 11.98; 23: 11.98; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Mangasuli - Laxmeshwar State Highway-73 from Km 223.379 to Km 229.200 & Km 248.42 to Km 253.30 (selected reaches)in Hubli Taluk of Dharwad Dist; 4: 73; 15: 10.52; 16: 0.3; 17: 10.82; 18: 6.87; 19: 1.52; 20: 8.39; 21: 6.87; 22: 1.52; 23: 8.39; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 3678.1 | 3599.43 |  | 3767.34 | 373.84 | 4141.18 |  |  |  |  | 13 | 58.71 | 71.71 | 13.55 | 49.47 | 63.02 | 13.55 | 49.47 | 63.02 | 100% | 4180.04 | 100.9% | 4.5519e-15 | 0 | 4.5519e-15 | -38.86
DHARWAD CIRCLE TOTAL |  |  |  |  | 22267.42 | 21513.87 |  | 24419.35 | 3223.06 | 27642.41 |  |  |  |  | 334.69 | 275.56 | 610.25 | 268.63 | 293.44 | 562.07 | 268.63 | 293.441 | 562.071 | 100% | 27556.74 | 99.69% | 6.1395e-14 | -0.001 | -0.001 | 85.67
BELGAUM CIRCLE
BELGAUM DIVISION
1 | 92 |  | Improvements to Sindanoor - Hemmadaga State Highway-30 from Km 168.17 to Km 304.20 (selected reaches)in Khanapur, Bailhongal & Savadatti Taluk of Belgaum Dist | 30 | 2551.42 | 2471.58 | CER No.: 28/2013-14 | 2962.74 | 295.66 | 3258.4 | N B Hiremath | 2014-02-21 | 2015-01-21 | 15.05.2015 | 25.5 | 40.83 | 66.33 | 9.84 | 51.49 | 61.33 | 9.84 | 51.49 | 61.33 | 100% | 3212.93 | 98.6% | 0 | 0 | 0 | 45.47 | Completed
2 | 93 |  | Improvements to Jath - Jamboti State Highway-31 from Km 127.50 to Km 219.00 (selected reaches) in Khanapur, Belagavi & Bailhongal Taluk of Belgaum Dist | 31 | 1635.19 | 1587.56 | CER No.: 31/2013-14 | 1777.8 | 177.31 | 1955.11 | M B Kallur | 2013-12-28 | 27-11-2014 | 12.02.2015 | 7.41 | 28.74 | 36.15 | 1 | 35.52 | 36.52 | 1 | 35.52 | 36.52 | 100% | 1940.72 | 99.26% | 0 | 0 | 0 | 14.39 | Completed
3 | 94 |  | Improvements to Munvalli - Kotamachagi State Highway-83 from Km 8.30 to Km 38.60 & Km 40.91 to Km 63.14 (selected reaches) in Ramadurga Taluk of Belgaum Dist | 83 | 1718.39 | 1668.19 | CER No.:32/2013-14 | 1932.42 | 193.12 | 2125.54 | N B Hiremath | 2013-12-28 | 2014-11-27 | 25.02.2015 | 14.18 | 30.39 | 44.57 | 0 | 29.83 | 29.83 | 0 | 29.83 | 29.83 | 100% | 2101.31 | 98.86% | 0 | 0 | 0 | 24.23 | Completed
4 | 95 |  | Improvements to Mangasuli - Laxmeshwar State Highway-73 from Km 122.67 to Km 204.16 (selected reaches) in Bailhongal Taluk of Belgaum Dist | 73 | 2161.26 | 2098.31 | CER NO:33/2013-14 | 2552.22 | 237.79 | 2790.01 | P R Nayak | 2013-12-28 | 2014-11-27 | 27.11.2014 | 21.23 | 34.73 | 55.96 | 10.76 | 45.2 | 55.96 | 10.76 | 45.2 | 55.96 | 100% | 2768.72 | 99.24% | 0 | 0 | 0 | 21.29 | Completed
5 | 96 | a | Improvements to Aurad - Sadashivagad State Highway-34 from Km.442.19 to Km 462.570 (selected reaches) in Ramadurg Taluk of Belgaum Dist | 34 | 2222.73 | 2156.82 | CER NO:34/2013-14 | 2633.1 | 262.76 | 2895.86 | P B Ibrahim | 2013-12-28 | 2014-11-27 | 25.11.2014 | 10.2 | 6.78 | 16.98 | 5.4 | 11.4 | 16.8 | 5.4 | 11.4 | 16.8 | 100% | 2883.91 | 99.59% | 0 | 0 | 0 | 11.95 | Completed
|  | b | 3: Improvements to Padabudri - Chikalgudda State Highway-01 from Km 393.08 to Km 446.69 (selected reaches)in Bailhongal Taluk of Belgaum Dist; 4: 1; 15: 9.23; 16: 14.02; 17: 23.25; 18: 4.51; 19: 18.78; 20: 23.29; 21: 4.51; 22: 18.776; 23: 23.286; 24: 99.98%; 27: 0; 28: 0.004; 29: 0.004
|  | C | 3: Improvements to Arbhavi - Challakere State Highway-45 from Km 35.93 to Km 79.05 (selected reaches) in Savadatti Taluk of Belgaum Dist; 4: 45; 15: 43.12; 16: 0; 17: 43.12; 18: 37.72; 19: 5.4; 20: 43.12; 21: 37.72; 22: 5.4; 23: 43.12; 24: 100%; 27: 0; 28: 0; 29: 0
6 | 97 | a | Improvements to Yaragatti - Babaleshwar State Highway-55 from Km 28.46 to Km 39.62 (seleted reaches) in Gokak Taluk of Belgaum Dist | 55 | 1261.53 | 1224.99 | CER No:35/2013-14 | 1492.94 | 147.36 | 1640.3 | P B Ibrahim | 2013-12-26 | 2014-11-25 | 31.03.2015 | 0 | 9 | 9 | 0 | 8.9 | 8.9 | 0 | 8.9 | 8.9 | 100% | 1635.75 | 99.72% | 0 | 0 | 0 | 4.55 | Completed
|  | b | 3: Improvements to Jamboti - Rabakavi State Highway-54 from Km 58.28 to Km 123.00 (in seleted reaches)in Gokak Taluk of Belgaum Dist; 4: 54; 15: 26.2; 16: 10; 17: 36.2; 18: 0; 19: 16.9; 20: 16.9; 21: 0; 22: 16.9; 23: 16.9; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 11550.52 | 11207.45 |  | 13351.22 | 1314 | 14665.22 |  |  |  |  | 157.07 | 174.49 | 331.56 | 69.23 | 223.42 | 292.65 | 69.23 | 223.416 | 292.646 | 100% | 14543.34 | 99.17% | 0 | 0.004 | 0.004 | 121.88
BIJAPUR DIVISION
7 | 98 | a | Improvements to Alamatti-Muddebihal from Km 0.00 to Km 27.00 (selected reaches) in Muddebihal Taluk of Bijapur Dist |  | 2291.82 | 2221.75 | CER No:37/2013-14 | 2448.85 | 243.74 | 2692.59 | S S Alur | 2013-12-28 | 2014-11-27 | 25.11.2014 | 6 | 21 | 27 | 0 | 13.75 | 13.75 | 0 | 13.75 | 13.75 | 100% | 2715.76 | 100.9% | 0 | 0 | 0 | -23.17 | Completed
|  | b | 3: Improvements to Sindagi-Kodangal State Highway-16 from Km 0.00 to Km 25.00 (selected reaches) in Sindagi Taluk of Bijapur Dist; 4: 16; 15: 0; 16: 24.1; 17: 24.1; 18: 0; 19: 16.2; 20: 16.2; 21: 0; 22: 16.2; 23: 16.2; 24: 100%; 27: 0; 28: 0; 29: 0
8 | 99 |  | Improvements to Yaragatti - Babaleshwar State Highway-55 from Km 78.90 to Km 110.00 (selected reaches) in Bijapur Taluk of Bijapur Dist | 55 | 1729 | 1605.2 | CER No:36/2013-14 | 1574.07 | 154.33 | 1728.4 | Sadashiv Chikkkareddy | 2013-12-28 | 2014-11-27 | 25.11.2014 | 0 | 31.1 | 31.1 | 0 | 16.82 | 16.82 | 0 | 16.82 | 16.82 | 100% | 1685.3 | 97.51% | 0 | 0 | 0 | 43.1 | Completed
9 | 100 |  | Improvements to Aurad - Sadashivagad State Highway-34 from Km 232.54 to Km 328.62 (selected reaches)in Sindagi, Indi & Bijapur Taluk of Bijapur Dist | 34 | 2049.93 | 1986.85 | CER No:38/2013-14 | 2111.94 | 211.05 | 2322.99 | S M Autade | 2013-12-28 | 2014-11-27 | 28.11.2014 | 22.49 | 32 | 54.49 | 0 | 41.65 | 41.65 | 0 | 41.65 | 41.65 | 100% | 2278.17 | 98.07% | 0 | 0 | 0 | 44.82 | Completed
Division Total |  |  |  |  | 6070.75 | 5813.8 |  | 6134.86 | 609.12 | 6743.98 |  |  |  |  | 28.49 | 108.2 | 136.69 | 0 | 88.42 | 88.42 | 0 | 88.42 | 88.42 | 100% | 6679.23 | 99.04% | 0 | 0 | 0 | 64.75
BAGALKOTE DIVISION
10 | 101 |  | lmprovements to Sankeshwar - Sangam State Highway 44 from 76.54 Km to Km 201.26 (selected reaches) in Mudhol, Badami & Hunagund Talukas of Bagalkote Dist & Gokak Taluka of Belaeavi Dist. | 44 | 2358.55 | 2284.03 | CER No:47/2013-14 | 2678.57 | 266.86 | 2945.43 | SS Alur | 2013-12-28 | 2014-11-27 | 31.03.2015 | 63.8 | 21.2 | 85 | 27.88 | 31.71 | 59.59 | 27.88 | 31.71 | 59.59 | 100% | 2950.32 | 100.2% | 0 | 0 | 0 | -4.89 | Completed
11 | 102a |  | Improvements to Jamboti - Rabakavi State Highway- 54 from Km 121.00 to Km 140.70 (selected reaches) in Mudhol & JamkhandiTalukas of Baealkote Dist | 54 | 893.14 | 866.24 | CER No:48/2013-14 | 911.12 | 90.23 | 1001.35 | B N Nagana Gouda | 2013-12-28 | 2014-11-27 | 31.03.2015 | 6.98 | 9.47 | 16.45 | 9.35 | 6.98 | 16.33 | 9.35 | 6.98 | 16.33 | 100% | 1003.71 | 100.2% | 0 | 0 | 0 | -2.36 | Completed
12 | 102b |  | 3: Improvements to Kagawad - Kaladagi State Highway- 53 from Km 93.31 to Km 119.58 (selected reaches) in Mudhol & JamkhandiTalukas of Basalkote Dist; 4: 53; 15: 14.43; 16: 0; 17: 14.43; 18: 11.72; 19: 1.6; 20: 13.32; 21: 11.72; 22: 1.6; 23: 13.32; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 3251.69 | 3150.27 |  | 3589.69 | 357.09 | 3946.78 |  |  |  |  | 85.21 | 30.67 | 115.88 | 48.95 | 40.29 | 89.24 | 48.95 | 40.29 | 89.24 | 100% | 3954.03 | 100.2% | 0 | 0 | 0 | -7.25
BELGAUM CIRCLE TOTAL |  |  |  |  | 20872.96 | 20171.52 |  | 23075.77 | 2280.21 | 25355.98 |  |  |  |  | 270.77 | 313.36 | 584.13 | 118.18 | 352.13 | 470.31 | 118.18 | 352.126 | 470.306 | 100% | 25176.6 | 99.29% | 0 | 0.004 | 0.004 | 179.38
NORTH ZONE TOTAL |  |  |  |  | 75617.74 | 72960.288 |  | 84298.52 | 9812.66 | 94111.18 |  |  |  |  | 942.22 | 1062.528 | 2004.748 | 440.59 | 1184.563 | 1625.153 | 440.59 | 1184.56 | 1625.15 | 100% | 92433.25 | 98.22% | 6.1395e-14 | 0.003 | 0.003 | 1677.93
SOUTH ZONE
DAVANAGERE DIVISION
1 | 103 | a | Improvements to Kumta - Kadamadagi State Highway-48 from Km 158.00 to Km 174.50 (selected reaches) in Honnali Taluka of Davanagere Dist | 48 | 3661.38 | 3449.62 | CER No.: 58/2013-14 | 4020.81 | 384.7 | 4405.51 | M/S Haigreeva infratech projects ltd | 2013-12-27 | 2014-11-26 | 2015-11-26 | 0 | 25.1 | 25.1 | 0 | 25.1 | 25.1 | 0 | 25.1 | 25.1 | 100% | 4410.33 | 100.1% | 0 | 0 | 0 | -4.82 | Completed
|  | b | 3: Improvements to Hulikal - Halageri State Highway-26 from Km 28.95 to Km 39.05 (selected reaches) in Honnali Taluka of Davanagere Dist; 4: 26; 15: 5.15; 16: 3.85; 17: 9; 18: 5.15; 19: 3.85; 20: 9; 21: 5.15; 22: 3.85; 23: 9; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Kumta - Kadamadagi State Highway-48 from Km 185.83 to Km 226.03 (selected reaches) in Channagiri Taluka of Davanagere Dist; 4: 48; 15: 0; 16: 33; 17: 33; 18: 0; 19: 33.55; 20: 33.55; 21: 0; 22: 33.55; 23: 33.55; 24: 100%; 27: 0; 28: 0; 29: 0
| Package Total |  |  |  | 3661.38 | 3449.62 |  | 4020.81 | 384.7 | 4405.51 |  |  |  |  | 5.15 | 61.95 | 67.1 | 5.15 | 62.5 | 67.65 | 5.15 | 62.5 | 67.65 | 100% | 4410.33 | 100.1% | 0 | 0 | 0 | -4.82
2 | 104 |  | Improvements to Mandya - Hadagali State Highway-47 from Km 275.63 to Km 293.89& Km 323.30 to Km 338.10 (selected reaches) in Davangere & Harapanahalli Taluka of Davanagere Dist | 47 | 1561.33 | 1503.91 | CER No.:39/2013-14 | 1804.32 | 10.69 | 1815.01 | M/S VDB Projects (P) Ltd | 2013-12-26 | 2014-11-25 | 2016-03-31 | 2.77 | 29.14 | 31.91 | 2.77 | 29.14 | 31.91 | 2.77 | 29.14 | 31.91 | 100% | 1796.64 | 98.99% | 0 | 0 | 0 | 18.37 | Completed
3 | 105 |  | Improvements to Mandya - Hadagali State Highway-47 from Km 293.83 to Km 323.30 (selected reaches) in Harapanahalli Taluka of Davanagere Dist | 47 | 1582.44 | 1531.97 | CER NO:13/2013-14 | 1849.4 | 250.16 | 2099.56 | M/S VDB Projects (P) Ltd | 2013-12-26 | 2014-11-25 | 2016-03-31 | 8.61 | 20.86 | 29.47 | 8.61 | 20.86 | 29.47 | 8.61 | 20.86 | 29.47 | 100% | 2086.02 | 99.36% | 0 | 0 | 0 | 13.54 | Completed
DIVISION TOTAL |  |  |  |  | 6805.15 | 6485.5 |  | 7674.53 | 645.55 | 3914.57 |  |  |  |  | 16.53 | 111.95 | 128.48 | 16.53 | 112.5 | 129.03 | 16.53 | 112.5 | 129.03 | 100% | 3882.66 | 99.18% | 0 | 0 | 0 | 31.91
CHITRADURGA DIVISION
4 | 106 | a | Improvements to Malpe- Molakalmooru State Highway-65 from Km 337.95 to Km 382.17 (selected reaches) in Molakalmooru Taluka of Chitradurga Dist | 65 | 2407.9 | 2240.45 | CER NO:46/2013-14 | 2887.1 | 278.8 | 3165.9 | Sri A. Balaram Reddy | 2014-02-13 | 2015-01-12 | 12.03.2015 | 0.42 | 11.53 | 11.95 | 0.42 | 11.43 | 11.85 | 0.42 | 11.43 | 11.85 | 100% | 3169.02 | 100.1% | 0 | 0 | 0 | -3.12 | Completed
|  | b | 3: Improvements to Mandya - Hadagali State Highway-47 from Km 178.31 to Km 267.30 (selected reaches) in Hosadurga Taluka of Chitradurga Dist; 4: 47; 15: 7.69; 16: 21.91; 17: 29.6; 18: 4.917; 19: 24.418; 20: 29.335; 21: 4.917; 22: 24.418; 23: 29.335; 24: 100%; 27: 0; 28: 0; 29: 0
| Package Total |  |  |  | 2407.9 | 2240.45 |  | 2887.1 | 278.8 | 3165.9 |  |  |  |  | 8.11 | 33.44 | 41.55 | 5.337 | 35.848 | 41.185 | 5.337 | 35.848 | 41.185 | 100% | 3169.02 | 100.1% | 0 | 0 | 0 | -3.12
DIVISION TOTAL |  |  |  |  | 2407.9 | 2240.45 |  | 2887.1 | 278.8 | 3165.9 |  |  |  |  | 8.11 | 33.44 | 41.55 | 5.337 | 35.848 | 41.185 | 5.337 | 35.848 | 41.185 | 100% | 3169.02 | 100.1% | 0 | 0 | 0 | -3.12
SHIMOGA SPECIAL DIVISION
5 | 107 | a | Improvements to Malpe - Molakalmur State Highway-65 from Km 145.65 to Km 186.40 (selected reaches) in Bhadravathi Taluka of Shimoga Dist | 65 | 2450 | 2258.4 | CER No:02/2013-14 | 2858.45 | 231.81 | 3090.26 | Sri Ibrahim Shereiff | 2013-12-26 | 2014-11-25 | 31.03.2015 | 0 | 24.35 | 24.35 | 0 | 24.36 | 24.36 | 0 | 24.36 | 24.36 | 100% | 2960.77 | 95.81% | 0 | 0 | 0 | 129.49 | Completed
|  | b | 3: Improvements to Hulikal - Halageri State Highway-26 from Km 62.05 to Km 86.36 (selected reaches) in Shimoga Taluka of Shimoga Dist; 4: 26; 15: 0; 16: 18.78; 17: 18.78; 18: 0; 19: 16.09; 20: 16.09; 21: 0; 22: 16.09; 23: 16.09; 24: 100%; 27: 0; 28: 0; 29: 0
| Package Total |  |  |  | 2450 | 2258.4 |  | 2858.45 | 231.81 | 3090.26 |  |  |  |  | 0 | 43.13 | 43.13 | 0 | 40.45 | 40.45 | 0 | 40.45 | 40.45 | 100% | 2960.77 | 95.81% | 0 | 0 | 0 | 129.49
6 | 108 | a | Improvements to Kuppalli - Malenahalli - Hirekerur State Highway-148 from Km 52.76 to Km 92.12 (selected reaches) in Shimoga Taluka of Shimoga Dist | 148 | 2566.4 | 2377.04 | CER No:01/2013-14 | 3012.24 | 292.25 | 3304.49 | Sri Ibrahim Shereiff | 2013-12-26 | 2014-11-25 | 20.11.2015 | 0 | 22.2 | 22.2 | 0 | 22.2 | 22.2 | 0 | 22.2 | 22.2 | 100% | 3202.94 | 96.93% | 0 | 0 | 0 | 101.55 | Completed
|  | b | 3: Improvements to Thirthahalli - Kundapura State Highway-52 from Km 0.00 to Km 20.4 (selected reaches) in Thirthahalli Taluka of Shimoga Dist; 4: 52; 15: 2.2; 16: 10.6; 17: 12.8; 18: 0; 19: 12.8; 20: 12.8; 21: 0; 22: 12.8; 23: 12.8; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Virajpet - Byndoor State Highway-27 from Km 112.00 to Km 122.60 (selected reaches) in Thirthahalli Taluka of Shimoga Dist; 4: 27; 15: 0; 16: 10.6; 17: 10.6; 18: 0; 19: 9.125; 20: 9.125; 21: 0; 22: 9.125; 23: 9.125; 24: 100%; 27: 0; 28: 0; 29: 0
| Package Total |  |  |  | 2566.4 | 2377.04 |  | 3012.24 | 292.25 | 3304.49 |  |  |  |  | 2.2 | 43.4 | 45.6 | 0 | 44.125 | 44.125 | 0 | 44.125 | 44.125 | 100% | 3202.94 | 96.93% | 0 | 0 | 0 | 101.55
7 | 109 |  | Improvements to Kuppalli - Malenahalli - Hirekerur State Highway-148 from Km 0.00 to Km 38.00 (selected reaches) in Thirthahalli Taluka of Shimoga Dist | 148 | 1794.3 | 1737.13 | CER NO.59/2013-14 | 2208.51 | 206.08 | 2414.59 | Sri Ibrahim Shereiff | 2013-12-26 | 2014-11-25 | 15.05.2015 | 1.1 | 33.1 | 34.2 | 3.85 | 33.15 | 37 | 3.85 | 33.15 | 37 | 100% | 2372.6 | 98.26% | 0 | 0 | 0 | 41.99 | Completed
DIVISION TOTAL |  |  |  |  | 6810.7 | 6372.57 |  | 8079.2 | 730.14 | 8809.34 |  |  |  |  | 3.3 | 119.63 | 122.93 | 3.85 | 117.725 | 121.575 | 3.85 | 117.725 | 121.575 | 100% | 8536.31 | 96.9% | 0 | 0 | 0 | 273.03
SHIMOGA DIVISION
8 | 110 |  | Improvements to Kuppalli - Malenahalli - Hirekerur State Highway-148 from Km 92.12 to Km 156.12 (selected reaches) in Shikaripura Taluka of Shimoga Dist | 148 | 3111 | 2866.86 | CER No:03/2013-14 | 3634.18 | 317.86 | 3952.04 | M/S Manjushri Cons. Co | 2013-12-26 | 2014-11-25 | 30.03.2015 | 0 | 58.4 | 58.4 | 0 | 58.57 | 58.57 | 0 | 58.57 | 58.57 | 100% | 3956.56 | 100.1% | 0 | 0 | 0 | -4.52 | Completed
9 | 111 |  | Improvements to Hulikal - Halageri State Highway-26 from Km 86.32 to Km 173.90 (selected reaches) in Hosanagar Taluka of Shimoga Dist | 26 | 2393.7 | 2165.08 | CER No:04/2013-14 | 2741.66 | 270.3 | 3011.96 | M/S G.D Thimmappa Sheregar | 2013-12-26 | 2014-11-25 | 31.03.2015 | 0 | 41.84 | 41.84 | 0 | 41.48 | 41.48 | 0 | 41.48 | 41.48 | 100% | 3043.84 | 101.1% | 0 | 0 | 0 | -31.88 | Completed
10 | 112 | a | Improvements to Kumta - Kadamadagi State Highway-48 from Km 116.66 to Km 158.00 (selected reaches) in Shikaripura Taluka of Shimoga Dist | 48 | 2824.6 | 2607.9 | CER NO 49/2013-14 | 3423.38 | 329.06 | 3752.44 | M/S Manjushri Cons. Co | 2014-03-04 | 2015-02-03 | 30.05.2015 | 0 | 10.82 | 10.82 | 0 | 12.143 | 12.143 | 0 | 12.143 | 12.143 | 100% | 3730.89 | 99.43% | 0 | 0 | 0 | 21.55 | Completed
|  | b | 3: Improvements to Kumta - Kadamadagi State Highway-48 from Km 82.00 to Km 116.66 (selected reaches) in Soraba Taluka of Shimoga Dist; 4: 48; 15: 3; 16: 15.45; 17: 18.45; 18: 10.89; 19: 14.938; 20: 25.828; 21: 10.89; 22: 14.938; 23: 25.828; 24: 100%; 27: 0; 28: 0; 29: 0
|  | c | 3: Improvements to Thirthahalli - Kundapura State Highway-52 from Km 25.00 to Km 44.80 (selected reaches) in Hosanagar Taluka of Shimoga Dist; 4: 52; 15: 0; 16: 19.1; 17: 19.1; 18: 0; 19: 19.1; 20: 19.1; 21: 0; 22: 19.1; 23: 19.1; 24: 100%; 27: 0; 28: 0; 29: 0
| Package Total |  |  |  | 2824.6 | 2607.9 |  | 3423.38 | 329.06 | 3752.44 |  |  |  |  | 3 | 45.37 | 48.37 | 10.89 | 46.181 | 57.071 | 10.89 | 46.181 | 57.071 | 100% | 10731.29 | 286% | 0 | 0 | 0 | -14.85
DIVISION TOTAL |  |  |  |  | 8329.3 | 7639.84 |  | 9799.22 | 917.22 | 10716.44 |  |  |  |  | 3 | 145.61 | 148.61 | 10.89 | 146.231 | 157.121 | 10.89 | 146.231 | 157.121 | 100% | 10731.29 | 100.1% | 0 | 0 | 0 | -14.85
SHIMOGA CIRCLE TOTAL |  |  |  |  | 24353.05 | 22738.36 |  | 28440.05 | 2571.71 | 31011.76 |  |  |  |  | 30.94 | 410.63 | 441.57 | 36.607 | 412.304 | 448.911 | 36.607 | 412.304 | 448.911 | 100% | 30729.61 | 99.09% | 0 | 0 | 0 | 282.15
BANGALORE CIRCLE
TUMKUR Division
1 | Pkg 113 | 113a | Improvements to Mandya - Hadagali State Highway-47 from Km 128.84 to Km 195.50 (selected reaches) in Tiputar & Chikkanayanahalli Taluk of Tumkur Dist | 47 | 2259.36 | 2196.4 | 54/2013-14 | 2764.27 | 684.43 | 3448.7 | Sri C H V N Reddy | 2014-03-04 | 2015-02-03 | 2015-12-30 | 0 | 46.42 | 46.42 | 8.25 | 38.2 | 46.45 | 8.25 | 38.2 | 46.45 | 100% | 3443.68 | 99.85% | 0 | 0 | 0 | 5.02 | Completed
|  | 113b | 3: Improvements to Bangalore - Jalsoor State Highway-85 from Km 63.30 to Km 87.85 (selected reaches) in Kunigal Taluk of Tumkur Dist; 4: 85; 15: 0; 16: 23.38; 17: 23.38; 18: 0; 19: 23.41; 20: 23.41; 21: 0; 22: 23.41; 23: 23.41; 24: 100%; 27: 0; 28: 0; 29: 0
2 | Pkg 114 | 114 | Improvements to Ramanagara - Ananthapur road from Km 346.00 to Km 429.33 (selected reaches) in Pavagada Taluk of Tumkur Dist | MDR | 1286.6 | 1250.62 | 51/2013-14 | 1425.95 | 344.01 | 1769.96 | M/S Karthik Enterprises | 2014-03-04 | 2015-02-03 | 03.06.2015 | 9.81 | 20.8 | 30.61 | 6.4 | 25.9 | 32.3 | 6.4 | 25.9 | 32.3 | 100% | 1714.54 | 96.87% | 0 | 0 | 0 | 55.42 | Completed
3 | Pkg 115 | 115 | Improvements to Kumta - Kadamadagi State Highway-48 from Km 348.91 to Km 392.16 (selected reaches) Vadhanakallu, Ranaga samudra, Shailapura, Harekyathanahalli, Pavagada, Kodamadagu, Bhairapura in Pavagada Taluk of Tumkur Dist | 48 | 1820.19 | 1750.12 | 52/2013-14 | 2061.18 | 205.85 | 2267.03 | Sri S S Alur | 2013-12-26 | 2014-11-25 | 25.05.2015 | 0 | 36.2 | 36.2 | 0 | 41.62 | 41.62 | 0 | 41.62 | 41.62 | 100% | 2243.15 | 98.95% | 0 | 0 | 0 | 23.88 | Completed
4 | Pkg 116 | 116 | Improvements to Ramanagara - Ananthapur roadfrom Km 64.30 to Km 145.40 (selected reaches) (Beechanahalli, Lakshmipura, Thirumalapalya, Gajanapalya, Kodagi halli in Kunigal Taluk of Tumkur Dist) (Bythrahosahalli, Jadeya, Turuvekare, Somanahalli in Turuvekere Taluk of Tumkur Dist) | MDR | 2565 | 2489.52 | 59/2013-14 | 3017.65 | 261.68 | 3279.33 | M/s.BSR Infratech P Ltd, Bangalore | 2013-12-26 | 2014-11-25 | 2015-07-31 | 12.74 | 33.79 | 46.53 | 0.35 | 46.99 | 47.34 | 0.35 | 46.99 | 47.34 | 100% | 3063.93 | 93.43% | 0 | 0 | 0 | 215.4 | Completed
5 | Pkg 117 | 117 | Improvements to Ramanagara - Ananthapur road from Km 145.40 to Km 197.00 & from Km 211.73 to Km 242.96 (selected reaches) (Nonavikere, Tiptur Town Limits, Bagavala, Baluvaneralu, B.Muddenahalli in Tiptur Taluk of Tumkur Dist) (Handanakere, Mattighatta, Kaimara cross, Navile, Navile palya, Karthikehal cross, Maruti nagar/TCB road Chikkanayanahalli Taluk of Tumkur Dist) | MDR | 4543 | 4370.573 | 66/2013-14 | 5384.24 | 98.9 | 5483.14 | M/s.BSR Infratech P Ltd, Bangalore | 2013-12-26 | 2014-11-25 | 2016-01-30 | 0 | 84.63 | 84.63 | 9.349 | 66.82 | 76.169 | 9.349 | 66.82 | 76.169 | 100% | 5283.67 | 96.36% | 0 | 0 | 0 | 199.47 | Completed
[5 empty] | 12474.15 | 12057.233 |  | 14653.29 | 1594.87 | 16248.16 |  |  |  |  | 22.55 | 245.22 | 267.77 | 24.349 | 242.94 | 267.289 | 24.349 | 242.94 | 267.289 | 600% | 15748.97 | 96.93% | 0 | 0 | 0 | 499.19
BANGALORE Division
6 | Pkg.118 | 118a | Improvements to Nelamangala - Chikkaballapura State Highway-74 from Km 12.96 to Km 53.16 (selected reaches)Basavanahalli, Hadyalu, Gollahalli Railway cross, Mallohalli, Arlumallige, Doddaballapura Town, Raja Gatta, Arlumallige Tankbund, Raja gatta Tankbund in DB Pura Taluk of Bangalore Dist | 74 | 1591.38 | 1421.16 | 67/2013-14 | 1477.18 | 138.08 | 1615.26 | Sri M Venkatarama Reddy | 2014-03-04 | 2015-02-03 | 2015-12-31 | 10.47 | 19.49 | 29.96 | 14.28 | 16.984 | 31.264 | 14.28 | 16.984 | 31.264 | 100% | 1223.62 | 75.75% | 0 | 0 | 0 | 391.64 | Completed
|  | 118b | 3: Improvements to Nelamangala - Chikkaballapura State Highway-74 from Km 52.33 to Km 64.83 (selected reaches) in Chikkaballapura Taluk of Chikkaballapura Dist; 4: 74; 15: 0; 16: 4.01; 17: 4.01; 18: 0; 19: 0.04; 20: 0.04; 21: 0; 22: 0.04; 23: 0.04; 24: 100%; 27: 0; 28: 0; 29: 0
[5 empty] | 1591.38 | 1421.16 |  | 1477.18 | 138.08 | 1615.26 |  |  |  |  | 10.47 | 23.5 | 33.97 | 14.28 | 17.024 | 31.304 | 14.28 | 17.024 | 31.304 | 100% | 1223.62 | 75.75% | 0 | 0 | 0 | 391.64
BANGALORE CIRCLE TOTAL |  |  |  |  | 14065.53 | 13478.393 |  | 16130.47 | 1732.95 | 17863.42 |  |  |  |  | 33.02 | 268.72 | 301.74 | 38.629 | 259.964 | 298.593 | 38.629 | 259.964 | 298.593 | 100% | 16972.59 | 95.01% | 0 | 0 | 0 | 890.83
MYSORE CIRCLE
MANDYA DIVISION
1 | 119 | 119a | Improvements to Bangalore - Jalsoor State Highway-85 from Km 90.97 to Km 112.40 & Km 160.00 to Km l7l.l0 (selected reaches) in Nagamangala & K R pet Taluks of Mandya Dist. | 85 | 2435 | 2297.42 | CER NO: 68/2012-13 | 2582.53 | 254.46 | 2836.99 | Sri S.R.Ravishankar | 2013-12-27 | 2014-11-26 | 30.06.2015 | 2 | 21.33 | 23.33 | 2 | 20.115 | 22.115 | 2 | 20.115 | 22.115 | 100% | 2756.38 | 97.16% | 0 | 0 | 0 | 80.61 | Completed
|  | 119b | 3: Improvements to Mandya - Hadagali State Highway-47 from Km 55.40 to Km 62.73 (selected reaches) in K R pet Taluk of Mandya Dist.; 4: 47; 15: 5.96; 16: 1.37; 17: 7.33; 18: 5.96; 19: 1.37; 20: 7.33; 21: 5.96; 22: 1.37; 23: 7.33; 24: 100%; 27: 0; 28: 0; 29: 0
|  | 119c | 3: lmprovements to Sira - Nanjanagud State Highway-84 from Km 198.45 to Km 243.01 (selected reaches) in T. Narisipura & Nanjangudu Taluks of Mysore district.; 4: 84; 15: 0; 16: 7.7; 17: 7.7; 18: 0; 19: 7.82; 20: 7.82; 21: 0; 22: 7.82; 23: 7.82; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 2435 | 2297.42 |  | 2582.53 | 254.46 | 2836.99 |  |  |  |  | 7.96 | 30.4 | 38.36 | 7.96 | 29.305 | 37.265 | 7.96 | 29.305 | 37.265 | 100% | 2756.38 | 97.16% | 0 | 0 | 0 | 80.61
CHAMARAJNAGAR DIVISION
2 | 120 | 120 | Improvements to Bagalakote - Biligirirangana betta State Highway-57 from Km 676.95 to Km 720.65 (selected reaches) in Chamarajanagar & Yalandur Taluks of Chamarajanagar district. | 57 | 2020 | 1940.79 | CER NO: 55/2013-14 | 2520.02 | 153.13 | 2673.15 | Sri.M.S.Revanna | 2013-12-27 | 2014-11-26 | 25.05.2015 | 0 | 34.1 | 34.1 | 1.02 | 35.223 | 36.243 | 1.02 | 35.223 | 36.243 | 100% | 2619.13 | 97.98% | 0 | 0 | 0 | 54.02 | Completed
3 | 121 | 121 | lmprovements to Ramanathapura-Therakanambi State Highway-86 from Km 118.40 to Km 160.00 (selected reaches) in Gundlupet Taluk of Chamarajanagar District . | 86 | 1503 | 1431.11 | CER NO: 56/2013-14 | 1788 | 78.7388 | 1866.7388 | M/s Sri Bapuji Constructions (P) Ltd | 2013-12-26 | 2014-11-25 | 23.06.2014 | 0 | 31.6 | 31.6 | 0 | 31.61 | 31.61 | 0 | 31.61 | 31.61 | 100% | 1848.01 | 99% | 0 | 0 | 0 | 18.7288 | Completed
DIVISION TOTAL |  |  |  |  | 3523 | 3371.9 |  | 4308.02 | 231.8688 | 4539.8888 |  |  |  |  | 0 | 65.7 | 65.7 | 1.02 | 66.833 | 67.853 | 1.02 | 66.833 | 67.853 | 100% | 4467.14 | 98.4% | 0 | 0 | 0 | 72.7488
MYSORE DIVISION
4 | 122 | 122 | Improvements to Ramanathapura-Therakanambi State Highway-86 from Km 79.00 to Km 107.35 (selected reaches) in H D kote & Hunsur Taluks of Mysore District. | 86 | 856 | 825.49 | CER NO: 07/2013-14 | 1068.42 | 38.26 | 1106.68 | Sri.H.B. Ravi kumar | 2013-12-26 | 2014-11-25 | 09.01.2015 | 0 | 14.94 | 14.94 | 0 | 15.092 | 15.092 | 0 | 15.094 | 15.094 | 100% | 1095.59 | 99% | 0 | -0.002 | -0.002 | 11.09 | Completed
5 | 123 | 123a | lmprovements to Bagalkote-Biligiriranganabetta State Highway-57 from Km 549.52 to Km 610.30 (selected reaches) in K R Nagar & Hunsur Taluks of Mysore Dist | 57 | 1868.75 | 1806.42 | CER NO: 57/2013-14 | 2310.31 | 226.475 | 2536.785 | Sri H.S.Ramesh | 2013-12-26 | 2014-11-25 | 30.06.2015 | 15.63 | 17.72 | 33.35 | 9.43 | 18.62 | 28.05 | 9.43 | 18.62 | 28.05 | 100% | 2461.44 | 97.03% | 0 | 0 | 0 | 75.345 | Completed
|  | 123b | 3: Improvements to Bangalore-Jalsur State Highway-85 from Km 171.1 to Km 192.51 (selected reaches) in K R nagar & Hunsur Taluks of Mysore District.; 4: 85; 15: 2.55; 16: 18.86; 17: 21.41; 18: 0.9; 19: 20.51; 20: 21.41; 21: 0.9; 22: 20.51; 23: 21.41; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 2724.75 | 2631.91 |  | 3378.73 | 264.735 | 3643.465 |  |  |  |  | 18.18 | 51.52 | 69.7 | 10.33 | 54.222 | 64.552 | 10.33 | 54.224 | 64.554 | 100% | 3557.03 | 97.63% | 0 | -0.002 | -0.002 | 86.435
MYSORE CIRCLE TOTAL |  |  |  |  | 8682.75 | 8301.23 |  | 10269.28 | 751.0638 | 11020.3438 |  |  |  |  | 26.14 | 147.62 | 173.76 | 19.31 | 150.36 | 169.67 | 19.31 | 150.362 | 169.672 | 100% | 10780.55 | 97.82% | 0 | -0.002 | -0.002 | 239.7938
Mangalore Circle
1 | 124 | 124a | Improvements to BANGALORE- JALSUR (SH-85) ROAD from CH:225.00km to 254.71km in Somwarpet Taluk of Kodagu District | 85 | 1683.5 | 1531.98 | CER.No : 11/2013-14 | 1889.78 | 282.77 | 2172.55 | M/s KBR Infratech Pvt Ltd | 26-12-2013 | 2014-11-26 | 2016-02-22 | 24.38 | 0.3 | 24.68 | 17.52 | 8.89 | 26.41 | 17.52 | 8.89 | 26.41 | 100% | 2161.06 | 99.47% | 0 | 0 | 0 | 11.49 | Completed
|  | 124b | 3: Improvement to Virajpet- Byndoor SH-27 from 41.85km to 103.80km (Selected Reaches) in Somwarpet Taluk of Kodagu District; 4: 27; 15: 8.46; 16: 1; 17: 9.46; 18: 7.04; 19: 0.48; 20: 7.52; 21: 7.04; 22: 0.48; 23: 7.52; 24: 100%; 27: 0; 28: 0; 29: 0
|  | 124c | 3: Improvement to Hiresavi- Chattalli SH-08 from 92.24km to 168.20km (Selected Reaches) in Somwarpet Taluk of Kodagu District; 4: 8; 15: 19.7; 16: 7.9; 17: 27.6; 18: 22.01; 19: 7.6; 20: 29.61; 21: 22.01; 22: 7.6; 23: 29.61; 24: 100%; 27: 0; 28: 0; 29: 0
DIVISION TOTAL |  |  |  |  | 1683.5 | 1531.98 |  | 1889.78 | 282.77 | 2172.55 |  |  |  |  | 52.54 | 9.2 | 61.74 | 46.57 | 16.97 | 63.54 | 46.57 | 16.97 | 63.54 | 100% | 2161.06 | 99.47% | 0 | 0 | 0 | 11.49
DAKISHNA KANNADA DIVISION
2 | 125 | 125 | Improvement to Subramanya-Udupi SH-37 from 36.40km to 94.60km (Selected Reaches) in Belthangady Taluk of Dakishna Kannada District | 37 | 612.6 | 571.85 | CER.No : 12/2013-14 | 611.23 | 148.24 | 759.47 | N S K Builders Pvt Ltd | 27-12-2013 | 26-11-2014 | 2015-06-30 | 28.52 | 1.94 | 30.46 | 28.52 | 1.94 | 30.46 | 28.52 | 1.94 | 30.46 | 100% | 756.5 | 99.61% | 0 | 0 | 0 | 2.97 | Completed
DIVISION TOTAL |  |  |  |  | 612.6 | 571.85 |  | 611.23 | 148.24 | 759.47 |  |  |  |  | 28.52 | 1.94 | 30.46 | 28.52 | 1.94 | 30.46 | 28.52 | 1.94 | 30.46 | 100% | 756.5 | 99.61% | 0 | 0 | 0 | 2.97
UDUPI DIVISION
3 | 126 | 126a | Improvements to Padubidre-Chikkalagudda Road (SH-1) (from km 28.00 to 76.80km ) in selected reaches | 1 | 2198.86 | 2112.43 | CER.No : 41/2013-14 | 2495.4 | 622.77 | 3118.17 | Abdul Rahiman | 26-12-2013 | 25-11-2014 | 2015-03-09 | 23.14 | 10.56 | 33.7 | 8.82 | 25.9 | 34.72 | 8.82 | 25.9 | 34.72 | 100% | 3073.99 | 98.58% | 0 | 0 | 0 | 44.18 | Completed
|  | 126b | 3: Improvements to Thirthahalli-Kundapur Road (SH-52) in Kundapur Taluk, Udupi District from (km50.70 to 80.00 km in selected reaches; 4: 52; 15: 19.55; 16: 5.25; 17: 24.8; 18: 8.78; 19: 15.98; 20: 24.76; 21: 8.78; 22: 15.98; 23: 24.76; 24: 100%; 27: 0; 28: 0; 29: 0
|  | 126c | 3: Improvements to Halageri-Halkal Road (SH-26) in Kundapur Taluk, Udupi District from km 180.62 to 187.42 km (NOGODI-KOLLUR-HALKAL PORTION); 4: 26; 15: 3; 16: 3.55; 17: 6.55; 18: 0; 19: 6.55; 20: 6.55; 21: 0; 22: 6.55; 23: 6.55; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | TOTAL 126 a,b &c |  | 2198.86 | 2112.43 |  | 2495.4 | 622.77 | 3118.17 |  |  |  |  | 45.69 | 19.36 | 65.05 | 17.6 | 48.43 | 66.03 | 17.6 | 48.43 | 66.03 | 100% | 3073.99 | 98.58% | 0 | 0 | 0 | 44.18
4 | 127 | 127a | mprovements to Virajpet -Byndoor Road (SH-27) in Karkala & Kundapur Taluk of Udupi District (from 309.00to 395.40 km ) in selected reaches | 27 | 1906.17 | 1760.95 | CER.No : 42/2013-14 | 2020.78 | 504.58 | 2525.36 | M/s Iqbal Ahmed Infra Project Pvt Ltd | 26-12-2013 | 25-11-2014 | 06.05.2015 | 34.705 | 13.816 | 48.521 | 26.51 | 22.2 | 48.71 | 26.51 | 22.2 | 48.71 | 100% | 2342.35 | 92.75% | 0 | 0 | 0 | 183.01 | Completed
|  | 127b | 3: Improvements to Malpe- Molakalmuru Road (SH-65) (13.35km to 29.00 km & 31.60 to 44.20 km) in Udupi & Karkala Taluk of Udupi District; 4: 65; 15: 19.11; 16: 8.165; 17: 27.275; 18: 14.675; 19: 12.019; 20: 26.694; 21: 14.675; 22: 12.019; 23: 26.694; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | TOTAL 127 a & b |  | 1906.17 | 1760.95 |  | 2020.78 | 504.58 | 2525.36 |  |  |  |  | 53.815 | 21.981 | 75.796 | 41.185 | 34.219 | 75.404 | 41.185 | 34.219 | 75.404 | 100% | 2342.35 | 92.75% | 0 | 0 | 0 | 0
DIVISION TOTAL |  |  |  |  | 4105.03 | 3873.38 |  | 4516.18 | 1127.35 | 5643.53 |  |  |  |  | 99.505 | 41.341 | 140.846 | 58.785 | 82.649 | 141.434 | 58.785 | 82.649 | 141.434 | 100% | 5416.34 | 95.97% | 0 | 0 | 0 | 0
MANGALOLRE CIRCLE TOTAL |  |  |  |  | 6401.13 | 5977.21 |  | 7017.19 | 1558.36 | 8575.55 |  |  |  |  | 180.565 | 52.481 | 233.046 | 133.875 | 101.559 | 235.434 | 133.875 | 101.559 | 235.434 | 100% | 8333.9 | 97.18% | 0 | 0 | 0 | 14.46
HASSAN CIRCLE
CHICKMAGALURU DIVISION
62 | Pkg 128 | 128a | Improvements to Virajpet - Byndoor (Koppa) State Highway-27 from Km 240.40 to Km 285.50 (selected reaches) in Koppa Taluk of Chickamagalur Dist | 27 | 2307 | 2167.91 | CER.No : 60/2013-14 | 2471.8 | 185.44 | 2657.24 | M/S Iqbal Ahmed InfraProject Pvt Ltd | 27-12-2013 | 26-11-2014 | 2016-03-31 | 9.2 | 14.3 | 23.5 | 9 | 16.63 | 25.63 | 9 | 16.63 | 25.63 | 100% | 2503.79 | 94.23% | 0 | 0 | 0 | 153.45 | Completed
|  | 128b | 3: Improvements to Virajpet - Byndoor (Chickamagalur) State Highway-27 from Km 195.75 to Km 233.67 (selected reaches) in Chickamagalur Taluk of Chickamagalur Dist; 4: 27; 15: 11.25; 16: 12; 17: 23.25; 18: 16.97; 19: 13.34; 20: 30.31; 21: 16.97; 22: 13.34; 23: 30.31; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 2307 | 2167.91 |  | 2471.8 | 185.44 | 2657.24 |  |  |  |  | 20.45 | 26.3 | 46.75 | 25.97 | 29.97 | 55.94 | 25.97 | 29.97 | 55.94 | 100% | 2503.79 | 94.23% | 0 | 0 | 0 | 153.45
63 | Pkg.129 | 129a | Improvements to Chickamaglur - Mallandur road from Km 6.50 to Km 21.75 (selected reaches) in Chickamaglur Taluk of Chickamaglur Dist | MDR | 1000 | 899.55 | CER.No : 61/2013-14 | 1128.76 | 149.74 | 1278.5 | Sri Abdul Rahiman | 27-12-2013 | 26-11-2014 | 26.11.2014 | 0 | 14.2 | 14.2 | 0 | 15.2 | 15.2 | 0 | 15.2 | 15.2 | 100% | 1289.1 | 100.8% | 0 | 0 | 0 | -10.6 | Completed
|  | 129b | 3: Improvements to Horanadu- Balur State Highway-106 from Km 0.00 to Km 22.00 (selected reaches) in Mudigere Taluk of Chickmaglur Dist; 4: 106; 15: 0; 16: 12.4; 17: 12.4; 18: 0; 19: 14.8; 20: 14.8; 21: 0; 22: 14.8; 23: 14.8; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 1000 | 899.55 |  | 1128.76 | 149.74 | 1278.5 |  |  |  |  | 0 | 26.6 | 26.6 | 0 | 30 | 30 | 0 | 30 | 30 | 100% | 1289.1 | 100.8% | 0 | 0 | 0 | -10.6
DIVISION TOTAL |  |  |  |  | 3307 | 3067.46 |  | 3600.56 | 335.18 | 3935.74 |  |  |  |  | 20.45 | 52.9 | 73.35 | 25.97 | 59.97 | 85.94 | 25.97 | 59.97 | 85.94 | 100% | 3792.89 | 96.37% | 0 | 0 | 0 | 142.85
HASSAN DIVISION
64 | Pkg 130 | 130a | Improvements to Mandya - Hadagali State Highway-47 from Km 85.54 to Km 128.84 (selected reaches) in channarayapatna Taluk of Hassan Dist | 47 | 2820.3 | 2593.87 | CER.No : 09/2013-14 | 3079.12 | 764.17 | 3843.29 | Sri C H V N Reddy | 28-12-2013 | 27-11-2014 | 2016-05-15 | 13.1 | 20.17 | 33.27 | 9.95 | 20.74 | 30.69 | 9.95 | 20.74 | 30.69 | 100% | 3803.74 | 98.97% | 0 | 0 | 0 | 39.55 | Completed
|  | 130b | 3: Improvements to Virajpet - Byndoor State Highway-27 from Km 146.27 to Km 167.45 (selected reaches) in Belur Taluk of Hassan Dist; 4: 27; 15: 0; 16: 17.73; 17: 17.73; 18: 0; 19: 22.58; 20: 22.58; 21: 0; 22: 22.58; 23: 22.58; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 2820.3 | 2593.87 |  | 3079.12 | 764.17 | 3843.29 |  |  |  |  | 13.1 | 37.9 | 51 | 9.95 | 43.32 | 53.27 | 9.95 | 43.32 | 53.27 | 100% | 3803.74 | 98.97% | 0 | 0 | 0 | 39.55
65 | Pkg.131 | 131 | Improvements to Bichenahalli- Doddakunchevu-Karekere Byadarahalli Heragu road (Connecting SH 112 A to SH 71) (selected reaches) in Hassan & Holenarsipur Taluk of Hassan Dist. | MDR | 3100 | 3008.96 | CER.No : 63/2013-14 | 3433.26 | 719.37 | 4152.63 | Sri Rayee Gowda | 28-12-2013 | 27-11-2014 | 2016-07-10 | 0 | 38.255 | 38.255 | 0 | 45.73 | 45.73 | 0 | 45.73 | 45.73 | 100% | 3934.3 | 94.74% | 0 | 0 | 0 | 218.33 | Completed
66 | Pkg.132 | 132a | Improvements to Muthigehiralli Chakenahalli Banakuppe Bittagowdanahalli road (Connecting SH 57 to NH 48) (selected reaches) in Channarayapatna, Holenarsipura & Hassan Taluks of Hassan Dist. | MDR | 2140 | 2072.24 | CER.No : 69/2012-13 | 2335.94 | 213.96 | 2549.9 | H N Rame Gowda | 2014-01-01 | 30-12-2014 | 30.05.2015 | 0 | 16.63 | 16.63 | 0 | 16.99 | 16.99 | 0 | 16.99 | 16.99 | 100% | 2540.36 | 99.63% | 0 | 0 | 0 | 9.54 | Completed
|  | 132b | 3: Improvements to Gandsi Santhemydana to Nonavinakere road (Connecting SH 57) from Km 16.00 to Km 37.00 (selected reaches) in Channarayapatna Taluk of Hassan Dist; 4: MDR; 15: 0; 16: 16; 17: 16; 18: 0; 19: 16; 20: 16; 21: 0; 22: 16; 23: 16; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 2140 | 2072.24 |  | 2335.94 | 213.96 | 2549.9 |  |  |  |  | 0 | 32.63 | 32.63 | 0 | 32.99 | 32.99 | 0 | 32.99 | 32.99 | 100% | 2540.36 | 99.63% | 0 | 0 | 0 | 9.54
67 | Pkg.133 | 133 | Improvements to MCF, Nittur, Bageshapura road (Connecting SH 21 to SH 102) (selected reaches) in Hassan Taluk of Hassan Dist | MDR | 1425 | 1378.4 | CER.No : 64/2013-14 | 1595.03 | 159.41 | 1754.44 | Sri Ramesh Kumar Kothari | 27-12-2013 | 26-11-2014 | 2015-09-30 | 1 | 21.6 | 22.6 | 0 | 22.6 | 22.6 | 0 | 22.6 | 22.6 | 100% | 1745.4 | 99.48% | 0 | 0 | 0 | 9.04 | Completed
68 | Pkg.134 | 134 | Improvements to Hyarane, Ankapura, Padavalahippe road (Connecting SH 21 to SH 08) (selected reaches) in Hassan & Holenarsipura Taluk of Hassan Dist | MDR | 2575 | 2480.53 | CER.No : 70/2012-13 | 2973.9 | 296.68 | 3270.58 | Sri H.N Ramegowda | 2014-03-04 | 2015-02-03 | 2015-08-31 | 0 | 32.91 | 32.91 | 5.5 | 35.31 | 40.81 | 5.5 | 35.31 | 40.81 | 100% | 3222.13 | 98.52% | 0 | 0 | 0 | 48.45 | Completed
DIVISION TOTAL |  |  |  |  | 12060.3 | 11534 |  | 13417.25 | 2153.59 | 15570.84 |  |  |  |  | 14.1 | 163.295 | 177.395 | 15.45 | 179.95 | 195.4 | 15.45 | 179.95 | 195.4 | 100% | 15245.93 | 97.91% | 0 | 0 | 0 | 324.91
HASSAN SPECIAL DIVISION
69 | Pkg 135 | 135a | Improvements to Virajpete - Byndoor State Highway-27 from Km 106.25 to Km 146.27 (selected reaches) in Sakaleshapura Taluk of Hassan Dist | 27 | 3004 | 2901.7 | CER.No : 65/2013-14 | 3442.09 | 855.28 | 4297.37 | Sri C H V N Reddy | 28-12-2013 | 27-11-2014 | 2016-05-15 | 0 | 33.48 | 33.48 | 0 | 33.08 | 33.08 | 0 | 33.08 | 33.08 | 100% | 4302.48 | 100.1% | 0 | 0 | 0 | -5.11 | Completed
|  | 135b | 3: Improvements to Belur - Somwarpet State Highway-112 from Km 0.00 to Km 63.50 (selected reaches) in Belur & Sakaleshapura Taluks of Hassan Dist; 4: 112; 15: 0; 16: 18.65; 17: 18.65; 18: 0; 19: 18.95; 20: 18.95; 21: 0; 22: 18.95; 23: 18.95; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 3004 | 2901.7 |  | 3442.09 | 855.28 | 4297.37 |  |  |  |  | 0 | 52.13 | 52.13 | 0 | 52.03 | 52.03 | 0 | 52.03 | 52.03 | 100% | 4302.48 | 100.1% | 0 | 0 | 0 | -5.11
70 | Pkg.136 | 136a | Improvements to Bangalore - Jalsoor State Highway-85 from Km 254.71 to Km 295.88 (selected reaches) in Sakaleshapura Taluk of Hassan Dist | 85 | 2398.5 | 2202.6 | CER.No : 10/2013-14 | 2893.74 | 718.52 | 3612.26 | Sri M T Nagaraj | 2014-03-04 | 2015-02-03 | 2017-03-31 | 0 | 40.07 | 40.07 | 0 | 17.23 | 17.23 | 0 | 17.23 | 17.23 | 100% | 3401.1 | 94.15% | 0 | 0 | 0 | 211.16 | Completed
|  | 136b | 3: Improvements to Ramanathapura -Therakanambi State Highway- 86 from Km 0.00 to Km 7.80 (selected reaches) in Arakalagud Taluk of Hassan Dist; 4: 86; 15: 0; 16: 7.8; 17: 7.8; 18: 0; 19: 7.8; 20: 7.8; 21: 0; 22: 7.8; 23: 7.8; 24: 100%; 27: 0; 28: 0; 29: 0
|  |  | Package Total |  | 2398.5 | 2202.6 |  | 2893.74 | 718.52 | 3612.26 |  |  |  |  | 0 | 47.87 | 47.87 | 0 | 25.03 | 25.03 | 0 | 25.03 | 25.03 | 100% | 3401.1 | 94.15% | 0 | 0 | 0 | 211.16
DIVISION TOTAL |  |  |  |  | 5402.5 | 5104.3 |  | 6335.83 | 1573.8 | 7909.63 |  |  |  |  | 0 | 100 | 100 | 0 | 77.06 | 77.06 | 0 | 77.06 | 77.06 | 100% | 7703.58 | 97.39% | 0 | 0 | 0 | 206.05
HASSAN CIRCLE TOTAL |  |  |  |  | 20769.8 | 19705.76 |  | 23353.64 | 4062.57 | 27416.21 |  |  |  |  | 34.55 | 316.195 | 350.745 | 41.42 | 316.98 | 358.4 | 41.42 | 316.98 | 358.4 | 100% | 26742.4 | 97.54% | 0 | 0 | 0 | 673.81
South Zone Total |  |  |  |  | 74272.26 | 70200.953 |  | 85210.63 | 10676.6538 | 95887.2838 |  |  |  |  | 305.215 | 1195.646 | 1500.861 | 269.841 | 1241.167 | 1511.008 | 269.841 | 1241.169 | 1511.01 | 100% | 93559.05 | 97.57% | 0 | -0.002 | -0.002 | 2101.0438
NORTH & SOUTH ZONE TOTAL |  |  |  |  | 149890 | 143161.241 |  | 169509.15 | 20489.3138 | 189998.4638 |  |  |  |  | 1247.435 | 2258.174 | 3505.609 | 710.431 | 2425.73 | 3136.161 | 710.431 | 2425.729 | 3136.16 | 100% | 185992.3 | 97.89% | 6.1395e-14 | 0.001 | 0.001 | 3778.9738
0.14
20.79

## District wise
Phase II Progress District Wise
Sl No | District | No Of Packages | No Of Packages Completed | Improvement in Km | Financial Progress in Lakhs
1 | Kalburgi | 4 | 4 | 120.6 | 12540.59
2 | Bidar | 1 | 1 | 41.072 | 2547.38
3 | Yadgir | 2 | 2 | 78.43 | 4479.02
4 | Bellary | 3 | 3 | 137.41 | 7546.18
5 | Raichur | 2 | 2 | 98.061 | 7564.58
6 | Koppal | 2 | 2 | 117.2 | 5022.16
7 | Dharwad | 2 | 2 | 63.02 | 4180.04
8 | Gadag | 1 | 1 | 57.23 | 4161.58
9 | Haveri | 3 | 3 | 103.001 | 8431.38
10 | Uttar Kannada | 5 | 5 | 338.82 | 10783.74
11 | Belgaum | 6 | 6 | 292.646 | 14543.34
12 | Vijayapura | 3 | 3 | 88.42 | 6679.23
13 | Bagalkote | 2 | 2 | 89.24 | 3954.03
14 | Davanagere | 3 | 3 | 129.03 | 8285.23
15 | Chitradurga | 1 | 1 | 41.185 | 3169.02
16 | Shimoga | 6 | 6 | 278.696 | 19267.6
17 | Bangalore | 1 | 1 | 31.304 | 1223.62
18 | C B pura | 0 | 0 | 0 | 0
19 | Ramanagara | 0 | 0 | 0 | 0
20 | Kolar | 0 | 0 | 0 | 0
21 | Tumkur | 5 | 5 | 267.289 | 15748.97
22 | Mandya | 1 | 1 | 37.265 | 2756.38
23 | Mysore | 2 | 2 | 64.554 | 3557.03
24 | Chamarajnagar | 2 | 2 | 67.853 | 4467.14
25 | Udupi | 2 | 2 | 141.434 | 5416.34
26 | Kodagu | 0 | 0 | 0 | 0
27 | Dakishna Kannada | 2 | 2 | 94 | 2917.56
28 | Chickmagaluru | 2 | 2 | 85.94 | 3792.89
29 | Hassan | 7 | 7 | 272.46 | 22949.51
TOTAL |  | 70 | 70 | 3136.16 | 185984.54

## Sheet1
Bangalore Circle
Division | PKG No | VO Status | EOT Status
Bangalore Rural | 293 | Approved | Under Scrutiny
294
295
296
297
Ramnagar | 298 | Under Scrutiny
299
300
301
302
303
304
305
Tumkur | 306 | Yet to be submitted | To be approved
| 307 | Approved | To be approved
| 308 | Under Discussion | Yet to be submitted
| 309 | Yet to be submitted | Yet to be submitted
| 310 | Yet to be submitted | Yet to be submitted
| 311 | Under Scrutiny | Yet to be submitted
| 312 | Yet to be submitted | Yet to be submitted
Madhugiri | 313 | - | Revised proposal Yet to be submitted
| 314 | Yet to be submitted | Sent to Government
| 315 | - | Revised programme of work to be submitted
| 316 | Yet to be submitted | Sent to Government
Kolar | 317 | Yet to be submitted | Revised programme of work to be submitted
| 318 | Yet to be submitted | Yet to be submitted
| 319 | Yet to be submitted | Yet to be submitted
| 320 | Approved | EOT1 approved EOT2 proposal Yet to be submitted
Chikkaballapura | 321 | Approved | -
| 322 | Approved | -
| 323 | Yet to be submitted | Sent to Government
| 324 | Yet to be submitted | Yet to be submitted
| 325 | Yet to be submitted | Yet to be submitted