## 2024-25
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE
Package wise Details of Phase-4 Stage-2
As on 28th FEBURARY 2026
1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Sl No | PKG No |  | Name of Work | SH/ MDR | CER No | Administrative Approved Amount (Rs. in lakhs) | Total Package Cost (Rs. in lakhs) | Technical sanctioned Amount (Rs. in lakhs) | Contract Amount (in Lakhs) | Variation Amount (Rs. in lakhs) | Revised Contract Amount including VO (Rs. in lakhs) | Revised Contract Amount With GST | Revised Contract Amount +PMC cost With GST | Name of Agency | Stipulated Date |  |  | Length Proposed as per DPR in Km | Length Proposed as per VO in Km | Physical Progress |  | Balance Length ( Km ) | Financial Progress |  | Balance (Financial amount) Rs. In Lakhs | Remarks | [8 empty] | Revised Contract Amount +PMC cost With GST
[15 empty] | Commencement | Completion | Revised Completion Date |  |  | Total Length Completed (in km) | % Progress |  | Total Cost (Rs. In Lakhs) | % Progress
Kalaburagi Circle
Bidar Division
1 | 429 | A | Improvements to SH-122 Maharastra Border Murki-Aurad-Handarki from Km 0.00 to Km 62.40 (in selected reaches) in Aurad Taluka of Bidar District. | SH- 122 | 9 | 2300 | 3300 | 2847.57 | 3360.22 | 836.68 | 4196.9 |  | 4999.3839 | M/s JS Infra Private Ltd, | 30.5.2022 | 30.11.2023 | 30.08.2024 | 9.7 | 11.4 | 11.4 | 100% | 0 | 4124.96 | 82.51% | 874.4239 | Work completed |  | 1 |  |  |  | 1 | 1890.9788 | #N/A
|  | B | Improvements to SH-34 Aurad - Sadashivagad, from Km 21.00 to Km 72.50 (in selected reaches) in Bhalki Taluka of Bidar District. | SH-34 | 18 | 1000 | [7 empty] | 15: 4.41; 16: 6.04; 17: 6.04; 18: 100%; 19: 0 |  |  |  |  | Wrong Entry | 2 | 2058.8756
2 | 430 |  | Improvements to road Rajeshwar to Mudbi New SH from Km 0.00 to Km 15.00 (in selected reaches) in Basavakalyan Taluka of Bidar District. | New SH | 22 | 950 | 950 | 812.39 | 974.88 | 97.07 | 1071.95 |  | 1278.3217 | Sri. Prashanth Joshi M/s Santhosh Buildwel Infra Pvt Ltd., | 2022-08-02 | 2023-11-01 | 31.03.2025 | 3.6 | 3.6 | 3.6 | 100% | 0 | 1073.09 | 83.95% | 205.2317 | Work Completed |  | 2 |  |  |  | 3 | 3050.1025
3 | 601 |  | Improvements to road SH-126 A.P Border with Putpak-Bhosaga from Km 147.20 to Km 156.00 (in selected reaches) in Basavakalyan Taluka of Bidar District. | SH-126 | 27 | 1000 | 1000 | 860.46 | 1035.9 | 102.18 | 1138.08 |  | 1357.1492 | Sri. Narayan Rao Vittalrao Kulkarni, Bijapur | 07.05.2022 | 06.04.2023 |  | 4.5 | 5.17 | 5.17 | 100% | 0 | 1326.03 | 97.71% | 31.1192 | Work Completed |  | 3 |  |  |  | 4 | 1977.2878
4 | 602 |  | Improvements to SH-122 Maharastra Border -Murki-Aurad-Handarki from Km 117.80 to Km 123.31 (in selected reaches) in Chitaguppa Taluka of Bidar District | SH -122 | 30 | 950 | 950 | 818.33 | 965.64 |  | 965.64 |  | 1152.974 | Kotarki Laxman Sangamesh ( M/S Kotarki Constructions Private Limited) | 2022-07-30 | 31.10.2024 | 31.10.2024 | 4 | 4 | 4 | 100% | 0 | 787.49 | 68.3% | 365.484 | Work Completed |  | 24 |  |  |  | 5 | 2251.5457
|  |  | Division Total |  |  | 6200 | 6200 | 5338.75 | 6336.64 | 1035.93 | 7372.57 |  | 8787.8287 | 15: 26.21; 16: 30.21; 17: 30.21; 19: 0; 20: 7311.57; 22: 1476.2587 | [5 empty] | 6 | 2706.8361
Kalaburagi Division | [13 empty] | 16: 0 | [5 empty] | 7 | 2900.442
5 | 431 |  | Improvements to SH-124 Barkhed-Bilagi, from Km 0.00 to Km 71.15 (in selected reaches) in Aland Taluka of Kalaburagi District. (Via Bhimapur, Kamanalli, Lingadalli-Madan Hipparga-Nimbal) | SH-124 | 33 | 2200 | 2200 | 1896.93 | 2371.17 |  | 2371.17 |  | 2829.3179 | Sri. Shivkant C Mahajan, | 2022-06-15 | 2023-12-14 |  | 8.55 | 8.55 | 8.55 | 100% | 0 | 2234.34 | 78.97% | 594.9779 | Work Completed.Final bill submitted |  | 4 |  |  |  | 8 | 2939.4542
6 | 432 | A | Improvements to road Bankalga cross to Mashal, MDR from Km 0.00 to Km 14.00 (in selected reaches) in Afzalpur Taluka of Kalaburagi District. | AFZ204 | 36 | 500 | 950 | 815.4 | 994.79 | 98.91 | 1093.7 | 1290.56 | 1304.0364 | Sri. Manzoor Ahmed Patel M/s M A P Construction, Kalaburagi | 2022-05-21 | 30.11.2023 |  | 2.92 | 3.7 | 3.7 | 100% | 0 | 1293.47 | 99.19% | 10.5664 | Work Completed |  | 5 |  |  |  | 9 | 2725.4484
|  | B | Improvements to S.H-124 Barked-Bilagi from Km 102.00 to Km 108.00 (in selected reaches) in Afzalpur Taluka of Kalaburagi District. | SH- 124 | 44 | 450 | [7 empty] | 15: 1.93; 16: 1.93; 17: 1.93; 18: 100%; 19: 0 | [5 empty] | 10 | 1771.5805
7 | 603 |  | Improvements to MDR from NH-218, Kattisangavi to Yenkanchi (SH-16) via Madari-Yengunta- Naribol-Biral(B)-Ganvar-Chigralli-ijeri-alur-kadkol-manashivanagi from Km 40.00 to 50.00 Km (in selected reaches) ( from chigralli cross to yedrami )in Jevargi Taluka of Kalaburagi District. | JEW45 | 45 | 950 | 950 | 817.94 | 940.64 |  | 940.64 |  | 1123.4676 | Sri. Mohammed Sirajuddin, Kalaburagai | 21-5-2022 | 30.12.2023 |  | 5.2 | 5.2 | 5.2 | 100% | 0 | 809.57 | 72.06% | 313.8976 | Work Completed |  | 6 |  |  | 5.355 | 11 | 1671.2955
8 | 433 |  | Improvements to road from Kadagunchi-Bodana road (MDR) to Tonasalli (SH125), MDR from Km 0.00 to Km17.50 and Km 26.50 to Km 35.00 (in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | New MDR | 50 | 2100 | 2100 | 1808.92 | 2261.15 | 190.03 | 2451.18 | 2892.39 | 2922.2758 | Sri. Shivkant C Mahajan, Kalaburagi | 15-6.2022 | 30.08.2024 |  | 9.935 | 10.435 | 9.935 | 95.21% | 0.5 | 2036.35 | 69.68% | 885.9258 | 0.5km Road asphalting work & Furniture Work pending | 1 | A |  |  |  | 12 | 1259.9329
9 | 434 | A | Improvements to road Narona -Chinchansoor, MDR from Km 0.00 to Km 6.30 (in selected reaches) in Aland Taluka of Kalaburagi District. | ALD11 | 54 | 400 | 2250 | 1935.72 | 2414.5 |  | 2414.5 |  | 2881.0881 | Sri.Santosh Subhash Guttedar | 2022-06-10 | 2023-12-09 |  | 1.85 | 1.85 | 1.85 | 100% | 0 | 1545.71 | 53.65% | 1335.3781 | Work Completed |  | 7 |  |  |  | 13 | 1390.0602
|  | B | Improvements to road from Malgathi cross to Bolewad via Nippani, MDR from Km 0.00 to Km 4.20 and Km 16.00 to Km 24.00 (in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | GUL205 | 55 | 1150 | [7 empty] | 15: 3.92; 16: 3.92; 17: 3.92; 18: 100%; 19: 0 | [5 empty] | 14 | 2220.5926
|  | C | Improvements to road from Aurad B(on NH-218) to Jambga(B) (on SH-51) MDR from Km 0.00 to Km 10.70(in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | GUL15 | 63 | 700 | [7 empty] | 15: 3.97; 16: 3.97; 17: 3.97; 18: 100%; 19: 0 | [5 empty] | 15 | 2646.7122
|  |  | Kalaburagi Division Total |  |  | 8450 | 8450 | 7274.91 | 8982.25 | 288.94 | 9271.19 | 4182.95 | 11060.1857 | 15: 38.275; 16: 39.555; 17: 39.055; 19: 0.5; 20: 7919.44; 22: 3140.7457 | [5 empty] | 16 | 1873.2053
Sedam Division | [13 empty] | 16: 0 | [5 empty] | 17 | 2916.0108
10 | 435 |  | Improvements to SH-122 Maharastra Border - Murki-Aurad-Handarki, from Km 153.80 to Km 164.00 Km and Km 207.00 to Km 218.77 (in selected reaches) in Sedam/ Chincholi Taluka of Kalaburagi District | SH-122 | 66 | 2250 | 2250 | 1938.02 | 2238.42 | 217.96 | 2456.38 | 2898.53 | 2930.5445 | Siddappagouda Patil | 31.5.2022 | 30.06.2024 |  | 11.81 | 11.45 | 11.45 | 100% | 0 | 2471.12 | 84.32% | 459.4245 | Work Completed |  | 8 |  |  |  | 18 | 2705.5646
11 | 600 |  | Improvements to SH-32 Umarga border-Aland-VK Salagar-Mahagaon -Sulepet road, from Km 80.00 to Km 118.00 via Herur Cross - Sulepet (in selected reaches) in Chincholi Taluka of Kalaburagi District. | SH-32 | 72 | 2250 | 2250 | 1938.3 | 2289.8 | 209.42 | 2499.22 |  | 2981.1003 | M/s Sharada Construction Pvt Ltd | 2022-06-15 | 01.05.2024 |  | 13.83 | 13.83 | 13.83 | 100% | 0 | 2319.54 | 77.81% | 661.5603 | Work Completed |  | 9 |  |  |  | 19 | 2882.3884
12 | 436 |  | Improvements to SH -126 Telangana border - Putpak-Bhosaga,from Km 60.00 to Km 75.00 (Chittapur Bus Depot to Tengali Cross SH-10) (in selected reaches) in Chittapur Taluka of Kalaburagi District. | SH-126 | 77 | 1000 | 1000 | 861.3 | 981.02 | 242.63 | 1223.65 |  | 1458.1357 | Manzoor Ahamed | 2022-06-23 | 2023-05-22 |  | 3.4 | 4.32 | 4.32 | 100% | 0 | 1388.86 | 95.25% | 69.2757 | Work Completed |  | 10 |  |  |  | 20 | 2826.6159
|  |  | Division Total |  |  | 5500 | 5500 | 4737.62 | 5509.24 | 670.01 | 6179.25 | 2898.53 | 7369.7805 | 15: 29.04; 16: 29.6; 17: 29.6; 19: 0; 20: 6179.52; 22: 1190.2605 | [5 empty] | 21 | 3114.9369
Yadgir Division | [31 empty] | 22 | 2921.4467
13 | 437 | A | Improvements to road Maharastra Border to Raichur Border (Markel- Kollur-Bilihar) road, MDR from Km 3.00 Km 9.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | New SH | 88 | 860 | 2150 | 1851.53 | 2090.18 | 199.72 | 2289.9 | 2702.08 | 2732.6693 | Shri.Siddappagouda Patil, Yadgir | 2022-06-15 | 30.05.2024 |  | 4.75 | 4.75 | 4.75 | 100% | 0 | 2105.58 | 77.05% | 627.0893 | work completed |  |  | B |  |  | 23 | 3168.9009
|  | B | Improvements to road NH-150A to SH-127 Sangam-Raichur Border, MDR from Km16.30 to Km 57.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | SHA35 | 90 | 860 | [7 empty] | 15: 4.95; 16: 5.31; 17: 5.31; 18: 100%; 19: 0; 23: work completed | [5 empty] | 24 | 2191.5448
|  | C | Improvements to road Kurakunda to Bilhar Via Hortur, Halgera, Godihal Kumanur, Arjunagi, Kandalli, MDR from Km 0.00 to Km 13.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | MDR | 91 | 430 | [7 empty] | 15: 2.3; 16: 2.3; 17: 2.3; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 25 | 2469.9691
14 | 438 |  | Improvements to SH-16 Sindagi - Kodangal from Km 125.22 to KM 155.62 (in selected reaches) in Gurmitkal Taluka of Yadgir District. | SH-16 | 95 | 950 | 950 | 816.04 | 942.546 | 91.62 | 1034.166 |  | 1233.7969 | Shri.Siddappagouda Patil, Yadgir | 31.5.2022 | 30.06.204 |  | 9.5 | 11.7 | 11.7 | 100% | 0 | 945.58 | 76.64% | 288.2169 | Work completed |  | 11 |  |  |  | 26 | 2117.5127
15 | 439 | A | Improvements to road Devargonal to Gogi, MDR from Km 12.80 to Km 20.80 (in selected reaches) in Shahpur Taluka of Yadgir District. | SHA55 | 92 | 700 | 950 | 817.92 | 977.38 | 97.14 | 1074.52 |  | 1281.4456 | Shri.Chandrarayya, Yadgir | 25.5.2022 | 24.4.2023 |  | 3.82 | 4.29 | 4.29 | 100% | 0 | 1163.13 | 90.77% | 118.3156 | Work Completed |  | 12 |  |  |  | 27 | 2512.4155
|  | B | Improvements to road Bheemarayan Gudi to Bijaspur, MDR from Km 10.00 to KM 17.50 (in selected reaches) in Shahpur Taluka of Yadgir District. | SHA59 | 93 | 250 | [7 empty] | 15: 1.5; 16: 1.5; 17: 1.5; 18: 100%; 19: 0 | [5 empty] | 28 | 2202.5555
16 | 440 |  | Improvements to SH-155 from Pattan cross(SH-10) to Narayanapura dam Km110.00 to KM 167.30 (in selected reaches) in Shorapur Taluka of Yadgir District. | SH-155 | 94 | 2700 | 2700 | 2323.03 | 2760.38 | 595.48 | 3355.86 |  | 3998.2913 | Sri. Basangouda Allikoti, Yadgir | 2022-06-15 | 31.05.2024 |  | 48.52 | 15.87 | 15.87 | 100% | 0 | 2998.93 | 75.01% | 999.3613 | Road work completed |  | 13 |  |  |  | 29 | 2070.9989
|  |  | Division Total |  |  | 6750 | 6750 | 5808.52 | 6770.486 | 983.96 | 7754.446 | 2702.08 | 9246.203 | 15: 75.34; 16: 45.72; 17: 45.72; 19: 0; 20: 7213.22; 22: 2032.983 | [5 empty] | 30 | 2710.9786
|  |  | Kalburgi Circle Total |  |  | 26900 | 26900 | 23159.8 | 27598.616 | 2978.84 | 30577.456 | 9783.56 | 36463.998 | 15: 168.865; 16: 145.085; 17: 144.585; 19: 0.5; 20: 28623.75; 22: 7840.248 | [5 empty] | 31 | 3572.5833
Ballary Circle | [31 empty] | 32 | 3469.7752
Ballary Division | [31 empty] | 33 | 2518.619
17 | 441 | A | Improvements to MDR road of Ballary - Kalyanadurga Ch.0.80 km to 2.00 Km ( double road) in Ballary taluk, Ballary district. | MDR BER6 | 96/21-22 | 600 | 1400 | 1197.28 | 1292.96 | 118.45 | 1411.41 |  | 1685.2429 | Sri. T Ramanjaneya Reddy, Mysore | 5.7.2022 | 4.10.2022 | 04.4.2024 | 1.08 | 0.65 | 0.65 | 100% | 0 | 734.92 | 43.61% | 950.3229 | Road work completed, Road Furniture work to be done | 2 |  | C |  |  | 34 | 2125.2502
|  | B | Improvements MDR road from Kampli-Kurugodu-Kuduthini-Haraginidoni-Ballary-Aluru via Moka village Devalapura -Kamalapura from ch.88.99 km to 90.39 Km (in selected reaches) in Ballary taluk,Ballary district. | SH-132(BER19) | 97/21-22 | 800 | [7 empty] | 15: 1.06; 16: 1.06; 17: 1.06; 18: 100%; 19: 0; 23: Road work completed, 1 bridge work under progress(out of 16 pile, 1 pile boring exculation work completed, pile casting to be done. | [5 empty] | 35 | 1307.1123
19 | 443 | A | Improvements to road from maruthi camp somasandra Siddammanahalli to Yarangalli village road chainage 5.00 Km to 9.50 Km in kurugodu Taluk Bellary District. | MDR | 111/21-22 | 400 | 950 | 813.27 | 934.45 | 92.99 | 1027.44 |  | 1225.8144 | Sri. Kalkutiginahal Masididipura Praveen Kumar (Sri Siddarameswara Construction), Ballary | 2022-08-06 | 2022-07-05 |  | 2.05 | 2.05 | 2.05 | 100% | 0 | 1103.68 | 90.04% | 122.1344 | Work Completed |  | 14 |  |  |  | 36 | 3079.5542
|  | B | Improvements to road from Kanivathimmalapura village to Ramasagara road Chainage 0.00 Km to 4.00 Km in Kampli Taluk Bellary District | MDR | 123/21-22 | 300 | [7 empty] | 15: 1.4; 16: 2; 17: 2; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 37 | 3068.5652
|  | C | Improvements to road from Kuduthini to orvaayi cross road chainage 15.00 Km to 18.50 Km in Kurgodu Taluk Bellary District. | MDR | 135/21-22 | 250 | [7 empty] | 15: 1.35; 16: 1.35; 17: 1.35; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 38 | 2068.4776
20 | 444 | A | Improvements to MDR road of Kudadarahaal-Haccholi-Vatthuvarani, ch.0.00 km to 17.40 Km(in selected reaches) in Siraguppa taluk, Ballary district. | MDR SRG5 | 143/21-22 | 1100 | 2250 | 1939.83 | 2116.21 | 194.08 | 2310.29 |  | 2758.1882 | Sri. Y Pitcheswara Rao ( Sri Srinivasa Construction india Pvt Ltd), Ballary | 2022-03-08 | 2024-02-02 |  | 5 | 13.9 | 13.9 | 100% | 0 | 1575.86 | 57.13% | 1182.3282 | Work Completed | [5 empty] | 39 | 2972.5755
|  | B | Improvements to MDR road from Kudadarahaal to Nadanga via Vatthuvarani ,kothalachintha ch.0.00 km to 9.50 Km (in selected reaches) in Siraguppa taluk , Ballary district. | MDR SRG-29 | 150/21-22 | 1150 | [7 empty] | 15: 8.52; 16: 0; 17: 0; 18: 0%; 19: 0; 23: Road dropped. | [5 empty] | 40 | 2390.5708
|  |  | Division total |  |  | 4600 | 4600 | 3950.38 | 4343.62 | 405.52 | 4749.14 |  | 5669.2455 | 15: 20.46; 16: 21.01; 17: 21.01; 20: 3414.46; 22: 2254.7855 | [5 empty] | 41 | 1934.8996
Vijayanagara Division | [31 empty] | 42 | 1926.23
18 | 442 | A | Improvements to MDR road from Nallapura to Hosachinnapura ch.6.00 km to 9.40 Km in Hospet taluk ,Ballary district. | MDR HSP-217 | 98/21-22 | 400 | 2300 | 1961.66 | 2315.76 | 156.75 | 2472.51 |  | 2949.9684 | Sri. Sali Basavaraj, Hosapete | 2022-06-17 | 2023-12-16 |  | 2.53 | 3.23 | 3.23 | 100% | 0 | 2469.58 | 83.72% | 480.3884 | Work Completed | [5 empty] | 43 | 3620.2497
|  | B | Improvements to MDR road Connecting Ingalagi village to NH -63 km0.00 to 3.00 Km in Hospet taluk, Ballary district | MDR HSP-221 | 99/21-22 | 500 | [7 empty] | 15: 1.93; 16: 1.949; 17: 1.949; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 44 | 2537.0353
|  | C | Improvements to MDR road from Devalapura -Kamalapura , ch.10.00 km to 18.00 Km (in selected reaches) in Hospet taluk, Ballary district. | MDR HSP-14 | 100/21-22 | 700 | [7 empty] | 15: 7.74; 16: 7.63; 17: 7.63; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 45 | 1753.5725
|  | D | Improvements to MDR Road from Kondanayakanahalii to Danapura via Nagenahalli Thanda, ch.0.00 km to 6.00 Km in Hosapete taluk, Ballary district | MDR HSP 213 | 108/21-22 | 700 | [7 empty] | 15: 2.78; 16: 5.7; 17: 4.62; 18: 81.05%; 19: 1.08; 23: 4.62Km Work Completed 1.08Km Length of Road done in Appendix-E HOA by PWD Vijayanagara Division | [5 empty] | 46 | 2640.6015
21 | 445 | A | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommnahally from ch.131.00 to ch 137.00 km, ch.140.00 to Ch 141.15.00 km & ch.153.00 to Ch 156.15 km in Kudligi taluk , Ballary district. | SH-131 (KDL44) | 171/21-22 | 1250 | 2250 | 1928.95 | 2276.15 | 210.5 | 2486.65 |  | 2966.1133 | Sri. Sali Basavarj , Hosapete | 2022-06-15 | 2023-12-14 |  | 7.1 | 8.31 | 8.31 | 100% | 0 | 2198.65 | 74.13% | 767.4633 | Work Completed |  | 15 |  |  |  | 47 | 3970.7818
|  | B | Improvements MDR road from Hosahalli to Kanamadagu via Hagaribommanahalli from ch.1.22 Km to ch .7.30 km & ch.7.70km to Ch 8.75 km in Kudligi taluk ,Ballary district. | MDR KDL 13 | 180/21-22 | 1000 | [7 empty] | 15: 6.67; 16: 6.605; 17: 6.605; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 48 | 2321.33
22 | 593 |  | Improvements SH -151 road from Itagi to Kanchikere via Chitageri,Kadabageri, Arasikere from ch.7.80 km to ch 25.00 km in Harapanahalli taluk, Ballary district. | SH-151 (HRP6) | 181/21-22 | 2150 | 2150 | 1841.5 | 2203.11 |  | 2203.11 |  | 2630.0914 | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi , | 2022-05-06 | 2023-11-05 |  | 10.25 | 10.25 | 9.36 | 91.32% | 0.89 | 1966.39 | 74.77% | 663.7014 | 9.36 Km Asphalt Completed, 0.89 Km work to be done (Pending due to Court Case) | 3 |  | D |  |  | 49 | 2660.532
23 | 446 | A | Improvements SH -45 road connecting Arabhavi and Challakere Via Gokak,Naragunda ch.217.80 km to ch 225.02 km in Hadagali taluk, Ballary district. | SH-45 (HDG202) | 190/21-22 | 950 | 1900 | 1621.59 | 1908.21 | 189.91 | 2098.12 |  | 2502.5703 | Sri Savajji Rajendraprasad (Varavi malleswara Contract Company Private Limited), Ballary , | 2022-06-16 | 2023-12-15 |  | 6.63 | 6.5 | 6.5 | 100% | 0 | 1617.73 | 64.64% | 884.8403 | Work Completed |  | 25 |  |  |  | 50 | 1739.3022
|  | B | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommanahalli from ch.159.00 km to ch 169.30 in Kudalagi taluk,Ballary district. | SH-131 (KDL44) | 200/21-22 | 950 | [7 empty] | 15: 5.41; 16: 5.23; 17: 5.23; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 51 | 2473.4473
|  |  | Division total |  |  | 8600 | 8600 | 7353.7 | 8703.23 | 557.16 | 9260.39 |  | 11048.7433 | 15: 51.04; 16: 55.404; 17: 53.434; 19: 1.97; 20: 8252.35; 22: 2796.3933 | [5 empty] | 52 | 2711.8571
Koppal Divison | [31 empty] | 53 | 1385.0197
24 | 447 |  | Improvements MDR road from Hosahalli to Koppala via Hirekasawadi,Halavarthi ch.0.00 km to ch 19.00 in Koppal taluk Koppal district. | MDR 206(KOP206) | 222/21-22 | 950 | 950 | 815.76 | 941.78 | 86.84 | 1028.62 |  | 1227.248 | Sri. Mallikarjuna H Ammapur, Lingasuguru | 2022-07-15 | 2023-06-16 |  | 3.36 | 3.71 | 3.71 | 100% | 0 | 914.72 | 74.53% | 312.528 | Work Completed |  | 16 |  |  |  | 54 | 3024.9636
25 | 599 |  | Improvement to SH-59 road from Kustagi- to Pattadakallu 0.00 km to 21.20 km ( in selected reaches) in Kushtagi taluk, Koppal district . | SH-59 | 250/21-22 | 1000 | 1000 | 861.31 | 1075.4 | 262.34 | 1337.74 |  | 1592.762 | Sri. Basavaraj Gowda Ganekal , Vijayapur | 2022-06-06 | 2023-05-05 |  | 5.3 | 6 | 6 | 100% | 0 | 1568.92 | 98.5% | 23.842 | 100% Completed and Third party inspection completed |  | 17 |  |  |  | 55 | 3065.3389
26 | 448 | A | Improvements MDR road from Ginigera to Irkalagada ch.3.00 km to ch 13.00 (selected reaches) in Koppal taluk ,Koppal district. | MDR (KOP18) | 300/21-22 | 1000 | 2250 | 1935.72 | 2438.92 | 243.34 | 2682.26 |  | 3197.0449 | Sri. Sharana Gowda,Raichur | 2022-07-01 | 2024-01-01 |  | 5.28 | 8.81 | 8.81 | 100% | 0 | 2262.85 | 70.78% | 934.1949 | Work Completed |  |  | E |  |  | 56 | 2718.955
|  | B | Improvements MDR road from Gaddi to Hampasadurga upto NH-13 Ch.13.10 km to ch.15.90 km in Koppal taluk ,Koppal district. | MDR KOP219 | 313/21-22 | 300 | [7 empty] | 15: 2.15; 16: 2.15; 17: 0; 18: 0%; 19: 0; 23: This Road is Dropped | [5 empty] | 57 | 3168.7079
|  | C | Improvements to SH-130 road from Yelburga-Kankagiri-Gangavathi-Munirabad , 70.00km to 74.00 and 79.00 km to 81.90 km in Gangavathi taluk Koppal District. | SH-130 | 333/21-22 | 950 | [7 empty] | 15: 3.79; 16: 2.9; 17: 2.9; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 58 | 3472.5683
27 | 449 |  | Improvements to SH-63 road from Raravi-Beluru Ch. 58.22 km to ch.75.42 km ( in selected reaches) in Kanakagiri taluk,Koppal District. | SH-63(GAN94) | 345/21-22 | 2250 | 2250 | 1939.1 | 2288.14 | 225.65 | 2513.79 |  | 2998.3061 | Sri. G Srinivas Rao ( Karunamaya Construction Company),Koppala | 2022-05-07 | 2023-11-24 |  | 9.97 | 10.21 | 10.12 | 99.12% | 0.09 | 2722.39 | 90.8% | 275.9161 | Completed and Third party inspection completed |  | 18 |  |  |  | 59 | 4256.4767
28 | 450 | A | Improvements toMDR road from Kavalooru to Mangalore ch. 12.00 km to ch.14.50 & Ch.16.00 km to ch.23.80 ( in Selected reaches)Yelaburga taluk, Koppal district. | MDR YL 7 | 223/21-22 | 1300 | 2300 | 1974.31 | 2363.16 | 235.13 | 2598.29 |  | 3098.5978 | Sri. Dodda Basana Gouda ( Doddabasanagouda & Company) Raichur | 44712 | 45259 |  | 6.8 | 12.04 | 12.04 | 100% | 0 | 3026.83 | 97.68% | 71.7678 | Completed and Third party inspection completed |  | 19 |  |  |  | 60 | 1488.0441
|  | B | Improvements to SH-129 road from Chikkahesaruru-Mudagal-Mungaragi ch. 85.20 km to 111.40 km ( in Selected reaches) in Yelaburga taluk ,Koppal district. | SH-129 | 224/21-22 | 1000 | [6 empty] | 0 | 15: 4.65; 16: 4.57; 17: 4.57; 18: 100%; 19: 0; 23: Completed and Third party inspection completed | [5 empty] | 61 | 4380.0102
|  |  | Division total |  |  | 8750 | 8750 | 7526.2 | 9107.4 | 1053.3 | 10160.7 |  | 12113.9588 | 15: 41.3; 16: 50.39; 17: 48.15; 19: 0.09; 20: 10495.71; 22: 1618.2488 | [5 empty] | 62 | 4500.8209
Raichur Division | [31 empty] | 63 | 2697.047
29 | 451 |  | Improvements to MDR road connecting Guragunta Gowdaruru, Machanur ,Yelaghatta to Hosuru Ch:0.00 km to 19.00 km ( in selected reaches) Lingasugur taluk, Raichur district. | MDR LIN 16 | 225/21-22 | 1300 | 1300 | 1120.5 | 1174.17 |  | 1174.17 |  | 1404.0313 | Sri. Mallikarjuna H Ammapur, Lingasuguru | 2022-07-15 | 2023-10-14 |  | 7.41 | 7.41 | 7.41 | 100% | 0 | 1347.23 | 95.95% | 56.8013 | Final Bill Under Progress |  | 20 |  |  |  | 64 | 1956.9278
30 | 452 | A | Improvements to SH-14 road from Ramadurga - Manvi via Badami,Pattadakallu,Hulagunda Ch:227.80 km to 236.00 in Manvi taluk, Raichur district. | SH-14 | 226/21-22 | 500 | 2000 | 1722.03 | 1745.03 | 174 | 1919.03 |  | 2292.9033 | Sri. Amaravaram Channa reddy ( ACR Projects), Bangalore | 2022-07-13 | 2024-01-12 |  | 2 | 2 | 2 | 100% | 0 | 2131.8 | 92.97% | 161.1033 | Work Completed |  | 21 |  |  |  | 65 | 1959.7491
|  | B | Improvements to MDR road from Kavithala to Veerapura cross via Anwari village, Ch:4.00 km to 13.30 km road via Anvaari village,in Lingasuguru& Manvi Taluk, Raichur district. | MAN 33 | 227/21-22 | 500 | [7 empty] | 15: 1.82; 16: 1.82; 17: 1.82; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 66 | 1859.4787
|  | C | Improvements to road from sindanooru taluk bappuru kuduthini lingasooguru ch KM 0.00 to 16.00 in Raichur District | LIN 206 | 207/21-22 | 1000 | [7 empty] | 15: 5.22; 16: 5.22; 17: 5.22; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 67 | 2547.4028
31 | 453 |  | Improvements to road from SH-23 to Mukunda-Singapura road via Channahalli,Sindrampura, Mavinamadaguch. 0.00 km to 15.70km ( In selected reaches) in Sindanooru taluk ,Raichur district. | MDR-SIN228 | 199/21-22 | 1000 | 1000 | 861.65 | 1059.83 | 263.64 | 1323.47 |  | 1575.9291 | Sri. Karabasappa Gouda S Patil, Vijayapur | 2022-07-13 | 2023-06-12 |  | 4.71 | 5.9 | 5.9 | 100% | 0 | 1444.25 | 91.64% | 131.6791 | Final Bill Under Progress |  | 22 |  |  |  | 68 | 2288.6421
32 | 454 | A | Improvements to MDR road from Gannadala to Jalahalli via Kakkaladoodi Kamaladinne, Maykaladoodi, Ch:0.00 km to 20.00km ( in Selected reaches) in Devadurga taluk, Raichur district. | MDR DEV 209 | 101/21-22 | 2000 | 2300 | 1978.77 | 2360.9 | 233.46 | 2594.36 |  | 3094.0341 | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi | 2022-05-06 | 2023-11-05 |  | 7.89 | 9.78 | 9.08 | 92.84% | 0.7 | 2448.13 | 79.12% | 645.9041 | 700 mtr CC Road Balance (Land Acquition) | 4 |  | F |  |  | 69 | 4119.7471
|  | B | Improvements to MDR road from Maladakallu cross Malledevaragoodda via karadigooda, Jagatagallu) Ch:0.00 km to 18.00 km ( In selected reaches) in Devadurga taluk ,Raichur district | MDR DEV 216 | 131/21-22 | 300 | [7 empty] | 15: 1.44; 16: 1.47; 17: 1.47; 18: 100%; 19: 0; 23: Road Furtuniture are balance | [5 empty] | 70 | 3257.7804
33 | 455 | A | Improvements to SH-61 road from Managooli-Bechaali upto NH-167 Ch. km 239.23 km to 241.19 km ( in Selected reaches) upto NH-167 in Raichur Taluk , Raichur district. | SH-61 | 141/21-22 | 200 | 950 | 807.67 | 742.7 |  | 742.7 |  | 889.7287 | Sri. Venkatesh Yadav, Manvi | 2022-05-20 | 2023-04-19 |  | 1.02 | 1.016 | 1.016 | 100% | 0 | 773.85 | 86.98% | 115.8787 | Work Completed |  | 23 |  |  |  | 71 | 2964.5057
|  | B | Improvements to road from SH-13 (NH-167) Yaragera Gillesooguru via Gannadala Ch KM 0.00 to 20.78 ( in Selected reaches) in Raichur Taluk ,Raichur district. | SH-13 | 151/21-22 | 500 | [7 empty] | 15: 2.7; 16: 2.9; 17: 2.9; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 72 | 2650.6564
|  | C | Improvements to road from NH-167 connecting H-127 via Ashapura Udumagal, Purathipli road CH KM 5.70 to 9.00 in Raicur Taluk, Raichur District. | MDR RA15 | 161/21-22 | 250 | [7 empty] | 15: 1.52; 16: 1.52; 17: 1.52; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 73 | 1847.3571
34 | 456 | A | Improvements to MDR road from Raichur-Buradipadha Ch:0.00 km to 6.00 km ( in Selected reaches) in Raichur Taluk ,Raichur district. | MDR RAI 6 | 212/21-22 | 700 | 2200 | 1875.75 | 2244.6 | 220.84 | 2465.44 |  | 2940.2066 | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi | 2022-06-04 | 2023-12-05 |  | 1.78 | 3.6 | 3.6 | 100% | 0 | 1747.55 | 59.44% | 1192.6566 | Road Furtuniture are balance | [5 empty] | 74 | 2408.8898
|  | B | Improvements to MDR road connecting Raichur and SH-127 via Ashapura, Purthipalli ch. 0.00 km to 5.00 km ( in Selected reaches) Raichur Taluk Raichur district | MDR RAI 5 | 242/21-22 | 700 | [7 empty] | 15: 1.85; 16: 1.45; 17: 1.3; 18: 89.66%; 19: 0.15; 23: LHS 150 mts., PQC Balance, drain 300 mtrs., is in progress & Road Furniture Balance | 5 |  | G |  |  | 75 | 5262.0064
|  | C | Improvements to MDR road from SH-167 ( Devasooguru Katagooda road) to Raichur -Yaklasapura via Ambavadi ch. 1.72 km to 3.10 km in Raichur taluk, Raichur District | MDR RAI 215 | 272/21-22 | 300 | [7 empty] | 15: 1.41; 16: 0; 17: 0; 18: 0%; 19: 0; 23: Work cancelled | [5 empty] | 76 | 3502.8688
|  | D | Improvements to MDR road from Basavana bhavi circle of Raichur -Singanodi road to Vidhanasaba nagara Ricemill ,ch. 0.00 km to 8.00 km ( selected reaches) in Raichur taluk , Raichur District. | MDR RAI 206 | 228/21-22 | 500 | [7 empty] | 15: 1.11; 16: 1.11; 17: 1.11; 18: 100%; 19: 0; 23: Road Furniture Balance | [5 empty] | 77 | 2813.4967
|  |  | Division total |  |  | 9750 | 9750 | 8366.37 | 9327.23 | 891.94 | 10219.17 |  | 12196.833 | 15: 41.88; 16: 45.196; 17: 44.346; 19: 0.85; 20: 9892.81; 22: 2304.023 | [5 empty] | 78 | 1507.9341
|  |  | Ballary Circle Total |  |  | 31700 | 31700 | 27196.65 | 31481.48 | 2907.92 | 34389.4 |  | 41028.7807 | 15: 154.68; 16: 172; 17: 166.94; 19: 2.91; 20: 32055.33; 22: 8973.4507 | [5 empty] | 79 | 2435.3875
Dharwad Cricle | [31 empty] | 80 | 2631.5617
Dharwad Division | [31 empty] | 81 | 4161.5824
35 | 457 | A | Improvements to Padubidri-Chikkalagudda SH-01 from Ch: 340.30 to 356.97 Km (in selected reaches) in Kalaghatagi taluk of Dharwad District. | SH-01 | 39 | 1900 | 2250 | 1939.79 | 2164.61 | 407.97 | 2572.58 |  | 3067.6897 | Sri. Mallikarjun Siddaramappa Patil | 21.09.2022 | 20.03.2024 |  | 9.695 | 9.695 | 9.695 | 100% | 0 | 2440.66 | 79.56% | 627.0297 | completed |  | 46 |  |  |  | 82 | 2753.6924
|  | B | Improvements to Managundi-Tadasinakoppa from Ch: 0.00 Km to 5.00 Km (in selected reaches) in Dharwad taluk of Dharwad District. | MDR | 40 | 350 | [7 empty] | 15: 2.04; 16: 2.62; 17: 2.62; 18: 100%; 19: 0; 23: completed | [5 empty] | 83 | 3581.079
36 | 458 | A | Improvements to Beedi-Belavanaki SH-56 from Ch: 62.40 to 69.28 Km (in selected reaches) in Navalagund taluk of Dharwad District. | SH-56 | 41 | 1020 | 2300 | 1980.05 | 2330.44 | 232.34 | 2562.78 |  | 3056.7908 | Sri. Mallikarjun B Kallur (M B Kallur Infrastructure Company) | 02-08-2022 | 2024-02-01 |  | 6.42 | 6.42 | 6.42 | 100% | 0 | 1934.42 | 63.28% | 1122.3708 | Completed |  |  | H |  |  | 84 | 2116.9749
|  | B | Improvements to Supa-Annigeri SH-28 from Ch:108.77 to 114.77 Km (in selected reaches) in Navalagund taluk of Dharwad District. | SH-28 | 42 | 280 | [7 empty] | 15: 1.53; 16: 2.18; 17: 2.18; 18: 100%; 19: 0; 23: Completed | [5 empty] | 85 | 3057.9823
|  | C | Improvements to Supa-Annigeri SH-28 from Ch: 84.70 to 99.30 Km (in selected reaches) in Hubballi taluk of Dharwad District. | SH-28 | 43 | 1000 | [7 empty] | 15: 6.42; 16: 6.42; 17: 6.42; 18: 100%; 19: 0; 23: Completed | [5 empty] | 86 | 3111.6863
37 | 459 | A | Improvements to Samshi-Gudageri road from 0.0 to 11.0Km in Kundagol taluka | MDR | 48 | 850 | 2200 | 1890.89 | 2171.13 | 521.83 | 2692.96 |  | 3208.9303 | Sri.Chandrashekhar Appasaheb Biradar | 03-08-2022 | 2024-02-02 | 29.07.2024 | 6.45 | 6.45 | 6.45 | 100% | 0 | 1883.19 | 58.69% | 1325.7403 | Completed |  |  | I |  |  | 87 | 1496.7193
|  | B | Improvements to Pashupatihal-Rottigavad MDR road Ch 0.0km to 3.18Km, 3.9 to 9.3Km and 11.00 to 13.5Km in Kundagol tq. | MDR | 49 | 750 | [7 empty] | 15: 5.73; 16: 9.702; 17: 9.702; 18: 100%; 19: 0; 23: Completed | [5 empty] | 88 | 2383.4144
|  | C | Improvements to Hireharakuni Shishuvinal road upto Kundagol tq limit (MDR) from Ch: 0.00 Km to 5.16 Km in Kundagol tq . | MDR | 58 | 450 | [7 empty] | 15: 3.75; 16: 3.75; 17: 3.75; 18: 100%; 19: 0; 23: Completed | [5 empty] | 89 | 761.9359
|  | D | Improvements to Varur-Hindasageri via (NH-04) from Surashettikoppa road upto Hubballi city limit road (MDR) from Ch: 0.0 Km to 2.0Km (in selected reaches) in Hubballi tq of Dharwad District. | MDR | 71 | 150 | [7 empty] | 15: 1.6; 16: 1.72; 17: 1.72; 18: 100%; 19: 0; 23: Completed | [5 empty] | 90 | 1830.6152
38 | 460 |  | Improvements to Veerapura Toll-Manturu MDR road from Ch: 0.40 to 3.00 Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 73 | 950 | 950 | 819.34 | 1005.17 | 99.02 | 1104.19 |  | 1316.4797 | Sri Chandrashekhar Appasaheb Biradar | 06-07-2022 | 05-06-2023 | 31.03.2024 | 2.08 | 2.1 | 2.1 | 100% | 0 | 511.98 | 38.89% | 804.4997 | Completed |  | 47 |  |  |  | 91 | 2349.4206
39 | 461 | A | Improvements from Anand Nagar Main Road to Gokul Main Road ( opposite RN Shetty Factory) in Hubballi taluk of Dharwad District. | MDR | 74 | 700 | 1700 | 1450.36 | 1562.04 | 155.47 | 1717.51 |  | 2050.6217 | Sri. Bhimshi Siddappa Biradar (B S Biradar) | 18-06-2022 | 17-09-2023 |  | 1.301 | 1.59 | 1.59 | 100% | 0 | 1712.11 | 83.49% | 338.5117 | Completed |  | 48 |  |  |  | 92 | 3212.9341
|  | B | Improvements to BRTS Road to Jakka Reddy Hospital, Lokappana Hakkala, Railway Underpass connecting to NH Division Office Adjoining to Vidyanagar Police Station, Lakshmi Temple in Hubballi Dharwad Mahanagar, Hubballi tq of Dharwad District. | MDR | 75 | 600 | [7 empty] | 15: 2.29; 16: 2.146; 17: 2.146; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 93 | 1940.7215
|  | C | Improvements to Hubballi Basaveshwara Nagar Gokul Road to join Ravi Nagar Road in Hubballi taluk of Dharwad District. | MDR | 76 | 400 | [7 empty] | 15: 1.46; 16: 1.762; 17: 1.762; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 94 | 2101.3057
40 | 462 |  | PKG-462 Improvements to Beedi-Belavanaki SH-56 from Ch: 33.42 to 48.83Km (in selected reaches) in Dharwad taluk of Dharwad District. | SH-56 | 78 | 2250 | 2250 | 1939.47 | 2115.98 | 437.24 | 2553.22 |  | 3044.8396 | M/s M B Kallur Infrastructure Company | 02-08-2022 | 01-02-2024 |  | 13.72 | 13.18 | 13.18 | 100% | 0 | 1802.91 | 59.21% | 1241.9296 | Completed. | [5 empty] | 95 | 2768.7211
41 | 463 | A | Improvements to Supa-Annigeri SH-28 from Ch: 67.0Km to 68.5 Km in Dharwad Tq. | SH-28 | 79 | 1210 | 2300 | 1967.98 | 2279.16 | 145.68 | 2424.84 |  | 2893.8222 | Sri. Beeranna Subray Gaonkar (BSG Infrastructure) | 06-07-2022 | 05-01-2024 | 05.12.2024 | 1.55 | 0.85 | 0.85 | 100% | 0 | 1045.65 | 36.13% | 1848.1722 | Road Work Completed Utility work Under progress | [5 empty] | 96 | 2883.9139
|  | B | Improvements to Gokul cross-Tarihala- Kanavi-Honnapur MDR from Ch: 4.2Km to 4.8Km and 6.2Km to 8.4Km in Hubballi tq. | MDR | 80 | 480 | [7 empty] | 15: 0.814; 16: 0.814; 17: 0.814; 18: 100%; 19: 0; 23: Completed | [5 empty] | 97 | 1635.751
|  | C | Improvements to Ittigatti-Kanavihonnapur MDR from Ch: 0.0 to 2.0Km in Dharwad tq. | MDR | 86 | 220 | [7 empty] | 15: 1.485; 16: 1.485; 17: 1.485; 18: 100%; 19: 0; 23: Completed | [5 empty] | 98 | 2715.7592
|  | D | Improvements to Gokul-Revadihal-Tarihal MDR road from Ch: 0.0 to 6.2Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 87 | 390 | [7 empty] | 15: 3.24; 16: 3.24; 17: 3.24; 18: 100%; 19: 0; 23: Completed | [5 empty] | 99 | 1685.3027
|  |  | Division Total |  |  | 13950 | 13950 | 11987.88 | 13628.53 | 1999.55 | 15628.08 |  | 18639.1742 | 15: 71.575; 16: 76.124; 17: 76.124; 19: 0; 20: 11330.92; 22: 7308.2542 | [5 empty] | 100 | 2278.1701
Gadag Division | [13 empty] | 16: 0 | [5 empty] | 101 | 2950.3218
42 | 464 | A | Improvements to Kalasapur-Mahalingapura- Anganakatti road (MDR) from Ch: 21.00 Km to 29.00 Km ( in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 89 | 640 | 2000 | 1722.68 | 1944.89 | 479.42 | 2424.31 |  | 2889.1445 | Sri K.V Hanchinal, Mundargi | 18-06-2022 | 17-12-2023 |  | 4.81 | 7.33 | 7.33 | 100% | 0 | 2247.38 | 77.79% | 641.7645 | Completed | [5 empty] | 102 | 1003.7115
|  | B | Improvements to Asundi-Kurtkoti-Mulagunda road (MDR) Ch: 2.20 Km to 8.00 Km and 8.60 Km to 10.00 Km (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 109 | 640 | [7 empty] | 15: 3.98; 16: 3.98; 17: 3.98; 18: 100%; 19: 0; 23: Completed |  | 1 |  |  |  | 103 | 4410.3504
|  | C | Improvements to Kalasapur-Mahalingapura- Anganakatti road Ch:0.30 Km to 2.60 and Ch: 7.00 Km to 21.00 (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 116 | 720 | [7 empty] | 15: 4.09; 16: 4.09; 17: 4.09; 18: 100%; 19: 0; 23: Completed | [5 empty] | 104 | 1796.6562
43 | 465 | A | Improvements to Bellatti-Guttala road Konchigeri- Nagaramadavu-Kerekoppa from Ch: Km 0.00 to 11.90 (in selected reaches) in Shirahatti taluk of Gadag Dist. | MDR | 117 | 1150 | 2300 | 1981.42 | 2435.67 |  | 2435.67 |  | 2906.8237 | Sri K.V Hanchinal, Mundargi | 18-06-2022 | 17-12-2023 |  | 7.44 | 7.44 | 7.44 | 100% | 0 | 2614.91 | 89.96% | 291.9137 | Completed |  | 2 |  |  |  | 105 | 2086.0396
|  | B | Improvements to Varavi cross-Bannikoppa road (MDR) from Ch-0.00 to 4.30 & Ch-8.30 to 20.00 Km (in selected reaches) in Shirahatti taluk of Gadag Dist. | MDR | 118 | 1150 | [7 empty] | 15: 7.65; 16: 7.65; 17: 7.65; 18: 100%; 19: 0; 23: Completed | [5 empty] | 106 | 3169.0431
44 | 466 | A | Improvements to Chikkahandigol-Belahoda-Madaganoor Ch0.0to4.5,5.4 to7.4,9.6 to11.0&11.8to13.0 in Naragund Tq | MDR | 119 | 1040 | 3050 | 2628.68 | 3200.62 | 723.24 | 3923.86 |  | 4673.5806 | Sri. Basavaraj V Bingi | 18-07-2022 | 17-01-2024 |  | 6.555 | 9.355 | 9.355 | 100% | 0 | 5887.78 | 126% | -1214.1994 | Completed |  | 3 |  |  |  | 107 | 2960.7876
|  | B | Improvements to Abbigeri-Yerebeleri-Kurudagi- Gujamagadi Ch5.0to7.5&9.0 to12.1 of Ron Tq | MDR | 120 | 400 | [7 empty] | 15: 2.29; 16: 2.63; 17: 2.63; 18: 100%; 19: 0; 23: Completed | [5 empty] | 108 | 3202.957
|  | C | Improvements to Kalakeri-Kanakikoppa-Naragund Ch17.0to21.13 in Naragund Tq | MDR | 121 | 460 | [7 empty] | 15: 2.96; 16: 3.46; 17: 3.46; 18: 100%; 19: 0; 23: Completed | [5 empty] | 109 | 2372.6206
|  | E | Improvements to Gajendragad-Soraba SH136 Ch67.0to69.9 in Naragund Tq | SH-136 | 124 | 350 | [7 empty] | 15: 2.42; 16: 2.8; 17: 2.8; 18: 100%; 19: 0; 23: Completed | [5 empty] | 110 | 3956.5847
|  | F | Improvements to Sindhanuru-Hemmadaga SH30 Ch159.77to161.7 of Naragund Tq | SH-30 | 125 | 700 | [7 empty] | 15: 1.55; 16: 1.59; 17: 1.59; 18: 100%; 19: 0; 23: Completed | [5 empty] | 111 | 3043.8636
|  | G | Improvements to Bagalakote Biligiriranganabetta SH57 Ch91.0to92.5 (in selected reaches) in Gadag Tq,Gadag Dt. | SH-57 | 126 | 100 | [7 empty] | 15: 0.255; 16: 0.255; 17: 0.255; 18: 100%; 19: 0; 23: Completed | [5 empty] | 112 | 3730.9142
|  | D | Improvements to Munavalli-Kotumachage (SH-83) road from Ch-87.30 km to 100.00 km in selected reaches of Ron Taluk, Gadag district | SH-83 | 122 | 1250 | 1250 | 1067.93 | 1264.5 | 304.95 | 1569.45 |  | 1869.5932 | Sri Ibrahim Sheriff | 13-07-2022 | 12-06-2023 |  | 7.55 | 7.55 | 7.55 | 100% | 0 |  |  |  | Completed | [5 empty] | 113 | 3443.703
45 | 467 | A | Improvements to Hallikeri-Shirahatti road (MDR) from Ch: 0.00 to 26.00 (in selected reaches) in Mundaragi taluk of Gadag Dist. | MDR | 139 | 1735 | 3100 | 2671.98 | 3331.77 | 316.89 | 3648.66 |  | 4349.5599 | Sri. H. P. Madhukar & Company, Hubli | 21-06-2022 | 20-12-2023 | 10.06.2024 | 10.73 | 10.75 | 10.75 | 100% | 0 | 3995.77 | 91.87% | 353.7899 | Completed |  | 4 |  |  |  | 114 | 1714.5589
|  | B | Improvements to Gajendragada-Soraba Sh-136 from Ch: 23.70 to 36.00 Km (in selected reaches) in Ron taluk of Gadag Dist. | SH-136 | 158 | 1365 | [7 empty] | 15: 8.96; 16: 8.96; 17: 8.96; 18: 100%; 19: 0; 23: Completed | [5 empty] | 115 | 2243.172
|  |  | Division Total |  |  | 11700 | 11700 | 10072.69 | 12177.45 | 1824.5 | 14001.95 |  | 16688.7018 | 15: 71.24; 16: 77.84; 17: 77.84; 19: 0; 20: 14745.84; 22: 73.2686 | [5 empty] | 116 | 3182.3059
Haveri Division | [13 empty] | 16: 0 | [5 empty] | 117 | 5283.6936
46 | 468 | A | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 284.51 Km to 294.51 Km (In Selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 159 | 1575 | 2775 | 2391.65 | 2846.55 | 676.41 | 3522.96 |  | 4196.6029 | Sri S B Dundigoudar (Bannur Infrastructures Private Limited) | 03-08-2022 | 02-02-2024 |  | 8.225 | 9.42 | 9.42 | 100% | 0 | 3946.09 | 94.03% | 250.5129 | Completed |  | 5 |  |  |  | 118 | 1223.6176
|  | B | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 294.51 Km to 303.200 Km (in selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 169 | 1200 | [7 empty] | 15: 6.617; 16: 9.22; 17: 9.22; 18: 100%; 19: 0; 23: Completed | [5 empty] | 119 | 2756.3997
47 | 605 | A | Improvements to Shiggoan-Savanur railway station road (MDR) from Ch: 8.10 Km to 13.10 Km (In Selected reaches) in Savanur taluk, Haveri District. | MDR | 160 | 500 | 2200 | 1895.22 | 2274.94 | 507.19 | 2782.13 |  | 3314.2224 | Sri S B Dundigoudar (Bannur Infrastructures Private Limited) | 03-08-2022 | 02-02-2024 |  | 2.785 | 2.785 | 2.785 | 100% | 0 | 2462.17 | 74.29% | 852.0524 | Completed |  | 6 |  |  |  | 120 | 2619.1521
|  | B | Improvements to Kumta-Tadas SH-69 road from Ch-134.50 Km to 142.00 Km (In Selected Reaches) in Shiggoan taluk of Haveri District. | SH-69 | 170 | 900 | [7 empty] | 15: 4.08; 16: 6.488; 17: 6.488; 18: 100%; 19: 0; 23: Completed | [5 empty] | 121 | 1848.0305
|  | C | Improvements to Savanur- Hurulikuppi road from Ch-0.00 Km to 5.65 Km (In Selected Reaches) in Savanur taluk of Haveri District. | MDR | 172 | 800 | [7 empty] | 15: 5.095; 16: 5.42; 17: 5.42; 18: 100%; 19: 0; 23: Completed | [5 empty] | 122 | 1095.6111
48 | 469 |  | Improvements to Birur-Sammasagi SH: 76 Ch: 189.00 Km to 201.60 Km in selected reaches and 203.82 Km to 217.19 Km In Selected Reaches of Hanagal taluk, Haveri District.(Balance work) | SH-76 | 173 | 2300 | 2300 | 1984.45 | 1379.58 | 137.74 | 1517.32 |  | 1823.2207 | Sri F B Patil | 19.02.2025 | 18.01.2026 |  | 15.735 | 13.875 | 13.875 | 100% | 0 | 101.42 | 5.563% | 1721.8007 | Road work completed Road furniture work under progress | 1 |  | J |  |  | 123 | 2466.4735
49 | 470 | A | Improvements to Havanur-Choudadanayyapura road Ch: 1.25 Km to 9.00 Km of Haveri taluk Haveri District | MDR | 174 | 630 | 2300 | 1979.52 | 2392.11 | 597.05 | 2989.16 |  | 3559.9105 | M/s JYOTI (Deveeka Constructions), | 03-08-2022 | 02-02-2024 | 29.07.2024 | 3.9 | 3.9 | 3.9 | 100% | 0 | 3091.32 | 86.84% | 468.5905 | Completed |  | 7 |  |  |  | 124 | 2161.0604
|  | B | Improvements to Halagi-Balehosur road Ch: 0.00 Km to 2.50 Km of Haveri taluk, Haveri District. | MDR | 175 | 250 | [7 empty] | 15: 1.68; 16: 2.41; 17: 2.41; 18: 100%; 19: 0; 23: Completed | [5 empty] | 125 | 756.5044
|  | C | Improvements to Agadi-Devagiri road Ch: 4.50 Km to 6.00 Km and 11.00 Km to 12.50 Km of Haveri taluk, Haveri District. | MDR | 176 | 425 | [7 empty] | 15: 1.388; 16: 1.953; 17: 1.953; 18: 100%; 19: 0; 23: Completed | [5 empty] | 126 | 3073.9906
|  | D | Improvements to Totadayellapura-Masoor-Guttala road Ch: 18.00 Km to 24.50 Km of Haveri taluk, Haveri District. | MDR | 177 | 495 | [7 empty] | 15: 3.03; 16: 3.83; 17: 3.83; 18: 100%; 19: 0; 23: Completed | [5 empty] | 127 | 2342.346
|  | E | Improvements to Agadi-Katenahalli road Ch: 0.80 Km to 6.50 Km Haveri taluk, Haveri District. | MDR | 178 | 500 | [7 empty] | 15: 3.428; 16: 3.428; 17: 3.428; 18: 100%; 19: 0; 23: Completed | [5 empty] | 128 | 2503.8133
50 | 471 | A | Improvements toTavargi - Tumminkatte road (MDR) from Ch: 0.00 Km to 22.50 Km (In Selected reaches) in Hirekerur taluk, Haveri District. | MDR | 179 | 1000 | 2300 | 1971.77 | 2266.4 | 328.51 | 2594.91 |  | 3094.5674 | Sri. Sachin Kollur (M/s Kollur Gurunath Construction Infra Private Limited), | 16-07-2022 | 15-01-2024 |  | 8.368 | 8.72 | 8.72 | 100% | 0 | 3108.49 | 100.4% | -13.9226 | Completed |  | 8 |  |  |  | 129 | 1289.1199
|  | B | Improvements to Road from Birur-Sammasagi SH: 76 to Join Halageri-Hulikal SH-26 Via Hirekerur-Masur-Kodamaggi- Hallur road Ch: 28.25 Km to 47.45 Km in selected reaches of Hirekerur taluk, Haveri District | SH-76 | 182 | 900 | [7 empty] | 15: 7.59; 16: 7.59; 17: 7.59; 18: 100%; 19: 0; 23: Completed | [5 empty] | 130 | 3822.9928
|  | C | Improvements to Road from Birur- Sammasagi SH: 76 to Join Byadagi - Rattihalli road Via Aladageri Ch: 0.00 Km to 7.10 Km in selected reaches of Hirekerur taluk, Haveri District. | SH-76 | 183 | 400 | [7 empty] | 15: 3.98; 16: 3.98; 17: 3.98; 18: 100%; 19: 0; 23: Completed | [5 empty] | 131 | 3934.3249
51 | 472 | A | Improvements to Sanguru - Tilavalli MDR Ch: 0.00 Km to 5.60 Km in Haveri taluk, Haveri District. | MDR | 184 | 590 | 2250 | 1938.94 | 2272.32 | 222.73 | 2495.05 |  | 2976.1903 | Sri. Santosh Veerayya Hiremath | 03-08-2022 | 02-02-2024 |  | 3.76 | 3.76 | 3.76 | 100% | 0 | 3021.82 | 101.5% | -45.6297 | Completed | [5 empty] | 132 | 2540.3829
|  | B | Improvements to Honnalli - Hanagal SH Via Tumminakatti - Rattihalli - Byadagi Road Ch: 0.00 Km to 9.62 Km in Byadagi taluk, Haveri District. | MDR | 185 | 1230 | [7 empty] | 15: 6.69; 16: 7.89; 17: 7.89; 18: 100%; 19: 0; 23: Completed |  | 9 |  |  |  | 133 | 1745.417
|  | C | Improvements to Ranebennur - Anavatti SH Via Yarekuppi - Joisarahalli - Ukkunda - Saravanda - Belakeri - Bisahalli - Anoor - Hamsabhavi - Chikkerur MDR Ch: 15.60 Km to 19.00 Km in Byadagi taluk, Haveri District. | MDR | 186 | 430 | [7 empty] | 15: 2.98; 16: 2.98; 17: 2.98; 18: 100%; 19: 0; 23: Completed | [5 empty] | 134 | 3222.1504
52 | 604 | A | Improvements to Ranebennur - Mudenuru Road Via Magoda - Itagi Road Ch: 0.00 Km to 14.10 Km in Ranebennur taluk, Haveri District. | MDR | 187 | 820 | 2200 | 1894.14 | 2105.65 | 208.62 | 2314.27 |  | 2762.1298 | Sri Shanmukappa R Ballary | 16-07-2022 | 15-01-2024 |  | 5.624 | 6.994 | 6.994 | 100% | 0 | 2173.98 | 78.71% | 588.1498 | Completed | [5 empty] | 135 | 4318.2076
|  | B | Improvements to Ranebennur - Bisalahalli Road Ch: 1.70 Km to 3.70 Km in Ranebennur taluk, Haveri District. | MDR | 188 | 430 | [7 empty] | 15: 1.65; 16: 1.65; 17: 1.65; 18: 100%; 19: 0; 23: Completed |  | 10 |  |  |  | 136 | 3465.7268
|  | C | Improvements to Aremallapura - Kuduhaal Road Via Medleri - Udagatti - Heeladahalli Road Ch: 0.00 Km to 9.60 Km & CH.14.20 to 15.00 Km in Ranebennur taluk, Haveri District. | MDR | 189 | 950 | [7 empty] | 15: 6.617; 16: 6.877; 17: 6.877; 18: 100%; 19: 0; 23: Completed | [5 empty] | 137 | 2659.3158
|  |  | Division Total |  |  | 16325 | 16325 | 14055.69 | 15537.55 | 2678.25 | 18215.8 |  | 21726.844 | 15: 103.222; 16: 113.17; 17: 113.17; 19: 0; 20: 17905.29; 22: 3821.554 | [5 empty] | 138 | 5070.7997
Karwar Division | [31 empty] | 139 | 4522.473
53 | 473 | A | Improvements to Kumta - Kodamadagu Road SH-48 from km 9.00 to 12.20 Km & 16.20 to 19.90 Km (In Selected reaches) in Honnavara Taluk And Kumta - Kodamadagu road SH-48 from Km 19.90 to 30.00 Km (In Selected Reaches) in Kumta Taluk of Uttara Kannada District. | SH-48 | 191 | 1900 | 2250 | 1939.63 | 2308.77 | 555.75 | 2864.52 |  | 3412.1763 | Sri Babu Sannakusa Moger (B.S.M Construction Company | 18-07-2022 | 17-01-2024 |  | 12.4 | 12.8 | 12.8 | 100% | 0 | 2834.31 | 83.06% | 577.8663 | Work Completed |  | 11 |  |  |  | 140 | 3264.072
|  | B | Improvements to Aghanashini - Kumta road MDR from Km 0.00 to 6.00 Km in Kumta Taluk of Uttara Kannada District. | MDR | 192 | 350 | [7 empty] | 15: 3; 16: 4.946; 17: 4.946; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 141 | 4707.8426
54 | 474 | A | Improvements to Gokarna - Vaddi road SH-143 Km 38.00 to 47.15 Km (In Selected Reaches) in Ankola Taluk of Uttara Kannada District | SH-143 | 193 | 1080 | 2300 | 1979.4 | 2474.25 | 615.64 | 3089.89 |  | 3678.7699 | Sri Shivakanth Mahajan (Mahajan Biz Ventures Pvt Ltd) | 2022-05-26 | 25-11-2023 |  | 7.5 | 5.4 | 5.4 | 100% | 0 | 3620.08 | 98.4% | 58.6899 | Work Completed | [5 empty] | 142 | 4103.692
|  | B | Improvements to Hyderabad to Shejwada road from 0.00 km to 2.00 km in Karwar taluk of Uttara Kannada district. | MDR | 194 | 120 | [7 empty] | 15: 1.32; 16: 0.48; 17: 0.48; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 143 | 2748.9919
|  | C | Improvements to Agasur - Shiragutte - kodasane road from 0.00 to 12.60 Km (in selected reaches) in Ankola Taluk of Uttara Kannada District. | MDR | 195 | 310 | [7 empty] | 15: 1.81; 16: 3.2; 17: 3.2; 18: 100%; 19: 0; 23: Work Completed |  | 12 |  |  |  | 144 | 1293.8664
|  | D | Improvements to Belur-Karwar-Ilakal State Highway road from 0.00 km to 4.00 km in Karwar taluk of Uttara Kannada district. | MDR | 196 | 220 | [7 empty] | 15: 2.72; 16: 4; 17: 4; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 145 | 3924.8578
|  |  | Improvements to Karwar-Kaiga-Ilakal road from 27.35 km to 32.00 km in widening and Resurfacing Karwar taluk of Uttara Kannada district. | MDR |  | 330 | [7 empty] | 15: 2.72; 16: 4; 17: 4; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 146 | 3475.2344
|  | E | Improvements to Aurad - Sadhashivagad SH-34 Ambrai Cross to Ulaga road MDR from Km 0.00 to 3.30 Km (In Selected Reaches) in Karwar Taluk of Uttara Kannada District. | SH-34 | 197 | 240 | [7 empty] | 15: 3.3; 16: 3.3; 17: 3.3; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 147 | 2614.1395
55 | 475 | A | Improvements to Heggera - Magod - Nagarbhastikere road MDR from Km 3.40 to 20.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 198 | 1190 | 2250 | 1890.2 | 2264.76 | 529.68 | 2794.44 |  | 3328.6653 | Sri Ramesh Sannppa Naik (R.S Nayak & Co.,) | 2022-07-28 | 27-01-2024 |  | 10.3 | 8.915 | 8.1 | 90.86% | 0.815 | 1498.54 | 45.02% | 1830.1253 | 8.10 Km asphalt completed, 0.815 km asphalt work to be done | 1 |  | K |  |  | 148 | 3658.6446
|  | B | Improvements to Magudu - Koodalagade road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 201 | 530 | [7 empty] | 15: 2.7; 16: 2.807; 17: 2.807; 18: 100%; 19: 0; 23: Road work completed Road furniture work to be done | [5 empty] | 149 | 3082.7183
|  | C | Improvements to koppa panchayath hadala- kacchodi road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Bhatkal Taluk of Uttara Kannada District. | MDR | 202 | 530 | [7 empty] | 15: 3.5; 16: 3.82; 17: 3.608; 18: 94.45%; 19: 0.212; 23: 3.20 km road work completed 0.408 km CC road completed 0.212 km asphlt work to be done | [5 empty] | 150 | 2179.8147
|  |  | Division Total |  |  | 6800 | 6800 | 5809.23 | 7047.78 | 1701.07 | 8748.85 |  | 10419.6115 | 15: 51.27; 16: 53.668; 17: 52.641; 19: 1.027; 20: 7952.93; 22: 2466.6815 | [5 empty] | 151 | 1444.1048
Sirsi Division | [13 empty] | 16: 0 | [5 empty] | 152 | 1776.1164
56 | 476 |  | Improvements to Khanapur - Taalguppa road SH-93 from Km 39.67 to 81.85 Km (In Selected Reaches) in Haliyal Taluk of Uttara Kannada District. | SH-93 | 1 | 970 | 970 | 826.73 | 975.53 | 241.09 | 1216.62 |  | 1449.2692 | Rudrayya G Belurmatt | 2022-06-18 | 2023-05-17 |  | 25.59 | 25.59 | 25.59 | 100% | 0 | 1429.38 | 98.63% | 19.8892 | Work Completed |  | 13 |  |  |  | 153 | 3141.8216
57 | 477 | A | Improvements to Ulavi - Diggi to Goa Border road SH-146 from Km 7.00 to 24.00 Km (In Selected Reaches) in Joida Taluk of Uttara Kannada District. | SH-146 | 2 | 490 | 980 | 834.81 | 1003.12 | 248.94 | 1252.06 |  | 1491.2219 | Sri. Neelkanth Ramachandra Nayak (N R Nayak And Co) | 10-05-2022 | 2023-04-09 |  | 3.52 | 4.04 | 4.04 | 100% | 0 | 1208.51 | 81.04% | 282.7119 | Work Completed |  | 14 |  |  |  | 154 | 3151.8894
|  | B | Improvements to Aurad - Sadhashivagad SH-34 from 604.07 Km to 687.82 Km (In Selected Reaches) in JoidaTaluk of Uttara Kannada District. | SH-34 | 3 | 490 | [7 empty] | 15: 16.305; 16: 20.842; 17: 20.842; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 155 | 1868.9602
58 | 478 | A | Improvements to Gokarna - Vaddi - Devanahalli road SH-143 from Km 65.20 to 73.15 Km in Sirsi Taluk of Uttara Kannada District. | SH-143 | 4 | 900 | 2300 | 1980.06 | 2450.03 | 244 | 2694.03 |  | 3211.666 | Sri Shanmukappa R Ballary | 2022-06-02 | 2023-12-01 | 31.03.2024 | 5.425 | 5.43 | 5.43 | 100% | 0 | 2824.88 | 87.96% | 386.786 | Work Completed |  | 15 |  |  |  | 156 | 2628.0201
|  | B | Improvements to Khanapur - Taalaguppa road SH-93 from Km 170.00 to 200.50 Km (In Selected reaches) in Siddapura Taluk of Uttara Kannada District. | SH-93 | 5 | 900 | [7 empty] | 15: 1.59; 16: 1.07; 17: 1.07; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 157 | 3786.2479
|  | C | Improvements to Bhatkal - Soraba road SH-50 from Km 85.90 to 86.70 Km, Km 87.20 to 93.965 Km, Km 96.50 to 96.90 Km, Km 97.30 to 98.80 Km & Km 99.55 to 100.90 in Siddapur Taluk of Uttara Kannada District. | SH-50 | 6 | 500 | [7 empty] | 15: 5.38; 16: 7.51; 17: 7.51; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 158 | 3011.2553
59 | 479 |  | Improvements to Karwar - Kaiga - Ilkal road SH-06 in Mundgod Taluk from Km125.80 to 146.10 Km (in Selected Reaches) of Uttara Kannada District. | SH-06 | 7 | 2250 | 2250 | 1941.54 | 2335.94 | 580.22 | 2916.16 |  | 3473.143 | Sri Shivakumar Policepatil (M/s S.S Policepatil Company) | 2022-05-31 | 2023-11-30 | 21-0.5-2024 | 15.71 | 17.848 | 17.848 | 100% | 0 | 2288.35 | 65.89% | 1184.793 | Work Completed |  |  | L |  |  | 159 | 3378.4189
|  |  | Division Total |  |  | 6500 | 6500 | 5583.14 | 6764.62 | 1314.25 | 8078.87 |  | 9625.3001 | 15: 73.52; 16: 82.33; 17: 82.33; 19: 0; 20: 7751.12; 22: 1874.1801 | [5 empty] | 160 | 3733.1444
|  |  | Dharwad Circle Total |  |  | 55275 | 55275 | 47508.63 | 55155.93 | 9517.62 | 64673.55 |  | 77099.6316 | 15: 370.827; 16: 403.132; 17: 402.105; 19: 1.027; 20: 59686.1; 22: 15543.9384 | [5 empty] | 161 | 4090.7032
Belagavi Circle | [31 empty] | 162 | 2403.5412
Vijayapura Division | [31 empty] | 163 | 2987.0047
60 | 480 | A | Improvements to road Shiradon Lingasur SH 41 from Ch: 71.43 Km to Ch: 82.00 Km and Ch: 93.50 Km to Ch: 100.23 Km (in selected reaches) in Sindagi Taluk in Vijayapur District. | SH 41 | 203 | 1100 | 2300 | 1965.37 | 2445.3 | 222.71 | 2668.01 |  | 3180.7197 | Sri Siddanagouda H Patil | 2022-07-12 | 2024-01-11 |  | 6.91 | 6.91 | 6.91 | 100% | 0 | 3163.08 | 99.45% | 17.6397 | Final bill submitted |  | 16 |  |  |  | 164 | 2272.5688 |  | 3192.33
|  | B | Improvements to road Ukkalli Dindawar- Sasanur from Ch. 50.50 Km to Ch. 62.86 Km (in selected reaches) in Basavanabagewadi Taluk in Vijayapur District | Upgraded To SH | 204 | 1200 | [7 empty] | 15: 6.47; 16: 7.845; 17: 7.845; 18: 100%; 19: 0; 23: Final bill submitted | [5 empty] | 165 | 4764.0761
61 | 481 |  | Improvements to Road Ukkalli - Dindawar - Sasanur MDR from Km 15.10 to 31.00 Km (In Selected reaches) in Basavanbagewadi Taluk of Vijayapura District. | Upgraded To SH | 205 | 1000 | 1000 | 855.39 | 1053.83 | 255.18 | 1308.99 |  | 1558.7392 | Sri Ramesh Sharanappa Koulagi | 2022-07-15 | 2023-06-14 |  | 4 | 4.63 | 4.63 | 100% | 0 | 1263.96 | 81.09% | 294.7792 | Final bill pending |  | 17 |  |  |  | 166 | 2485.5806 |  | 1566.23
62 | 482 |  | Improvements to road from SH-55 to Shegunashi - Mamadapur - Doodihal up to NH-218 from Ch. 0.00Km to Ch. 12.10 Km (in selected reaches) in Vijayapur Taluk in Vijayapur District | MDR/BJP-64 | 206 | 1000 | 1000 | 852.44 | 1037.42 | 32.55 | 1069.97 |  | 1276.6469 | Sri Bhimshi Siddappa Biradar (M/s B S Biradar) | 44735 | 45068 |  | 5.18 | 4.74 | 4.74 | 100% | 0 | 1092.72 | 85.59% | 183.9269 | Final bill submitted |  | 18 |  |  |  | 167 | 3892.2134 |  | 1280.24
63 | 483 |  | Improvements to Kawadimatti - Donkamadu MDR from Ch 0.00 Km to Ch 19.60 Km (In Selected reaches) in Muddebihal Taluk of Vijayapura District. | MDR/MDD-208 | 208 | 2300 | 2300 | 1971.27 | 2444.37 | 239.78 | 2684.15 |  | 3199.8624 | Sri Siddanagoud H Patil | 2022-05-11 | 2023-11-10 |  | 9.61 | 10.365 | 10.365 | 100% | 0 | 2943.18 | 91.98% | 256.6824 | Final bill submitted |  | 19 |  |  |  | 168 | 2696.1882 |  | 3211.63
64 | 484 |  | Improvements to road Inchigeri Horti Roogi MDR from Ch: 13.00 Km to Ch: 33.60 Km (in selected reaches) in Indi Taluk in Vijayapur District. | MDR/IND-11 | 209 | 1000 | 1000 | 854.06 | 1007.79 | 96.86 | 1104.65 |  | 1317.5961 | Sri Hanamanth Rayappa Chinchali | 2022-08-03 | 2023-07-02 |  | 6.06 | 6.09 | 6.09 | 100% | 0 | 1265.07 | 96.01% | 52.5261 | Final bill submitted |  | 20 |  |  |  | 169 | 3438.5978 |  | 1321.73
65 | 485 |  | Improvements to Minchanala - Atharga - Thamba - Koralli MDR from Ch.37.60 to 51.40 Km (In Selected reaches) in Sindagi Taluk of Vijayapura District. | MDR/SND-9 | 211 | 1000 | 1000 | 855.43 | 940.95 | - | 940.95 |  | 1124.4527 | Sri Babasaheb Bapusaheb Gunjate, Maharshtra | 2022-08-02 | 2023-07-01 |  | 6.02 | 6.02 | 6.01 | 99.83% | 0.01 | 660.13 | 58.71% | 464.3227 | Final bill submitted |  | 21 |  |  |  | 170 | 4692.9505 |  | 1125.86
66 | 486 |  | Improvements to road from Jorapur Water Tank to Connecting NH-50 in Vijayapura Taluk of Vijayapura District. | SH | 213 | 2000 | 2000 | 1714.14 | 2074.19 | 515.71 | 2589.9 |  | 3084.3996 | Sri Sunil M Ullagaddi | 2022-07-13 | 2024-01-12 |  | 3.69 | 3.53 | 3.53 | 100% | 0 | 2559.72 | 82.99% | 524.6796 | Final bill submitted |  | 22 |  |  |  | 171 | 4549.7059 |  | 3098.86
67 | 594 |  | Improvements to road Shiradon Lingasur SH 41 from Ch: 15.15 Km to Ch: 23.50 Km (Loni Cross to Baraola - in selected reaches) in Chadachana Taluk in Vijayapur District. | SH-41 | 210 | 950 | 950 | 811.24 | 1005.13 | 97.12 | 1102.25 |  | 1314.0567 | Sri Suresh S Kanamuchanal, | 2022-07-12 | 2023-06-11 |  | 5.56 | 5.56 | 5.56 | 100% | 0 | 1299.49 | 98.89% | 14.5667 | Final Bill Submitted |  | 23 |  |  |  | 172 | 1977.8444 |  | 1318.86
|  |  | Division Total |  |  | 11550 | 11550 | 9879.34 | 12008.98 | 1459.91 | 13468.87 |  | 16056.4733 | 15: 53.5; 16: 55.69; 17: 55.68; 19: 0.01; 20: 14247.35; 22: 1809.1233 | [5 empty] | 173 | 2307.1742
Bagalkot Division | [13 empty] | 16: 0 | [5 empty] | 174 | 3530.8826
68 | 487 |  | Improvements to Bagalkote - Sangama Cross (NH-367) to Almatti Dam Taluka border (NH 50) MDR from Ch. 0.00 to 29.65 Km (In Selected reaches) in Bagalkote Taluk of Bagalkote District. | MDR | 214 | 2300 | 2300 | 1961.25 | 2439.15 | 241.25 | 2680.4 |  | 3195.2719 | B N Naganagoudar Contractors | 2022-06-23 | 2023-12-22 |  | 13.5 | 14 | 14 | 100% | 0 | 3073 | 96.17% | 122.2719 | work completed, 3rd Party Inspection done |  | 24 |  |  |  | 175 | 3828.0793
69 | 488 |  | Improvements to Sureban Chitharagi Kudalasangama SH 133 from Ch.43.70 to 58.20 Km (In Selected reaches) in Badami Taluk of Bagalkote District. | SH-133 | 215 | 2000 | 2000 | 1709.03 | 2044.44 |  | 2044.44 |  | 2440.6724 | Sri Earanna Mamadapur | 2022-06-23 | 2023-12-22 | 17.12.2024 | 8.33 | 8.33 | 8.33 | 100% | 0 | 1433.73 | 58.74% | 1006.9424 | work Completed & Final bill Submitted |  | 49 |  |  |  | 176 | 2864.4375
70 | 489 | A | Improvements to Jamakhandi Galagali via Mudaganoor MDR from Ch.14.82 to 27.00 Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-3 | 216 | 800 | 2300 | 1966.72 | 2422.82 | 239.44 | 2662.26 |  | 3173.957 | B N Naganagoudar Contractors | 2022-05-11 | 2023-11-10 |  | 9.61 | 6.66 | 6.66 | 100% | 0 | 3116.47 | 98.19% | 57.487 | Work completed |  | 25 |  |  |  | 177 | 3455.3058
|  | B | Improvements to Badagandi – Sangam MDR from Ch.5.00 to 6.72Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-6 | 217 | 0 | [7 empty] | 15: 0; 16: 0; 17: 0; 18: 0%; 19: 0; 23: work dropped | [5 empty] | 178 | 5274.8561
|  | C | Improvements to Sankeshwar – Sangam SH-44 from Ch.110.00 to 124.00 Km (In Selected reaches) (Nerbudihal village limit) in Badami Taluk of Bagalkote District | SH-44 | 218 | 500 | [7 empty] | 15: 1.8; 16: 1.8; 17: 1.8; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 179 | 3160.3117
|  | D | Construction of bridge/box culvert at Ch:0.20Km in sulikere Kagalagomba Ge-mu-road of beelagi constituency at Badami taluk, Bagalakote Dist. |  |  | 200 | [7 empty] | 15: 0; 16: 0; 23: _ | [5 empty] | 180 | 4915.2494
|  | E | Constrution of Bridge/Box Culvert at CH:3.50km in Kanakatti Anavala Ge-mu-ra of Beelagi constituency at Badami taluk, Bagalkote Dist. |  |  | 300 | [7 empty] | 15: 0; 16: 0; 23: _ | [5 empty] | 181 | 2359.6957
|  | F | Improvements at Construction of Bridge/box culverts at SH-44 Ch:107.00 km in Sankeshwar Sangam near Kadarakoppa village of Bellary constituency at Badam taluk Bagalkote Dist. |  |  | 500 | [7 empty] | 15: 0; 16: 0; 23: _ | [5 empty] | 182 | 2585.6115
71 | 490 | A | Improvements to Ramdurga Manvi SH14 from Ch 104.00 to 116.00 Km (In Selected reaches) in Hungunda Taluk of Bagalkote District. | SH-14 | 219 | 1200 | 2250 | 1924.08 | 2366.62 |  | 2366.62 |  | 2824.3974 | Sri Appanna Rangappa Roogi (A R Roogi And Co) | 2022-07-29 | 2024-01-28 |  | 5.56 | 5.56 | 5.56 | 100% | 0 | 2790.07 | 98.78% | 34.3274 | Work completed |  | 26 |  |  |  | 183 | 2489.1104
|  | B | Improvements to Hungunda Paltti Cross MDR from Ch 6.00 to 12.80 Km in Hungunda Taluk of Bagalkote District. | MDR | 220 | 1050 | [7 empty] | 15: 6.38; 16: 6.38; 17: 6.38; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 184 | 3340.6713
72 | 491 |  | Improvements to road Shankeshwar - Sangam SH-44 from Ch.81.54 to 97.74 Km (In Selected reaches) in Mudhol Taluk of Bagalkot District. | SH-44 | 221 | 3300 | 3300 | 2829.91 | 3593.99 | 354.91 | 3948.9 |  | 4706.4521 | Sri Jayasheel N Shetty | 2022-07-16 | 2024-01-15 |  | 14.89 | 14.84 | 14.84 | 100% | 0 | 4936.14 | 104.9% | -229.6879 | Work completed |  | 27 |  |  |  | 185 | 1829.1589
73 | 492 | A | Improvements to Jambotti – Rabakavi SH-54 from Ch.130.47 to 131.13 Km, Ch.132.09 to Ch.133.70, CH.135.39 to 139.20 & CH.139.70 to 141.56 (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | SH-54 | 230 | 1650 | 3250 | 2774.06 | 3435.07 | 812.73 | 4247.8 |  | 5058.2315 | Sri Kashinath N Kankale (Kankale Constructions Private Limited) | 2022-07-29 | 2024-01-28 |  | 3.18 | 3.67 | 3.67 | 100% | 0 | 4877.87 | 96.43% | 180.3615 | Work completed |  |  | 50 |  |  | 186 | 5623.5102
|  | B | Improvements to Road Madhurakhandi – Kallalli - Jagadala – Chimada MDR from Ch.0.00 to 10.80 Km (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | MDR/JMK-9 | 231 | 650 | [7 empty] | 15: 4.05; 16: 4.04; 17: 4.04; 18: 100%; 19: 0; 23: Work completed & Road Furniture yet to be start | [5 empty] | 187 | 2631.7579
|  | C | Improvements to Bidari - Honawada Road via Thodalabagi - MDR from Ch.10.12 Km to 15.25 Km & Ch.25.60 Km to 31.00 Km in Jamkhandi Taluk of Bagalkote District. | MDR/JMK-24 | 229 | 950 | [7 empty] | 15: 4.74; 16: 5.72; 17: 5.72; 18: 100%; 19: 0; 23: Work completed & Road Furniture yet to be start | [5 empty] | 188 | 3434.6943
|  |  | Division Total |  |  | 15400 | 15400 | 13165.05 | 16302.09 | 1648.33 | 17950.42 |  | 21398.9822 | 15: 72.04; 16: 71; 17: 71; 19: 0; 20: 20227.28; 22: 1171.7022 | [5 empty] | 189 | 4595.9751
Belagavi Division | [13 empty] | 16: 0 | [5 empty] | 190 | 7487.0339
74 | 493 |  | Improvements to SH-20, Raichur-Bachi Roadfrom Ch. 333.00 Km to 393.53 Km (In Selected Reaches) in Belagavi Taluk Belagavi District. | SH-20 | 232 | 2150 | 2150 | 1849.43 | 2184.4 | 530.13 | 2712.53 |  | 3231.338 | Sri Manjunath B Garag, | 2022-06-24 | 2023-12-23 |  | 5.39 | 6.484 | 6.484 | 100% | 0 | 3434.12 | 106.3% | -202.782 | Final bill submitted |  | 28 |  |  |  | 191 | 2792.4643 |  | 3245.58
75 | 494 | A | Improvements to Yadiyurappa Margra (OLD PB Road) from Ch. 0.00 Km to 3.81 Km and from SPM Road to VRL Office Joining Road ( In slected Reaches) in Belagavi Taluk, Belagavi Districts. | MDR | 233 | 820 | 2300 | 1984.83 | 2483.21 | 118.85 | 2602.09 |  | 3103.2556 | M/s KKB Engineer Construction Private Limited | 2022-08-03 | 2024-02-02 |  | 1.61 | 1.93 | 1.93 | 100% | 0 | 2774.71 | 89.41% | 328.5456 | F.B Pending |  | 29 |  |  |  | 192 | 2740.1249 |  | 3113.45
|  | B | Improvements to SH-54, Jamboti-Rabakavi Road, Vajapeyee Marga ( Belagavi Panaji SH-4A, From Benco Cross to 3rd Gate) from Ch. 23.80 Km to 27.60 Km in Belagavi Taluk, Belagavi District. | SH-54 | 234 | 1480 | [7 empty] | 15: 1.64; 16: 1.966; 17: 1.966; 18: 100%; 19: 0; 23: F.B Pending | [5 empty] | 193 | 2714.4416
76 | 495 | A | Improvements to SH-93, Khanapur-Talugupppa Road, From Ch. 0.00 to 34.58 Km (in Selected Reach) in Khanapur Taluk, Belagavi District. | SH-93 | 236 | 500 | 1000 | 854.47 | 924.36 |  | 924.36 |  | 1104.8606 | Sri Jayadev Parugouda Biradar | 2022-08-03 | 2023-07-02 |  | 8 | 9.365 | 5.55 | 59.26% | 3.815 | 235.71 | 21.33% | 869.1506 | DBM-2.425 km, DBM 1.955 km & BC 2.405 km work yet to be done. (Letter dtd: 31.10.2025, issued to Executive Engineer PWD Belagavi to submint rescending proposal | 2 |  |  |  | M | 194 | 2310.8038 |  | 1106.01
|  | B | Improvements to SH-138 Nagaragali-katakol road from Ch. 0.00 Km to 15.95 Km (Selected Reaches) in KhanapurTaluk, Belagavi District. | SH-138 | 237 | 500 | [7 empty] | 15: 5.43; 16: 5.43; 17: 0; 18: 0%; 19: 5.43; 23: WMM-1.353 km Completed & balance work under progress (Letter dtd: 31.10.2025, issued to Executive Engineer PWD Belagavi to submit rescending proposal | [5 empty] | 195 | 5974.3223
77 | 496 |  | Improvements to Jatt-Jamboti (SH-31), from Ch. 125.55 Km to 137.45 Km (Selected Reaches) in Bailhongal Taluk, Belagavi District. | SH-31 | 238 | 2300 | 2300 | 1983.23 | 2382.74 | 499.7 | 2882.44 |  | 3434.0422 | Sri B.K Matagar, Belagavi | 2022-07-21 | 2024-01-20 |  | 11.9 | 11.79 | 11.79 | 100% | 0 | 3585.77 | 104.4% | -151.7278 | Final bill submitted |  | 30 |  |  |  | 196 | 2369.5558 |  | 3448.89
78 | 497 | A | Improvements to SH-103 Gokak Savadathi Road From Ch. 29.50 Km to Ch.37.40 Km (in Selected Reaches) Belagavi Districts. | SH-103 | 239 | 750 | 1100 | 945.81 | 1006.06 | 95.4 | 1101.45 |  | 1315.3358 | Sri Prashanth Kagal, Belagavi | 2022-08-03 | 2023-07-02 |  | 4.75 | 4.745 | 4.745 | 100% | 0 | 1279.3 | 97.26% | 36.0358 | Final bill submitted |  | 31 |  |  |  | 197 | 2464.0528 |  | 1317.9
|  | B | Improvements to SH 01 Padabudri Chikkalagudda SH 01 From Ch 420.56 Km to 421.98 Km in Bailahingal Taluk Belagavi District | SH-01 | 240 | 350 | [7 empty] | 15: 1.42; 16: 1.42; 17: 1.42; 18: 100%; 19: 0; 23: Final bill submitted | [5 empty] | 198 | 2723.4779
79 | 498 | A | Improvements to MDR-SAU89 SAVADATTI-SANGRESHKOPPA Road Via Mamani Kere from Ch. 0.00 Km to 8.00 Km in Savadatti Taluk, Belagavi District | MDR-SAU89 | 241 | 1000 | 2250 | 1934.43 | 2350.32 | 232.31 | 2582.64 |  | 3079.472 | Sri Mallanagowda H Patil, Belagavi | 2022-08-02 | 2024-02-10 |  | 7.8 | 7.783 | 7.78 | 99.96% | 0.003 | 2098.89 | 68.16% | 980.582 | Final bill submitted |  | 32 |  |  |  | 199 | 2967.4845 |  | 3090.18
|  | B | Improvements to MDR SAU-4 Saundatti Hanchinal Road From Km Ch 0.00 to 6.00 Km (Selected Reaches) in Saundatti Taluka, Belagavi District | MDR SAU-4 | 267 | 740 | [7 empty] | 15: 4.04; 16: 4.04; 17: 4.04; 18: 100%; 19: 0; 23: Final bill submitted | [5 empty] | 200 | 828.8075
|  | C | Improvements to MDR from Yallamma Temple to SH-34 Joining Road, From Km Ch 0.00 to 2.00 Km in Savadatti Taluka, Belagavi District. | MDR | 268 | 510 | [7 empty] | 15: 2; 16: 2; 17: 2; 18: 100%; 19: 0; 23: Final bill submitted | [5 empty] | 201 | 2160.7569
80 | 499 | A | Improvements to SH-34 AURAD-SADASHIVAGADA ROAD from Ch. 445.94 Km to 453.94 (Selected Reaches) in Ramadurga Taluk, Belagavi District | SH-34 | 269 | 1210 | 2250 | 1936.94 | 2400.44 | 229.42 | 2629.86 |  | 3135.233 | Sri Govindan S Y (Y Shivanna And Brothers) | 2022-05-07 | 2023-11-06 |  | 5.61 | 5.61 | 5.61 | 100% | 0 | 2982.68 | 95.13% | 152.553 | Final bill submitted |  | 33 |  |  |  | 202 | 2166.2555 |  | 3146.68
|  | B | Improvements to SH-139 YARAGATTI-MUDHOL ROAD, From Km Ch 11.83 to 22.60 Km (Selected Reaches) in Ramadurg Taluka, Belagavi District. | SH-139 | 270 | 1040 | [7 empty] | 15: 6.47; 16: 6.7; 17: 6.7; 18: 100%; 19: 0; 23: Final bill submitted | [5 empty] | 203 | 3468.6838
81 | 596 |  | Improvements to Jatti Jamboti SH-31 from Ch 179.88 to 188.58 Km (In Selected reaches) in Belagavi Taluk of Belagavi District. | SH-31 | 235 | 1000 | 1000 | 861.4 | 988.47 | 96 | 1084.48 |  | 1293.9167 | Sri Balkrishna G Godse, Belagavi | 2022-08-03 | 2023-07-02 |  | 4.885 | 4.795 | 4.795 | 100% | 0 | 819.8 | 63.36% | 474.1167 | Final bill submitted |  | 34 |  |  |  | 204 | 3775.7154 |  | 1297.6
|  |  | Division Total |  |  | 14350 | 14350 | 12350.54 | 14720 | 1801.81 | 16519.85 |  | 19697.4539 | 15: 70.945; 16: 74.058; 17: 64.81; 19: 9.248; 20: 17210.98; 22: 2486.4739 | [5 empty] | 205 | 3144.787
Chikkodi Division | [13 empty] | 16: 0 | [5 empty] | 206 | 2535.3788
82 | 500 |  | Improvements to Nippani Kottalagi Road SH-72 Form Ch 1.40 Km to Ch 17.00 Km & Ch 17.90 Km to 22.60 Km (in selected reaches) Via Nippani Akkola Galataga Nej cross, Nippani Taluk Belagavi Districts. | SH-72 | 8 | 2250 | 2250 | 1938.47 | 2287.4 | 220.81 | 2508.21 |  | 2991.7113 | Sri Sadashiv S Bennalli, | 2022-05-13 | 2023-11-12 |  | 9.065 | 9.065 | 9.065 | 100% | 0 | 2910.7 | 97.29% | 81.0113 | Work Completed |  | 35 |  |  |  | 207 | 2685.5833 |  | 3001.12
83 | 501 |  | Improvements to SH-73 Managasuli-Laxmeshwar Road from Ch: 37.00 Km to 40.00, Km, Ch: 52.00 Km 54.00 Km, And, 55.00 Km to 67.00 Km in (Selected Reaches) Raibag Taluk, Belagavi District. | SH-73 | 10 | 975 | 975 | 839.47 | 1024.13 | 98.43 | 1122.56 |  | 1338.4888 | Sri Prakash B Wantamutte, | 2022-05-07 | 2023-04-06 |  | 6.17 | 6.85 | 6.85 | 100% | 0 | 1298.44 | 97.01% | 40.0488 | Work completed |  | 36 |  |  |  | 208 | 5087.0828 |  | 1339.81
84 | 502 | A | Improvements to Shettyhalli Ichalkaranji Road SH-78 From Km 76.90 to Km 81.90 (From Malikwad Bus stand to sadalaga) (in selected reaches) Chikkodi Taluk Belagavi Districts. | SH-78 | 11 | 470 | 1400 | 1201.32 | 1465.77 | 142.66 | 1608.43 |  | 1917.7932 | Sri Prakash B Wantamutte, | 2022-05-07 | 2023-08-06 |  | 3 | 3 | 3 | 100% | 0 | 1766.84 | 92.13% | 150.9532 | Work Completed |  | 37 |  |  |  | 209 | 3734.894
|  | B | Improvements to Nippani Kottalagi Road SH-72 From Km 31.70 to Km 35.70 (From Nej Crosss to nanadi) (in selected reaches) Chikkodi Taluk Belagavi Districts. | SH-72 | 12 | 470 | [7 empty] | 15: 2.89; 16: 2.89; 17: 2.89; 18: 100%; 19: 0; 20: 807.78; 23: Work Completed | [5 empty] | 210 | 1485.1218 |  | 1924.51
|  | C | Improvements to Nippani Kottalagi Road SH-72 from km 40.00 to km 47.00 (From Yadur Veerabadreshwar temple to Kallol) Chikkodi Taluk Belagavi Districts. | SH-72 | 13 | 460 | [7 empty] | 15: 3.01; 16: 3.07; 17: 3.07; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 211 | 2299.419
85 | 503 | A | Improvements to Road from Jinaral Cross to Hidakal Dam, Godageri MDR from Ch:0.00 to 14.00 Km (In Selected Reaches) Hukkeri Taluk, Belagavi District. | MDR | 14 | 1750 | 2300 | 1979.99 | 2378.23 | 579.39 | 2957.62 |  | 3522.701 | Sri B.K Matagar, Belagavi | 21-07-2022 | 20-01-2024 |  | 9.15 | 10.57 | 10.57 | 100% | 0 | 3487.13 | 98.99% | 35.571 | Work Completed |  | 38 |  |  |  | 212 | 1795.0433 |  | 3530.9
|  | B | Improvements to MDR-HUK-73 Nerli-Ammanagi Road from Ch:0.00 Km to 0.85 Km and 2.75 Km to 5.50 Km (In Selected Reaches) Hukkeri Taluk, Belagavi District. | MDR HUK-73 | 15 | 550 | [7 empty] | 15: 3.23; 16: 3.23; 17: 0; 18: 0%; 19: 3.23; 23: Deleted | [5 empty] | 213 | 3784.6313
86 | 504 | A | Improvements to SH-31, JATH-JAMBOTI Road, from Ch. 106.82 Km to 115.05 Km and 121.18 Km to 121.78 Km in Gokak Taluka, Belagavi District | SH-31 | 16 | 1440 | 2300 | 1981.76 | 2362.27 | 565.88 | 2928.15 |  | 3487.9557 | Sri B B Dasanavar, Gokak | 2022-08-29 | 2024-02-28 |  | 6.325 | 6.325 | 6.325 | 100% | 0 | 3508.9 | 100.6% | -20.9443 | Work Completed |  | 39 |  |  |  | 214 | 2568.8054 |  | 3496.8
|  | B | Improvements to Jamboti rabhakavi Road SH-54 From Km 62.08 to 66.70 (Akkatangerahal to Telaginahatti) From Km 83.00 to 84.20 (Hanamapur Cross) And From Km 54.28 to 55.755 Gokak Taluk Belagavi Districts. | SH-54 | 17 | 860 | [7 empty] | 15: 4.9; 16: 4.9; 17: 4.9; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 215 | 3151.2092
87 | 505 | A | Improvements to MDR from Koujalagi-Kalliguddi Road from Ch. 0.00 Km to 5.50 Km in Mudalagi Taluk, Belagavi District. | MDR | 19 | 400 | 2200 | 1894.33 | 2405.86 | 327.49 | 2733.35 |  | 3256.6473 | Sri Jayasheel N Shetty, Gokak | 2022-07-05 | 2024-01-04 |  | 3 | 3 | 3 | 100% | 0 | 3308.18 | 101.6% | -51.5327 | Work Completed |  | 40 |  |  |  | 216 | 3496.2132 |  | 3261.69
|  | B | Improvements to SH, Haleyaragudri to Hosayaragudri Road (Avaraadi-Timmapur Road), from Ch. 0.00 Km to 10.00 Km (Selected Reaches) in Mudalagi Taluk, Belagavi District. | MDR | 20 | 1800 | [7 empty] | 15: 10; 16: 9.4; 17: 9.4; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 217 | 3728.076
88 | 506 | A | Improvements to Kagawad-Kaladagi Sh-53 Road from Ch: 22.40 Km to 24.10 Km, Ch: 24.90 Km 29.60 Km, 32.55 Km to 35.00 km, 44.39 Km to 44.90 Km in Raibag Taluk, Belagavi District. | SH-53 | 21 | 1430 | 2250 | 1937.43 | 2380.35 | 576.37 | 2956.72 |  | 3520.9359 | M/s Tarade Brothers Constructions Pvt Ltd., | 2022-07-21 | 2024-01-20 |  | 9.6 | 11.25 | 11.25 | 100% | 0 | 3710.57 | 105.4% | -189.6341 | Work completed |  | 41 |  |  |  | 218 | 1664.5934 |  | 3528.93
|  | B | Improvements to Chikkodi Railway Station-Mugalakod-Handigundi MDR from Ch: 10.03 Km to 14.00 Km, And Ch: 19.00 Km to 39.15 Km in (Selected Reaches) Raibag Taluk, Belagavi District. | MDR | 23 | 820 | [7 empty] | 15: 5.1; 16: 7.24; 17: 7.24; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 219 | 5149.828
89 | 507 |  | Improvements to State Border to Aralihatti, Jakaratti, Madabhavi,, Shiddewadi, Koulagudda, Ainapur, Krishna Kittur upto Taluka Border Road from Ch: 0.00 Km to 28.50 Km in Kagawad Taluk, Belagavi District. | MDR | 24 | 2300 | 2300 | 1980.93 | 2431.99 | 592.51 | 3024.5 |  | 3601.635 | M/s Sahyadri Construction Co., Sangli, Maharshtra | 2022-07-21 | 20-10.2023 |  | 16.52 | 16.52 | 16.52 | 100% | 0 | 3660.04 | 101.6% | -58.405 | Work Completed |  | 42 |  |  |  | 220 | 3358.3347 |  | 3609.83
90 | 508 |  | Improvements to Maharastra State Border to Kakamari-talasang-Savalagi District Border Road from Ch: 2.40 Km to 11.60 Km and Ch: 12.70 Km to 21.20 Km in (in selected reaches) Athani Taluk, Belagavi District. (Upgraded SH) | MDR | 25 | 2250 | 2250 | 1936.46 | 2323.75 | 571.39 | 2895.14 |  | 3448.2555 | Sri S C Chikaraddi, Vijayapura | 2022-07-05 | 2024-01-04 |  | 16 | 17.7 | 17.695 | 99.97% | 0.005 | 3312.4 | 96.06% | 135.8555 | Work Completed |  | 43 |  |  |  | 221 | 3604.5779 |  | 3456.22
91 | 509 |  | Improvements to Harugeri-Raibag-Nagaramunnolli MDR from Ch. 16.00 Km to 18.68 And Ch: 23.80 to 37.00 ( Selected Reaches) in Raibag Taluk, Belagavi District. | MDR | 26 | 1275 | 1275 | 1095.51 | 1343.7 | 241.83 | 1585.53 |  | 1889.0232 | Sri Mainuddin Mulla (S A Mulla) | 2022-07-21 | 2023-10-20 |  | 6.2 | 6.33 | 6.33 | 100% | 0 | 2011.06 | 106.5% | -122.0368 | Work Completed |  | 44 |  |  |  | 222 | 2950.8691 |  | 1892.8
92 | 510 | A | Improvements to MDR-HUDALI-DHARANATTI-MUTYANATTI ROAD, from Ch. 5.50 Km to 10.00 Km in Belagavi Taluka, Belagavi District. | MDR | 271 | 500 | 1000 | 859.24 | 990.38 |  | 990.38 |  | 1182.843 | M/s DEV Structural India Pvt Ltd, Belagavi | 2022-07-30 | 2023-06-29 |  | 4.505 | 4.505 | 4.505 | 100% | 0 | 1109.81 | 93.83% | 73.033 | Work Completed |  | 45 |  |  |  | 223 | 1642.2508
|  | B | Improvements to MDR HUK-203 Basapur Hagedal Shahabadar Ukkad Road From Km 0.00 to Km 2.00 & Km 4.00 to Km 7.15 in Hukkeri Taluk Belagavi Districts. | MDR | 28 | 500 | [7 empty] | 15: 2.15; 16: 2.15; 17: 2.15; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 224 | 2176.606
|  |  | Division Total |  |  | 20500 | 20500 | 17644.91 | 21393.83 | 3916.76 | 25310.59 |  | 30157.9901 | 15: 120.815; 16: 127.995; 17: 124.76; 19: 3.235; 20: 30891.85; 22: 73.9201 | [5 empty] | 225 | 3345.4801
|  |  | Belagavi Circle Total |  |  | 61800 | 61800 | 53039.84 | 64424.9 | 8826.81 | 73249.73 |  | 87310.8996 | 15: 317.3; 16: 328.743; 17: 316.25; 19: 12.493; 20: 82577.46; 22: 5541.2196 | [5 empty] | 226 | 2780.6678
|  |  | North Circle Total |  |  | 175675 | 175675 | 150904.92 | 178660.926 | 24231.19 | 202890.136 | 9783.56 | 241903.3098 | 15: 1011.672; 16: 1048.96; 17: 1029.88; 19: 16.93; 20: 202942.64; 22: 37898.8566 | [5 empty] | 227 | 3916.9872
Shivamogga Circle | [31 empty] | 228 | 2997.1128
Davanagere Division | [31 empty] | 229 | 3299.8376
93 | 511 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:186.35 Km to 194.05Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | SH-65 | 29 | 1100 | 2300 | 1976.51 | 2323.26 |  | 2323.26 |  | 2774.0987 | Sri Paramesh Ramappa, Davanagere | 27.07.2022 | 26.01.2024 |  | 7.7 | 7.7 | 7.7 | 100% | 0 | 2026.89 | 73.06% | 747.2087 | Road Furniture work is in progress | [5 empty] | 230 | 3174.1487 |  | 2774.1
|  | B | Improvements to Road From Nalluru -Devarahalli MDR From Ch:5.00 Km to 11.00 Km in Channagiri Taluk of Davanagere District | CNG12 | 31 | 650 | [7 empty] | 15: 4.97; 16: 4.97; 17: 4.97; 18: 100%; 19: 0; 23: Road Furniture work is in progress |  | 1 |  |  |  | 231 | 4149.0991
|  | C | Improvements to Road From Pandomatti to Neethigere MDR From Ch:0.00 Km to 16.00 Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | CNG27 | 32 | 550 | [7 empty] | 15: 3.92; 16: 3.92; 17: 3.92; 18: 100%; 19: 0; 23: Road Furniture work is in progress | [5 empty] | 232 | 4884.6111
94 | 512 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:233.00Km to 242.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District. | SH-65 | 34 | 1000 | 3000 | 2579.78 | 2937.46 | 725.96 | 3663.42 |  | 4365.4536 | M/s Udayshivakumar Infra Private Limited, Davanagere | 21.07.2022 | 20.01.2024 |  | 8.78 | 5.9 | 5.603 | 94.97% | 0.297 | 4229.69 | 96.89% | 135.7636 | Final Bill submited |  | 22 |  |  |  | 233 | 3083.5153 |  | 4365.46
|  | B | Improvements to Road From Davanagere Budihala Arasapura MDR From Ch:4.80Km to 12.75Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG9 | 35 | 800 | [7 empty] | 15: 3.3; 16: 3.3; 17: 3.3; 18: 100%; 19: 0; 23: All Works are completed in all aspects. Final Bill submited | [5 empty] | 234 | 3254.6306
|  | C | Improvements to Road From Bethur to Dhoddabathi MDR From Ch:0.00Km to 12.00Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 37 | 700 | [7 empty] | 15: 3.47; 16: 3.47; 17: 3.47; 18: 100%; 19: 0; 23: All Works are completed in all aspects. Final Bill submited | [5 empty] | 235 | 3469.7179
|  | D | Improvements to Road From Malpe-Molakalmuru SH-65 to Rampura MDR From Ch:0.00Km to 11.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 38 | 500 | [7 empty] | 15: 2.45; 16: 2.79; 17: 2.79; 18: 100%; 19: 0; 23: All Works are completed in all aspects. Final Bill submited | [5 empty] | 236 | 2003.1029
95 | 513 | A | Improvements to Road From Mandya - Hadagali SH-47 From Ch:261.25Km to 293.83Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | SH-47 | 46 | 1350 | 2250 | 1932.48 | 2162.65 | 527.21 | 2689.86 |  | 3205.9594 | M/s Udayshivakumar Infra Private Limited, Davanagere | 06.07.2022 | 05.01.2024 | 31.03.2025 | 12.33 | 13.83 | 13.83 | 100% | 0 | 2422.28 | 75.56% | 783.6794 | Road Furniture work is in progress |  |  | N |  |  | 237 | 4386.2943 |  | 2583.85
|  | B | Improvements to Road From Aluruhatti -Anagodu MDR From Ch:0.00Km to 13.245Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG12 | 47 | 900 | [7 empty] | 15: 6.78; 16: 7.07; 17: 7.07; 18: 100%; 19: 0; 23: Road work Completed. Road Furnitures work to be started | [5 empty] | 238 | 2237.1346
96 | 514 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:302.60Km to 306.40Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District. (Four Lane road) | SH-65 | 298 | 700 | 2250 | 1935.87 | 2307.96 |  | 2307.96 |  | 2755.3734 | M/s S Narayana Reddy, Channarayapattana | 24.08.2022 | 23.02.2024 | 31.10.2025 | 1.97 | 1.97 | 0 | 0% | 1.97 | 1025.29 | 37.21% | 1730.0834 | 1.3 Km GSB work on LHS Completed and Divider work is under progresss | 1 |  |  |  |  | 239 | 2631.3746 |  | 2755.38
|  | B | Improvements to Road From Rangapura Gadimakunte MDR From Ch:6.50Km to 12.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL208 | 51 | 650 | [7 empty] | 15: 6.5; 16: 6.5; 17: 0; 18: 0%; 19: 6.5; 23: 2.80 WMM work completed |  |  | O |  |  | 240 | 2173.9697
|  | C | Improvements to Road From Jagaluru Kadabanakatte MDR From Ch:9.00Km to 14.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL34 | 52 | 400 | [7 empty] | 15: 3.015; 16: 3.015; 17: 3.015; 18: 100%; 19: 0; 23: Road Furniture work is in progress | [5 empty] | 241 | 4767.7435
|  | D | Improvements to Road From Baramasagara - Bilichodu -Basavanakote MDR From Ch:13.00Km to 37.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL3 | 53 | 200 | [7 empty] | 15: 1.21; 16: 1.21; 17: 1.21; 18: 100%; 19: 0; 23: Road Furniture work is in progress | [5 empty] | 242 | 3209.4269
|  | E | Improvements to Road From Bilichodu-Sokke MDR From Ch:10.00Km to 16.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL4 | 56 | 300 | [7 empty] | 15: 3.57; 16: 3.57; 17: 3.37; 18: 94.4%; 19: 0.2; 23: 0.2 Km GSB work is in progress | [5 empty] | 243 | 4254.6154
97 | 515 | A | Improvements to Road From Malebennuru - Ekegundhi - Nandhigudi Joining MDR From Ch-0.00Km to 6.00Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR11 | 57 | 475 | 3250 | 2789.13 | 3321.56 |  | 3321.56 |  | 3965.5172 | M/s Bale Constructions, Deodurga, Raichur | 21.09.2022 | 20.03.2024 |  | 3.21 | 3.21 | 2.62 | 81.62% | 0.59 | 2184.3 | 55.08% | 1781.2172 | 0.590 Km work is under progress | 2 |  |  |  |  | 244 | 2612.6241 |  | 3965.51
|  | B | Improvements to Road From Palya-Mooginagundhi Joining MDR From Ch:0.00Km to 12.67Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR12 | 59 | 475 | [7 empty] | 15: 3.7; 16: 3.7; 17: 0; 18: 0%; 19: 3.7; 23: 3.7 Km GSB work completed. WMM Work under progress |  |  | P |  |  | 245 | 2035.8043
|  | C | Improvements to Road From Nalluru to Sasivehalli MDR From Ch:8.00Km to 16.63Km in Honnalli Taluk of Davanagere District | HNN15 | 60 | 1000 | [7 empty] | 15: 8.63; 16: 8.63; 17: 4; 18: 46.35%; 19: 4.63; 23: 4.630 km BM work completed | [5 empty] | 246 | 1755.0809
|  | D | Improvements to Road From Kurki to Kulambi MDR From Ch:16.40Km to 22.70Km in Honnalli Taluk of Davanagere District | HNN49 | 61 | 700 | [7 empty] | 15: 6.3; 16: 6.3; 17: 3.35; 18: 53.17%; 19: 2.95; 23: 5.45 km WMM completed 3.35km SDBC completed | [5 empty] | 247 | 2031.449
|  | E | Improvements to Road of Honnali -Katthige MDR From Ch:3.00Km to 13.20Km (In Selected Reaches) in Honnalli Taluk of Davanagere District | HNN21 | 62 | 600 | [7 empty] | 15: 4.32; 16: 4.32; 17: 4.32; 18: 100%; 19: 0; 23: Road Furniture work is in progress | [5 empty] | 248 | 2475.0476
|  |  | Division Total |  |  | 13050 | 13050 | 11213.77 | 13052.89 | 1253.17 | 14306.06 |  | 17066.4023 | 15: 96.125; 16: 95.375; 17: 74.538; 19: 20.837; 20: 11888.45; 22: 5177.9523 | [5 empty] | 249 | 3293.4171
Chitradurga Division | [31 empty] | 250 | 2617.0994
98 | 516 | A | Improvements to Kumta - Kadamadagi road State Highway 48 from KM 267.00 to 268.50 KM ( In Selected Reaches) in Chitradurga Taluk of Chitradurga District | SH-48 | 64 | 680 | 2300 | 1980.98 | 2302.2 | 342.29 | 2644.49 |  | 3153.224 | M/s Balajikrupa Projects Private Limited, Bangalore | 20.06.2022 | 19.12.2023 |  | 0.6 | 0.6 | 0.6 | 100% | 0 | 2547.22 | 80.78% | 606.004 | Work completed |  | 2 |  |  |  | 251 | 2753.8264 |  | 2749.32
|  | B | Improvements to Road from National Highway 13 (from Emperor Hotel) to State Highway 48 (Kumta - Kadamadagi Road) from KM 0.00 to 4.00 KM ( In Selected Reaches) in Chitradurga Taluk of Chitradurga District. | MDR | 65 | 1170 | [7 empty] | 15: 1.02; 16: 1.02; 17: 1.02; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 252 | 1883.5638
|  | C | Improvements to Jodichikkenahalli-Yerehalli Road via Kasavanahalli, IngalaDala, Kurumaradikere, kannedalu MDR from KM 11.65 to 30.10 KM (In Selected Reaches) in Chitradurga Taluk of Chitradurga District | CHD203 | 67 | 450 | [7 empty] | 15: 4.29; 16: 4.29; 17: 4.29; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 253 | 2706.433
99 | 517 | A | Improvements to SH-47- Kakanur MDR from KM 0.00 to 13.00 KM (In Selected Reaches) in Holalakere Taluk of Chitradurga District | HLK202 | 68 | 770 | 2300 | 1960.81 | 2322.26 | 543.865 | 2866.125 |  | 3414.4201 | Sri Rajasekharappa T, Chitradurga | 02.08.2022 | 01.02.2024 |  | 7.52 | 10.42 | 10.42 | 100% | 0 | 2728.21 | 79.9% | 686.2101 | Work completed | [5 empty] | 254 | 3347.9683 |  | 2772.67
|  | B | Improvements to Sivaganga - Janakkal - Hosadurga Newly Upgraded State Highway from KM 0.00 to 16.55 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District | NEW SH | 69 | 650 | [7 empty] | 15: 6.53; 16: 7.02; 17: 7.02; 18: 100%; 19: 0; 23: Work completed |  |  | Q |  |  | 255 | 1611.9469
|  | C | Improvements to State Highway-153-Singhenahalli- to join State Highway 48 Kasturiba Nagar via Talikatte- Malladihalli-Ramaghatta-Hirehemmiganur Newly Upgraded State Highway from KM 0.00 to 38.30 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District. | NEW SH | 70 | 880 | [7 empty] | 15: 7.56; 16: 7.56; 17: 7.56; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 256 | 4901.2566
100 | 518 | A | Improvements to Mandya -Hadagali Road State Highway - 47 from KM 183.00 to 212.00 KM (In Selected Reaches) in Hosadurga Taluk of Chitradurga District | SH-47 | 81 | 1700 | 2300 | 1976.39 | 2402.26 | 584.43 | 2986.69 |  | 3556.9442 | Sri C Halappa, Chowlahiriyuru, Kadur tq, Chikkamagaluru | 15.07.2022 | 14.01.2024 |  | 8.25 | 11.08 | 11.08 | 100% | 0 | 2891.35 | 81.29% | 665.5942 | Work completed |  | 3 |  |  |  | 257 | 1566.8201 |  | 3556.93
|  | B | Improvements to Sivaganga-Janakal Hosadurga Newly Upgraded State Highway from KM 24.00 to 29.2 KM (in Selected Reaches) in Hosadurga Taluk of Chitradurga District | NEW SH | 82 | 600 | [7 empty] | 15: 4.4; 16: 4.78; 17: 4.78; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 258 | 3359.4697
101 | 519 | A | Improvements to State Highway 48 Vishwanathahalli to join Shiragadi (via Chikkajajur, Madadakere, Bharamgiri, Doddaghatta, Adivala, Ranganathpur) Newly Upgraded State Highway KM 71.55 to 105.15 KM (Bharamgiri-Hosadurga road) (in Selected Reaches) in Hiriyur Taluk of Chitradurga District | NEW SH | 83 | 600 | 2250 | 1935.16 | 2302.09 | 223.62 | 2525.71 |  | 3012.3066 | Sri H Narayanappa, Tumkur | 23.06.2022 | 22.09.2023 |  | 3.8 | 4.37 | 4.37 | 100% | 0 | 2649.38 | 87.95% | 362.9266 | Work completed |  | 4 |  |  |  | 259 | 2280.8767 |  | 3012.3
|  | B | Improvements to road from State Highway-24 to Shiragadi MDR from KM 0.00 km to 7.60 KM (in Selected Reaches) in Hiriyur taluk of Chitradurga District. | HRY 5 | 84 | 700 | [7 empty] | 15: 6.75; 16: 6.75; 17: 6.75; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 260 | 2842.7451
|  | C | Improvements to JJ Halli - Yalladekere Road via Obalapura, Veeravvanagatihalli, Chigalikatte Newly upgraded MDR from KM 8.00 km to 26.00 KM (in Selected Reaches) in Hiriyur Taluk of Chitradurga District | NEW MDR | 85 | 950 | [7 empty] | 15: 8.8; 16: 8.8; 17: 8.8; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 261 | 2684.5499
102 | 520 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 6.48 to 46.38 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 102 | 1400 | 2300 | 1979.02 | 2339.81 | 562.42 | 2902.23 |  | 3457.3248 | Sri Anwar Basha.K, Chitradurga | 29.07.2022 | 28.01.2024 |  | 10.97 | 10.97 | 10.97 | 100% | 0 | 3289.27 | 95.14% | 168.0548 | Work completed |  | 5 |  |  |  | 262 | 2624.4846 |  | 3457.32
|  | B | Improvements to Belagatta- Haikal, Nayakanhatti Suramanahalli -Chikkunti -Siddaiahkote - Rayapur -Molakalmooru Newly Upgraded State Highway Road from KM 39.80 km to 89.40 KM (in Selected Reaches) in Molakalmooru Taluk of Chitradurga District | NEW SH | 103 | 900 | [7 empty] | 15: 5.26; 16: 5.26; 17: 5.26; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 263 | 3171.0445
103 | 521 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 2.40 to 6.48 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 104 | 530 | 950 | 814.7 | 880.09 |  | 880.09 |  | 1051.965 | M/s Balajikrupa Projects Private Limited, Bangalore | 20.06.2022 | 19.05.2023 |  | 3.88 | 3.88 | 3.88 | 100% | 0 | 800.05 | 76.05% | 251.915 | Work completed |  | 6 |  |  |  | 264 | 3303.5756 |  | 1051.96
|  | B | Improvements to road from Pathappanagudi to Shira border via Jajur, Parashurampura, Dharmapura, Sakkara, Newly upgraded State Highway road From KM 0.00 to 46.10 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 105 | 420 | [7 empty] | 15: 4; 16: 4; 17: 4; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 265 | 1840.3818
104 | 522 |  | Improvements to Yalagodu-Turavanur Doddaghatta MDR from KM 0.00 to 22.20 KM (in Selected Reaches) in Chitradurga Taluk of Chitradurga District | CHD12 | 106 | 800 | 800 | 687.2 | 804.42 | 194.1 | 998.52 |  | 1189.6061 | M/s Subba Reddy & son’s Construction Private Limited | 29.07.2022 | 28.06.2023 |  | 9 | 10.5 | 10.5 | 100% | 0 | 928.01 | 78.01% | 261.5961 | Work completed |  |  | R |  |  | 266 | 2099.4801 |  | 1189.56
|  |  | Division Total |  |  | 13200 | 13200 | 11334.26 | 13353.13 | 2450.725 | 15803.855 |  | 18835.7909 | 15: 92.63; 16: 101.3; 17: 101.3; 19: 0; 20: 15833.49; 22: 3002.3009 | [5 empty] | 267 | 1593.1443 |  | 17790.06
Shivamogga Special Division | [31 empty] | 268 | 2380.102
105 | 523 | A | Improvements to road from State Highway-148 to join State Highway-148 via Sirigere, Thamadihalli, Bilguni, Adagadi, Mandaghatta, Dhyavanakere, Ragihosahalli, Rechikoppa, Shettikere, Shantikere, Koragi, Horabilu, Tuppuru, Byadanal, Kattigehalli Newly upgraded MDR road from KM 0.00 to 23.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 107 | 700 | 2300 | 1958.93 | 2263.76 | 554.4 | 2818.16 |  | 3357.7903 | Sri Sharanappa Sangappa Alur (M/s S S Alur Construction Company), Vijayapura | 16.07.2022 | 15.01.2024 | 15.12.2024 | 7 | 7 | 7 | 100% | 0 | 2301.15 | 68.53% | 1056.6403 | Work completed | [5 empty] | 269 | 2871.4439 |  | 3357.79
|  | B | Improvements to State Highway 148 via Sirigare Manjerikoppa, Maleshankara Temple, Yerebisu, Koodi, Gammanagadde to join State Highway 148 newly upgraded MDR road from KM 0.00 to 20.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 110 | 500 | [7 empty] | 15: 4.9; 16: 4.9; 17: 4.9; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 270 | 1444.8271
|  | C | Improvements to Koodligere-Kammaraghatta State Highway-115 road from KM 7.00 to 17.70 KM (in Selected Reaches) in Bhadravathi Taluk of Shivamogga District | SH-115 | 112 | 700 | [7 empty] | 15: 6; 16: 8.45; 17: 8.45; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 271 | 1099.3047
|  | D | Improvements to From Bhadravathi to Sasivehalli (Honnali Taluk Border) via Holehonnur, Sidlipura, Sanyasikodamge, Nagasamudra, Managotte, Anaveri, Nimbegundi, Saidarakallalli Newly upgraded State Highway road from KM 0.00 to 35.10 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | NEW SH | 113 | 400 | [7 empty] | 15: 3; 16: 0.415; 17: 0.415; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 272 | 2193.2682
106 | 524 | A | Improvements to NH-26 near Hittur Cross from Umblebailu (SH-65) via Ganidalu-uralalli-Lakkinakoppa kadekal- Kuskur-Siddarahalli-Matturu Malalikoppa-Madaripalya, NH-13 & SH-57 to 100 feet road from Vinobhanagar Police Chowki to Sominakoppa, Gejjenahalli, Tyajavalli, Devabalu, Edavala Newly upgraded State Highway road from KM 0.00 to 46.60 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW SH | 114 | 1800 | 2800 | 2406.91 | 2738.49 |  | 2738.49 |  | 3271.1804 | Sri Ibrahim Sharief, Thirthahalli | 21.06.2022 | 20.12.2023 |  | 14 | 14 | 14 | 100% | 0 | 2792.4 | 85.36% | 478.7804 | Work completed |  | 7 |  |  |  | 273 | 1612.2482 |  | 3271.18
|  | B | Improvements to Tumkur - Honnavar State Highway-68 road from KM 6.20 to 9.50 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | SH-68 | 115 | 1000 | [7 empty] | 15: 1.26; 16: 1.26; 17: 1.26; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 274 | 2290.7621
107 | 525 | A | Improvements to Begaru -Kalmane MDR road from KM 0.00 to 7.80 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | TRT 08 | 127 | 600 | 2300 | 1963.07 | 2447.18 | 229.48 | 2676.66 |  | 3190.8887 | Sri Abdul Kalam Azad, Thirthahalli | 21.06.2022 | 20.12.2023 |  | 6.85 | 6.85 | 6.85 | 100% | 0 | 3116.2 | 97.66% | 74.6887 | Work completed | [5 empty] | 275 | 2287.1993 |  | 3190.88
|  | B | Improvements to Padubidri - Chikkalagudda State Highway - 01 road from KM 113.00 to 131.00 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | SH-01 | 128 | 860 | [7 empty] | 15: 6.65; 16: 6.65; 17: 6.65; 18: 100%; 19: 0; 23: Work completed |  | 8 |  |  |  | 276 | 2753.7575
|  | C | Improvements to Kuppalli- Kavisaila-Ayanur-Soodur-Gamma-Mallenahalli join to Hirekerur State Highway 148 road from KM 4.40 to 37.00 KM (in Selected Reaches) inTirthahalli Taluk of Shimoga District | SH-148 | 129 | 840 | [7 empty] | 15: 7.25; 16: 7.25; 17: 7.25; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 277 | 3407.7409
|  |  | Division Total |  |  | 7400 | 7400 | 6328.91 | 7449.43 | 783.88 | 8233.31 |  | 9819.8594 | 15: 56.91; 16: 56.775; 17: 56.775; 20: 8209.75; 22: 1610.1094 | [5 empty] | 278 | 729.9677 |  | 9819.85
Shivamogga Division | [13 empty] | 16: 0 | [5 empty] | 279 | 2185.4481
108 | 526 |  | Improvements to Kuppalli- Kavishaila, via Ayanur, Soodur, Gama, Mallenahalli to join Hirekerur State Highway 148 road from KM 92.12 to 156.12 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-148 | 130 | 2300 | 2300 | 1980.33 | 2332.64 | 214.12 | 2546.76 |  | 3037.8919 | Sri Dayananda Shetty (M/s Manjushri construction Company), Kundapura | 21.06.2022 | 20.12.2023 |  | 11.6 | 11.2 | 11.2 | 100% | 0 | 2523.27 | 83.06% | 514.6219 | Work completed |  | 9 |  |  |  | 280 | 1918.8236 |  | 3037.89
109 | 527 |  | Improvements to Kumta Kadamadagi State Highway 48 road from KM 139.03 to 158.03 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-48 | 132 | 2200 | 2200 | 1895.35 | 2209.37 | 212.54 | 2421.91 |  | 2889.165 | Sri Vivekanand Karikal (V P Karikal) | 16.07.2022 | 15.01.2024 |  | 9.85 | 9.85 | 9.85 | 100% | 0 | 2951.52 | 102.2% | -62.355 | Work completed |  | 10 |  |  |  | 281 | 973.5126 |  | 2889.16
110 | 528 | A | Improvements to Gajendragada to Soraba State Highway 136 road from KM 280.37 to 282.07 KM and KM 294.82 to 311.29 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-136 | 133 | 1210 | 2250 | 1927.75 | 2345.68 | 547.95 | 2893.63 |  | 3446.3298 | Sri Dayananda Shetty (M/s Manjushri construction Company), Kundapura | 21.06.2022 | 20.12.2023 |  | 8.2 | 8.2 | 8.2 | 100% | 0 | 2434.08 | 70.63% | 1012.2498 | Work completed |  | 11 |  |  |  | 282 | 1297.7378 |  | 3446.33
|  | B | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 28.50 to 37.00 KM & KM 53.80 to 59.16 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-77 | 134 | 1040 | [7 empty] | 15: 8.9; 16: 8.5; 17: 8.5; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 283 | 1783.9216
111 | 529 | A | Improvements to Haveri-Sagar State Highway 62 road from KM 99.01 to 109.87 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-62 | 136 | 1140 | 2300 | 1975.47 | 2350.79 | 234.2 | 2584.99 |  | 3082.923 | Sri B. Ramakrishna Sheregar (G D Thimmappa Sheregar), Udupi | 30.07.2022 | 29.01.2024 | 31-05-2025 | 2.6 | 1.4 | 1.4 | 100% | 0 | 1436.46 | 46.59% | 1646.463 | Work completed | [5 empty] | 284 | 2231.5246 |  | 2806.57
|  | B | Improvements to Padubidri-Chikkalagudda State Highway- 01 road from KM 158.00 to 160.00 KM (in Selected Reaches) in Hosnagar Taluk of Shivamogga District. | SH-01 | 137 | 550 | [7 empty] | 15: 1.2; 16: 1.5; 17: 1.5; 18: 100%; 19: 0; 23: Work completed |  |  | S |  |  | 285 | 2007.5906
|  | C | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 66.00 to 74.00 KM and KM 76.27 to 87.20 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-77 | 138 | 610 | [7 empty] | 15: 6; 16: 9.16; 17: 9.16; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 286 | 2461.3173
|  |  | Division Total |  |  | 9050 | 9050 | 7778.9 | 9238.48 | 1208.81 | 10447.29 |  | 12456.3096 | 15: 48.35; 16: 49.81; 17: 49.81; 20: 9345.33; 22: 3110.9796 | [5 empty] | 287 | 1611.6748 |  | 12179.95
Chikkamangalore Division | [31 empty] | 288 | 1619.0178
112 | 530 | A | Imrovemets to Mudigere - Gowdahalli - Hosakere - Devrunda Road MDR from Km 0.00 to Km 28.40 (In Selected Reaches) in MudigereTaluk of Chickmagalur District. | MDI-13 | 335 | 1650 | 2300 | 1957.35 | 2131.49 | 511.18 | 2642.67 |  | 3150.686 | M/s SLV Earth Movers Pvt Ltd | 2022-11-10 | 2024-05-09 |  | 12.917 | 17.23 | 17.23 | 100% | 0 | 3066.54 | 97.33% | 84.146 | Work completed |  | 12 |  |  |  | 289 | 3674.1108 |  | 3150.68
|  | B | Improvements to Aladagudde - Biskal Road MDR from Km 0.00 to Km 16.50 (In Selected Reaches) in Chickmagalur Taluk of Chickmagalur District. | CHK-22 | 336 | 650 | [7 empty] | 15: 4.7; 16: 5.22; 17: 5.22; 18: 100%; 19: 0 | [5 empty] | 290 | 3670.6876
113 | 531 | A | Improvements to Kuduregundi - Muttinarajya Road MDR from Km 0.00 to Km 29.00 (In Selected Reaches) in Narasimharajpura Taluk of Chickmagalur District. | NRP3 | 337 | 450 | 900 | 759.69 | 797.27 | 79.3 | 876.57 |  | 1046.9027 | Sri B. M R Rushyashringa Hegde, Chikkamangalore | 21.07.2022 | 20.06.2023 | 31.03.2024 | 4.5 | 4.5 | 4.5 | 100% | 0 | 970.39 | 92.69% | 76.5127 | Work completed |  | 13 |  |  |  | 291 | 2142.8376 |  | 953.33
|  | B | Improvements to Masage - Halanduru Road MDR from Km 0.00 to Km 15.00 (In Selected Reaches) in Sringeri Taluk of Chickmagalur District. | SNG8 | 338 | 450 | [7 empty] | 15: 4.04; 16: 3.74; 17: 3.74; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 292 | 3008.0181
114 | 532 | A | Improvements to B.B. Hills Road MDR from Km 0.00 to Km 38.00(In Selected Reaches) in Chickmagalur Taluk of Chickmagalur District | CHK-13 | 339 | 1400 | 2600 | 2215.68 | 2626.22 |  | 2626.22 |  | 3135.5426 | Sri Sudharshan H B (M/s Conc Shade Constructions Pvt Ltd) | 30.07.2022 | 29.01.2024 |  | 12.496 | 12.5 | 12.5 | 100% | 0 | 3040.77 | 96.98% | 94.7726 | Work completed |  | 14 |  |  |  | 293 | 2902.357 |  | 3135.54
|  | B | Improvements to Sakarayapattana - Javagal Road MDR from Km0.00 to Km 20.00 (In Selected Reaches) Kadur Taluk of Chickmagalur District. | KDR-22 | 340 | 1200 | [7 empty] | 15: 12.02; 16: 12.02; 17: 12.02; 18: 100%; 19: 0 | [5 empty] | 294 | 1593.3157
115 | 533 | A | Improvements to NH-206 - mallikoppa via kesarakoppa to join Tarikere Mangalore road from Km 0.00 to Km 15.00 (In Selected Reaches) in Tarikere Taluk of Chickmagalur District. | MDR | 341 | 700 | 5250 | 4473.8 | 5597.74 | 1116.98 | 6714.72 |  | 7997.2768 | Sri C Halappa, Chikkamagaluru | 25.05.2022 | 24.11.2023 |  | 5 | 5 | 5 | 100% | 0 | 7402.02 | 92.56% | 595.2568 | Work completed |  | 15 |  |  |  | 295 | 1416.1317 |  | 7997.27
|  | B | Improvement to Road from Birur NH-206 to join Tarikere Hosadurga Via Koratigere Nagamangala MDR from Km 0.00 to km 12.00 (In Selected reaches) in Ajjampura Taluk of Chickmagalur District. | TRK-205 | 342 | 575 | [7 empty] | 15: 4.62; 16: 4.62; 17: 4.62; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 296 | 2548.1714
|  | C | Improvements to Shivani - Rangapura Road MDR from Km 0.00 to km 11.00 (In Selected reaches) in Ajjampura Taluk of Chickmagalur District | TRK-204 | 343 | 425 | [7 empty] | 15: 3.38; 16: 4.4; 17: 4.4; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 297 | 1518.6496
|  | D | Improvement to Kallattipura - Lalbag Road MDR from Km 0.00 to km 20.00 (In Selected reaches) in Tarikere Taluk of Chikmagalur District. | TRK-5 | 344 | 550 | [7 empty] | 15: 5.09; 16: 5.09; 17: 5.09; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 298 | 4057.0619
|  | E | Improvements to Channapura-Giribhomanahalli Road Via Giriyapura Yagati -Maravanji MDR from Km 0.00 to Km 45.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District | KDR-201 | 346 | 950 | [7 empty] | 15: 8.35; 16: 8.95; 17: 8.95; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 299 | 1399.2315
|  | F | Improvements to Road joining Jodilingadalli to SH-152 from Km 0.00 to Km 9.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | KDR- New | 347 | 400 | [7 empty] | 15: 3.41; 16: 9.56; 17: 9.56; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 300 | 1891.0567
|  | G | Improvements to Panchanahalli - Timmlapura Road Via Timmalapura Panchanahalli Hoskerehalligate Niduvalli Garagadahalli Anandpuragate Kankanadu Vanabogihalli Honnenhalli Sannenhalli MDR from Km 0.00 to Km 21.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | KDR-223 | 348 | 750 | [7 empty] | 15: 7; 16: 7; 17: 7; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 301 | 856.7497
|  | H | Improvements to Belgur-Panchanalli Road joining SH-152 from Km 0.00 to Km 5.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District | MDR | 349 | 250 | [7 empty] | 15: 2.5; 16: 3.2; 17: 3.2; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 302 | 1678.8419
|  | I | Improvements to Road joining SH-152 to NH-206 from Km 0.00 to Km 12.00 (In Selected Reaches) in Kadur Taluk of Chikmagalur District. | MDR |  | 400 | [7 empty] | 15: 3.56; 16: 5.36; 17: 5.36; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 303 | 4240.4335
|  | J | Improvements to Road joining SH-152 to Singatgere-Panchanalli Road from Km 0.00 to Km 5.5.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | MDR | 299 | 250 | [7 empty] | 15: 1.8; 16: 2.1; 17: 2.1; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 304 | 1745.7641
|  |  | Division Total |  |  | 11050 | 11050 | 9406.52 | 11152.72 | 1707.46 | 12860.18 |  | 15330.4081 | 15: 95.383; 16: 110.49; 17: 110.49; 19: 0; 20: 14479.72; 22: 850.6881 | [5 empty] | 305 | 2779.6425 |  | 15236.82
|  |  | Shivamogga Circle Total |  |  | 53750 | 53750 | 46062.36 | 54246.65 | 7404.045 | 61650.695 |  | 73508.7703 | 15: 389.398; 16: 413.75; 17: 392.913; 19: 20.837; 20: 59756.74; 22: 13752.0303 | [5 empty] | 306 | 4222.2388 |  | 55026.68
Mangalore Circle | [31 empty] | 307 | 1861.4583
Udupi Division | [31 empty] | 308 | 2702.8814
116 | 534 | A | Improvements to Padubidre-Chikkalagudda Road (SH-01) from km 50.00 to 52.050 km in (selected reaches) Hebri Taluk of Udupi District. | SH-1 | 140 | 700 | 2300 | 1957.76 | 2293.14 | 524.63 | 2817.77 |  | 3357.3108 | Sri Jeevan Shetty, Udupi | 29.07.2022 | 28.01.2024 |  | 1.428 | 1.43 | 1.428 | 99.86% | 0.002 | 2510.96 | 74.79% | 846.3508 | Work Completed. |  | 16 |  |  |  | 309 | 1866.3652
|  | B | Improvements to Mangalore - Athradi SH-67 from Km 47.28 Km to Km 48.28 in (selected reaches) Karkala Taluka of Udupi Dist.. | SH-67 | 142 | 325 | [7 empty] | 15: 1; 16: 0.8; 17: 0.8; 18: 100%; 19: 0; 23: Work Completed. | [5 empty] | 310 | 1164.7436
|  | C | Improvements to Kalyanpura - Mudaru SH from Ch Km 27.50 to Km 32.00 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 144 | 225 | [7 empty] | 15: 1.7; 16: 1.87; 17: 1.87; 18: 100%; 19: 0; 23: Work Completed. | [5 empty] | 311 | 3440.2638
|  | D | Improvement to Subramanya-Udupi SH-37 from Km 119.50 to Km 126.10 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | SH-37 | 145 | 450 | [7 empty] | 15: 3; 16: 3.16; 17: 3.16; 18: 100%; 19: 0; 23: Work Completed. | [5 empty] | 312 | 1673.5381
|  | E | Improvements to Kalyanpura - Mudaru SH from Ch Km 41.00 to Km 48.00 (selected reaches) from single lane to intermediate lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 146 | 600 | [7 empty] | 15: 5.64; 16: 6.04; 17: 6.04; 18: 100%; 19: 0; 23: Work Completed. | [5 empty] | 313 | 4723.5183
117 | 535 | A | Improvements to Subramanya -Udupi road SH37 from Ch Km 139.40 to Km 153.30 (selceted reaches) in Kapu Taluk of Udupi District.(Via palli Kattigeri, belle, manipura, Kasaba) | SH-37 | 147 | 1250 | 2200 | 1882.23 | 2290.58 | 565.74 | 2856.32 |  | 3401.552 | Sri Udaya Shetty, M/s USK Construction Company DP, Udupi, Ph No: 9480345814 | 27.05.2022 | 26.11.2023 |  | 9.466 | 6.7 | 6.7 | 100% | 0 | 3257.43 | 95.76% | 144.122 | Work Completed. |  | 17 |  |  |  | 314 | 5413.9248
|  | B | Improvements to Mangalore- Atharadi road SH67 from Ch Km 49.98 to Km 71.74 (selected reaches) in Kapu Taluk of Udupi District. | SH-67 | 148 | 950 | [7 empty] | 15: 6.696; 16: 5.37; 17: 5.37; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 315 | 3215.4635
118 | 536 | A | Improvements to Mudradi-Seethanadi- Bhramavara road Development of 4Lane from Ch Km 14.90 to Km 27.70 (selceted reaches) in Bhramavara Taluk of Udupi District.(Via. Havanji, Kolalagiri, Kukkehalli and Perdoor) | Newly Upgraded SH | 149 | 2250 | 4500 | 3844.3 | 4548.15 | 1131.04 | 5679.19 |  | 6764.952 | Sri Uppinakudru Rajesh Karanth, Kundapura | 22.06.2022 | 21.12.2023 |  | 5.485 | 5.485 | 5.485 | 100% | 0 | 6569.49 | 97.11% | 195.462 | Completed. | [5 empty] | 316 | 2068.3339
|  | B | Improvements to Koteshwara-Kodi- Kundapura road from Ch Km 0.00 to Km 2.50 MDR in Kundapura Taluk of Udupi District. ( Via :Koteshwara-Kodi- Kundapura ) | KDP204 | 152 | 275 | [7 empty] | 15: 2; 16: 1.83; 17: 1.83; 18: 100%; 19: 0; 23: Completed. |  |  | twenty four |  |  | 317 | 3002.2709
|  | C | Improvements to Brahmavara-Jannadi- Biddalkatte-Sauda-Shankaranarayana- Siddapura road from Ch 2.50 Km to 12.00 Km(selceted reaches)MDR in Brahmavara Taluk of Udupi District. ( Via : Koteshwara-Kodi- Kundapura ) | KDP5 | 153 | 875 | [7 empty] | 15: 6.14; 16: 5.01; 17: 4.83; 18: 96.41%; 19: 0.18; 23: 0.180Km is stopped due to land acquisition problem. | [5 empty] | 318 | 3691.1361
|  | D | Improvements to Kota-Goliyangadi road from Ch Km14.80 to Km 20.20 Major District road in Kundapura Taluk of Udupi District. ( Via: Koteshwara-Kodi- Kundapura ) | UDP4 | 154 | 650 | [7 empty] | 15: 5; 16: 5.15; 17: 5.15; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 319 | 3177.9081
|  | E | Improvements to Someshwara- Koteshwara road MDR from Ch Km 34.00 to 41.50 Km (selected reaches) in Kundapura Taluk of Udupi District. ( Via. Haladi-Bidkalakatte) | KDP9 | 155 | 450 | [7 empty] | 15: 4.1; 16: 4.189; 17: 4.189; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 320 | 4345.2229
119 | 537 | A | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 339.50 to Km 346.20 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 156 | 900 | 2250 | 1926.01 | 2265.8 |  | 2265.8 |  | 2705.4617 | Sri B.Ramakrishna Sheregar, M/s G.D. Thimmappa Sheregar, Udupi | 30.07.2022 | 29.01.2024 |  | 4.876 | 5.136 | 5.136 | 100% | 0 | 2722.99 | 100.6% | -17.5283 | Completed. |  | 18 |  |  |  | 321 | 2336.8095
|  | B | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 346.20 to 356.45 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 157 | 1350 | [7 empty] | 15: 9.291; 16: 9.471; 17: 9.441; 18: 99.68%; 19: 0.03; 23: Completed. | [5 empty] | 322 | 3213.8949
|  |  | Division Total |  |  | 11250 | 11250 | 9610.3 | 11397.67 | 2221.41 | 13619.08 |  | 16229.2766 | 15: 65.822; 16: 61.641; 17: 61.429; 19: 0.212; 20: 15060.87; 22: 1168.4066 | [5 empty] | 323 | 2178.1093
Mangalore Division | [31 empty] | 324 | 2377.2489
120 | 538 | A | Improvements to Subramanya - Udupi State Highway 37 from Ch Km 3.50 to Km 14.00 (Selected reaches) in Kadaba Taluk of Dakshina Kannada District. | SH37 | 243 | 825 | 2200 | 1892.88 | 2109.97 | 200.64 | 2310.61 |  | 2757.7902 | Pavithra Engineering and Constructions, Mangalore | 04.08.2022 | 03.02.2024 |  | 7.08 | 7.08 | 7.08 | 100% | 0 | 1707.04 | 61.9% | 1050.7502 | Completed |  |  | T |  |  | 325 | 2089.375
|  | B | Improvements to Bangalore-Jalsoor State Highway -85 from Ch Km 291.51 toKm 337.91 (Selected reaches) from single lane to intermediate Lane in Sullia Taluk of Dakshina Kannada District. | SH85 | 244 | 1375 | [7 empty] | 15: 10.21; 16: 10.21; 17: 10.21; 18: 100%; 19: 0; 23: Completed |  |  |  |  | VO Submitted pending due to approval | 326 | 1763.4647
121 | 539 | A | Improvements to Subramanya- Udupi State Highway -37 from Km 72.75 to Km 94.65 in (Selected reaches) Belthangady Taluk of Dakshina KannadaDistrict. | SH37 | 245 | 2250 | 2750 | 2349.14 | 2809.36 | 695.11 | 3504.47 |  | 4174.0824 | Sri Udaya Shetty, M/s USK Construction Company DP, Udupi Ph No: 9480345814 | 30.05.2022 | 29.11.2023 |  | 12.02 | 9.3 | 9.3 | 100% | 0 | 3858.71 | 92.44% | 315.3724 | Completed |  | 19 |  |  |  | 327 | 1500.9228
|  | B | Improvements to Dharmasthala- Thottataddy-Chibidre MDR from Ch Km 0.00 to Km 10.80 (selected reaches) and Puduvettu Kayarthadka Nidle MDR from Ch Km 0.00 to Km 8.00 (selected reaches) in Belthangady Taluk of Dakshina Kannada District. | BEL26 | 246 | 500 | [7 empty] | 15: 3.03; 16: 3.03; 17: 3.03; 18: 100%; 19: 0; 23: Completed | [5 empty] | 328 | 3907.803
122 | 540 |  | Improvements to Mani-Ullala road from Ch Km 18.68 to Km 21.00 (4 Lane ) (selected reaches) in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 453 | 1000 | 1000 | 859.63 | 995.97 | 241.33 | 1237.3 |  | 1474.2151 | Sri Mohammed Rafi K M, Mangalore | 15.06.2022 | 14.05.2023 |  | 1.81 | 1.46 | 1.46 | 100% | 0 | 1329.27 | 90.17% | 144.9451 | completed. |  | 20 |  |  |  | 329 | 3867.8942
123 | 541 | A | Improvements to Mangalore- Athradi State Highway-67 from Ch Km 32.00 to Km 36.50 to (2 lane) road in Mangalore Taluk of DakshinaKannada District. | SH-67 | 248 | 515 | 2250 | 1925 | 2344.17 | 584.06 | 2928.23 |  | 3487.1124 | Sri Kishore Kumar, Brahma lingeshwara constructions, Kapu | 29.07.2022 | 28.01.2024 |  | 3.7 | 2.02 | 2.02 | 100% | 0 | 3092.32 | 88.68% | 394.7924 | Completed |  | 21 |  |  |  | 330 | 3114.135
|  | B | Improvements to Gantalkatte- Mudukonaje- Anegudde-Ammanottu-Marnadu Major District Road from Ch Km 7.70 to Km 10.30 from single lane to intermediate Lane in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 249 | 340 | [7 empty] | 15: 2.02; 16: 2.02; 17: 2.02; 18: 100%; 19: 0; 23: Completed | [5 empty] | 331 | 3083.1704
|  | C | Improvements to Kandandale- Moodbidre- Bantwala road MDR from Ch Km 21.00 to Km 26.00 (2 lane) (selected reaches) in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 251 | 700 | [7 empty] | 15: 5.18; 16: 5.18; 17: 5.18; 18: 100%; 19: 0; 23: Completed | [5 empty] | 332 | 3950.8683
|  | D | Improvements to Kallamundkuru-Paaladkka Mithabailu road Kanthawa High school MDR from Ch Km 0.00 to Km 4.50 (selected reaches) in Mangalore Taluk of Dakshina KannadaDistrict. | Newly Upgraded MDR | 252 | 230 | [7 empty] | 15: 1.82; 16: 1.97; 17: 1.97; 18: 100%; 19: 0; 23: Completed | [5 empty] | 333 | 3838.1557
|  | E | Improvements to Mangalpette- Taalipadi road MDR from Ch Km 1.80 to 5.00 Km (in selected reaches) in Mangalore Taluk of Dakshina Kannada District | MNG19 | 253 | 225 | [7 empty] | 15: 1.36; 16: 0.9; 17: 0.9; 18: 100%; 19: 0; 23: Completed | [5 empty] | 334 | 5432.2905
|  | F | Improvements to Halleangadi-Pakshikere road MDRfrom Ch Km 0.60 to 3.00 Km in Mangalore Taluk of Dakshina Kannada District (via: Indiranagar to Pakshikere church) | MNG36 | 254 | 240 | [7 empty] | 15: 1.8; 16: 1.8; 17: 1.8; 18: 100%; 19: 0; 23: completed. | [5 empty] | 335 | 4651.6289
124 | 542 | A | Improvements to Puttur- Uppinangadi- Guruvayanakere development of 4Lane from Ch Km 1.40 to Km 11.60 to (selected reaches) in Puttur Taluk of DakshinaKannada District | PUT8 | 255 | 1000 | 2250 | 1939.47 | 2202.45 | 544.59 | 2747.04 |  | 3273.5472 | Sri Dayananda Shetty, M/s Manjushri Construction Co., Udupi | 30.07.2022 | 29.01.2024 |  | 2.3 | 2.3 | 2.3 | 100% | 0 | 1459.82 | 44.59% | 1813.7272 | Completed | [5 empty] | 336 | 1864.7579
|  | B | Improvements to Saradka Periyaltada MDR road from Ch Km 0.00 to 9.00 Km (selected reaches) in Bantwala Taluk of Dakshina Kannada District | PUT10 | 256 | 975 | [7 empty] | 15: 6.6; 16: 5.15; 17: 5.15; 18: 100%; 19: 0; 23: Completed | [5 empty] | 337 | 1258.7395
|  | C | Improvements to Subramanya- Manjeshwara SH-100 road from Ch Km 48.000 to Km 50.00 in Puttur Taluk of Dakshina KannadaDistrict | SH100 | 257 | 275 | [7 empty] | 15: 1.78; 16: 1.78; 17: 1.78; 18: 100%; 19: 0; 23: Completed | [5 empty] | 338 | 1656.7109
125 | 543 | A | Improvements to Marvuru - Adyapadi - Unele- Kandavara MDR Ch road from Km 0.00 to Km 2.00 (selected reaches) and Maddya Peddiyangadi MDR from Km 0.00 to Km 2.00 (selected reaches) in Mangalore Taluk of Dakshina Kannada District. | MNG105 MNG202 | 258 | 400 | 2100 | 1793.48 | 2410.19 | 560.44 | 2970.63 |  | 3534.9717 | Sri Udaya Shetty, M/s USK Construction Company DP, Udupi Ph No: 9480345814 | 30.05.2022 | 29.11.2023 |  | 3.67 | 2.82 | 2.82 | 100% | 0 | 3465.24 | 98.03% | 69.7317 | Completed |  |  | 23 |  |  | 339 | 1613.8491
|  | B | Improvements to Parari-Ulayaibettu-Mallur MDR From Ch 2.40 km to 4.40 km in Mangalore Taluk of Dakshina Kannada District | MNG82 | 259 | 200 | [7 empty] | 15: 0.85; 16: 0.85; 17: 0.85; 18: 100%; 19: 0; 23: Completed | [5 empty] | 340 | 2503.1855
|  | C | Improvements to Bhatrakere - Katlasar - Kukkudakatte - Nirakere - Todar -Mastikatte - Road MDR from Ch 0.00 to 5.00 Km (selected reaches) in Mangalore Taluk of Dakshina Kannada District | Newly Upgraded MDR | 260 | 500 | [7 empty] | 15: 3.72; 16: 3.72; 17: 3.72; 18: 100%; 19: 0; 23: Completed | [5 empty] | 341 | 2028.4253
|  | D | Improvement to Surthakal- Kabaka SH 101 development of 4lane from Km 1.60 to Km 4.80 ( in selected reaches) in Mangalore Taluka of Dakishna Kannada District. | SH-101 | 261 | 1000 | [7 empty] | 15: 1.7; 16: 1.83; 17: 1.83; 18: 100%; 19: 0; 23: Completed | [5 empty] | 342 | 2468.2653
126 | 544 | A | Improvements to Moodabidre-Bantwal, Moodabidre-Kadandale MDR from Ch 40.80 Km to 42.80 Km (in selected reaches) in Bantwal taluk of Dakshina Kannada district. (via: Poochmooguru- Bantwal) | Newly Upgraded SH | 262 | 200 | 2250 | 1926.72 | 2372.16 | 226.54 | 2598.7 |  | 3098.2954 | Sri Jagdeep D Suvarna,Kumta | 04.08.2022 | 03.02.2024 |  | 1.13 | 1.13 | 0 | 0% | 1.13 | 926.06 | 29.89% | 2172.2354 | 1.13 k.m. BC work pending, | [5 empty] | 343 | 4918.2487
|  | B | Improvements to Mani -Ullala MDR from Ch 0.00 Km to 2.50 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 263 | 240 | [7 empty] | 15: 1.83; 16: 1.83; 17: 1.83; 18: 100%; 19: 0; 23: Completed | 3 |  |  |  |  | 344 | 2418.7884
|  | C | Improvements to Ganjimata Niddodi road via Yedapadavu Kuppepadavu-Arla Soranadu Road Rayi Moorje road from Ch 20.00 Km to 25.85 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 264 | 410 | [7 empty] | 15: 5.74; 16: 5.74; 17: 5.74; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 345 | 3625.6625
|  | D | Improvements to Manihalla-Agilamogaru road from Ch 0.00 Km to 15.50 Km MDR (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 454 | 700 | [7 empty] | 15: 6.75; 16: 6.75; 17: 6.75; 18: 100%; 19: 0; 23: Completed | [5 empty] | 346 | 1878.9783
|  | E | Improvements to Vogga Ulli road from Ch 6.00 Km to 14.20 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district.(Via Maninalkaru kakkepadvu Ulli). | BNT19 | 266 | 700 | [7 empty] | 15: 4.28; 16: 4.28; 17: 4.28; 18: 100%; 19: 0; 23: Completed | [5 empty] | 347 | 2764.0106
|  |  | Division Total |  |  | 14800 | 14800 | 12686.32 | 15244.27 | 3052.71 | 18296.98 |  | 21800.0144 | 15: 90.38; 16: 83.15; 17: 82.02; 19: 1.13; 20: 15838.46; 22: 5961.5544 | [5 empty] | 348 | 4204.27
|  |  | Mangalore Circle Total |  |  | 26050 | 26050 | 22296.62 | 26641.94 | 5274.12 | 31916.06 |  | 38029.291 | 15: 156.202; 16: 144.791; 17: 143.449; 19: 1.342; 20: 30899.33; 22: 7129.961 | [5 empty] | 349 | 5274.0311
Bangalore Circle | [31 empty] | 350 | 3832.0962
Bangalore Rural Division | [31 empty] | 351 | 4598.4748
127 | 545 | A | Improvements to Bangalore-Anekal-Bannerghatta Road (SH-87) from Km 16.80 to Km 20.00 & Km 26.25 to Km 28.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | ANK52 | 273 | 350 | 5800 | 4961.68 | 6005.718 | 1365 | 7370.718 |  | 8779.4142 | RAMESH THAMMANNAGOWDA( GANAPATHI STONE CRUSHERS PVT LTD | 2022-10-21 | 2024-04-21 | 19.04.2025 | 3.2 | 3.25 | 3.25 | 100% | 0 | 6048.33 | 68.89% | 2731.0842 | Completed | [5 empty] | 352 | 3478.0392
|  | B | Improvements to MDR From NH-7 to SH-87 Via Hulimangala, Jigani from Km 6.50 to Km 9.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 274 | 450 | [7 empty] | 15: 2.2; 16: 2.4; 17: 2.4; 18: 100%; 19: 0; 23: Completed |  | 16 |  |  |  | 353 | 1365.9471
|  | C | Improvements to MDR From Bagganadoddi to Amani Bidarakere via Mysuruammanadoddi, Shavayanadoddi, Yellamanadoddi, Pujaganahapalaya, Krishnaiahndoddi, Mahntalingapura, Kallubalu,Bukkasagara, Harapanahalli, Koppagate Connecting from Km 0.00 to Km 14.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | SH-87 | 275 | 1000 | [7 empty] | 15: 4.805; 16: 3.767; 17: 3.767; 18: 100%; 19: 0; 23: Completed |  |  |  |  | Balance length 1.055 Km has been developed by KRDCL work has been completed. This length has been not tackled.Work completed | 354 | 2176.3883
|  | D | Improvements to New SH From Magadi Road (SH-85) to Gunjuru (SH-35) via Hamahappanahalli cross-Chandrappa Circle- Doddaaladamara-Ramohalli-Kumbalgodu-Agara-Thataguni- Kaggalipura-Bannerughatta-Hommadevanahalli-Bettadasapura-Vipro Junction-Hosuru Road (NH-7) Konnapana Agragara-Sarjapura Main Road-(Kodathi gate) Kachamaranahalli from Km 6.00 to Km 13.60 & Km 17.80 to Km 29.40 (in selected reaches) in Bangalore SouthTaluk of Bangalore Rural District | New SH | 276 | 1300 | [7 empty] | 15: 6.08; 16: 7.412; 17: 7.412; 18: 100%; 19: 0; 23: Completed | [5 empty] | 355 | 2340.9263
|  | E | Improvements to MDR From Bylalu to Lakshmipura Ondane Mailikallu from Km 6.20 to Km 8.50 (in selected reaches) in Bangalore South Taluk of Bangalore Rural District | BNS210 | 277 | 300 | [7 empty] | 15: 2.3; 16: 8.5; 17: 8.5; 18: 100%; 19: 0; 23: Completed | [5 empty] | 356 | 3402.8852
|  | F | Improvements to MDR Connecting BM Road to Karubele via H Gollahalli from Km 2.50 to Km 5.00 (in selected reaches) inBangalore South Taluk of Bangalore Rural District | BNS214 | 278 | 300 | [7 empty] | 15: 2; 16: 1.87; 17: 1.87; 18: 100%; 19: 0; 23: Completed | [5 empty] | 357 | 1834.0382
|  | G | Improvements to MDR from NH-75 (Makali) to Bettahalsuru connecting SH-104 via Honnasandra Cross, Aluru, APMC Yard,Basaveshwara Temple, Kodipalaya, Madhure, Kakolu,Rajanakunte, Thimmasandra, Betta Halasuru, NH-7, Muthagada Halli, Begur, Chikkanahalli and mylanahalli from Km 0.00 to Km 7.65 (Change to Ch:19.00) (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | SH | 279 | 800 | [7 empty] | 15: 6.05; 16: 6.56; 17: 6.56; 18: 100%; 19: 0; 23: Completed | [5 empty] | 358 | 2405.9629
|  | H | Improvements to MDR from Singanayakanahalli to Madappanahalli via Shyanubhoganahalli Ch: 0.50 KM to 2.35 KM(in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 280 | 300 | [7 empty] | 15: 1.85; 16: 1.85; 17: 1.85; 18: 100%; 19: 0; 23: Completed | [5 empty] | 359 | 2240.7481
|  | I | Improvements to MDR from Gollahalli To Hesarghatta CH 8.20 KM to CH : 9.60 KM in Bangalore North Taluk, of Bangalore District | MDR | 281 | 180 | [7 empty] | 15: 1.4; 16: 1.118; 17: 1.118; 18: 100%; 19: 0; 23: Completed | [5 empty] | 360 | 5658.9428
|  | J | Improvements to Road from Channapattana Kavanapura- SRS Betta- Avverahalli-Kailancha-Nagohalli-Hunasanhalli-Uragahalli-Bidadi-Ganakallu-Nelamangala from Ch;65.70 to70.00 Km ( Mallasandra to Sondekoppa) in Bangalore North Taluk, of Bangalore District | MDR | 282 | 820 | [7 empty] | 15: 4.3; 16: 6.347; 17: 6.347; 18: 100%; 19: 0; 23: Completed | [5 empty] | 361 | 4055.3391
128 | 546 | A | Improvements to Chandapura -Dommasandra MDR from Km 1.50 to Km 6.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 282 | 450 | 900 | 767.38 | 813.38 | 78.18 | 891.56 |  | 1064.7179 | GOVINDALLI HUCHEGOWDA NAGARAJU ( G.H NAGARAJU ) | 2022-12-02 | 2023-11-02 |  | 4 | 3.96 | 3.96 | 100% | 0 | 376.2 | 35.33% | 688.5179 | Completed |  |  | V |  | 0.20 Km approch roads has to be tackled. Drain work under progress & Box Culverts has been completed. | 362 | 2931.4676
|  | B | Improvements to Iggaluru to Gumlapura MDR from Km 29.25 to Km 30.56 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 283 | 250 | [7 empty] | 15: 1.2; 16: 1.2; 17: 1.2; 18: 100%; 19: 0; 23: Road work completed and Road furniture work under progress |  |  |  |  | 1.20 km WMM Work in Progress. Remaining work yet to be tackled. Tree cutting and poleshifting work is in progress. | 363 | 1606.293
|  | C | Improvements to MDR FromVenkateshwara circle, Shanimahathama Temple via to Ragavendra Circle, Srirama Temple, Tilaknagara & Shanimahathama Temple MDR from Km 34.00 to Km 36.00 in Anekal Taluk of Bangalore Rural District | MDR | 284 | 200 | [7 empty] | 15: 1.56; 16: 0.94; 17: 0.94; 18: 100%; 19: 0; 23: Completed | [5 empty] | 364 | 1989.2155
129 | 547 | A | Improvements to MDR from Dommasandra (Bangalore) to Sulikunte Colony via Shantigiri Asharama, Kodathi, JHC, Wipro, NEZ, Mulluru from Km 0.00 to Km 10.50 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District | BNE18 | 286 | 1100 | 2100 | 1706.8 | 1908.91 | 174.05 | 2082.96 |  | 2486.0891 | M S VENKATESH( M S V Construtions Company ) | 16/9/2022 | 16/03/2024 |  | 6.46 | 5.18 | 5.08 | 98.07% | 0.1 | 416.61 | 16.76% | 2069.4791 | 5.08 Km Road Work completed Balance 100m work has been stopperd due to land acquisition problem |  |  | W |  | Drain work of 3210 m complted & 6 Culverts completed, Out of 6 culvert remaining work under progress | 365 | 2636.0342
|  | B | Improvements to MDR from Bendiganahalli (NH-04) to Bommenahalli Budigere via Raghumenahalli, Hancharahalli, Jyothipura, Thirumenhalli from Km 0.00 to Km 13.00 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District. | MDR | 287 | 1000 | [7 empty] | 15: 7.9; 16: 7.653; 17: 7.653; 18: 100%; 19: 0; 23: Work Completed |  |  |  |  | 2300 m Drain work completed out of 4600 m. 4 box culvert work completed. Balance 1.3 km Road work is under progress | 366 | 2949.3616
130 | 548 |  | Improvements to Bangalore Nandi MDR Connecting SH-104 to Bandikodigehalli MDR via Hosuru Bande, Bagaluru from Km 12.60 to Km 23.50 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 288 | 1500 | 1500 | 1303.47 | 1333.33 | 126.45 | 1459.78 |  | 1744.0737 | Sri C R Girish (Ram And Company), Bangalore | 2022-11-03 | 2024-02-03 |  | 9.2 | 4.5 | 0.7 | 15.56% | 3.8 | 114.28 | 6.552% | 1629.7937 | 0.7Km Road Work completed and Remaining reach WMM Work Under Progress | 1 |  | X | 3.80km DBMwork completed, Drain work of 225m completed out of 990m & 2.7km WMM work completed and work has been stopped due to TDR Issues | 225m drain work completed out of 990m, 1KM BC Work completed and remaining work under progress | 367 | 2296.1315
131 | 549 | A | Improvements to Hesarughatta Tank bund road (SH-39)from Km 4.00 to Km 7.00 in Bangalore North Taluk of Bangalore Rural District | SH-39 | 288 | 400 | 950 | 823.82 | 897.96 | 25.84 | 923.8 |  | 1103.6935 | Govindalli Huchegowda Nagaraju (G.H Nagaraju) | 2022-12-02 | 2023-02-11 |  | 2.9 | 2.69 | 2.685 | 100% | 0.005 | 556.78 | 50.45% | 546.9135 | Completed |  | 1 |  |  |  | 368 | 1704.1556
|  | B | Improvements to MDR from Lakshmipura Cross to Golhalli Hesrughatta Road SH-39 via Lakshmipura, Abbigere, Chikkabanavara, Pipe line Road, Ganegarahalli, Somashettyhalli from Km 0.00 to Km 10.20 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 289 | 550 | [7 empty] | 15: 5.3; 16: 4.69; 17: 4.69; 18: 100%; 19: 0; 23: Completed | [5 empty] | 369 | 2712.4828
132 | 550 | A | Improvements to MDR from Muthkuru to NH-207 via Bylahalli, Muthgadahalli-Thottanuru-Thiruvaranga from Km 0.00 to Km 8.10 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS9 | 289 | 475 | 3800 | 3285.45 | 3903.51 | 960.4 | 4863.91 |  | 5793.6894 | M/s Munikrishnappa | 2023-03-24 | 2024-09-23 |  | 4.9 | 4.9 | 4.9 | 100% | 0 | 2198.54 | 37.95% | 3595.1494 | Road work completed and Road furniture work under progress |  |  | Y |  | 4.05km BM & 3.5KM SDBC has been laid CC Drain work of 230m completed, 3 culvert completed & 2 culvert work under progress Remaining work under progress | 370 | 4938.6349
|  | B | Improvements to Siddalagatta - Anekal SH 35 road road MDR from Km 25.64 to Km 34.84 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS25 | 290 | 475 | [7 empty] | 15: 4.604; 16: 4.604; 17: 4.604; 18: 100%; 19: 0; 23: Road work completed and Road furniture work under progress | [5 empty] | 371 | 1375.8605
|  | C | Improvements to MDR from NGD (SH 74) to Thayagadahalli (BTS Road) via Byrashettyhalli-Bolamarahalli from Km 0.00 to Km 5.10 in Nelamangala Taluk of Bangalore Rural District | NLM10 | 291 | 450 | [7 empty] | 15: 5.1; 16: 5.1; 17: 5.1; 18: 100%; 19: 0; 23: Completed | [5 empty] | 372 | 6139.5437
|  | D | Improvements to MDR from NH-04 to Sompura via Devarahosahalli-Kamalapura Agalakuppe from Km 7.00 to Km 12.00 (in selected reaches) in Nelamangala Taluk of Bangalore Rural District | MDR | 292 | 500 | [7 empty] | 15: 2.66; 16: 1.96; 17: 1.96; 18: 100%; 19: 0; 23: Completed | [5 empty] | 373 | 2508.2059
|  | E | Improvements to Kodigehalli-Kanakenahalli road MDR from Km 0.00 to Km 19.00 (in selected reaches) in DoddaballapuraTaluk of Bangalore Rural District | DOD7 | 293 | 950 | [7 empty] | 15: 9.25; 16: 7.15; 17: 7.15; 18: 100%; 19: 0; 23: Road work completed and Road furniture work under progress |  |  |  |  | 0.250km Road work complete, 560 m Drain work completed, 01 Culvert completed. | 374 | 4499.8954
|  | F | Improvements to Devanahalli-Kempapura road (SH-96) from Km10.00 to Km 12.25 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | SH-96 | 294 | 500 | [7 empty] | 15: 1.4; 16: 1.62; 17: 1.62; 18: 100%; 19: 0; 23: Completed |  |  |  |  | 4 Culverts completed & Drain Work of 1600m completed. | 375 | 3414.5569
|  | G | Improvements to MDR from Devanahalli town to NH-44 from Kempegowda Circle to Road to rani Circle from Km 0.00 to Km 3.60 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | DVN9 | 295 | 450 | [7 empty] | 15: 1.47; 16: 0; 19: 0; 23: Road dropped | [5 empty] | 376 | 2229.7275
|  |  | Division Total |  |  | 15050 | 15050 | 12848.6 | 14862.808 | 2729.92 | 17592.728 |  | 20971.6779 | 15: 102.089; 16: 99.221; 17: 95.316; 19: 3.905; 20: 9710.74; 22: 11260.9379 | [5 empty] | 377 | 3765.107
Ramanagara Special Division | [13 empty] | 16: 0 | [5 empty] | 378 | 2087.8728
133 | 551 | A | Improvements to Road from Channapattana Kavanapura- SRS Betta- Avverahalli-Kailancha-Nagohalli-Hunasanhalli-Uragahalli-Bidadi- Ganakallu-Nelamangala from Ch;3.00 to 5.20 Km( in selected Reaaches) in Channapattana Taluk of Ramanagara District | MDR | 327 | 250 | 2100 | 1772.07 | 2180.6 | 520.74 | 2701.34 |  | 3216.8558 | GOVINDALLI HUCHEGOWDA NAGARAJU ( G.H NAGARAJU ) | 8.5.2022 | 2.5.2024 | 28.03.2024 | 1.875 | 2 | 2 | 100% | 0 | 2502.95 | 77.81% | 713.9058 | completed | [5 empty] | 379 | 6633.6047
|  | B | Improvements to Road joining SH-33 from Harohalli- Maralvadi-hunasanhalli- Bannimukkodlu- Aalnatha kodihalli- Sathanur- Muttatti-kabbalu- channapattana- thittamaranahalli- bevoor from CH: 98.80 K M to 105 KM(in selected reaches) | SH-33 | 328 | 550 | [7 empty] | 15: 6.2; 16: 7.97; 17: 7.97; 18: 100%; 19: 0; 23: completed |  | 2 |  |  |  | 380 | 3204.8824
|  | C | Improvements to MDR From Channapatna to Ramanagara Border Via Kannamangala, Angarahalli, Gollahallidoddi from Km 7.35 to Km 16.00 (In selected reaches) in Channapatna Taluk of Ramanagara District. | MDR | 329 | 700 | [7 empty] | 15: 6.45; 16: 4.05; 17: 4.05; 18: 100%; 19: 0; 23: completed | [5 empty] | 381 | 5046.7929
|  | D | Improvements to New SH Connecting From NH- 275 to Krishnapura Via Byrapattana, Chikkalooru, V.V.Halli, Ankushanahalli from Km 5.30 to 11.30 Km (In selected reaches) in Channapatna Taluk of Ramanagara District. | New SH | 330 | 600 | [7 empty] | 15: 6; 16: 6; 17: 6; 18: 100%; 19: 0; 23: completed | [5 empty] | 382 | 7045.0652
134 | 552 |  | Improvements toNew SH From Kodihalli to Sathanuru Via Doddalahalli from Km 0.00 to Km 25.30 (In selected reaches) in Kanakapura Taluk of Ramanagara District. | New SH | 331 | 2000 | 2000 | 1700.07 | 2018.18 | 503.91 | 2522.09 |  | 3004.1514 | M/s Sri Chowdeshwari Concrete India Private Limited Kudulur Prasad Dinesh kumar | 6.27.2022 | 12.27.2023 |  | 20 | 13.25 | 12 | 90.57% | 1.25 | 2077.96 | 69.17% | 926.1914 | 12 Km Road work completed, 446 m DBM Work completed on LHS and 250m on RHS completed at mullahalli village, 2020 mts drain work completed and for Road Widening work, distmantling work to be taken up at Nallahalli Village limit | 2 |  | Z |  | Balance 1.250 KM Work under Progress. 22 Culverts completed and drain work completed. | 383 | 5982.2626
|  |  | Division Total |  |  | 4100 | 4100 | 3472.14 | 4198.78 | 1024.65 | 5223.43 |  | 6221.0072 | 15: 40.525; 16: 33.27; 17: 32.02; 19: 1.25; 20: 4580.91; 22: 1640.0972 | and instructed EE,PWD,Ramnagara special division to resolve the issue |  |  |  |  | 384 | 6531.8135
Ramanagara Division | [13 empty] | 16: 0 | [5 empty] | 385 | 1700.599
135 | 553 | A | Improvements to Hunasanahalli – Chikkanahalli( SH-3 Via Kanakapura, Ramanagara) , Magadi from Ch: km 82.67 to 94.40 km in Magadi Taluk of Ramanagara District. | SH-3 | 332 | 950 | 1950 | 1693.41 | 2045.15 | 508.45 | 2553.6 |  | 3041.2231 | .KADAIAH PRAKASH (KPJ CONSTRUCTIONS PRIVATE LIMITED ) | 9.2.2022 | 3.2.2024 |  | 12 | 12.24 | 12.24 | 100% | 0 | 2371.14 | 77.97% | 670.0831 | completed |  | 3 |  |  |  | 386 | 2182.2888
|  | B1 | Improvements to Hunasanahalli Chikkahalli Road SH -3 Via Kanakapura, Ramanagara, Magadi from Km 48.40 to Km 82.67 (In selected reaches) in Ramanagara Taluk of Ramanagara District. | [10 empty] | 15: 9.2; 16: 2.65; 17: 2.62; 18: 98.87%; 19: 0.03; 23: completed | [5 empty] | 387 | 3624.5778
|  | B2 | Improvements to NH 275-Channapatna to Nelamangala via kavanapura S.R.S betta, Avverahalli, Kailancha, Nagohalli, Hunasanahalli, Urgalli, Bidadi, Ch:5.20 to 35.70km (Change of road) | SH-3 | 334 | 1000 | [7 empty] | 16: 8.86; 17: 8.86; 18: 100%; 19: 0; 23: completed | [5 empty] | 388 | 3988.5745
|  |  | Division Total |  |  | 1950 | 1950 | 1693.41 | 2045.15 | 508.45 | 2553.6 |  | 3041.2231 | 15: 21.2; 16: 23.75; 17: 23.72; 19: 0.03; 20: 2371.14; 22: 670.0831 | [5 empty] | 389 | 2721.8236
Tumkur Division | [31 empty] | 390 | 3445.8654
136 | 554 | A | Improvements to Doddagangavadi Gate - Chowdanakuppe Road SH 111 from Km 12.00 to Km 15.25 (in selected reaches) in Kunigal Taluk of Tumakuru District | SH 111 | 350 | 350 | 1000 | 850.31 | 858.74 |  | 858.74 |  | 1027.3603 | Sri Rakshith Kempeere Gowda K Gowda & Company, Bangalore | 30.07.2022 | 29.06.2023 |  | 1.89 | 2.26 | 2.26 | 100% | 0 | 657.58 | 64.01% | 369.7803 | Road furniture work balance |  |  | AA |  |  | 391 | 3123.9012
|  | B | Improvements to MDR (old NH48) Road in Kunigal Town from Km 71.40 to Km 71.65 (in selected reaches) in Kunigal Taluk of Tumakuru District | KNL227 | 351 | 100 | [7 empty] | 15: 0; 16: 0; 17: 0; 18: 0%; 19: 0; 23: Work completed | [5 empty] | 392 | 4719.2524
|  | C | Improvements to MDR connecting from NH48-Join Anchepalya - yelagalavdi Road via mallagatta,Begur,Kundur, Rajgere, Boregowdanapallya from Km 0.00 to Km 10.00 (in selected reaches) & bridge at Ch 2.25 Km in Kunigal Taluk of Tumakuru District | KNL27 | 352 | 550 | [7 empty] | 15: 1.125; 16: 1.125; 17: 1.125; 18: 100%; 19: 0; 23: Road furniture work balance | [5 empty] | 393 | 5759.029
137 | 555 | A | Improvements to Bagepalli- Halaguru Road SH 94 from Km 140.00 to Km 141.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | SH 94 | 353 | 100 | 1000 | 847.55 | 1024.96 | 247.93 | 1272.89 |  | 1516.0117 | Sri Somashekara S N (M/s Athreya Construction), Bangalore | 20.06.2022 | 19.05.2023 | 29.03.2023 | 0.63 | 0.63 | 0.63 | 100% | 0 | 1496.24 | 98.7% | 19.7717 | Completed |  | 4 |  |  |  | 394 | 1351.2294
|  | B | Improvements to New SH road connecting from NH 206 to NH 4 Via Tumkur Chelur Bukkapatna from Km 0.00 to Km 13.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | NEW SH | 354 | 400 | [7 empty] | 15: 5.95; 16: 7.73; 17: 7.73; 18: 100%; 19: 0; 23: Completed | [5 empty] | 395 | 3555.9264
|  | C | Improvements to K K Road to Kalyanapura Road Via Lakkenahalli, Tavrakere, Honnenahalli MDR from Km 0.00 to Km 1.75 & Km 6.90 to Km 15.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | MDR | 355 | 500 | [7 empty] | 15: 3.78; 16: 3.78; 17: 3.78; 18: 100%; 19: 0; 23: Completed | [5 empty] | 396 | 1635.3826
138 | 556 | A | Improvements to MDR from NH-4 to join Aregujjanahalli Road Via Maidala from Km 0.00 to Km 9.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-219 | 356 | 250 | 1350 | 1147.63 | 1415.18 | 335.49 | 1750.67 |  | 2084.7494 | Sri Suresh S Kanaji, Bangalore | 01.07.2022 | 30.09.2023 | 23.05.2023 | 1.35 | 1.32 | 1.32 | 100% | 0 | 2119.58 | 101.7% | -34.8306 | Completed |  | 5 |  |  |  | 397 | 2099.54
|  | B | Improvements to SH 33 from Km 23.70 to Km 26.40 in selected reaches in Tumakuru Taluk of Tumakuru District | SH-33 | 357 | 250 | [7 empty] | 15: 1.7; 16: 1.346; 17: 1.346; 18: 100%; 19: 0; 23: Completed | [5 empty] | 398 | 5675.4018
|  | C | Improvements to Hillstation road MDR from Km 0.00 to Km 5.20 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-16 | 358 | 275 | [7 empty] | 15: 2.19; 16: 2.19; 17: 2.19; 18: 100%; 19: 0; 23: Completed | [5 empty] | 399 | 1743.1083
|  | D | Improvements to K.B Road to AJ Road Via Amruthagiri Bittanakurike MDR from Km 0.00 to Km 10.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-203 | 359 | 275 | [7 empty] | 15: 2; 16: 2.009; 17: 2.009; 18: 100%; 19: 0; 23: Completed | [5 empty] | 400 | 7345.1453
|  | E | Improvements to Tumkur - Urdigere Road MDR from Km 0.00 to Km 6.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-9 | 360 | 300 | [7 empty] | 15: 0.66; 16: 0.73; 17: 0.73; 18: 100%; 19: 0; 23: Completed | [5 empty] | 401 | 2827.0181
139 | 557 | A | Improvements to Tumkur Chelur Bukkapatna Road MDR from Km 22.00 to Km 30.00 (in selected reaches) in Gubbi Taluk of Tumakuru District | GBB3 | 361 | 500 | 1000 | 855.44 | 1013.06 | 99.91 | 1112.97 |  | 1327.4365 | Sri N G Ramalingegowda, (N G R Constructions),Tumkur | 13.07.2022 | 12.06.2023 | 31.01.2024 | 1.45 | 1.45 | 1.45 | 100% | 0 | 1353.75 | 102% | -26.3135 | Completed |  | 6 |  |  |  | 402 | 3377.5118
|  | B | Improvements to Gubbi Hebbur Road MDR from Km 3.00 to Km 7.725 (in selected reaches) in Gubbi Taluk of Tumakuru District | GBB12 | 362 | 500 | [7 empty] | 15: 4.67; 16: 4.67; 17: 4.67; 18: 100%; 19: 0; 23: Completed | [5 empty] | 403 | 4467.2565
140 | 558 | A | Improvements to Bochihalli-Turuvekere-Dabbegataa Road MDR from Km 0.00 to Km 1.20, Km 4.39 to Km 4.58, Km 14.70 to Km 15.40, Km 19.00 to Km 20.00, Km 20.70 to Km 30.00, Km 32.00 to Km 35.80 (in selected reaches) in Turuvekere Taluk of Tumakuru District | NEW SH | 363 | 1485 | 2250 | 1917.79 | 2299.36 | 223.27 | 2522.63 |  | 3008.3853 | Sri Rame Gowda H N, Hassan | 20.06.2022 | 19.12.2023 | 22.06.2023 | 10.43 | 12.456 | 12.456 | 100% | 0 | 2240.05 | 74.46% | 768.3353 | Completed |  | 7 |  |  |  | 404 | 3084.4495
|  | B | Improvements to Hirisave - Nonavinakere Road MDR from Km 65.80 to Km 78.80 (in selected reaches) in Turuvekere Taluk of Tumakuru District | TVK24 | 364 | 765 | [7 empty] | 15: 4.44; 16: 4.44; 17: 4.44; 18: 100%; 19: 0; 23: Completed | [5 empty] | 405 | 2442.9757
141 | 559 | A | Improvements to Mandya Hadagali Road SH 47 from Km 128.80 to Km 142.72 & Km 146.72 to Km 164.54 (in selected reaches) in Tiptur Taluk of Tumakuru District | SH 47 | 365 | 1200 | 2400 | 2058.45 | 2510.99 | 132.59 | 2643.58 |  | 3153.43 | Sri B M Rangegowda M/s BMRG Projects (India) Private Ltd., Channarayapatna. | 16.07.2022 | 15.01.2024 |  | 7.63 | 8.395 | 8.395 | 100% | 0 | 2476.19 | 78.52% | 677.24 | Completed |  | 8 |  |  |  | 406 | 1740.3169
|  | B | Improvements to New SH Road connecting from NH-275 to join SH-47 via Dasavara, Makali, Ujjani, hittalapura, Huliyurdurga, K Honnamachanahalli, Kilara, Paduvagere, Hanumapura, Kodavatti, Yediyur, Mayasandra, Turuvekere, Nonavinakere, Hedgarahalli from Km 85.86 to Km 100.26 (in selected reaches) in Tiptur Taluk of Tumakuru District (Yediyur Tiptur Road MDR from Km 37.20 to Km 51.00 in selected reaches in Tiptur Taluk of Tumakuru District) | TPT8 | 366 | 1200 | [7 empty] | 15: 7.57; 16: 7.57; 17: 7.57; 18: 100%; 19: 0; 23: Completed | [5 empty] | 407 | 3937.7375
142 | 560 |  | Improvements to Mandya Hadagali Road SH 47 from Km 164.54 to Km 195.05 (in selected reaches) in Chiknayakanahalli Taluk of Tumakuru District | SH 47 | 367 | 2300 | 2300 | 1974.47 | 2468.03 | 615.93 | 3083.96 |  | 3671.691 | Sri Raghupathy Pandeti (M/s FUTURO INFRA LLP), Bangalore | 20.06.2022 | 19.12.2023 |  | 12.45 | 12.6 | 12.6 | 100% | 0 | 3491.12 | 95.08% | 180.571 | Completed |  | 9 |  |  |  | 408 | 4479.9615
|  |  | Division Total |  |  | 11300 | 11300 | 9651.64 | 11590.32 | 1655.12 | 13245.44 |  | 15789.0643 | 15: 69.915; 16: 74.701; 17: 74.701; 19: 0; 20: 13834.51; 22: 1954.5543 | [5 empty] | 409 | 1999.2609
Madhugiri Division | [31 empty] | 410 | 2339.0058
143 | 561 |  | Improvements to Sira- Amarapura Road MDR from Km 0.00 to Km 42.20 (in selected reaches) in Sira Taluk of Tumakuru District | SRA3 | 162 | 2000 | 2000 | 1715.76 | 1954.76 | 0 | 1954.76 |  | 2334.9612 | Sri Sachin Kollur (M/s Kollur Gurunath Construction Infra Private Limited), Bidar | 14.07.2022 | 13.01.2024 |  | 12.25 | 12.25 | 12.25 | 100% | 0 | 786.21 | 33.67% | 1548.7512 | Road furniture work under progress |  |  |  |  | BB | 411 | 2462.8637
144 | 562 |  | Improvements to Midigeshi-Chandanadur Road MDR from Km 38.00 to Km 47.70 (in selected reaches) in Madhugiri Taluk of Tumakuru District | MDG -9 | 163 | 1000 | 1000 | 855.6 | 1009.34 | 235.19 | 1244.53 |  | 1482.6799 | Sri C R Girish (Ram And Company), Bangalore | 03.06.2022 | 02.05.2023 |  | 7.12 | 8.32 | 8.32 | 100% | 0 | 1409.09 | 95.04% | 73.5899 | Completed |  | 10 |  |  |  | 412 | 1607.274
145 | 563 | A | Improvements to Bagepalli- Halaguru Road SH 94 from Km 94.57 to Km 103.87 (in selected reaches) in Koratagere Taluk of Tumakuru District | SH 94 | 164 | 550 | 1600 | 1370.81 | 1369.86 | 136.24 | 1506.1 |  | 1799.8438 | Sri C R Girish (Ram And Company), Bangalore | 2.09.2022 | 1.12.2023 |  | 3.33 | 3.33 | 3.33 | 100% | 0 | 1837.71 | 102.1% | -37.8662 | Completed |  | 11 |  |  |  | 413 | 2496.4161
|  | B | Improvements to New SH road connecting from NH 48 (Nelahalu) to SH 158 (Chikkamaluru) Road Via Koratagere, Byrenahalli from Km 20.00 to Km 25.00 (in selected reaches) in Koratagere Taluk of Tumakuru District | NEW SH | 165 | 400 | [7 empty] | 15: 1.9; 16: 2.825; 17: 2.825; 18: 100%; 19: 0; 23: Completed | [5 empty] | 414 | 2578.1989
|  | C | Improvements to Byrenahalli - Thondebavi Road MDR from Km 0.00 to Km 13.10 (in selected reaches) in Koratagere Taluk of Tumakuru District | KTG -8 | 166 | 650 | [7 empty] | 15: 4.67; 16: 3.53; 17: 3.53; 18: 100%; 19: 0; 23: Completed | [5 empty] | 415 | 2437.7411
146 | 564 | A | Improvements to Kumta-Kadamadagi Road SH 48 from Km 352.00 to Km 392.16 (in selected reaches) in Pavagada-Taluk of Tumakuru District | SH 48 | 167 | 750 | 1000 | 855.85 | 900.6 | 89.81 | 990.41 |  | 1182.8224 | Sri B B Umesha, Bangalore | 07.07.2022 | 31.12.2024 |  | 4.145 | 4.65 | 4.65 | 100% | 0 | 844.56 | 71.4% | 338.2624 | Completed |  |  | 17 |  |  | 416 | 1728.6245
|  | B | Improvements to Pavagada Hindpur MDR from Km 0.00 to Km 29.60 (in selected reaches) in Pavagada Taluk of Tumakuru District | PVG-4 | 168 | 250 | [7 empty] | 15: 1.235; 16: 1.383; 17: 1.383; 18: 100%; 19: 0; 23: Completed | [5 empty] | 417 | 2121.4372
|  |  | Division Total |  |  | 5600 | 5600 | 4798.02 | 5234.56 | 461.24 | 5695.8 |  | 6800.3073 | 15: 34.65; 16: 36.288; 17: 36.288; 20: 4877.57; 22: 1922.7373 | [5 empty] | 418 | 2563.1896
Chikballapura Division | [31 empty] | 419 | 3687.7209
147 | 565 | A | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 87.70 to Km 106.80 (in selected reaches) in Bagepalli Taluk of Chikballapura District | SH 05 | 368 | 1000 | 3000 | 2572.17 | 3062.3 | 752.63 | 3814.93 |  | 4544.1096 | Sri C.R Girish Ram & Company Engineers and Contractors, Bangalore | 27.06.2022 | 26.12.2023 |  | 5.9 | 8.9 | 8.9 | 100% | 0 | 4265.93 | 93.88% | 278.1796 | Road furniture work under progress |  |  | 42 |  |  | 420 | 2008.0109
|  | B | Improvements to Chinthamani- K.Y Road Via Bikkanahalli, N.Kotturu, Kotagal, Sujjanahalli, Nandhanahosalli, Paapatimmanahalli New MDR from Km 3.20 to Km 13.00 (in selected reaches) in Chinthamani Taluk of Chikballapura District | NEW MDR | 369 | 1000 | [7 empty] | 15: 8.6; 16: 8.225; 17: 8.225; 18: 100%; 19: 0; 23: Road furniture work under progress | [5 empty] | 421 | 2946.9947
|  | C | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 78.00 to Km 86.50 (in selected reaches) in Sidlagatta Taluk of Chikballapura District | SH 05 | 370 | 1000 | [7 empty] | 15: 5.65; 16: 5.65; 17: 5.65; 18: 100%; 19: 0; 23: Road furniture work under progress | [5 empty] | 422 | 1993.9782
148 | 566 |  | Improvements to Chinthamani (SH 82) to Gauribidanuru connecting Road Via Cheluru, Bagepalli, Yallodu, Mallenahalli Cross, Vatadahosahalli Road New SH from Km 80.40 to Km 90.30 & Km 95.80 to Km 103.90 (in selected reaches) in Gauribidanuru Taluk of Chikballapura District | NEW SH | 371 | 1000 | 1000 | 859.92 | 900.57 | 212.56 | 1113.13 |  | 1327.6993 | Sri Jayaprakash, (Jayaprakash Engineers And Contractors),Bangalore | 01.07.2022 | 31.05.2023 | 28.03.2023 | 8.1 | 8.475 | 8.475 | 100% | 0 | 1272.27 | 95.83% | 55.4293 | Completed |  | 12 |  |  |  | 423 | 976.8344
149 | 567 | A | Improvements to Vijayapura- Nandhi Road New SH from Km 0.00 to Km 5.40 (in selected reaches) in Chikballapura Taluk of Chikballapura District | NEW SH | 372 | 800 | 2300 | 1964.56 | 2138.64 | 297.27 | 2435.91 |  | 2906.8283 | Sri Jayaprakash, (Jayaprakash Engineers And Contractors),Bangalore | 2022-11-29 | 2024-05-28 |  | 5.05 | 5.051 | 5.051 | 100% | 0 | 2002.72 | 68.9% | 904.1083 | Completed |  | 13 |  |  |  | 424 | 1789.2667
|  | B | Improvements to Melur- Chadalapura Road MDR from Km 7.00 to Km 13.00 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR17 | 373 | 600 | [7 empty] | 15: 4.2; 16: 4.2; 17: 4.2; 18: 100%; 19: 0; 23: Completed | [5 empty] | 425 | 1568.6681
|  | C | Improvements to SH-58 to Chickballapur connecting Road via Namagondlu and Kethenahally Road MDR from Km 33.30 to Km 35.50 & Km 41.10 to Km 44.00 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR15 | 374 | 500 | [7 empty] | 15: 4.1; 16: 3.9; 17: 3.9; 18: 100%; 19: 0; 23: Completed | [5 empty] | 426 | 2341.4
|  | D | Improvements to Gudibanda to join SH-58 and on to state border Via Ramapatna, Mandikal, Nallakadirenahally, Venkatapura, D.Palya and Melya MDR from Km 6.40 to Km 11.40 Km & Km 18.00 to Km 20.20 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR21 | 375 | 400 | [7 empty] | 15: 3.5; 16: 3.685; 17: 3.685; 18: 100%; 19: 0; 23: Completed | [5 empty] | 427 | 2670.6599
|  |  | Division Total |  |  | 6300 | 6300 | 5396.65 | 6101.51 | 1262.46 | 7363.97 |  | 8778.6373 | 15: 45.1; 16: 48.086; 17: 48.086; 20: 7540.92; 22: 1237.7173 | [5 empty] | 428 | 2570.2356
Kolar Division | [31 empty] | 429 | 3114.545
150 | 568 | A | Improvements to Bangarapete - Kamasamudram Road MDR from Km 0.90 to Km 3.45, Km 4.695 to Km 9.50 & Km 10.00 to Km 11.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT11 | 376 | 800 | 3000 | 2542.09 | 2643.8 | 653.33 | 3297.13 |  | 3932.6087 | Sri Amaravaram Channa Reddy (ACR projects), Bangalore | 30.07.2022 | 29.01.2024 |  | 5.16 | 6.615 | 6.615 | 100% | 0 | 2602.97 | 66.19% | 1329.6387 | Completed |  |  | DD |  |  | 430 | 684.4228
|  | B | Improvements to Budhikote Kanamanahalli Road Via Balamande MDR from Km 0.00 to Km 3.00 & Km 16.25 to Km 20.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT 10 | 377 | 200 | [7 empty] | 15: 1.87; 16: 1.87; 17: 1.87; 18: 100%; 19: 0; 23: Completed | [5 empty] | 431 | 1845.5885
|  | C | Improvements to Devanahalli-Kempapura Road SH-96 from Km 83.00 to Km 95.51 (in selected reaches) in K G F Taluk of Kolar District | SH 96 | 378 | 600 | [7 empty] | 15: 2.98; 16: 3.4; 17: 3.4; 18: 100%; 19: 0; 23: Completed | [5 empty] | 432 | 666.7015
|  | D | Improvements to Station Road MDR from Km 0.20 to Km 1.80 (in selected reaches) in K G F Taluk of Kolar District | BGT26 | 379 | 200 | [7 empty] | 15: 1.6; 16: 1.6; 17: 1.6; 18: 100%; 19: 0; 23: Completed | [5 empty] | 433 | 1437.7994
|  | E | Improvements to K G F State fund Road MDR from Km 2.92 to Km 4.20 (in selected reaches) in K G F Taluk of Kolar District | BGT5 | 380 | 200 | [7 empty] | 15: 1.1; 16: 1.19; 17: 1.19; 18: 100%; 19: 0; 23: Completed | [5 empty] | 434 | 1545.713
|  | F | Improvements to Kolar- Malur- Hosur Road New SH from Km 12.60 to Km 22.50 (in selected reaches) in Malur Taluk of Kolar District | NEW SH | 381 | 1000 | [7 empty] | 15: 6.57; 16: 6.76; 17: 6.76; 18: 100%; 19: 0; 23: Completed | [5 empty] | 435 | 1356.077
151 | 569 |  | Improvements to Kolar- Malur- Hosur Road New SH from Km 0.00 to Km 12.60 (in selected reaches) in Kolar Taluk of Kolar District | NEW SH | 382 | 1000 | 1000 | 858.84 | 793.65 | 196.96 | 990.61 |  | 1183.1078 | Sri C Narayanaswamy (CNS Constructions), Kolar | 2022-11-04 | 2023-10-03 |  | 6.55 | 6.55 | 6.55 | 100% | 0 | 990.9 | 83.75% | 192.2078 | Completed |  | 14 |  |  |  | 436 | 1318.1891
152 | 570 | A | Improvements to Andhra Border K Bayyapalli to Andhra Border Road Via Rayalamana dinne, Mulabagal, Vammasandra, Gukunte, Shankarapura New SH from Km 3.20 to Km 14.60 & Km 33.35 to Km 33.80 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW SH | 383 | 800 | 3800 | 3234.93 | 3889.97 | 968.77 | 4858.74 |  | 5786.7542 | Sri B Bhaskar Naidu (Seethal Constructions), Bangalore | 02.07.2022 | 01.01.2024 |  | 5.7 | 5.835 | 5.835 | 100% | 0 | 5894.98 | 101.9% | -108.2258 | Completed | [5 empty] | 437 | 1681.3042
|  | B | Improvements to Mudavadi Kothamangal Road MDR from Km 14.32 to Km 21.04 (in selected reaches) in Mulabagal Taluk of Kolar District | MUL9 | 384 | 700 | [7 empty] | 15: 5.9; 16: 5.35; 17: 5.35; 18: 100%; 19: 0; 23: Completed |  | 15 |  |  |  | 438 | 623.8994
|  | C | Improvements to Mulabagal Punganur Road to Mulabagal Ramasandra connecting Road Via Byrakuru, Chikura Hosahalli, Rajendrahalli, Gudipalli, Nachahalli, Gukunte New MDR from Km 0.00 to Km 5.00 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW MDR | 385 | 300 | [7 empty] | 15: 2.45; 16: 2.108; 17: 2.108; 18: 100%; 19: 0; 23: Completed | [5 empty] | 439 | 978.1297
|  | D | Improvements to Kothapalli- Masthi Road SH 99 from Km 9.00 to Km 18.60 (in selected reaches) in Srinivaspura Taluk of Kolar District | SH 99 | 386 | 1100 | [7 empty] | 15: 7.45; 16: 7.6; 17: 7.6; 18: 100%; 19: 0; 23: Completed | [5 empty] | 440 | 1015.3469
|  | E | Improvements to Bayyapalli- Bandapalli Road MDR from Km 0.00 to Km 10.20 (in selected reaches) in Srinivaspura Taluk of Kolar District | SRI 9 | 387 | 900 | [7 empty] | 15: 10.2; 16: 10.115; 17: 10.115; 18: 100%; 19: 0; 23: Completed | [5 empty] | 441 | 185
|  |  | Division Total |  |  | 7800 | 7800 | 6635.86 | 7327.42 | 1819.06 | 9146.48 |  | 10902.4708 | 15: 57.53; 16: 58.993; 17: 58.993; 19: 0; 20: 9488.85; 22: 1413.6208 | [5 empty] | 442 | 1753.5855
|  |  | Bangalore Circle Total |  |  | 52100 | 52100 | 44496.32 | 51360.548 | 9460.9 | 60821.448 |  | 72504.3878 | 15: 371.009; 16: 374.309; 17: 369.124; 19: 5.185; 20: 52404.64; 22: 20099.7478 | [5 empty] | 443 | 1097.6707
Mysore Circle | [31 empty] | 444 | 874.5103
Mandya Division | [31 empty] | 445 | 1795.5607
153 | 571 | A | Improvements to Road from 142 Km of Sira-Najangudu to join 40th km of NH-48 Dudda road (MDR) from 0.00 km to 11.02 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 398 | 500 | 2000 | 1713.37 | 1711.76 | 312.53 | 2024.29 |  | 2416.9671 | Sri Kari Gowda C (M/s C.K.G Constructions Pvt Ltd.)Mysore | 04--07-2022 | 03--01-2024 |  | 3.63 | 5.75 | 5.75 | 100% | 0 | 2020.84 | 83.61% | 396.1271 | Work completed | [5 empty] | 446 | 1104.4462
|  | B | Improvements to Road from MN road to join BN road Via M K Road, Hulivana, Chamalapura, Keelara, Dodda Banasawadi, Chikka Banasawadi & Hodaghatta (MDR) from 3.80 km to 11.28 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 399 | 500 | [7 empty] | 15: 2.62; 16: 2.66; 17: 2.66; 18: 100%; 19: 0; 23: Work completed |  | 1 |  |  |  | 447 | 480.9574
|  | C | Improvements to Chinnayakanahalli- Tubinakere Road (MDR) from 1.10 km to 12.40 (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 400 | 200 | [7 empty] | 15: 1.55; 16: 1.55; 17: 1.55; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 448 | 1345.9772
|  | D | Improvements to BN Road to TM Hosur-Alagudu-Molenahalli-Koppalu Via Kodiyala-Yaliyur Road (Via T.M.Hosur) (MDR) from 9.00 km to 11.50 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 401 | 200 | [7 empty] | 15: 1.71; 16: 2.46; 17: 2.46; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 449 | 1861.8061
|  | E | Improvements to Srirangapatna chanarayapatna road darasaguppe road to join nelamane village (MDR) from 0.00 km to 2.60 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 402 | 200 | [7 empty] | 15: 1.167; 16: 1.167; 17: 1.167; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 450 | 2939.8404
|  | F | Improvements to Road joning Mandya - Madduru Taluk border Via Cheeranahalli (MDR) from km 1.20 km to 8.85 km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 403 | 200 | [7 empty] | 15: 1.695; 16: 1.72; 17: 1.72; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 451 | 1214.1802
|  | G | Improvements to Arakere - Mandya- Bannur road to Bannahally-Bettahally Road (MDR) from 0.00 km to 4.32 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 404 | 200 | [7 empty] | 15: 1.78; 16: 1.28; 17: 1.28; 18: 100%; 19: 0; 23: Asphalt work completed 0.5km, tackled in ORF | [5 empty] | 452 | 1193.8458
154 | 572 | A | Improvements to Road from M G M Road to Join K B Road Via K Shettihalli, Yadaganahalli, Sabbana Halli, Hebbakavadi Nala, Bheemana Halli, Bidara Hosahalli (MDR) from 0.00 km to 14.75 km (In Selected Reaches) in Madduru Taluk of Mandya District. | MDR | 405 | 500 | 1000 | 857.2 | 835.09 | 46.01 | 881.1 |  | 1053.8589 | Sri Kari Gowda C (M/s C.K.G Constructions Pvt Ltd.)Mysore | 04--07-2022 | 03-06--2023 |  | 4.1 | 4.04 | 4.04 | 100% | 0 | 735.53 | 69.79% | 318.3289 | Work completed |  | 2 |  |  |  | 453 | 994.0424
|  | B | Improvements to Road from Hebberelu Village to join Lingasandra Cross Via Byalada kere, Navile, Bettada Rangaswami Temple, Lingasandra (MDR) from 0.00 km to 12.50 km (In Selected Reaches) in Madduru Taluk of Mandya District. | MDR | 406 | 500 | [7 empty] | 15: 4.086; 16: 4.25; 17: 4.25; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 454 | 1716.9687
155 | 573 | A | Improvements to Bindiganavile -Kadabahalli Road to join Bindiganavile -Kadabahalli Road via Mangaravally, Bydarahalli, Acharyapura & Vaddarahatti (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 410 | 300 | 1000 | 855.98 | 844.3 | 80.8 | 925.1 |  | 1105.7588 | Sri K R Manjunatha (KRM Constructions) Mysore | 30.08.2022 | 29.07.2023 |  | 2.655 | 2.655 | 2.655 | 100% | 0 | 854.19 | 77.25% | 251.5688 | Work completed, Road furniture pending. | 3 | 3 |  |  |  | 455 | 563.7234
|  | B | Improvements to Bindiganavile-ayyarahalli road via garudanahalli road (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 411 | 300 | [7 empty] | 15: 2.512; 16: 2.512; 17: 2.512; 18: 100%; 19: 0; 23: Work completed, Road furniture pending. | [5 empty] | 456 | 557.5862
|  | C | Improvements to Mylarpatna to join NH 48 near Kalinganahalli gate (MDR) from 0.00 km to 7.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 412 | 400 | [7 empty] | 15: 3.458; 16: 4.6; 17: 3.458; 18: 75.17%; 19: 1.142; 23: BM completed | [5 empty] | 457 | 1630.6566
156 | 574 | A | Improvements to Road from 2/15Mile of S.A road to join Hariharapura-Lingapura (MDR) from 6.00 km to 36.50 km(In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 413 | 380 | 1750 | 1497.08 | 1497.21 | 161.73 | 1658.94 |  | 1982.281 | Sri K R Manjunatha (KRM Constructions) Mysore | 02.08.2022 | 02.11.2023 |  | 3.125 | 3.125 | 3.125 | 100% | 0 | 1665.82 | 84.04% | 316.461 | Road furnitures work pending | [5 empty] | 458 | 1335.5903
|  | B | Improvements to Road from K.R.Pet-Bandihole road to join Kikkeri-Mandagere road via Heggadahalli, Hoddarahalli, ICL Factory, Ramenahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 414 | 250 | [7 empty] | 15: 2.415; 16: 2.415; 17: 2.415; 18: 100%; 19: 0; 23: Road furnitures work pending | 4 |  | EE |  |  | 459 | 947.8156
|  | C | Improvements to Road from G.Boppanahalli – Halekothamaranahalli - Nayakanahalli, Malgur, Singapura. (MDR) from 4.50 km to 12.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 415 | 200 | [7 empty] | 15: 1.7; 16: 3.6; 17: 3.6; 18: 100%; 19: 0; 23: Work Completed | [5 empty] | 460 | 486.2514
|  | D | Improvements to Road to Join Somanahalli to Somanathapura Via Mamballi (MDR) from km 0.00 to km 1.90 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 416 | 150 | [7 empty] | 15: 1.115; 16: 1.04; 17: 1.04; 18: 100%; 19: 0; 23: work completed | [5 empty] | 461 | 1034.8802
|  | E | Improvements to Road from S.A road to join Gondihalli via Madapura (MDR) from km 6.00 to km 9.40 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 417 | 190 | [7 empty] | 15: 1.95; 16: 2.16; 17: 1.95; 18: 90.28%; 19: 0.21; 23: Work under progress | [5 empty] | 462 | 959.9878
|  | F | Improvements to Road from Nargonahalli to join Vitalapura via Giddanakoppalu, Gavimata, Kapanahalli (MDR) from km 0.00 to km 1.00 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 418 | 100 | [7 empty] | 15: 0.7; 16: 0.85; 17: 0.7; 18: 82.35%; 19: 0.15; 23: Work under progress | [5 empty] | 463 | 524.1119
|  | G | Improvements to Hosaholalu-Ballekere-Natanahalli road (MDR) from 7.50 km to 8.50 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 419 | 100 | [7 empty] | 15: 0.774; 16: 0.774; 17: 0.774; 18: 100%; 19: 0; 23: Road furnitures work pending | [5 empty] | 464 | 1537.3776
|  | H | Improvements to Road from Bookinakere to join Bommalapura via Chokanahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 420 | 240 | [7 empty] | 15: 2.3; 16: 3.03; 17: 3.03; 18: 100%; 19: 0; 23: Road furnitures work pending | [5 empty] | 465 | 1837.6146
|  | I | Improvements to Road from Shrirangapatna - Arasikere Road (SH-07) to join Goodehosahalli Via Anegola, Bolamaranahalli & Kadahemmige (MDR) from 3.00 km to 6.71 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | SH | 421 | 140 | [7 empty] | 15: 1.344; 16: 1.344; 17: 1.344; 18: 100%; 19: 0; 23: Road furnitures work pending | [5 empty] | 466 | 4719.9351
157 | 575 | A | Improvements to Mandya- Thendekere from 17.00 km to 19.50 km (In Selected Reaches) in Pandavapura Taluk of Mandya District. |  | 426 | 200 | 1000 | 855.06 | 1081.23 | 245.02 | 1326.25 |  | 1579.1006 | C Ashoka (STG INFRASYS PRIVATE LIMITED), Mandya | 23.08.2022 | 23.07.2023 |  | 1.413 | 1.635 | 1.635 | 100% | 0 | 1534.12 | 97.15% | 44.9806 | Road furnitures work pending |  | 4 |  |  |  | 467 | 2079.9997
|  | B | Improvements to Mundalakoppalu-Chikanahalli-Halebidu-Neelanahalli Road on the Kerettonnur-Melukote road due to Mandya- Thendekere from 0.00 km to 7.40 km (In Selected Reaches) in Pandavapura Taluk of Mandya District. |  | 427 | 300 | [7 empty] | 15: 1.827; 16: 4.5; 17: 4.5; 18: 100%; 19: 0; 23: Road furnitures work pending | [5 empty] | 468 | 2401.452
|  | C | Improvements to road from 7th KM of Mandya-Hadagali Road to join 15th Km Mandya-Hadagali Road via Mallamanayakkattu – Gadadar – Modacakkanahalli - Kannatti from 0.00 km to 5.00 km (In Selected Reaches) in Mandya Taluk of Mandya District. |  | 428 | 500 | [7 empty] | 15: 3.36; 16: 4.2; 17: 4.2; 18: 100%; 19: 0; 23: Road furnitures work pending | [5 empty] | 469 | 728.97
158 | 598 | A | Road joining NH-209 to SH-84 Via Halaguru, K. Belluru, Rudrakshipura, Madduru, Koppa & Kowdle (SH) | NH/SH | 407 | 100 | 1000 | 856.29 | 865.04 | 85.36 | 950.4 |  | 1135.6179 | Sri Chikkaboregowda Karigowda (CKG Constructions Private Limited), Mysore | 04--07--2022 | 03--06-2023 |  | 1.085 | 1.29 | 1.29 | 100% | 0 | 1071.65 | 94.37% | 63.9679 | Road furnitures work pending | [5 empty] | 470 | 1607.5225
|  | B | Improvements to NH-209 to join Pandithhalli-Shimsha (PS) road (MDR) | MDR | 408 | 400 | [7 empty] | 15: 3.134; 16: 3.19; 17: 3.19; 18: 100%; 19: 0; 23: Road furnitures work pending |  | 5 |  |  |  | 471 | 1555
|  | C | Improvements to Road from Malavalli to join 16th km of Mandya-Bannur road (Sulthan Road) (MDR) (In Selected Reaches) in Malavally Tq | MDR | 409 | 500 | [7 empty] | 15: 1.58; 16: 2.03; 17: 2.03; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 472 | 2595.7215
159 | 606 |  | Improvements to K R Pete-Sravanabelagola Road MDR from 0.00km to 2.30 km (in Selected reaches) in K R Pete taluk of Mandya District | MDR |  | 457.79 | 550 | 550 | 475.8 | 46.18 | 521.98 |  | 625.0224 | Sri R.P. Revanna, K.R Pete | 13.03.2023 | 12.02.2024 |  | 1.255 | 1.255 | 0.5 | 39.84% | 0.755 | 158.68 | 25.39% | 0 | 500 Meter completed Remaing work yet to start Land Problem | 5 | 6 |  |  |  | 473 | 1738.0015
|  |  | Division Total |  |  | 8207.79 | 8300 | 7184.98 | 7310.43 | 977.63 | 8288.06 |  | 9898.6067 | 15: 60.04; 16: 71.082; 17: 68.825; 19: 1.502; 20: 8040.83; 22: 1391.4343 | [5 empty] | 474 | 2791.0359
Mysore Division | [31 empty] | 475 | 568.3158
160 | 576 | A | Improvements to Koratagere-Bavali Road (SH-33) in Mysore Town | SH | 426 | 250 | 2500 | 2153.14 | 2611.65 |  | 2611.65 |  | 3117.3169 | Sri Govinde Gowda (Govinde Gowda AND Sons) Mysore | 27.06.2022 | 26.12.2023 |  | 2.5 | 2.41 | 2.41 | 100% | 0 | 3372.5 | 108.2% | -255.1831 | Completed |  | 7 |  |  |  | 476 | 1562.1746
|  | B | Improvements to Bagalakote-Biligiriranganabetta (SH-57) in Nanjanagudu Tq | SH | 427 | 1350 | [7 empty] | 15: 9.31; 16: 9.33; 17: 9.33; 18: 100%; 19: 0; 23: Completed | [5 empty] | 477 | 733.4064
|  | C | Improvements to Ramanathapura - Therakanambi (SH-86) in Nanjanagudu Tq | SH | 428 | 700 | [7 empty] | 15: 4.15; 16: 4.15; 17: 4.15; 18: 100%; 19: 0; 23: Completed | [5 empty] | 478 | 1016.6974
|  | D | Improvements to Hura road to Ramanathapura-Therakanambi SH via Hanchipura road (MDR) (In Selected Reaches) in Nanjanagudu Tq | MDR | 429 | 200 | [7 empty] | 15: 1.52; 16: 1.55; 17: 1.55; 18: 100%; 19: 0; 23: Completed | [5 empty] | 479 | 1272.6572
161 | 577 | A | Improvements to KRS to join Mysore Ring Road in Mysore Tq |  | 430 | 500 | 2000 | 1716.13 | 1866.97 |  | 1866.97 |  | 2231.3751 | Sri Aravindkumar (Aravindakumar P B), Mandya | 05.08.2022 | 04.02.2024 |  | 4.13 | 4.13 | 4.13 | 100% | 0 | 2093.25 | 93.81% | 138.1251 | Completed |  | 8 |  |  |  | 480 | 2701.5517
|  | B | Improvements to Gungral Chathra to K Nagenahalli (MDR) in Mysore Tq | MDR | 431 | 250 | [7 empty] | 15: 2.13; 16: 2.13; 17: 2.13; 18: 100%; 19: 0; 23: Completed | [5 empty] | 481 | 655.4594
|  | C | Improvements to Mysore Naguvanahalli Road (MDR) in Mysore Tq | MDR | 432 | 250 | [7 empty] | 15: 1.525; 16: 1.525; 17: 1.525; 18: 100%; 19: 0; 23: Completed | [5 empty] | 482 | 1003.2693
|  | D | Improvements to Shrirangapatna - MM Hills Road (SH-79) in TNPura Tq | SH | 433 | 500 | [7 empty] | 15: 1.35; 16: 1.35; 17: 1.35; 18: 100%; 19: 0; 23: Completed | [5 empty] | 483 | 2295.6898
|  | E | Improvements to B.M. Road to Beedanahalli-Hanumanalu-Maragowdanahalli to Sulthan road (MDR) in TN Pura Tq | MDR | 434 | 200 | [7 empty] | 15: 0.8; 16: 0.8; 17: 0.8; 18: 100%; 19: 0; 23: Completed | [5 empty] | 484 | 1104.3661
|  | F | Improvements to Mugur -Bannhalli hundi road (MDR) in TN Pura Tq | MDR | 435 | 300 | [7 empty] | 15: 6.5; 16: 6.5; 17: 6.5; 18: 100%; 19: 0; 23: Completed | [5 empty] | 485 | 455
162 | 595 | A | Improvements to Sira - Nanjangudu (SH-84) from 227.00 km to 227.75 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | SH | 422 | 200 | 1000 | 859.94 | 854.48 |  | 854.48 |  | 1022.4926 | Sri Chikkaboregowda Karigowda (CKG Constructions Private Limited), Mysore | 27.06.2022 | 26.05.2023 |  | 0.75 | 0.75 | 0.75 | 100% | 0 | 813.4 | 79.55% | 209.0926 | Completed |  | 9 |  |  |  | 486 | 1643.5221
|  | B | Improvements to Hanumapura to join Doddahomma via P.Marahalli-Avathalapura (MDR) from 1.00 km to 8.00 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | MDR | 451 | 800 | [7 empty] | 15: 5.98; 16: 5.98; 17: 5.975; 18: 99.92%; 19: 0.005; 23: Completed | [5 empty] | 487 | 2821.5968
|  |  | Division Total |  |  | 5500 | 5500 | 4729.21 | 5333.1 | 0 | 5333.1 | 0 | 6371.1845 | 15: 40.645; 16: 40.605; 17: 40.6; 19: 0.005; 20: 6279.15; 22: 92.0345 | [5 empty] | 488 | 380.4594
Hunsur Division | [31 empty] | 489 | 1724.0565
163 | 578 | A | Improvements to Kattemalalavadi to Sannenahalli - Kothegala Road MB Road from 0.00 km to 3.60 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 388 | 350 | 3200 | 2749.81 | 2958.59 |  | 2958.59 |  | 3536.5631 | Sri V T Dinesh Kumar, Kodagu | 30.07.2022 | 29.01.2024 |  | 2.425 | 2.425 | 2.425 | 100% | 0 | 3083.19 | 87.18% | 453.3731 | Completed |  | 10 |  |  |  | 490 | 2443.5596
|  | B | Improvements to Hunsur - Dharmapura Road (MDR) from 0.00 km to 14.40 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. | MDR | 389 | 300 | [7 empty] | 15: 1.82; 16: 1.82; 17: 1.82; 18: 100%; 19: 0; 23: Completed | [5 empty] | 491 | 5590.0102
|  | C | Improvements to Tarikallu - Singaramaranahally Road (Via Karimuddanahally) (MDR) from 10.00 km to 13.50 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. | MDR | 390 | 300 | [7 empty] | 15: 1.85; 16: 1.85; 17: 1.85; 18: 100%; 19: 0; 23: Completed | [5 empty] | 492 | 3912.9911
|  | D | Improvements to Rathnapuri to Hosavaranchi Road Via Kuddinirumuddanahalli join road from 0.30 km to 9.50 Km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 391 | 250 | [7 empty] | 15: 1.88; 16: 1.88; 17: 1.88; 18: 100%; 19: 0; 23: Completed | [5 empty] | 493 | 2945.4085
|  | E | Improvements to KR Nagar-Kattemalavadi-Channamgere Road via Makodu Ravandur- Attigodu- Sangarashettihalli from 23.71 km to 27.71 km (In Selected Reaches) in Piriyapatna Taluk of Mysore District. |  | 392 | 400 | [7 empty] | 15: 2.7; 16: 2.7; 17: 2.7; 18: 100%; 19: 0; 23: Completed | [5 empty] | 494 | 3132.9168
|  | F | Improvements to Poonadahalli – Chikkaneru - Haranahalli from 9.20 km to 15.20 km (In Selected Reaches) in Piriyapatna Taluk of Mysore District. |  | 393 | 600 | [7 empty] | 15: 3.8; 16: 3.8; 17: 3.8; 18: 100%; 19: 0; 23: Completed | [5 empty] | 495 | 128.5714
|  | G | Improvements to Koratagere - Bavali SH-33 from 213.37 km to 278.00 km (In Selected Reaches) in H D Kote Taluk of Mysore District. | SH | 394 | 1000 | [7 empty] | 15: 6.2; 16: 6.2; 17: 6.2; 18: 100%; 19: 0; 23: Completed | [5 empty] | 496 | 3285.1096
164 | 579 | A | Improvements to Holenarasipura – Saligrama - KR Nagara SH-108 from 19.50 km to 32.00 km (In Selected Reaches) in KR Nagar Taluk of Mysore District. | SH | 395 | 400 | 1000 | 858.04 | 766.1 |  | 766.1 |  | 918.1728 | Sri K .R Santhosh, Mysore | 30.07.2022 | 29.06.2023 | EOT Proposal Received from Division | 2.7 | 2.7 | 2.7 | 100% | 0 | 325.16 | 35.41% | 593.0128 | Completed | [5 empty] | 497 | 1207.0764
|  | B | Improvements to Ramanathapura - Terakanambi Road to Mysore - Bhantwala Road Via- Chikkahanasoge- Channamgere (SH) from 0.00 km to 7.00 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. | SH | 396 | 300 | [7 empty] | 15: 2.275; 16: 2.275; 17: 2.275; 18: 100%; 19: 0; 23: Completed |  |  | FF |  |  | 498 | 1411.7467
|  | C | Improvements to K R Nagar - Bettadapura road to join K R Nagar-Malali-Hosakote-Ravanduru Road (SH) from 8.00 km to 17.50 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. | SH | 397 | 300 | [7 empty] | 15: 2.1; 16: 2.1; 17: 2.1; 18: 100%; 19: 0; 23: Completed | [5 empty] | 499 | 2416.0093
|  |  | Division Total |  |  | 4200 | 4200 | 3607.85 | 3724.69 | 0 | 3724.69 |  | 4454.7359 | 15: 27.75; 16: 27.75; 17: 27.75; 19: 0; 20: 3408.35; 22: 1046.3859 | [5 empty] | 500 | 2894.7496
Chamarajanagar Division | [31 empty] | 501 | 1295.2799
165 | 580 | A | Improvements to Badanaguppe - Nanjedevanapura Road (MDR) from 3.80 km to 5.80 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. |  | 440 | 200 | 1000 | 858.22 | 931.12 |  | 931.12 |  | 1112.8994 | Sri Budanoor Thammaiah Sidappa ( M/s B T SIDDAPPA AND CO ) Mandya | 15 .07.2022 | 14.06.2023 |  | 1.64 | 1.64 | 1.64 | 100% | 0 | 1168.58 | 105% | -55.6806 | Completed |  | 11 |  |  |  | 502 | 1744.702
|  | B | Improvements to Kodimole Basavanapura Hebbasur Byadamudlu-Basavapura Road (MDR) from 1.60 km to 6.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 436 | 450 | [7 empty] | 15: 4.32; 16: 4.32; 17: 4.32; 18: 100%; 19: 0; 23: Completed | [5 empty] | 503 | 2932.6625
|  | C | Improvements to Santhemarahalli Hebbasur Road (MDR) from 6.95 km to 10.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 437 | 200 | [7 empty] | 15: 1.06; 16: 1.06; 17: 1.06; 18: 100%; 19: 0; 23: Completed | [5 empty] | 504 | 2824.2696
|  | D | Improvements to Udigala Kothalavadi V Swamy Hills Road (MDR) from 7.20 km to 8.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District |  | 438 &439 | 150 | [7 empty] | 15: 0.98; 16: 0.98; 17: 0.98; 18: 100%; 19: 0; 23: Completed | [5 empty] | 505 | 2591.4202
166 | 581 | A | Improvements to Road joining T Narasipura (Muguru Cross) to Santhemaralli (SH) from 0.00 km to 8.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | SH | 440 | 1000 | 1800 | 1551.14 | 1824.5 | 181.04 | 2005.54 |  | 2392.162 | Sri Chandrashekar, (M/s KRCM Buildcon Private Limited) Chamarajnagar | 27.06.2022 | 26.12.2023 |  | 3.49 | 3.49 | 3.49 | 100% | 0 | 1776.89 | 74.28% | 615.272 | Completed |  | 12 |  |  |  | 506 | 3128.1373
|  | B | Improvements to Kuderu-Thoravalli-Kesthuru-Mariyala Road (MDR) from 1.50 km to 9.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 441 | 800 | [7 empty] | 15: 6.03; 16: 6.059; 17: 6.059; 18: 100%; 19: 0; 23: Completed | [5 empty] | 507 | 2350.0432
167 | 582 | A | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Tammadahalli, Kengaki, Sagade, Maliyuru, Kulagana, Kebbepura, Hemmaragala & Badanavalu (SH) from 15.45 km to 18.45 km & 22.450 km to 29.45 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | SH | 442 | 670 | 2250 | 1935.38 | 2400.54 |  | 2400.54 |  | 2864.6097 | Sri Nayan Reddy | 2022-08-30 | 2024-02-29 |  | 5.14 | 5.14 | 5.14 | 100% | 0 | 1653.67 | 68.89% | 1210.9397 | Work completed | 6 |  | GG |  |  | 508 | 2291.3492
|  | B | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Veeranapura, Harave & Heggawadi (SH) from 15.16 km to 18.80 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | SH/NH | 443 | 240 | [7 empty] | 15: 2.1; 16: 2.1; 17: 2.1; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 509 | 1807.6942
|  | C | Improvements to Road joining Kurubara Hundi Via Hasaguli, Manchahalli (MDR) from 3.00 km to 5.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 444 | 100 | [7 empty] | 15: 0.55; 16: 0.55; 17: 0.55; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 510 | 1108.3304
|  | D | Improvements to Road joining Taggaluru to Bettadamadalli (MDR) from 6.70 km to 9.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 445 | 100 | [7 empty] | 15: 0.865; 16: 0.865; 17: 0.865; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 511 | 1476.8906
|  | E | Improvements to Road joining Chirakanahalli road to Kurubara Hundi (MDR) from 0.00 km to 2.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 446 | 130 | [7 empty] | 15: 0.965; 16: 0.965; 17: 0.965; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 512 | 2480.5305
|  | F | Improvements to Road joining NH-766 to Shrikantapura road Via Chikkahundi (MDR) from 0.00 km to 8.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 447 | 810 | [7 empty] | 15: 6.15; 16: 6.15; 17: 5.44; 18: 88.46%; 19: 0.71; 23: Work completed except 700m, due to huge pipe line shifting and land litigations. | [5 empty] | 513 | 978.4319
|  | G | Improvements to Hullapura Kadbur Road (MDR) from 13.00 km to 17.00 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 448 | 200 | [7 empty] | 15: 1.535; 16: 1.535; 17: 1.535; 18: 100%; 19: 0; 23: Work completed | [5 empty] | 514 | 526.1464
168 | 583 | A | Improvements to Hanur to Ellemalla-Kodalli Via Tabetta from 0.00 km to 16.40 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. |  | 449 | 1000 | 2000 | 1721.42 | 1623.13 |  | 1623.13 |  | 1943.7313 | Sri K .R Santhosh Mysore | 30.07.2022 | 29.01.2024 |  | 6 | 6 | 6 | 100% | 0 | 1237.35 | 63.66% | 706.3813 | Completed |  | 13 |  |  |  | 515 | 1184.6984
|  | B | Improvements to Shrirangapatna - MalaiMahadeshwara Betta Road (SH-79) from km 107.50 km to 128.60 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. | SH | 450 | 1000 | [7 empty] | 15: 6.6; 16: 6.6; 17: 6.6; 18: 100%; 19: 0; 23: Completed | [5 empty] | 516 | 2165.3925
|  |  | Division Total |  |  | 7050 | 7050 | 6066.16 | 6779.29 | 181.04 | 6960.33 |  | 8313.4024 | 15: 47.425; 16: 47.454; 17: 46.744; 19: 0.71; 20: 5836.49; 22: 2476.9124 | [5 empty] | 517 | 1527.8854
|  |  | Mysore Circle Total |  |  | 24957.79 | 25050 | 21588.2 | 23147.51 | 1158.67 | 24306.18 |  | 29037.9295 | 15: 175.86; 16: 186.891; 17: 183.919; 19: 2.217; 20: 23564.82; 22: 5006.7671 | [5 empty] | 518 | 1356.3292
Hassan Circle | [31 empty] | 519 | 1820.3199
Hassan Division | [31 empty] | 520 | 1934.8378
169 | 584 |  | Improvements to Huliyaru -Keralapura Road SH-102 from Km 15.00 to Km 70.88 (In Selected Reaches) in Arsikere Taluk of Hassan District. | SH-102 | 301 | 2000 | 2000 | 1706.05 | 2079.45 | 206.48 | 2285.93 |  | 2725.5813 | Sri Ramesh Kumar Kothari, Hassan | 14.07.2022 | 13.01.2024 |  | 12.235 | 12.235 | 12.235 | 100% | 0 | 2322.1 | 85.2% | 403.4813 | Completed. |  | 1 |  |  |  | 521 | 620.0463
170 | 585 |  | Improvement to Arkalgudu -Kodagu Border Road from Km 0.00 to Km 28.80 (In Selected Reaches) in Arakalgud Taluk of Hassan District | ARK-34 | 302 | 2000 | 2000 | 1714.84 | 2026.59 |  | 2026.59 |  | 2419.7054 | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 16.86 | 16.86 | 16.86 | 100% | 0 | 1718.95 | 71.04% | 700.7554 | Completed |  | 2 |  |  |  | 522 | 928.0059
171 | 586 | A | Improvement to Road from Siddapura to join TDH Road via Kithanakere Barekattahalli MDR from Km 0.00 to km 7.00 (In Selected reaches) in Hassan Taluk of Hassan District | HSS-247 | 303 | 600 | 2150 | 1824.94 | 2224.07 |  | 2224.07 |  | 2654.5506 | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 5.04 | 5.04 | 5.04 | 100% | 0 | 2993.34 | 112.8% | -338.7894 | Completed | [5 empty] | 523 | 1491.1461
|  | B | Improvement to Road from Heragu road to join Dudda Shanthigrama Road via Kommanahalli Handrangi S.Devalapura Chattanahalli and Alasinahalli MDR from Km 0.00 to Km 9.00 (In Selected Reachs) in Hassan Taluk of Hassan District | MDR | 304 | 600 | [7 empty] | 15: 5.428; 16: 5.428; 17: 5.428; 18: 100%; 19: 0; 23: Completed |  | 3 |  |  |  | 524 | 2883.6066
|  | C | Improvements to road from Markuli cross to Athichowdenahall road via varasanahalli from 0.00 Km to 12.00 Km ( in Selected Reach ) in Holenarasipura taluk of Hassan District. | HNP-18 | 305 | 950 | [7 empty] | 15: 9.47; 16: 9.47; 17: 9.47; 18: 100%; 19: 0; 23: Completed | [5 empty] | 525 | 2915.9404
172 | 587 | A | Improvements to Hirisave- Kerisave from B.M.Road to join Kabbali Road MDR from Km 7.30 to Km 20.00 (In Selected Reaches) in Channarayapatna Taluk of Hassan District. | CRP-206 | 306 | 550 | 1000 | 849.86 | 1052.05 | 104.86 | 1156.91 |  | 1379.1935 | Sri Ramegowda H.N, Channarayapatna | 14.07.2022 | 13.06.2023 |  | 4.64 | 5.54 | 5.54 | 100% | 0 | 1231.16 | 89.27% | 148.0335 | Completed. |  | 4 |  |  |  | 526 | 2143.2658
|  | B | Improvements to B.M.Road to Turuvekere Border Via M.Honnenahalli-Dodderi-Hebbalalu-Akkanahalli Cross - Shettihalli -Ungaragere-Kabbali Mundakanahalli-Didaga- D.Tumakuru-Bidarekere-Uggenahalli Road MDR from Km 24.00 to Km 30.00 (In Selected Reaches) in Channarayapatna Taluk of Hassan District | CRP-42 | 307 | 450 | [7 empty] | 15: 4.16; 16: 3.81; 17: 3.81; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 527 | 2806.4755
173 | 588 | A | Improvement to Road from Kandli -Bylahalli -Bikkodu Road to TDH Road via Kyathanahalli Ugane Marenahalli Chinnenahalli Shankadakoppalu Mudlapura, Kabbli, Krishnapura MDR from Km.0.00 to Km 18.00 (In Selected Reaches) in Hassan Taluk of Hassan District. | HSS-203 | 308 | 950 | 2300 | 1967.47 | 2400.41 |  | 2400.41 |  | 2864.9864 | Sri P.R Thimmegowda, Channarayapatna | 14.07.2022 | 13.01.2024 |  | 7.038 | 7.038 | 7.038 | 100% | 0 | 3053.96 | 106.6% | -188.9736 | Completed. |  | 5 |  |  |  | 528 | 841.9729
|  | B | Improvement to Road from Alur to join Thuruvekere Via Doddakanagal, Vertikere, Kadadaravally, Kondajji, Yalagunda, Nittur-Bageshpura, Chindenahalligadi, Dasrigatta from Km 0.00 to Km 124.00 (In Selected Reaches) in Hassan Taluk of Hassan District | New SH | 309 | 575 | [7 empty] | 15: 3.71; 16: 3.71; 17: 3.71; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 529 | 791.2691
|  | C | Improvement to Road from Kandli - Bylahalli -Bikkodu Road to MSF Road from Km.4.30 to Km 7.00 (In Selected Reaches) in Hassan Taluk of Hassan District. | HSS 207 | 310 | 375 | [7 empty] | 15: 2.55; 16: 2.55; 17: 2.55; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 530 | 2386.4723
|  | D | Improvement to Road from Ring road to Adlimane road to Thamalapura - Chikkakondagula - Kopplu - Thejur - Shanka Cross to HHAPC road through Rachanahalli Road from Km 0.00 to Km 9.00(In Selected reaches) in Hassan Taluk of Hassan District | HSS2 & VR | 311 | 400 | [7 empty] | 15: 2.4; 16: 2.4; 17: 2.4; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 531 | 504.4653
174 | 589 | A | Improvements to Adgoor Sankenahalli Road MDR from Km 0.00 to Km 12.00 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-12 | 315 | 600 | 1800 | 1533.36 | 1868.7 |  | 1868.7 |  | 2230.3971 | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 3.995 | 3.995 | 4 | 100% | 0 | 1557.23 | 69.82% | 673.1671 | Completed. | [5 empty] | 532 | 2360.9039
|  | B | Improvements to Road from NH-75 to join NH-173 from Km 70.00 to Km 91.10 (In Selected Reaches) (Halebeedu Gangooru Road from Km 0.00 to Km 8.00) and C M Road to Rajanashiriyuru MDR from Km 0.00 to Km 4.90 (In Selected Reaches) in Belur Taluk of Hassan District. | New SH | 316 | 800 | [7 empty] | 15: 5.67; 16: 5.67; 17: 5.67; 18: 100%; 19: 0; 23: Completed. |  | 6 |  |  |  | 533 | 7037.0205
|  | C | Improvements to Road from B T Road to join KBPB MDR from Km 0.00 to Km 6.70 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-58 | 317 | 100 | [7 empty] | 15: 0.93; 16: 0.93; 17: 0.93; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 534 | 1324.915
|  | D | Improvements to road from B.T Road to C.M Road Shivaladahalli MDR from 0.00km to 6.00km ( in selected reaches) in Belur Taluk of Hassan District. | BLR-307 | 318 | 150 | [7 empty] | 15: 1.5; 16: 1.5; 17: 1.5; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 535 | 4079.7387
|  | E | Imrovements to road to C.M road to Hanike K B Hall Road via Mallanahalli, Mukthganne Honnenahalli MDR from 0.00km to 6.30km (in Selected reaches) in Belur Taluk of Hassan District. | BLR-28 | 319 | 150 | [7 empty] | 15: 1.3; 16: 1.3; 17: 1.3; 18: 100%; 19: 0; 23: Completed. | [5 empty] | 536 | 3737.8057
175 | 597 | A | Improvements to Hanbal -Devrunda Road MDR from km 0.00 to km 12.60 (in selected reaches) in Sakleshpura Taluk of Hassan District. |  | 312 | 750 | 1500 | 1272.37 | 1361.2 | 135.82 | 1497.02 |  | 1787.5032 | Sri Rajesab Imamasab Banagar, Haveri | 14.07.2022 | 13.10.2023 |  | 5.62 | 5.62 | 5.62 | 100% | 0 | 1400.41 | 78.34% | 387.0932 | Completed |  | 7 |  |  |  | 537 | 1373.072
|  | B | Improvement to Road from BM Road to Ningegowdana koppalu shattihalli MDR from 7.00 Km to 16.00 Km (In Selected Reaches) in Hassan Taluk of Hassan District. |  | 314 | 750 | [7 empty] | 15: 5.873; 16: 5.873; 17: 5.873; 18: 100%; 19: 0; 23: Completed | [5 empty] | 538 | 1400.4361
|  |  | Division Total |  |  | 12750 | 12750 | 10868.89 | 13012.47 | 447.16 | 13459.63 |  | 16061.9175 | 15: 98.419; 16: 98.969; 17: 98.974; 20: 14277.15; 22: 1784.7675 | [5 empty] | 539 | 3703.9703
Kodagu Division | [31 empty] | 540 | 1098.1237
176 | 590 |  | Improvements to Hunsur-Talakaveri Road SH-90 from Ch 21.60 km to 61.00 km (selected reaches) in VirajpeteTaluk of Kodagu District | SH-90 | 321 | 1350 | 2300 | 1975.07 | 2407.87 | 240.22 | 2648.09 |  | 3157.3744 | Sri Manuganahalli Shivanna Revanna, Annapoorneshwari Construciton, Mysore | 24.06.2022 | 23.12.2023 |  | 16 | 17.35 | 17.35 | 100% | 0 | 2498.36 | 79.13% | 659.0144 | Completed |  | 1 |  |  |  | 541 | 2799.2382
|  | B | Improvements to Konanur - Makutta SH-91 from Ch 50.26 to to 75.00 km (selected reaches) in Virajpete Taluk of Kodagu District. | SH-91 | 322 | 950 | [7 empty] | 15: 5.83; 16: 6.118; 17: 6.118; 18: 100%; 19: 0; 23: Completed | [5 empty] | 542 | 354.3363
177 | 591 |  | Improvements to Virajapete-Byndoor State Highway-27 from Ch 82.00 Km to 104.00 Km(selected reaches) in Somwarpete Taluk of Kodagu district | SH27 | 323 | 1175 | 1175 | 1005.99 | 1227.22 | 122.29 | 1349.51 |  | 1609.0408 | Sri Nagaraj M T, Arakalagud, Hassan |  |  |  | 14.37 | 16.77 | 16.77 | 100% | 0 | 1512.64 | 94.01% | 96.4008 | Completed |  | 2 |  |  |  | 543 | 1685.9252
178 | 592 | A | Improvements to Virajapete-Byndoor State Highway-27 road from Ch 53Km to 60.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | SH27 | 324 | 400 | 1125 | 962.02 | 1164.2 | 116.42 | 1280.62 |  | 1527.0242 | Sri Purushotham Rai, Somwaarpete, Kodagu | 16.06.2022 | 15.12.2023 |  | 4.5 | 4.5 | 4.5 | 100% | 0 | 1232.17 | 80.69% | 294.8542 | Completed |  | 3 |  |  |  | 544 | 848.2085
|  | B | Improvements to Gopalpur-Banavara-Hebbale road from 2.00 Km to 7.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | upgraded road | 325 | 325 | [7 empty] | 15: 3.3; 16: 3.34; 17: 3.34; 18: 100%; 19: 0; 23: Completed | [5 empty] | 545 | 3563.2824
|  | C | Improvements to Konanur - Makutta road State Highway 91 from 32.00 Km to 36.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | SH 91 | 326 | 400 | [7 empty] | 15: 2.85; 16: 3.31; 17: 3.31; 18: 100%; 19: 0; 23: Completed | [5 empty] | 546 | 151.1974
|  |  | Division Total |  |  | 4600 | 4600 | 3943.08 | 4799.29 | 478.93 | 5278.22 | 0 | 6293.4393 | 15: 46.85; 16: 51.388; 17: 51.388; 19: 0; 20: 5243.17; 22: 1050.2693 | [5 empty] | 547 | 21.6098
|  |  | Hassan Circle Total |  |  | 17350 | 17350 | 14811.97 | 17811.76 | 926.09 | 18737.85 | 0 | 22355.3567 | 15: 145.269; 16: 150.357; 17: 150.362; 19: 0; 20: 19520.32; 22: 2835.0367 | [5 empty] | 548 | 180.7379
|  |  | South Total |  |  | 174207.79 | 174300 | 149255.47 | 173208.408 | 24223.825 | 197432.233 | 0 | 235435.7353 | 15: 1237.738; 16: 1270.098; 17: 1239.767; 19: 29.581; 20: 186145.85; 22: 48823.5429 | [5 empty] | 549 | 219.0906
|  |  | South & North Total |  |  | 349882.79 | 349975 | 300160.39 | 351869.334 | 48455.015 | 400322.369 | 9783.56 | 477339.0451 | 15: 2249.41; 16: 2319.058; 17: 2269.647; 19: 49.411; 20: 389088.49; 22: 86722.3995 | [5 empty] | 550 | 514.1661
[9 empty] | 475.79 |  |  |  | 477339.0451 | 15: 0; 16: 2293.65 | [5 empty] | 551 | 1444.8636
[6 empty] | 345490 |  |  | 352345.124 | 5204.1908 |  |  | 235435.7353 | 16: 49.411; 17: 49.411; 20: 5105.21; 21: 172070.0978 | [5 empty] | 552 | 1912.1215
[10 empty] | 405526.5598 |  |  |  | 11: 5124.97; 22: 367292.92 | [5 empty] | 553 | 1414.6043
|  |  |  | -49.411 |  | 4392.79 |  |  |  | 478521.3406 | 560451.3166 |  |  | 20: 383983.28 |  |  |  |  | 31184467000 | 554 | 355.8085
[5 empty] | 498.04 | [5 empty] | 5604.5132 |  |  | 11: 50.5405 |  |  |  |  | 31097687775 | 555 | 770.1369
[9 empty] | 70469.0248 |  | 405926.8822 |  |  | 11: 400372.9095; 17: 49.411; 22: 4523.17; 23: 4055.17 |  |  | 468 |  | 86779225 | 556 | 1580.5503
[5 empty] | 714.602 |  |  |  | 422814.1488 |  |  |  |  | 19: 547.451; 20: -21795.57; 22: 16510.86; 23: 14200.47 |  |  | 2310.39 |  |  | 557 | 901.6526
[5 empty] | 353059.726 |  | 0 | [6 empty] | 22: 160096.98; 23: 157786.59 |  |  | 2310.39 |  |  | 558 | 1430
[14 empty] | 15: 2294.601; 22: 340409.57; 23: 338099.18 |  |  | 2310.39 |  |  | 559 | 1645.3062
[32 empty] | 560 | 2382.7559 | bar: 22
[32 empty] | 561 | 442.2903
[14 empty] | 18: 556.793 | [5 empty] | 562 | 1017.3915
[14 empty] | 20: 49.411 | [5 empty] | 563 | 1785.0458
[14 empty] | 13: 967.102; 16: -20.237 | [5 empty] | 564 | 658.886
[14 empty] | 13: 59.483 | [5 empty] | 565 | 2926.2208
[14 empty] | 15: 142 | [5 empty] | 566 | 847.27
[32 empty] | 567 | 1753.4537
[32 empty] | 568 | 1617.9332
[32 empty] | 569 | 884.1342
[32 empty] | 570 | 2715.3299
[32 empty] | 571 | 1162.9886
[32 empty] | 572 | 733.8697
[32 empty] | 573 | 407.2903
[32 empty] | 574 | 1644.5011
[32 empty] | 575 | 1607.3328
[32 empty] | 576 | 3165.0224
[32 empty] | 577 | 1548.2395
[32 empty] | 578 | 1473.5106
[14 empty] | 11: 3403.88 | [5 empty] | 579 | 369.2673
[14 empty] | 11: 3136.16 | [5 empty] | 580 | 702.9002
[14 empty] | 11: 3829.49 | [5 empty] | 581 | 1092.7362
[14 empty] | 11: 3434.27; 13: 0 | [5 empty] | 582 | 655.7065
[14 empty] | 11: 1858.79 | [5 empty] | 583 | 940.8818
[14 empty] | 11: 15586.41 | [5 empty] | 584 | 1366.1676
[14 empty] | 12: #REF! | [5 empty] | 585 | 1433.0401
[32 empty] | 586 | 1726.4351
[32 empty] | 587 | 1193.579
[32 empty] | 588 | 1558.3995
[32 empty] | 589 | 529.0973
[32 empty] | 590 | 1260.8566
[32 empty] | 591 | 777.5545
[32 empty] | 592 | 1114.1748
[32 empty] | 593 | 1135
[32 empty] | 594 | 1268.6179
[32 empty] | 595 | 840.4232
[32 empty] | 596 | 452.6612
[32 empty] | 597 | 930.7612
[32 empty] | 598 | 180
[32 empty] | 599 | 1110.8069
[32 empty] | 600 | 1746.1693
[32 empty] | 601 | 1233.5464
[32 empty] | 602 | 60
[32 empty] | 603 | 337.1873
[32 empty] | 604 | 2229.6766
[32 empty] | 605 | 1607.0003
[32 empty] | 606 | 25

## Width Wise
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE | [17 empty] | 10.75
Package wise Details of Phase-4 Stage-2 | [15 empty] | 10.75 |  | 10.525
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE | [15 empty] | 8.965 |  | 0.225
SHDP - PHASE - IV Stage-2 PROGRESS REPORT
As on 28th FEBURARY 2026
0 | PKG No |  | Name of Work | SH/ MDR | Length Proposed as per DPR in Km | Length Proposed as per VO in Km | Total Length Completed |  |  |  | Total
[7 empty] | 14 m Width | 7 m Width | 5.50 m Width | 3.75 m Width | [5 empty] | -1.7
Kalaburagi Circle | [15 empty] | -1.63
Bidar Division | [15 empty] | 0
1 | 429 | A | Improvements to SH-122 Maharastra Border Murki-Aurad-Handarki from Km 0.00 to Km 62.40 (in selected reaches) in Aurad Taluka of Bidar District. | SH- 122 | 9.7 | 11.4 |  | 11.4 |  |  | 11.4 |  | 0 | 0 |  | -0.67
|  | B | Improvements to SH-34 Aurad - Sadashivagad, from Km 21.00 to Km 72.50 (in selected reaches) in Bhalki Taluka of Bidar District. | SH-34 | 4.41 | 6.04 |  | 4.41 | 1.63 |  | 6.04 |  | 0 | 0 |  | 0 |  | 7.16
2 | 430 |  | Improvements to road Rajeshwar to Mudbi New SH from Km 0.00 to Km 15.00 (in selected reaches) in Basavakalyan Taluka of Bidar District. | New SH | 3.6 | 3.6 |  | 3.6 |  |  | 3.6 |  | 0 | 0 |  | -4 |  | wrong entry
3 | 601 |  | Improvements to road SH-126 A.P Border with Putpak-Bhosaga from Km 147.20 to Km 156.00 (in selected reaches) in Basavakalyan Taluka of Bidar District. | SH-126 | 4.5 | 5.17 |  |  | 5.17 |  | 5.17 |  | 0 | 0 |  | 0
4 | 602 |  | Improvements to SH-122 Maharastra Border -Murki-Aurad-Handarki from Km 117.80 to Km 123.31 (in selected reaches) in Chitaguppa Taluka of Bidar District | SH -122 | 4 | 4 |  | 4 |  |  | 4 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 26.21 | 30.21 | 0 | 23.41 | 6.8 | 0 | 30.21 |  | 0 | 0 |  | -0.78
Kalaburagi Division | [12 empty] | 0 | 0 |  | 0
5 | 431 |  | Improvements to SH-124 Barkhed-Bilagi, from Km 0.00 to Km 71.15 (in selected reaches) in Aland Taluka of Kalaburagi District. (Via Bhimapur, Kamanalli, Lingadalli-Madan Hipparga-Nimbal) | SH-124 | 8.55 | 8.55 |  | 8.55 |  |  | 8.55 |  | 0 | 0 |  | 0
6 | 432 | A | Improvements to road Bankalga cross to Mashal, MDR from Km 0.00 to Km 14.00 (in selected reaches) in Afzalpur Taluka of Kalaburagi District. | AFZ204 | 2.92 | 3.7 |  |  | 3.7 |  | 3.7 |  | 0 | 0 |  | 0
|  | B | Improvements to S.H-124 Barked-Bilagi from Km 102.00 to Km 108.00 (in selected reaches) in Afzalpur Taluka of Kalaburagi District. | SH- 124 | 1.93 | 1.93 |  |  | 1.93 |  | 1.93 |  | 0 | 0 |  | 0
7 | 603 |  | Improvements to MDR from NH-218, Kattisangavi to Yenkanchi (SH-16) via Madari-Yengunta- Naribol-Biral(B)-Ganvar-Chigralli-ijeri-alur-kadkol-manashivanagi from Km 40.00 to 50.00 Km (in selected reaches) ( from chigralli cross to yedrami )in Jevargi Taluka of Kalaburagi District. | JEW45 | 5.2 | 5.2 |  |  | 5.2 |  | 5.2 |  | 0 | 0 |  | 0
8 | 433 |  | Improvements to road from Kadagunchi-Bodana road (MDR) to Tonasalli (SH125), MDR from Km 0.00 to Km17.50 and Km 26.50 to Km 35.00 (in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | New MDR | 9.935 | 10.435 |  |  | 9.935 |  | 9.935 |  | 0 | 0 |  | 0
9 | 434 | A | Improvements to road Narona -Chinchansoor, MDR from Km 0.00 to Km 6.30 (in selected reaches) in Aland Taluka of Kalaburagi District. | ALD11 | 1.85 | 1.85 |  | 1.85 |  |  | 1.85 |  | 0 | 0 |  | -0.78
|  | B | Improvements to road from Malgathi cross to Bolewad via Nippani, MDR from Km 0.00 to Km 4.20 and Km 16.00 to Km 24.00 (in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | GUL205 | 3.92 | 3.92 |  |  | 3.92 |  | 3.92 |  | 0 | 0 |  | 0
|  | C | Improvements to road from Aurad B(on NH-218) to Jambga(B) (on SH-51) MDR from Km 0.00 to Km 10.70(in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | GUL15 | 3.97 | 3.97 |  | 3.97 |  |  | 3.97 |  | 0 | 0 |  | 0.36
|  |  | Division Total |  | 38.275 | 39.555 | 0 | 14.37 | 24.685 | 0 | 39.055 |  | 0 | 0 |  | 0
Sedam Division | [12 empty] | 0 | 0 |  | -0.92
10 | 435 |  | Improvements to SH-122 Maharastra Border - Murki-Aurad-Handarki, from Km 153.80 to Km 164.00 Km and Km 207.00 to Km 218.77 (in selected reaches) in Sedam/ Chincholi Taluka of Kalaburagi District | SH-122 | 11.81 | 11.45 |  |  | 11.45 |  | 11.45 |  | 0 | 0 |  | -0.56
11 | 600 |  | Improvements to SH-32 Umarga border-Aland-VK Salagar-Mahagaon -Sulepet road, from Km 80.00 to Km 118.00 via Herur Cross - Sulepet (in selected reaches) in Chincholi Taluka of Kalaburagi District. | SH-32 | 13.83 | 13.83 |  |  | 13.83 |  | 13.83 |  | 0 | 0 |  | 0
12 | 436 |  | Improvements to SH -126 Telangana border - Putpak-Bhosaga,from Km 60.00 to Km 75.00 (Chittapur Bus Depot to Tengali Cross SH-10) (in selected reaches) in Chittapur Taluka of Kalaburagi District. | SH-126 | 3.4 | 4.32 |  | 4.32 |  |  | 4.32 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 29.04 | 29.6 | 0 | 4.32 | 25.28 | 0 | 29.6 |  | 0 | 0 |  | -0.36
Yadgir Division | [12 empty] | 0 | 0 |  | 0
13 | 437 | A | Improvements to road Maharastra Border to Raichur Border (Markel- Kollur-Bilihar) road, MDR from Km 3.00 Km 9.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | New SH | 4.75 | 4.75 |  |  | 4.75 |  | 4.75 |  | 0 | 0 |  | -2.2
|  | B | Improvements to road NH-150A to SH-127 Sangam-Raichur Border, MDR from Km16.30 to Km 57.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | SHA35 | 4.95 | 5.31 |  | 0.36 | 4.95 |  | 5.31 |  | 0 | 0 |  | -0.47
|  | C | Improvements to road Kurakunda to Bilhar Via Hortur, Halgera, Godihal Kumanur, Arjunagi, Kandalli, MDR from Km 0.00 to Km 13.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | MDR | 2.3 | 2.3 |  |  | 2.3 |  | 2.3 |  | 0 | 0 |  | 0
14 | 438 |  | Improvements to SH-16 Sindagi - Kodangal from Km 125.22 to KM 155.62 (in selected reaches) in Gurmitkal Taluka of Yadgir District. | SH-16 | 9.5 | 11.7 |  | 11.7 |  |  | 11.7 |  | 0 | 0 |  | 32.65
15 | 439 | A | Improvements to road Devargonal to Gogi, MDR from Km 12.80 to Km 20.80 (in selected reaches) in Shahpur Taluka of Yadgir District. | SHA55 | 3.82 | 4.29 |  |  | 4.29 |  | 4.29 |  | 0 | 0 |  | 29.62
|  | B | Improvements to road Bheemarayan Gudi to Bijaspur, MDR from Km 10.00 to KM 17.50 (in selected reaches) in Shahpur Taluka of Yadgir District. | SHA59 | 1.5 | 1.5 |  |  | 1.5 |  | 1.5 |  | 0 | 0 |  | 24.28
16 | 440 |  | Improvements to SH-155 from Pattan cross(SH-10) to Narayanapura dam Km110.00 to KM 167.30 (in selected reaches) in Shorapur Taluka of Yadgir District. | SH-155 | 48.52 | 15.87 |  |  | 15.87 |  | 15.87 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 75.34 | 45.72 | 0 | 12.06 | 33.66 | 0 | 45.72 |  | 0 | 0 |  | 0
|  |  | Kalaburgi Circle Total |  | 168.865 | 145.085 | 0 | 54.16 | 90.425 | 0 | 144.585 |  | 0 | 0 |  | 0.43
Ballary Circle | [12 empty] | 0 | 0 |  | 0
Ballary Division | [12 empty] | 0 | 0 |  | 0
17 | 441 | A | Improvements to MDR road of Ballary - Kalyanadurga Ch.0.80 km to 2.00 Km ( double road) in Ballary taluk, Ballary district. | MDRBER6 | 1.08 | 0.65 | 0.65 |  |  |  | 0.65 |  | 0 | 0 |  | -0.6
|  | B | Improvements MDR road from Kampli-Kurugodu-Kuduthini-Haraginidoni-Ballary-Aluru via Moka village Devalapura -Kamalapura from ch.88.99 km to 90.39 Km (in selected reaches) in Ballary taluk,Ballary district. | SH-132(BER19) | 1.06 | 1.06 | 1.06 |  |  |  | 1.06 |  | 0 | 0 |  | 0
19 | 443 | A | Improvements to road from maruthi camp somasandra Siddammanahalli to Yarangalli village road chainage 5.00 Km to 9.50 Km in kurugodu Taluk Bellary District. | MDR | 2.05 | 2.05 |  |  | 2.05 |  | 2.05 |  | 0 | 0 |  | -8.9
|  | B | Improvements to road from Kanivathimmalapura village to Ramasagara road Chainage 0.00 Km to 4.00 Km in Kampli Taluk Bellary District | MDR | 1.4 | 2 |  |  | 0.12 | 1.88 | 2 |  | 0 | 0 |  | 8.52
|  | C | Improvements to road from Kuduthini to orvaayi cross road chainage 15.00 Km to 18.50 Km in Kurgodu Taluk Bellary District. | MDR | 1.35 | 1.35 |  |  | 1.35 |  | 1.35 |  | 0 | 0 |  | -0.55
20 | 444 | A | Improvements to MDR road of Kudadarahaal-Haccholi-Vatthuvarani, ch.0.00 km to 17.40 Km(in selected reaches) in Siraguppa taluk, Ballary district. | MDR SRG5 | 5 | 13.9 |  |  | 13.9 |  | 13.9 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR road from Kudadarahaal to Nadanga via Vatthuvarani ,kothalachintha ch.0.00 km to 9.50 Km (in selected reaches) in Siraguppa taluk , Ballary district. | MDR SRG-29 DROPPED | 8.52 | [7 empty] | 0 | 0 |  | -0.7
|  |  | Division total |  | 20.46 | 21.01 | 1.71 | 0 | 17.42 | 1.88 | 21.01 |  | 0 | 0 |  | -0.019
Vijayanagara Division | [12 empty] | 0 | 0 |  | 0.11
18 | 442 | A | Improvements to MDR road from Nallapura to Hosachinnapura ch.6.00 km to 9.40 Km in Hospet taluk ,Ballary district. | MDR HSP-217 | 2.53 | 3.23 |  |  | 3.23 |  | 3.23 |  | 0 | 0 |  | -1.84
|  | B | Improvements to MDR road Connecting Ingalagi village to NH -63 km0.00 to 3.00 Km in Hospet taluk, Ballary district | MDR HSP-221 | 1.93 | 1.949 |  | 0.745 | 0.885 | 0.319 | 1.949 |  | 0 | 0 |  | -1.21
|  | C | Improvements to MDR road from Devalapura -Kamalapura , ch.10.00 km to 18.00 Km (in selected reaches) in Hospet taluk, Ballary district. | MDR HSP-14 | 7.74 | 7.63 |  |  | 7.63 |  | 7.63 |  | 0 | 0 |  | 0.065
|  | D | Improvements to MDR Road from Kondanayakanahalii to Danapura via Nagenahalli Thanda, ch.0.00 km to 6.00 Km in Hosapete taluk, Ballary district | MDR HSP 213 | 2.78 | 5.7 |  |  | 2.59 | 2.03 | 4.62 |  | 0 | 0 |  | 0.89
21 | 445 | A | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommnahally from ch.131.00 to ch 137.00 km, ch.140.00 to Ch 141.15.00 km & ch.153.00 to Ch 156.15 km in Kudligi taluk , Ballary district. | SH-131(KDL44) | 7.1 | 8.31 |  |  | 8.31 |  | 8.31 |  | 0 | 0 |  | 0.13
|  | B | Improvements MDR road from Hosahalli to Kanamadagu via Hagaribommanahalli from ch.1.22 Km to ch .7.30 km & ch.7.70km to Ch 8.75 km in Kudligi taluk ,Ballary district. | MDR KDL 13 | 6.67 | 6.605 |  |  | 6.605 |  | 6.605 |  | 0 | 0 |  | 0.18
22 | 593 |  | Improvements SH -151 road from Itagi to Kanchikere via Chitageri,Kadabageri, Arasikere from ch.7.80 km to ch 25.00 km in Harapanahalli taluk, Ballary district. | SH-151(HRP6) | 10.25 | 10.25 |  | 9.36 |  |  | 9.36 |  | 0 | 0 |  | -2.394
23 | 446 | A | Improvements SH -45 road connecting Arabhavi and Challakere Via Gokak,Naragunda ch.217.80 km to ch 225.02 km in Hadagali taluk, Ballary district. | SH-45(HDG202) | 6.63 | 6.5 |  |  | 6.5 |  | 6.5 |  | 0 | 0 |  | 0
|  | B | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommanahalli from ch.159.00 km to ch 169.30 in Kudalagi taluk,Ballary district. | SH-131(KDL44) | 5.41 | 5.23 |  | 0.33 | 4.9 |  | 5.23 |  | 0 | 0 |  | -0.35
|  |  | Division total |  | 51.04 | 55.404 | 0 | 10.435 | 40.65 | 2.349 | 53.434 |  | 0 | 0 |  | -0.7
Koppal Divison | [12 empty] | 0 | 0 |  | -3.53
24 | 447 |  | Improvements MDR road from Hosahalli to Koppala via Hirekasawadi,Halavarthi ch.0.00 km to ch 19.00 in Koppal taluk Koppal district. | MDR 206(KOP206) | 3.36 | 3.71 |  | 3.71 |  |  | 3.71 |  | 0 | 0 |  | 2.15
25 | 599 |  | Improvement to SH-59 road from Kustagi- to Pattadakallu 0.00 km to 21.20 km ( in selected reaches) in Kushtagi taluk, Koppal district . | SH-59 | 5.3 | 6 | 0.72 | 0.28 | 5 |  | 6 |  | 0 | 0 |  | 0.89
26 | 448 | A | Improvements MDR road from Ginigera to Irkalagada ch.3.00 km to ch 13.00 (selected reaches) in Koppal taluk ,Koppal district. | MDR (KOP18) | 5.28 | 8.81 |  |  | 8.81 |  | 8.81 |  | 0 | 0 |  | -0.15
|  | B | Improvements MDR road from Gaddi to Hampasadurga upto NH-13 Ch.13.10 km to ch.15.90 km in Koppal taluk ,Koppal district. | MDR KOP219 | 2.15 | 2.15 |  |  |  |  | 0 |  | 0 | 0 |  | -5.24
|  | C | Improvements to SH-130 road from Yelburga-Kankagiri-Gangavathi-Munirabad,70.00km to 74.00 and 79.00 km to 81.90 km in Gangavathi taluk Koppal District. | SH-130 | 3.79 | 2.9 |  | 1.08 | 1.82 |  | 2.9 |  | 0 | 0 |  | 0.08
27 | 449 |  | Improvements to SH-63 road from Raravi-Beluru Ch. 58.22 km to ch.75.42 km ( in selected reaches) in Kanakagiri taluk,Koppal District. | SH-63(GAN94) | 9.97 | 10.21 | 0.46 | 9.66 |  |  | 10.12 |  | 0 | 0 |  | -6.85
28 | 450 | A | Improvements toMDR road from Kavalooru to Mangalore ch. 12.00 km to ch.14.50 & Ch.16.00 km to ch.23.80 ( in Selected reaches)Yelaburga taluk, Koppal district. | MDR YL 7 | 6.8 | 12.04 |  |  | 12.04 |  | 12.04 |  | 0 | 0 |  | 0
|  | B | Improvements to SH-129 road from Chikkahesaruru-Mudagal-Mungaragi ch. 85.20 km to 111.40 km ( in Selected reaches) in Yelaburga taluk ,Koppal district. | SH-129 | 4.65 | 4.57 |  |  | 4.57 |  | 4.57 |  | 0 | 0 |  | 0
|  |  | Division total |  | 41.3 | 50.39 | 1.18 | 14.73 | 32.24 | 0 | 48.15 |  | 0 | 0 |  | 0
Raichur Division | [12 empty] | 0 | 0 |  | 0
29 | 451 |  | Improvements to MDR road connecting Guragunta Gowdaruru, Machanur ,Yelaghatta to Hosuru Ch:0.00 km to 19.00 km ( in selected reaches) Lingasugur taluk, Raichur district. | MDR LIN 16 | 7.41 | 7.41 |  |  | 7.41 |  | 7.41 |  | 0 | 0 |  | 0
30 | 452 | A | Improvements to SH-14 road from Ramadurga - Manvi via Badami,Pattadakallu,Hulagunda Ch:227.80 km to 236.00 in Manvi taluk, Raichur district. | SH-14 | 2 | 2 |  |  | 2 |  | 2 |  | 0 | 0 |  | -1.19
|  | B | Improvements to MDR road from Kavithala to Veerapura cross via Anwari village, Ch:4.00 km to 13.30 km road via Anvaari village,in Lingasuguru& Manvi Taluk, Raichur district. | MAN 33 | 1.82 | 1.82 |  |  | 1.82 |  | 1.82 |  | 0 | 0 |  | -1.19
|  | C | Improvements to road from sindanooru taluk bappuru kuduthini lingasooguru ch KM 0.00 to 16.00 in Raichur District | LIN 206 | 5.22 | 5.22 |  |  | 5.22 |  | 5.22 |  | 0 | 0 |  | -0.03
31 | 453 |  | Improvements to road from SH-23 to Mukunda-Singapura road via Channahalli,Sindrampura, Mavinamadaguch. 0.00 km to 15.70km ( In selected reaches) in Sindanooru taluk ,Raichur district. | MDR-SIN228 | 4.71 | 5.9 |  |  | 5.9 |  | 5.9 |  | 0 | 0 |  | 0.004
32 | 454 | A | Improvements to MDR road from Gannadala to Jalahalli via Kakkaladoodi Kamaladinne, Maykaladoodi, Ch:0.00 km to 20.00km ( in Selected reaches) in Devadurga taluk, Raichur district. | MDR DEV 209 | 7.89 | 9.78 |  |  | 9.08 |  | 9.08 |  | 0 | 0 |  | -0.2
|  | B | Improvements to MDR road from Maladakallu cross Malledevaragoodda via karadigooda, Jagatagallu) Ch:0.00 km to 18.00 km ( In selected reaches) in Devadurga taluk ,Raichur district | MDR DEV 216 | 1.44 | 1.47 |  |  | 1.47 |  | 1.47 |  | 0 | 0 |  | 0
33 | 455 | A | Improvements to SH-61 road from Managooli-Bechaali upto NH-167 Ch. km 239.23 km to 241.19 km ( in Selected reaches) upto NH-167 in Raichur Taluk , Raichur district. | SH-61 | 1.02 | 1.016 |  |  | 1.016 |  | 1.016 |  | 0 | 0 |  | -1.82
|  | B | Improvements to road from SH-13 (NH-167) Yaragera Gillesooguru via Gannadala Ch KM 0.00 to 20.78 ( in Selected reaches) in Raichur Taluk ,Raichur district. | SH-13 | 2.7 | 2.9 |  |  | 2.9 |  | 2.9 |  | 0 | 0 |  | 0.55
|  | C | Improvements to road from NH-167 connecting H-127 via Ashapura Udumagal, Purathipli road CH KM 5.70 to 9.00 in Raicur Taluk, Raichur District. | MDR RA15 | 1.52 | 1.52 |  |  | 1.52 |  | 1.52 |  | 0 | 0 |  | 1.41
34 | 456 | A | Improvements to MDR road from Raichur-Buradipadha Ch:0.00 km to 6.00 km ( in Selected reaches) in Raichur Taluk ,Raichur district. | MDR RAI 6 | 1.78 | 3.6 | 1.78 | 1.82 |  |  | 3.6 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR road connecting Raichur and SH-127 via Ashapura, Purthipalli ch. 0.00 km to 5.00 km ( in Selected reaches) Raichur Taluk Raichur district | MDR RAI 5 | 1.85 | 1.45 | 1.3 |  |  |  | 1.3 |  | 0 | 0 |  | -2.466
|  | C | Improvements to MDR road from SH-167 ( Devasooguru Katagooda road) to Raichur -Yaklasapura via Ambavadi ch. 1.72 km to 3.10 km in Raichur taluk, Raichur District | MDR RAI 215 | 1.41 | 0 |  |  |  |  | 0 |  | 0 | 0 |  | -12.26
|  | D | Improvements to MDR road from Basavana bhavi circle of Raichur -Singanodi road to Vidhanasaba nagara Ricemill ,ch. 0.00 km to 8.00 km ( selected reaches) in Raichur taluk , Raichur District. | MDR RAI 206 | 1.11 | 1.11 | 1.11 |  |  |  | 1.11 |  | 0 | 0 |  | 0
|  |  | Division total |  | 41.88 | 45.196 | 4.19 | 1.82 | 38.336 | 0 | 44.346 |  | 0 | 0 |  | 0
|  |  | Ballary Circle Total |  | 154.68 | 172 | 7.08 | 26.985 | 128.646 | 4.229 | 166.94 |  | 0 | 0 |  | 0
Dharwad Cricle | [12 empty] | 0 | 0 |  | -0.58
Dharwad Division | [12 empty] | 0 | 0 |  | 0
35 | 457 | A | Improvements to Padubidri-Chikkalagudda SH-01 from Ch: 340.30 to 356.97 Km (in selected reaches) in Kalaghatagi taluk of Dharwad District. | SH-01 | 9.695 | 9.695 |  | 9.695 |  |  | 9.695 |  | 0 | 0 |  | -0.65
|  | B | Improvements to Managundi-Tadasinakoppa from Ch: 0.00 Km to 5.00 Km (in selected reaches) in Dharwad taluk of Dharwad District. | MDR | 2.04 | 2.62 |  |  | 2.62 |  | 2.62 |  | 0 | 0 |  | 0
36 | 458 | A | Improvements to Beedi-Belavanaki SH-56 from Ch: 62.40 to 69.28 Km (in selected reaches) in Navalagund taluk of Dharwad District. (B) | SH-56 | 6.42 | 6.42 |  |  | 6.42 |  | 6.42 |  | 0 | 0 |  | 0
|  | B | Improvements to Supa-Annigeri SH-28 from Ch:108.77 to 114.77 Km (in selected reaches) in Navalagund taluk of Dharwad District. | SH-28 | 1.53 | 2.18 |  |  | 2.18 |  | 2.18 |  | 0 | 0 |  | -3.972
|  | C | Improvements to Supa-Annigeri SH-28 from Ch: 84.70 to 99.30 Km (in selected reaches) in Hubballi taluk of Dharwad District. | SH-28 | 6.42 | 6.42 |  | 0.43 | 5.99 |  | 6.42 |  | 0 | 0 |  | 0
37 | 459 | A | Improvements to Samshi-Gudageri road from 0.0 to 11.0Km in Kundagol taluka | MDR | 6.45 | 6.45 |  |  | 6.45 |  | 6.45 |  | 0 | 0 |  | -0.12
|  | B | Improvements to Pashupatihal-Rottigavad MDR road Ch 0.0km to 3.18Km, 3.9 to 9.3Km and 11.00 to 13.5Km in Kundagol tq. | MDR | 5.73 | 9.702 |  |  | 9.702 |  | 9.702 |  | 0 | 0 |  | -0.02
|  | C | Improvements to Hireharakuni Shishuvinal road upto Kundagol tq limit (MDR) from Ch: 0.00 Km to 5.16 Km in Kundagol tq . | MDR | 3.75 | 3.75 |  |  |  | 3.75 | 3.75 |  | 0 | 0 |  | -0.289
|  | D | Improvements to Varur-Hindasageri via (NH-04) from Surashettikoppa road upto Hubballi city limit road (MDR) from Ch: 0.0 Km to 2.0Km (in selected reaches) in Hubballi tq of Dharwad District. | MDR | 1.6 | 1.72 |  |  | 1.6 | 0.12 | 1.72 |  | 0 | 0 |  | 0.144
38 | 460 | A | Improvements to Veerapura Toll-Manturu MDR road from Ch: 0.40 to 3.00 Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 2.08 | 2.1 | 2.1 |  |  |  | 2.1 |  | 0 | 0 |  | -0.302
39 | 461 | A | Improvements from Anand Nagar Main Road to Gokul Main Road ( opposite RN Shetty Factory) in Hubballi taluk of Dharwad District. | MDR | 1.301 | 1.59 |  | 1.59 |  |  | 1.59 |  | 0 | 0 |  | 0.54
|  | B | Improvements to BRTS Road to Jakka Reddy Hospital, Lokappana Hakkala, Railway Underpass connecting to NH Division Office Adjoining to Vidyanagar Police Station, Lakshmi Temple in Hubballi Dharwad Mahanagar, Hubballi tq of Dharwad District. | MDR | 2.29 | 2.146 |  |  |  | 2.146 | 2.146 |  | 0 | 0 |  | 0.7
|  | C | Improvements to Hubballi Basaveshwara Nagar Gokul Road to join Ravi Nagar Road in Hubballi taluk of Dharwad District. | MDR | 1.46 | 1.762 |  |  | 0.737 | 1.025 | 1.762 |  | 0 | 0 |  | 0
40 | 462 | A | PKG-462 Improvements to Beedi-Belavanaki SH-56 from Ch: 33.42 to 48.83Km (in selected reaches) in Dharwad taluk of Dharwad District. | SH-56 | 13.72 | 13.18 |  | 2.1 | 11.08 |  | 13.18 |  | 0 | 0 |  | 0
41 | 463 | A | Improvements to Supa-Annigeri SH-28 from Ch: 67.0Km to 68.5 Km in Dharwad Tq. | SH-28 | 1.55 | 0.85 | 0.85 |  |  |  | 0.85 |  | 0 | 0 |  | 0
|  | B | Improvements to Gokul cross-Tarihala- Kanavi-Honnapur MDR from Ch: 4.2Km to 4.8Km and 6.2Km to 8.4Km in Hubballi tq. | MDR | 0.814 | 0.814 | 0.6 | 0.214 |  |  | 0.814 |  | 0 | 0 |  | -4.549
|  | C | Improvements to Ittigatti-Kanavihonnapur MDR from Ch: 0.0 to 2.0Km in Dharwad tq. | MDR | 1.485 | 1.485 |  |  | 1.485 |  | 1.485 |  | 0 | 0 |  | 0
|  | D | Improvements to Gokul-Revadihal-Tarihal MDR road from Ch: 0.0 to 6.2Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 3.24 | 3.24 |  | 0.65 | 2.59 |  | 3.24 |  | 0 | 0 |  | -2.52
|  |  | Division Total |  | 71.575 | 76.124 | 3.55 | 14.679 | 50.854 | 7.041 | 76.124 |  | 0 | 0 |  | 0
Gadag Division | [12 empty] | 0 | 0 |  | 0
42 | 464 | A | Improvements to Kalasapur-Mahalingapura- Anganakatti road (MDR) from Ch: 21.00 Km to 29.00 Km ( in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 4.81 | 7.33 |  |  | 7.33 |  | 7.33 |  | 0 | 0 |  | 0
|  | B | Improvements to Asundi-Kurtkoti-Mulagunda road (MDR) Ch: 2.20 Km to 8.00 Km and 8.60 Km to 10.00 Km (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 3.98 | 3.98 |  |  | 3.98 |  | 3.98 |  | 0 | 0 |  | 0
|  | C | Improvements to Kalasapur-Mahalingapura- Anganakatti road Ch:0.30 Km to 2.60 and Ch: 7.00 Km to 21.00 (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 4.09 | 4.09 |  | 1.55 | 2.54 |  | 4.09 |  | 0 | 0 |  | -2.8
43 | 465 | A | Improvements to Bellatti-Guttala road Konchigeri- Nagaramadavu-Kerekoppa from Ch: Km 0.00 to 11.90 (in selected reaches) in Shirahatti taluk of Gadag Dist. | MDR | 7.44 | 7.44 |  |  | 7.44 |  | 7.44 |  | 0 | 0 |  | -0.34
|  | B | Improvements to Varavi cross-Bannikoppa road (MDR) from Ch-0.00 to 4.30 & Ch-8.30 to 20.00 Km (in selected reaches) in Shirahatti taluk of Gadag Dist. | MDR | 7.65 | 7.65 |  |  | 7.65 |  | 7.65 |  | 0 | 0 |  | -0.5
44 | 466 | A | Improvements to Chikkahandigol-Belahoda-Madaganoor Ch0.0to4.5,5.4 to7.4,9.6 to11.0&11.8to13.0 in Naragund Tq | MDR | 6.555 | 9.355 |  |  | 9.355 |  | 9.355 |  | 0 | 0 |  | -0.38
|  | B | Improvements to Abbigeri-Yerebeleri-Kurudagi- Gujamagadi Ch5.0to7.5&9.0 to12.1 of Ron Tq | MDR | 2.29 | 2.63 |  |  | 2.63 |  | 2.63 |  | 0 | 0 |  | -0.04
|  | C | Improvements to Kalakeri-Kanakikoppa-Naragund Ch17.0to21.13 in Naragund Tq | MDR | 2.96 | 3.46 |  |  | 3.46 |  | 3.46 |  | 0 | 0 |  | 0
|  | E | Improvements to Gajendragad-Soraba SH136 Ch67.0to69.9 in Naragund Tq | SH-136 | 2.42 | 2.8 |  |  | 2.8 |  | 2.8 |  | 0 | 0 |  | 0
|  | F | Improvements to Sindhanuru-Hemmadaga SH30 Ch159.77to161.7 of Naragund Tq | SH-30 | 1.55 | 1.59 |  | 1.59 |  |  | 1.59 |  | 0 | 0 |  | -0.02
|  | G | Improvements to Bagalakote Biligiriranganabetta SH57 Ch91.0to92.5 (in selected reaches) in Gadag Tq,Gadag Dt. | SH-57 | 0.255 | 0.255 |  | 0.255 | 0 |  | 0.255 |  | 0 | 0 |  | 0
|  | D | Improvements to Munavalli-Kotumachage (SH-83) road from Ch-87.30 km to 100.00 km in selected reaches of Ron Taluk, Gadag district | SH-83 | 7.55 | 7.55 |  |  | 7.55 |  | 7.55 |  | 0 | 0 |  | -6.6
45 | 467 | A | Improvements to Hallikeri-Shirahatti road (MDR) from Ch: 0.00 to 26.00 (in selected reaches) in Mundaragi taluk of Gadag Dist. | MDR | 10.73 | 10.75 |  |  | 10.75 |  | 10.75 |  | 0 | 0 |  | 0
|  | B | Improvements to Gajendragada-Soraba Sh-136 from Ch: 23.70 to 36.00 Km (in selected reaches) in Ron taluk of Gadag Dist. | SH-136 | 8.96 | 8.96 |  | 0 | 8.96 |  | 8.96 |  | 0 | 0 |  | -1.195
|  |  | Division Total |  | 71.24 | 77.84 | 0 | 3.395 | 74.445 | 0 | 77.84 |  | 0 | 0 |  | -2.603
Haveri Division | [12 empty] | 0 | 0 |  | 0
46 | 468 | A | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 284.51 Km to 294.51 Km (In Selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 8.225 | 9.42 |  | 9.42 | 0 |  | 9.42 |  | 0 | 0 |  | -2.408
|  | B | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 294.51 Km to 303.200 Km (in selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 6.617 | 9.22 |  | 9.22 | 0 |  | 9.22 |  | 0 | 0 |  | -0.325
47 | 605 | A | Improvements to Shiggoan-Savanur railway station road (MDR) from Ch: 8.10 Km to 13.10 Km (In Selected reaches) in Savanur taluk, Haveri District. | MDR | 2.785 | 2.785 |  | 2.785 | 0 |  | 2.785 |  | 0 | 0 |  | 1.86
|  | B | Improvements to Kumta-Tadas SH-69 road from Ch-134.50 Km to 142.00 Km (In Selected Reaches) in Shiggoan taluk of Haveri District. | SH-69 | 4.08 | 6.488 |  | 6.488 | 0 |  | 6.488 |  | 0 | 0 |  | 0
|  | C | Improvements to Savanur- Hurulikuppi road from Ch-0.00 Km to 5.65 Km (In Selected Reaches) in Savanur taluk of Haveri District. | MDR | 5.095 | 5.42 |  |  | 5.42 |  | 5.42 |  | 0 | 0 |  | -0.73
48 | 469 |  | Improvements to Birur-Sammasagi SH: 76 Ch: 189.00 Km to 201.60 Km in selected reaches and 203.82 Km to 217.19 Km In Selected Reaches of Hanagal taluk, Haveri District. | SH-76 | 15.735 | 13.875 | 0 | 13.875 | 0 |  | 13.875 |  | 0 | 0 |  | -0.565
49 | 470 | A | Improvements to Havanur-Choudadanayyapura road Ch: 1.25 Km to 9.00 Km of Haveri taluk Haveri District | MDR | 3.9 | 3.9 |  |  |  | 3.9 | 3.9 |  | 0 | 0 |  | -0.8
|  | B | Improvements to Halagi-Balehosur road Ch: 0.00 Km to 2.50 Km of Haveri taluk, Haveri District. | MDR | 1.68 | 2.41 |  |  | 2.41 |  | 2.41 |  | 0 | 0 |  | 0
|  | C | Improvements to Agadi-Devagiri road Ch: 4.50 Km to 6.00 Km and 11.00 Km to 12.50 Km of Haveri taluk, Haveri District. | MDR | 1.388 | 1.953 |  | 0.255 | 1.698 |  | 1.953 |  | 0 | 0 |  | -0.352
|  | D | Improvements to Totadayellapura-Masoor-Guttala road Ch: 18.00 Km to 24.50 Km of Haveri taluk, Haveri District. | MDR | 3.03 | 3.83 |  |  | 3.83 |  | 3.83 |  | 0 | 0 |  | 0
|  | E | Improvements to Agadi-Katenahalli road Ch: 0.80 Km to 6.50 Km Haveri taluk, Haveri District. | MDR | 3.428 | 3.428 |  |  | 3.428 |  | 3.428 |  | 0 | 0 |  | 0
50 | 471 | A | Improvements toTavargi - Tumminkatte road (MDR) from Ch: 0.00 Km to 22.50 Km (In Selected reaches) in Hirekerur taluk, Haveri District. | MDR | 8.368 | 8.72 |  |  | 8.72 |  | 8.72 |  | 0 | 0 |  | 0
|  | B | Improvements to Road from Birur-Sammasagi SH: 76 to Join Halageri-Hulikal SH-26 Via Hirekerur-Masur-Kodamaggi- Hallur road Ch: 28.25 Km to 47.45 Km in selected reaches of Hirekerur taluk, Haveri District | SH-76 | 7.59 | 7.59 |  |  | 7.59 |  | 7.59 |  | 0 | 0 |  | -1.2
|  | C | Improvements to Road from Birur- Sammasagi SH: 76 to Join Byadagi - Rattihalli road Via Aladageri Ch: 0.00 Km to 7.10 Km in selected reaches of Hirekerur taluk, Haveri District. | SH-76 | 3.98 | 3.98 |  |  | 0 | 3.98 | 3.98 |  | 0 | 0 |  | 0
51 | 472 | A | Improvements to Sanguru - Tilavalli MDR Ch: 0.00 Km to 5.60 Km in Haveri taluk, Haveri District. | MDR | 3.76 | 3.76 |  |  | 3.76 |  | 3.76 |  | 0 | 0 |  | -1.37
|  | B | Improvements to Honnalli - Hanagal SH Via Tumminakatti - Rattihalli - Byadagi Road Ch: 0.00 Km to 9.62 Km in Byadagi taluk, Haveri District. | MDR | 6.69 | 7.89 |  | 7.89 |  |  | 7.89 |  | 0 | 0 |  | 0
|  | C | Improvements to Ranebennur - Anavatti SH Via Yarekuppi - Joisarahalli - Ukkunda - Saravanda - Belakeri - Bisahalli - Anoor - Hamsabhavi - Chikkerur MDR Ch: 15.60 Km to 19.00 Km in Byadagi taluk, Haveri District. | MDR | 2.98 | 2.98 |  |  | 2.98 |  | 2.98 |  | 0 | 0 |  | -0.26
52 | 604 | A | Improvements to Ranebennur - Mudenuru Road Via Magoda - Itagi Road Ch: 0.00 Km to 14.10 Km in Ranebennur taluk, Haveri District. | MDR | 5.624 | 6.994 |  |  | 6.994 |  | 6.994 |  | 0 | 0 |  | -9.948
|  | B | Improvements to Ranebennur - Bisalahalli Road Ch: 1.70 Km to 3.70 Km in Ranebennur taluk, Haveri District. | MDR | 1.65 | 1.65 |  |  | 1.65 |  | 1.65 |  | 0 | 0 |  | 0
|  | C | Improvements to Aremallapura - Kuduhaal Road Via Medleri - Udagatti - Heeladahalli Road Ch: 0.00 Km to 9.60 Km & CH.14.20 to 15.00 Km in Ranebennur taluk, Haveri District. | MDR | 6.617 | 6.877 |  |  | 6.877 |  | 6.877 |  | 0 | 0 |  | -0.4
|  |  | Division Total |  | 103.222 | 113.17 | 0 | 49.933 | 55.357 | 7.88 | 113.17 |  | 0 | 0 |  | -1.946
Karwar Division | [12 empty] | 0 | 0 |  | 2.1
53 | 473 | A | Improvements to Kumta - Kodamadagu Road SH-48 from km 9.00 to 12.20 Km & 16.20 to 19.90 Km (In Selected reaches) in Honnavara Taluk And Kumta - Kodamadagu road SH-48 from Km 19.90 to 30.00 Km (In Selected Reaches) in Kumta Taluk of Uttara Kannada District. | SH-48 | 12.4 | 12.8 |  |  | 12.8 |  | 12.8 |  | 0 | 0 |  | 0.84
|  | B | Improvements to Aghanashini - Kumta road MDR from Km 0.00 to 6.00 Km in Kumta Taluk of Uttara Kannada District. | MDR | 3 | 4.946 |  |  | 4.946 |  | 4.946 |  | 0 | 0 |  | -1.39
54 | 474 | A | Improvements to Gokarna - Vaddi road SH-143 Km 38.00 to 47.15 Km (In Selected Reaches) in Ankola Taluk of Uttara Kannada District | SH-143 | 7.5 | 5.4 |  |  | 5.4 |  | 5.4 |  | 0 | 0 |  | -1.28
|  | B | Improvements to Hyderabad to Shejwada road from 0.00 km to 2.00 km in Karwar taluk of Uttara Kannada district. | MDR | 1.32 | 0.48 |  |  | 0.48 |  | 0.48 |  | 0 | 0
|  | C | Improvements to Agasur - Shiragutte - kodasane road from 0.00 to 12.60 Km (in selected reaches) in Ankola Taluk of Uttara Kannada District. | MDR | 1.81 | 3.2 |  |  | 3.2 |  | 3.2 |  | 0 | 0 |  | 0
|  | D-A | Improvements to Belur-Karwar-Ilakal State Highway road from 0.00 km to 4.00 km in Karwar taluk of Uttara Kannada district. | MDR | 2.72 | 4 |  |  |  | 4 | 4 |  | 0 | 0 |  | 2.2
|  | D-B | Improvements to Karwar-Kaiga-Ilakal road from 27.35 km to 32.00 km in widening and Resurfacing Karwar taluk of Uttara Kannada district. | MDR | 2.72 | 4 |  | 2.474 | 1.526 |  | 4 |  | 0 | 0 |  | -0.107
|  | E | Improvements to Aurad - Sadhashivagad SH-34 Ambrai Cross to Ulaga road MDR from Km 0.00 to 3.30 Km (In Selected Reaches) in Karwar Taluk of Uttara Kannada District. | SH-34 | 3.3 | 3.3 |  |  | 3.3 |  | 3.3 |  | 0 | 0 |  | -0.108
55 | 475 | A | Improvements to Heggera - Magod - Nagarbhastikere road MDR from Km 3.40 to 20.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 10.3 | 8.915 |  |  | 8.1 |  | 8.1 |  | 0 | 0 |  | -1.371
|  | B | Improvements to Magudu - Koodalagade road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 2.7 | 2.807 |  |  | 2.807 |  | 2.807 |  | 0 | 0 |  | 0
|  | C | Improvements to koppa panchayath hadala- kacchodi road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Bhatkal Taluk of Uttara Kannada District. | MDR | 3.5 | 3.82 |  |  |  | 3.608 | 3.608 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 51.27 | 53.668 | 0 | 2.474 | 42.559 | 7.608 | 52.641 |  | 0 | 0 |  | -0.52
Sirsi Division | [12 empty] | 0 | 0 |  | -4.537
56 | 476 |  | Improvements to Khanapur - Taalguppa road SH-93 from Km 39.67 to 81.85 Km (In Selected Reaches) in Haliyal Taluk of Uttara Kannada District. | SH-93 | 25.59 | 25.59 |  |  | 25.59 |  | 25.59 |  | 0 | 0 |  | -0.005
57 | 477 | A | Improvements to Ulavi - Diggi to Goa Border road SH-146 from Km 7.00 to 24.00 Km (In Selected Reaches) in Joida Taluk of Uttara Kannada District. | SH-146 | 3.52 | 4.04 |  |  | 4.04 |  | 4.04 |  | 0 | 0 |  | 0.52
|  | B | Improvements to Aurad - Sadhashivagad SH-34 from 604.07 Km to 687.82 Km (In Selected Reaches) in JoidaTaluk of Uttara Kannada District. | SH-34 | 16.305 | 20.842 |  |  | 20.842 |  | 20.842 |  | 0 | 0 |  | -2.13
58 | 478 | A | Improvements to Gokarna - Vaddi - Devanahalli road SH-143 from Km 65.20 to 73.15 Km in Sirsi Taluk of Uttara Kannada District. | SH-143 | 5.425 | 5.43 |  |  | 5.43 |  | 5.43 |  | 0 | 0 |  | -2.138
|  | B | Improvements to Khanapur - Taalaguppa road SH-93 from Km 170.00 to 200.50 Km (In Selected reaches) in Siddapura Taluk of Uttara Kannada District. | SH-93 | 1.59 | 1.07 |  | 1.07 |  |  | 1.07 |  | 0 | 0 |  | -8.81
|  | C | Improvements to Bhatkal - Soraba road SH-50 from Km 85.90 to 86.70 Km, Km 87.20 to 93.965 Km, Km 96.50 to 96.90 Km, Km 97.30 to 98.80 Km & Km 99.55 to 100.90 in Siddapur Taluk of Uttara Kannada District. | SH-50 | 5.38 | 7.51 |  |  | 7.51 |  | 7.51 |  | 0 | 0 |  | -31.278
59 | 479 |  | Improvements to Karwar - Kaiga - Ilkal road SH-06 in Mundgod Taluk from Km125.80 to 146.10 Km (in Selected Reaches) of Uttara Kannada District. | SH-06 | 15.71 | 17.848 |  |  | 17.848 |  | 17.848 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 73.52 | 82.33 | 0 | 1.07 | 81.26 | 0 | 82.33 |  | 0 | 0 |  | 0
|  |  | Dharwad Circle Total |  | 370.827 | 403.132 | 3.55 | 71.551 | 304.475 | 22.529 | 402.105 |  | 0 | 0 |  | 0
Belagavi Circle | [12 empty] | 0 | 0 |  | -1.375
Vijayapura Division | [12 empty] | 0 | 0 |  | -0.63
60 | 480 | A | Improvements to road Shiradon Lingasur SH 41 from Ch: 71.43 Km to Ch: 82.00 Km and Ch: 93.50 Km to Ch: 100.23 Km (in selected reaches) in Sindagi Taluk in Vijayapur District. | SH 41 | 6.91 | 6.91 |  | 6.91 |  |  | 6.91 |  | 0 | 0 |  | 0.44
|  | B | Improvements to road Ukkalli Dindawar- Sasanur from Ch. 50.50 Km to Ch. 62.86 Km (in selected reaches) in Basavanabagewadi Taluk in Vijayapur District | Upgraded To SH | 6.47 | 7.845 |  |  | 7.845 |  | 7.845 |  | 0 | 0 |  | -0.755
61 | 481 |  | Improvements to Road Ukkalli - Dindawar - Sasanur MDR from Km 15.10 to 31.00 Km (In Selected reaches) in Basavanbagewadi Taluk of Vijayapura District. | Upgraded To SH | 4 | 4.63 |  | 4.63 |  |  | 4.63 |  | 0 | 0 |  | -0.03
62 | 482 |  | Improvements to road from SH-55 to Shegunashi - Mamadapur - Doodihal up to NH-218 from Ch. 0.00Km to Ch. 12.10 Km (in selected reaches) in Vijayapur Taluk in Vijayapur District | MDR/BJP-64 | 5.18 | 4.74 |  |  | 4.74 |  | 4.74 |  | 0 | 0 |  | 0.01
63 | 483 |  | Improvements to Kawadimatti - Donkamadu MDR from Ch 0.00 Km to Ch 19.60 Km (In Selected reaches) in Muddebihal Taluk of Vijayapura District. | MDR/MDD-208 | 9.61 | 10.365 |  |  | 10.365 |  | 10.365 |  | 0 | 0 |  | 0.16
64 | 484 |  | Improvements to road Inchigeri Horti Roogi MDR from Ch: 13.00 Km to Ch: 33.60 Km (in selected reaches) in Indi Taluk in Vijayapur District. | MDR/IND-11 | 6.06 | 6.09 |  |  | 6.09 |  | 6.09 |  | 0 | 0 |  | 0
65 | 485 |  | Improvements to Minchanala - Atharga - Thamba - Koralli MDR from Ch.37.60 to 51.40 Km (In Selected reaches) in Sindagi Taluk of Vijayapura District. | MDR/SND-9 | 6.02 | 6.02 |  |  | 6.01 |  | 6.01 |  | 0 | 0 |  | -2.18
66 | 486 |  | Improvements to road from Jorapur Water Tank to Connecting NH-50 in Vijayapura Taluk of Vijayapura District. | SH | 3.69 | 3.53 | 3.53 |  |  |  | 3.53 |  | 0 | 0 |  | 0
67 | 594 |  | Improvements to road Shiradon Lingasur SH 41 from Ch: 15.15 Km to Ch: 23.50 Km (Loni Cross to Baraola - in selected reaches) in Chadachana Taluk in Vijayapur District. | SH-41 | 5.56 | 5.56 |  | 5.56 |  |  | 5.56 |  | 0 | 0 |  | -0.5
|  |  | Division Total |  | 53.5 | 55.69 | 3.53 | 17.1 | 35.05 | 0 | 55.68 |  | 0 | 0 |  | 0
Bagalkot Division | [12 empty] | 0 | 0 |  | 2.95
68 | 487 |  | Improvements to Bagalkote - Sangama Cross (NH-367) to Almatti Dam Taluka border (NH 50) MDR from Ch. 0.00 to 29.65 Km (In Selected reaches) in Bagalkote Taluk of Bagalkote District. | MDR | 13.5 | 14 |  | 14 |  |  | 14 |  | 0 | 0 |  | 0
69 | 488 |  | Improvements to Sureban Chitharagi Kudalasangama SH 133 from Ch.43.70 to 58.20 Km (In Selected reaches) in Badami Taluk of Bagalkote District. | SH-133 | 8.33 | 8.33 |  | 8.33 |  |  | 8.33 |  | 0 | 0 |  | 0
70 | 489 | A | Improvements to Jamakhandi Galagali via Mudaganoor MDR from Ch.14.82 to 27.00 Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-3 | 9.61 | 6.66 |  |  | 6.66 |  | 6.66 |  | 0 | 0
|  | B | Improvements to Badagandi – Sangam MDR from Ch.5.00 to 6.72Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-6 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0
|  | C | Improvements to Sankeshwar – Sangam SH-44 from Ch.110.00 to 124.00 Km (In Selected reaches) (Nerbudihal village limit) in Badami Taluk of Bagalkote District | SH-44 | 1.8 | 1.8 |  | 1.8 |  |  | 1.8 |  | 0 | 0
|  | D | Improvements to Constrution of Bridge/Box Culvert at CH:3.50km in Kanakatti Anavala Ge-mu-ra of Beelagi constituency at Badami taluk, Bagalkote Dist. | [7 empty] | 0 |  | 0 | 0 |  | 0 |  |  | 0.27 |  |  | 4.16
|  | E | Improvements at Construction of bridge/box culvert at Ch:0.20Km in sulikere Kagalagomba Ge-mu-road of beelagi constituency at Badami taluk, Bagalakote Dist. | [7 empty] | 0 |  | 0 | 0 |  | 0
|  | F | Improvements at Construction of Bridge/box culverts at SH-44 Ch:107.00 km in Sankeshwar Sangam near Kadarakoppa village of Bellary constituency at Badam taluk Bagalkote Dist. | [7 empty] | 0 |  | 0 | 0 |  | 0.05
71 | 490 | A | Improvements to Ramdurga Manvi SH14 from Ch 104.00 to 116.00 Km (In Selected reaches) in Hungunda Taluk of Bagalkote District. | SH-14 | 5.56 | 5.56 |  | 1.4 | 4.16 |  | 5.56 |  | 0 | 0 |  | -0.49
|  | B | Improvements to Hungunda Paltti Cross MDR from Ch 6.00 to 12.80 Km in Hungunda Taluk of Bagalkote District. | MDR | 6.38 | 6.38 |  |  | 6.38 |  | 6.38 |  | 0 | 0 |  | 0.01
72 | 491 | A | Improvements to road Shankeshwar - Sangam SH-44 from Ch.81.54 to 97.74 Km (In Selected reaches) in Mudhol Taluk of Bagalkot District. | SH-44 | 14.89 | 14.84 |  | 14.84 |  |  | 14.84 |  | 0 | 0 |  | -0.98
73 | 492 | A | Improvements to Jambotti – Rabakavi SH-54 from Ch.130.47 to 131.13 Km, Ch.132.09 to Ch.133.70, CH.135.39 to 139.20 & CH.139.70 to 141.56 (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | SH-54 | 3.18 | 3.67 |  | 3.67 |  |  | 3.67 |  | 0 | 0 |  | 1.04
|  | B | Improvements to Road Madhurakhandi – Kallalli - Jagadala – Chimada MDR from Ch.0.00 to 10.80 Km (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | MDR/JMK-9 | 4.05 | 4.04 |  |  | 4.04 |  | 4.04 |  | 0 | 0 |  | 0
|  | C | Improvements to Bidari - Honawada Road via Thodalabagi - MDR from Ch.10.12 Km to 15.25 Km & Ch.25.60 Km to 31.00 Km in Jamkhandi Taluk of Bagalkote District. | MDR/JMK-24 | 4.74 | 5.72 |  |  | 5.72 |  | 5.72 |  | 0 | 0 |  | -1.094
|  |  | Division Total |  | 72.04 | 71 | 0 | 44.04 | 26.96 | 0 | 71 |  | 0 | 0 |  | -0.32
Belagavi Division | [12 empty] | 0 | 0 |  | -0.326
74 | 493 |  | Improvements to SH-20, Raichur-Bachi Roadfrom Ch. 333.00 Km to 393.53 Km (In Selected Reaches) in Belagavi Taluk Belagavi District. | SH-20 | 5.39 | 6.484 |  | 6.484 |  |  | 6.484 |  | 0 | 0 |  | 2.45
75 | 494 | A | Improvements to Yadiyurappa Margra (OLD PB Road) from Ch. 0.00 Km to 3.81 Km and from SPM Road to VRL Office Joining Road ( In slected Reaches) in Belagavi Taluk, Belagavi Districts. | MDR | 1.61 | 1.93 |  |  | 1.93 |  | 1.93 |  | 0 | 0 |  | 5.43
|  | B | Improvements to SH-54, Jamboti-Rabakavi Road, Vajapeyee Marga ( Belagavi Panaji SH-4A, From Benco Cross to 3rd Gate) from Ch. 23.80 Km to 27.60 Km in Belagavi Taluk, Belagavi District. | SH-54 | 1.64 | 1.966 | 1.966 |  |  |  | 1.966 |  | 0 | 0 |  | 0.11
76 | 495 | A | Improvements to SH-93, Khanapur-Talugupppa Road, From Ch. 0.00 to 34.58 Km (in Selected Reach) in Khanapur Taluk, Belagavi District. | SH-93 | 8 | 9.365 |  |  | 5.55 |  | 5.55 |  | 0 | 0 |  | 0.005
|  | B | Improvements to SH-138 Nagaragali-katakol road from Ch. 0.00 Km to 15.95 Km (Selected Reaches) in KhanapurTaluk, Belagavi District. | SH-138 | 5.43 | 5.43 |  |  |  |  | 0 |  | 0 | 0 |  | 0
77 | 496 |  | Improvements to Jatt-Jamboti (SH-31), from Ch. 125.55 Km to 137.45 Km (Selected Reaches) in Bailhongal Taluk, Belagavi District. | SH-31 | 11.9 | 11.79 | 1.06 | 10.73 |  |  | 11.79 |  | 0 | 0 |  | 0.02
78 | 497 | A | Improvements to SH-103 Gokak Savadathi Road From Ch. 29.50 Km to Ch.37.40 Km (in Selected Reaches) Belagavi Districts. | SH-103 | 4.75 | 4.745 |  |  | 4.745 |  | 4.745 |  | 0 | 0 |  | 0
|  | B | Improvements to SH 01 Padabudri Chikkalagudda SH 01 From Ch 420.56 Km to 421.98 Km in Bailahingal Taluk Belagavi District | SH-01 | 1.42 | 1.42 |  |  | 1.42 |  | 1.42 |  | 0 | 0 |  | 0
79 | 498 | A | Improvements to MDR-SAU89 SAVADATTI-SANGRESHKOPPA Road Via Mamani Kere from Ch. 0.00 Km to 8.00 Km in Savadatti Taluk, Belagavi District | MDR-SAU89 | 7.8 | 7.783 |  |  |  | 7.78 | 7.78 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR SAU-4 Saundatti Hanchinal Road From Km Ch 0.00 to 6.00 Km (Selected Reaches) in Saundatti Taluka, Belagavi District | MDR SAU-4 | 4.04 | 4.04 | 0.75 | 3.29 |  |  | 4.04 |  | 0 | 0 |  | -0.23
|  | C | Improvements to MDR from Yallamma Temple to SH-34 Joining Road, From Km Ch 0.00 to 2.00 Km in Savadatti Taluka, Belagavi District. | MDR | 2 | 2 | 2 |  |  |  | 2 |  | 0 | 0 |  | 0.09
80 | 499 | A | Improvements to SH-34 AURAD-SADASHIVAGADA ROAD from Ch. 445.94 Km to 453.94 (Selected Reaches) in Ramadurga Taluk, Belagavi District | SH-34 | 5.61 | 5.61 | 1.2 | 4.41 |  |  | 5.61 |  | 0 | 0 |  | 6.135
|  | B | Improvements to SH-139 YARAGATTI-MUDHOL ROAD, From Km Ch 11.83 to 22.60 Km (Selected Reaches) in Ramadurg Taluka, Belagavi District. | SH-139 | 6.47 | 6.7 |  | 6.7 |  |  | 6.7 |  | 0 | 0 |  | 0
81 | 596 |  | Improvements to Jatti Jamboti SH-31 from Ch 179.88 to 188.58 Km (In Selected reaches) in Belagavi Taluk of Belagavi District. | SH-31 | 4.885 | 4.795 |  | 4.795 |  |  | 4.795 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 70.945 | 74.058 | 6.976 | 36.409 | 13.645 | 7.78 | 64.81 |  | 0 | 0 |  | -0.68
Chikkodi Division | [12 empty] | 0 | 0 |  | 0
82 | 500 |  | Improvements to Nippani Kottalagi Road SH-72 Form Ch 1.40 Km to Ch 17.00 Km & Ch 17.90 Km to 22.60 Km (in selected reaches) Via Nippani Akkola Galataga Nej cross, Nippani Taluk Belagavi Districts. | SH-72 | 9.065 | 9.065 | 3.025 | 6.04 |  |  | 9.065 |  | 0 | 0 |  | 0
83 | 501 |  | Improvements to SH-73 Managasuli-Laxmeshwar Road from Ch: 37.00 Km to 40.00, Km, Ch: 52.00 Km 54.00 Km, And, 55.00 Km to 67.00 Km in (Selected Reaches) Raibag Taluk, Belagavi District. | SH-73 | 6.17 | 6.85 |  | 6.85 |  |  | 6.85 |  | 0 | 0 |  | -0.06
84 | 502 | A | Improvements to Shettyhalli Ichalkaranji Road SH-78 From Km 76.90 to Km 81.90 (From Malikwad Bus stand to sadalaga) (in selected reaches) Chikkodi Taluk Belagavi Districts. | SH-78 | 3 | 3 |  | 3 |  |  | 3 |  | 0 | 0 |  | -1.42
|  | B | Improvements to Nippani Kottalagi Road SH-72 From Km 31.70 to Km 35.70 (From Nej Crosss to nanadi) (in selected reaches) Chikkodi Taluk Belagavi Districts. | SH-72 | 2.89 | 2.89 |  | 0.26 | 2.63 |  | 2.89 |  | 0 | 0 |  | 3.23
|  | C | Improvements to Nippani Kottalagi Road SH-72 from km 40.00 to km 47.00 (From Yadur Veerabadreshwar temple to Kallol) Chikkodi Taluk Belagavi Districts. | SH-72 | 3.01 | 3.07 |  |  | 3.07 |  | 3.07 |  | 0 | 0 |  | 0
85 | 503 | A | Improvements to Road from Jinaral Cross to Hidakal Dam, Godageri MDR from Ch:0.00 to 14.00 Km (In Selected Reaches) Hukkeri Taluk, Belagavi District. | MDR | 9.15 | 10.57 | 1.84 | 8.73 |  |  | 10.57 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR-HUK-73 Nerli-Ammanagi Road from Ch:0.00 Km to 0.85 Km and 2.75 Km to 5.50 Km (In Selected Reaches) Hukkeri Taluk, Belagavi District. | MDR | 3.23 | 3.23 |  |  |  |  | 0 |  | 0 | 0 |  | 0
86 | 504 | A | Improvements to SH-31, JATH-JAMBOTI Road, from Ch. 106.82 Km to 115.05 Km and 121.18 Km to 121.78 Km in Gokak Taluka, Belagavi District | SH-31 | 6.325 | 6.325 | 6.325 |  |  |  | 6.325 |  | 0 | 0 |  | 0.6
|  | B | Improvements to Jamboti rabhakavi Road SH-54 From Km 62.08 to 66.70 (Akkatangerahal to Telaginahatti) From Km 83.00 to 84.20 (Hanamapur Cross) And From Km 54.28 to 55.755 Gokak Taluk Belagavi Districts. | SH-54 | 4.9 | 4.9 |  | 4.9 |  |  | 4.9 |  | 0 | 0 |  | -1.65
87 | 505 | A | Improvements to MDR from Koujalagi-Kalliguddi Road from Ch. 0.00 Km to 5.50 Km in Mudalagi Taluk, Belagavi District. | MDR | 3 | 3 |  |  | 3 |  | 3 |  | 0 | 0 |  | -2.14
|  | B | Improvements to SH, Haleyaragudri to Hosayaragudri Road (Avaraadi-Timmapur Road), from Ch. 0.00 Km to 10.00 Km (Selected Reaches) in Mudalagi Taluk, Belagavi District. | SH | 10 | 9.4 |  |  | 9.4 |  | 9.4 |  | 0 | 0 |  | 0
88 | 506 | A | Improvements to Kagawad-Kaladagi Sh-53 Road from Ch: 22.40 Km to 24.10 Km, Ch: 24.90 Km 29.60 Km, 32.55 Km to 35.00 km, 44.39 Km to 44.90 Km in Raibag Taluk, Belagavi District. | SH-53 | 9.6 | 11.25 |  | 11.01 | 0.24 |  | 11.25 |  | 0 | 0 |  | -1.695
|  | B | Improvements to Chikkodi Railway Station-Mugalakod-Handigundi MDR from Ch: 10.03 Km to 14.00 Km, And Ch: 19.00 Km to 39.15 Km in (Selected Reaches) Raibag Taluk, Belagavi District. | MDR | 5.1 | 7.24 |  |  | 7.24 |  | 7.24 |  | 0 | 0 |  | -0.13
89 | 507 |  | Improvements to State Border to Aralihatti, Jakaratti, Madabhavi,, Shiddewadi, Koulagudda, Ainapur, Krishna Kittur upto Taluka Border Road from Ch: 0.00 Km to 28.50 Km in Kagawad Taluk, Belagavi District. | MDR | 16.52 | 16.52 |  |  | 16.52 |  | 16.52 |  | 0 | 0 |  | 0
90 | 508 |  | Improvements to Maharastra State Border to Kakamari-talasang-Savalagi District Border Road from Ch: 2.40 Km to 11.60 Km and Ch: 12.70 Km to 21.20 Km in (in selected reaches) Athani Taluk, Belagavi District. (Upgraded SH) | MDR | 16 | 17.7 | 1.3 | 3.615 | 12.78 |  | 17.695 |  | 0 | 0 |  | 0
91 | 509 |  | Improvements to Harugeri-Raibag-Nagaramunnolli MDR from Ch. 16.00 Km to 18.68 And Ch: 23.80 to 37.00 ( Selected Reaches) in Raibag Taluk, Belagavi District. | MDR | 6.2 | 6.33 | 3.07 | 3.26 |  |  | 6.33 |  | 0 | 0 |  | -3.945
92 | 510 | A | Improvements to MDR-HUDALI-DHARANATTI-MUTYANATTI ROAD, from Ch. 5.50 Km to 10.00 Km in Belagavi Taluka, Belagavi District. | MDR | 4.505 | 4.505 |  |  | 4.505 |  | 4.505 |  | 0 | 0 |  | 1.05
|  | B | Improvements to MDR HUK-203 Basapur Hagedal Shahabadar Ukkad Road From Km 0.00 to Km 2.00 & Km 4.00 to Km 7.15 in Hukkeri Taluk Belagavi Districts. | MDR | 2.15 | 2.15 |  | 2.15 |  |  | 2.15 |  | 0 | 0 |  | -18.208
|  |  | Division Total |  | 120.815 | 127.995 | 15.56 | 49.815 | 59.385 | 0 | 124.76 |  | 0 | 0 |  | 0
|  |  | Belagavi Circle Total |  | 317.3 | 328.743 | 26.066 | 147.364 | 135.04 | 7.78 | 316.25 |  | 0 | 0 |  | 0 |  |  |  | 0.025 | 13.875 | 25.822 | 4.158 | 43.88
|  |  | North Circle Total |  | 1011.672 | 1048.96 | 36.696 | 300.06 | 658.586 | 34.538 | 1029.88 |  | 0 | 0 |  | 0
Shivamogga circle | [12 empty] | 0 | 0 |  | 0
Davanagere Division | [12 empty] | 0 | 0 |  | 0
93 | 511 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:186.35 Km to 194.05Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | SH-65 | 7.7 | 7.7 |  | 7.7 |  |  | 7.7 |  | 0 | 0 |  | 3.177
|  | B | Improvements to Road From Nalluru -Devarahalli MDR From Ch:5.00 Km to 11.00 Km in Channagiri Taluk of Davanagere District | CNG12 | 4.97 | 4.97 |  | 0.21 | 4.76 |  | 4.97 |  | 0 | 0 |  | 0
|  | C | Improvements to Road From Pandomatti to Neethigere MDR From Ch:0.00 Km to 16.00 Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | CNG27 | 3.92 | 3.92 |  |  | 3.92 |  | 3.92 |  | 0 | 0 |  | 0
94 | 512 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:233.00Km to 242.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | SH-65 | 8.78 | 5.9 |  | 5.603 |  |  | 5.603 |  | 0 | 0 |  | -0.34
|  | B | Improvements to Road From Davanagere Budihala Arasapura MDR From Ch:4.80Km to 12.75Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG9 | 3.3 | 3.3 |  | 3.06 | 0.24 |  | 3.3 |  | 0 | 0 |  | -1.5
|  | C | Improvements to Road From Bethur to Dhoddabathi MDR From Ch:0.00Km to 12.00Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 3.47 | 3.47 |  |  | 3.47 |  | 3.47 |  | 0 | 0 |  | -0.29
|  | D | Improvements to Road From Malpe-Molakalmuru SH-65 to Rampura MDR From Ch:0.00Km to 11.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 2.45 | 2.79 |  |  | 1.79 | 1 | 2.79 |  | 0 | 0 |  | 1.97
95 | 513 | A | Improvements to Road From Mandya - Hadagali SH-47 From Ch:261.25Km to 293.83Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | SH-47 | 12.33 | 13.83 |  | 7 | 6.83 |  | 13.83 |  | 0 | 0 |  | 6.5
|  | B | Improvements to Road From Aluruhatti -Anagodu MDR From Ch:0.00Km to 13.245Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG12 | 6.78 | 7.07 |  |  | 7.07 |  | 7.07 |  | 0 | 0 |  | 0 |  | 7.058
96 | 514 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:302.60Km to 306.40Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District. (Four Lane road) | SH-65 | 1.97 | 1.97 |  |  |  |  | 0 |  | 0 | 0 |  | 0
|  | B | Improvements to Road From Rangapura Gadimakunte MDR From Ch:6.50Km to 12.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL208 | 6.5 | 6.5 |  |  |  |  | 0 |  | 0 | 0 |  | 0.2
|  | C | Improvements to Road From Jagaluru Kadabanakatte MDR From Ch:9.00Km to 14.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL34 | 3.015 | 3.015 |  |  | 0.595 | 2.42 | 3.015 |  | 0 | 0 |  | 0.59
|  | D | Improvements to Road From Baramasagara - Bilichodu -Basavanakote MDR From Ch:13.00Km to 37.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL3 | 1.21 | 1.21 |  |  | 1.21 |  | 1.21 |  | 0 | 0 |  | 3.7
|  | E | Improvements to Road From Bilichodu-Sokke MDR From Ch:10.00Km to 16.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL4 | 3.57 | 3.57 |  |  |  | 3.37 | 3.37 |  | 0 | 0 |  | 4.63
97 | 515 | A | Improvements to Road From Malebennuru - Ekegundhi - Nandhigudi Joining MDR From Ch-0.00Km to 6.00Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR11 | 3.21 | 3.21 |  | 0.79 | 1.83 |  | 2.62 |  | 0 | 0 |  | 2.95
|  | B | Improvements to Road From Palya-Mooginagundhi Joining MDR From Ch:0.00Km to 12.67Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR12 | 3.7 | 3.7 |  |  |  |  | 0 |  | 0 | 0 |  | 0
|  | C | Improvements to Road From Nalluru to Sasivehalli MDR From Ch:8.00Km to 16.63Km in Honnalli Taluk of Davanagere District | HNN15 | 8.63 | 8.63 |  |  | 4 |  | 4 |  | 0 | 0 |  | 21.587
|  | D | Improvements to Road From Kurki to Kulambi MDR From Ch:16.40Km to 22.70Km in Honnalli Taluk of Davanagere District | HNN49 | 6.3 | 6.3 |  |  | 3.35 |  | 3.35 |  | 0 | 0 |  | 0
|  | E | Improvements to Road of Honnali -Katthige MDR From Ch:3.00Km to 13.20Km (In Selected Reaches) in Honnalli Taluk of Davanagere District | HNN21 | 4.32 | 4.32 |  |  | 4.32 |  | 4.32 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 96.125 | 95.375 | 0 | 24.363 | 43.385 | 6.79 | 74.538 |  | 0 | 0 |  | 0
Chitradurga Division | [12 empty] | 0 | 0 |  | 0
98 | 516 | A | Improvements to Kumta - Kadamadagi road State Highway 48 from KM 267.00 to 268.50 KM ( In Selected Reaches) in Chitradurga Taluk of Chitradurga District | SH-48 | 0.6 | 0.6 | 0.6 |  |  |  | 0.6 |  | 0 | 0 |  | -2.9
|  | B | Improvements to Road from National Highway 13 (from Emperor Hotel) to State Highway 48 (Kumta - Kadamadagi Road) from KM 0.00 to 4.00 KM ( In Selected Reaches) in Chitradurga Taluk of Chitradurga District. | MDR | 1.02 | 1.02 | 1.02 |  |  |  | 1.02 |  | 0 | 0 |  | -0.49
|  | C | Improvements to Jodichikkenahalli-Yerehalli Road via Kasavanahalli, IngalaDala, Kurumaradikere, kannedalu MDR from KM 11.65 to 30.10 KM (In Selected Reaches) in Chitradurga Taluk of Chitradurga District | CHD203 | 4.29 | 4.29 |  |  |  | 4.29 | 4.29 |  | 0 | 0 |  | 0
99 | 517 | A | Improvements to SH-47- Kakanur MDR from KM 0.00 to 13.00 KM (In Selected Reaches) in Holalakere Taluk of Chitradurga District | HLK202 | 7.52 | 10.42 |  |  | 10.42 |  | 10.42 |  | 0 | 0 |  | -2.83
|  | B | Improvements to Sivaganga - Janakkal - Hosadurga Newly Upgraded State Highway from KM 0.00 to 16.55 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District | NEW SH | 6.53 | 7.02 |  |  | 7.02 |  | 7.02 |  | 0 | 0 |  | -0.38
|  | C | Improvements to State Highway-153-Singhenahalli- to join State Highway 48 Kasturiba Nagar via Talikatte- Malladihalli-Ramaghatta-Hirehemmiganur Newly Upgraded State Highway from KM 0.00 to 38.30 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District. | NEW SH | 7.56 | 7.56 |  |  | 7.56 |  | 7.56 |  | 0 | 0 |  | -0.57
100 | 518 | A | Improvements to Mandya -Hadagali Road State Highway - 47 from KM 183.00 to 212.00 KM (In Selected Reaches) in Hosadurga Taluk of Chitradurga District | SH-47 | 8.25 | 11.08 | 3.3 | 7.78 |  |  | 11.08 |  | 0 | 0 |  | 0
|  | B | Improvements to Sivaganga-Janakal Hosadurga Newly Upgraded State Highway from KM 24.00 to 29.2 KM (in Selected Reaches) in Hosadurga Taluk of Chitradurga District | NEW SH | 4.4 | 4.78 |  | 4.78 |  |  | 4.78 |  | 0 | 0 |  | 0
101 | 519 | A | Improvements to State Highway 48 Vishwanathahalli to join Shiragadi (via Chikkajajur, Madadakere, Bharamgiri, Doddaghatta, Adivala, Ranganathpur) Newly Upgraded State Highway KM 71.55 to 105.15 KM (Bharamgiri-Hosadurga road) (in Selected Reaches) in Hiriyur Taluk of Chitradurga District | NEW SH | 3.8 | 4.37 |  | 4.37 |  |  | 4.37 |  | 0 | 0 |  | 0
|  | B | Improvements to road from State Highway-24 to Shiragadi MDR from KM 0.00 km to 7.60 KM (in Selected Reaches) in Hiriyur taluk of Chitradurga District. | HRY 5 | 6.75 | 6.75 |  |  | 6.75 |  | 6.75 |  | 0 | 0 |  | 0
|  | C | Improvements to JJ Halli - Yalladekere Road via Obalapura, Veeravvanagatihalli, Chigalikatte Newly upgraded MDR from KM 8.00 km to 26.00 KM (in Selected Reaches) in Hiriyur Taluk of Chitradurga District | NEW MDR | 8.8 | 8.8 |  |  | 8.8 |  | 8.8 |  | 0 | 0 |  | 0
102 | 520 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 6.48 to 46.38 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 10.97 | 10.97 |  | 10.97 |  |  | 10.97 |  | 0 | 0 |  | 0
|  | B | Improvements to Belagatta- Haikal, Nayakanhatti Suramanahalli -Chikkunti -Siddaiahkote - Rayapur -Molakalmooru Newly Upgraded State Highway Road from KM 39.80 km to 89.40 KM (in Selected Reaches) in Molakalmooru Taluk of Chitradurga District | NEW SH | 5.26 | 5.26 |  | 5.26 |  |  | 5.26 |  | 0 | 0 |  | -1.5
103 | 521 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 2.40 to 6.48 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 3.88 | 3.88 |  | 3.88 |  |  | 3.88 |  | 0 | 0 |  | -8.67
|  | B | Improvements to road from Pathappanagudi to Shira border via Jajur, Parashurampura, Dharmapura, Sakkara, Newly upgraded State Highway road From KM 0.00 to 46.10 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 4 | 4 |  |  | 4 |  | 4 |  | 0 | 0 |  | 0
104 | 522 |  | Improvements to Yalagodu-Turavanur Doddaghatta MDR from KM 0.00 to 22.20 KM (in Selected Reaches) in Chitradurga Taluk of Chitradurga District | CHD12 | 9 | 10.5 |  |  | 10.5 |  | 10.5 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 92.63 | 101.3 | 4.92 | 37.04 | 55.05 | 4.29 | 101.3 |  | 0 | 0 |  | 0
Shivamogga Special Division | [12 empty] | 0 | 0 |  | -2.45
105 | 523 | A | Improvements to road from State Highway-148 to join State Highway-148 via Sirigere, Thamadihalli, Bilguni, Adagadi, Mandaghatta, Dhyavanakere, Ragihosahalli, Rechikoppa, Shettikere, Shantikere, Koragi, Horabilu, Tuppuru, Byadanal, Kattigehalli Newly upgraded MDR road from KM 0.00 to 23.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 7 | 7 |  |  | 7 |  | 7 |  | 0 | 0 |  | 2.585
|  | B | Improvements to State Highway 148 via Sirigare Manjerikoppa, Maleshankara Temple, Yerebisu, Koodi, Gammanagadde to join State Highway 148 newly upgraded MDR road from KM 0.00 to 20.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 4.9 | 4.9 |  |  |  | 4.9 | 4.9 |  | 0 | 0 |  | 0
|  | C | Improvements to Koodligere-Kammaraghatta State Highway-115 road from KM 7.00 to 17.70 KM (in Selected Reaches) in Bhadravathi Taluk of Shivamogga District | SH-115 | 6 | 8.45 |  | 8.45 |  |  | 8.45 |  | 0 | 0 |  | 0
|  | D | Improvements to From Bhadravathi to Sasivehalli (Honnali Taluk Border) via Holehonnur, Sidlipura, Sanyasikodamge, Nagasamudra, Managotte, Anaveri, Nimbegundi, Saidarakallalli Newly upgraded State Highway road from KM 0.00 to 35.10 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | NEW SH | 3 | 0.415 |  | 0.415 |  |  | 0.415 |  | 0 | 0 |  | 0
106 | 524 | A | Improvements to NH-26 near Hittur Cross from Umblebailu (SH-65) via Ganidalu-uralalli-Lakkinakoppa kadekal- Kuskur-Siddarahalli-Matturu Malalikoppa-Madaripalya, NH-13 & SH-57 to 100 feet road from Vinobhanagar Police Chowki to Sominakoppa, Gejjenahalli, Tyajavalli, Devabalu, Edavala Newly upgraded State Highway road from KM 0.00 to 46.60 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW SH | 14 | 14 |  | 12.8 | 1.2 |  | 14 |  | 0 | 0 |  | 0
|  | B | Improvements to Tumkur - Honnavar State Highway-68 road from KM 6.20 to 9.50 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | SH-68 | 1.26 | 1.26 | 1.26 |  |  |  | 1.26 |  | 0 | 0 |  | 0
107 | 525 | A | Improvements to Begaru -Kalmane MDR road from KM 0.00 to 7.80 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | TRT 08 | 6.85 | 6.85 |  |  | 6.85 |  | 6.85 |  | 0 | 0 |  | 0.135
|  | B | Improvements to Padubidri - Chikkalagudda State Highway - 01 road from KM 113.00 to 131.00 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | SH-01 | 6.65 | 6.65 |  | 6.65 |  |  | 6.65 |  | 0 | 0 |  | 0
|  | C | Improvements to Kuppalli- Kavisaila-Ayanur-Soodur-Gamma-Mallenahalli join to Hirekerur State Highway 148 road from KM 4.40 to 37.00 KM (in Selected Reaches) inTirthahalli Taluk of Shimoga District | SH-148 | 7.25 | 7.25 |  |  | 7.25 |  | 7.25 |  | 0 | 0 |  | 0.4
|  |  | Division Total |  | 56.91 | 56.775 | 1.26 | 28.315 | 22.3 | 4.9 | 56.775 |  | 0 | 0 |  | 0
Shivamogga Division | [12 empty] | 0 | 0 |  | 0
108 | 526 |  | Improvements to Kuppalli- Kavishaila, via Ayanur, Soodur, Gama, Mallenahalli to join Hirekerur State Highway 148 road from KM 92.12 to 156.12 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-148 | 11.6 | 11.2 |  | 11.2 |  |  | 11.2 |  | 0 | 0 |  | 0.4
109 | 527 |  | Improvements to Kumta Kadamadagi State Highway 48 road from KM 139.03 to 158.03 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-48 | 9.85 | 9.85 |  | 9.85 |  |  | 9.85 |  | 0 | 0 |  | 1.2
110 | 528 | A | Improvements to Gajendragada to Soraba State Highway 136 road from KM 280.37 to 282.07 KM and KM 294.82 to 311.29 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-136 | 8.2 | 8.2 |  | 8.2 |  |  | 8.2 |  | 0 | 0 |  | -0.3
|  | B | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 28.50 to 37.00 KM & KM 53.80 to 59.16 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-77 | 8.9 | 8.5 |  | 8.5 |  |  | 8.5 |  | 0 | 0 |  | -3.16
111 | 529 | A | Improvements to Haveri-Sagar State Highway 62 road from KM 99.01 to 109.87 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-62 | 2.6 | 1.4 |  |  | 1.4 |  | 1.4 |  | 0 | 0 |  | -1.46
|  | B | Improvements to Padubidri-Chikkalagudda State Highway- 01 road from KM 158.00 to 160.00 KM (in Selected Reaches) in Hosnagar Taluk of Shivamogga District. | SH-01 | 1.2 | 1.5 | 1.5 |  |  |  | 1.5 |  | 0 | 0 |  | 0
|  | C | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 66.00 to 74.00 KM and KM 76.27 to 87.20 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-77 | 6 | 9.16 |  | 6.7 | 2.46 |  | 9.16 |  | 0 | 0 |  | -4.313
|  |  | Division Total |  | 48.35 | 49.81 | 1.5 | 44.45 | 3.86 | 0 | 49.81 |  | 0 | 0 |  | -0.52
Chikkamangalore Division | [12 empty] | 0 | 0 |  | 0
112 | 530 | A | Imrovemets to Mudigere - Gowdahalli - Hosakere - Devrunda Road MDR from Km 0.00 to Km 28.40 (In Selected Reaches) in MudigereTaluk of Chickmagalur District. | MDI-13 | 12.917 | 17.23 |  |  | 17.23 |  | 17.23 |  | 0 | 0 |  | 0.3
|  | B | Improvements to Aladagudde - Biskal Road MDR from Km 0.00 to Km 16.50 (In Selected Reaches) in Chickmagalur Taluk of Chickmagalur District. | CHK-22 | 4.7 | 5.22 |  |  | 5.22 |  | 5.22 |  | 0 | 0 |  | -0.004
113 | 531 | A | Improvements to Kuduregundi - Muttinarajya Road MDR from Km 0.00 to Km 29.00 (In Selected Reaches) in Narasimharajpura Taluk of Chickmagalur District. | NRP3 | 4.5 | 4.5 |  |  | 4.5 |  | 4.5 |  | 0 | 0 |  | 0
|  | B | Improvements to Masage - Halanduru Road MDR from Km 0.00 to Km 15.00 (In Selected Reaches) in Sringeri Taluk of Chickmagalur District. | SNG8 | 4.04 | 3.74 |  |  | 3.74 |  | 3.74 |  | 0 | 0 |  | 0
114 | 532 | A | Improvements to B.B. Hills Road MDR from Km 0.00 to Km 38.00(In Selected Reaches) in Chickmagalur Taluk of Chickmagalur District | CHK-13 | 12.496 | 12.5 |  |  | 12.5 |  | 12.5 |  | 0 | 0 |  | 0
|  | B | Improvements to Sakarayapattana - Javagal Road MDR from Km0.00 to Km 20.00 (In Selected Reaches) Kadur Taluk of Chickmagalur District. | KDR-22 | 12.02 | 12.02 |  | 7 | 5.02 |  | 12.02 |  | 0 | 0 |  | -1.02
115 | 533 | A | Improvements to NH-206 - mallikoppa via kesarakoppa to join Tarikere Mangalore road from Km 0.00 to Km 15.00 (In Selected Reaches) in Tarikere Taluk of Chickmagalur District. | MDR | 5 | 5 |  |  | 5 |  | 5 |  | 0 | 0 |  | 0
|  | B | Improvement to Road from Birur NH-206 to join Tarikere Hosadurga Via Koratigere Nagamangala MDR from Km 0.00 to km 12.00 (In Selected reaches) in Ajjampura Taluk of Chickmagalur District. | TRK-205 | 4.62 | 4.62 |  |  | 4.62 |  | 4.62 |  | 0 | 0 |  | -0.6
|  | C | Improvements to Shivani - Rangapura Road MDR from Km 0.00 to km 11.00 (In Selected reaches) in Ajjampura Taluk of Chickmagalur District | TRK-204 | 3.38 | 4.4 |  |  | 4.4 |  | 4.4 |  | 0 | 0 |  | -6.15
|  | D | Improvement to Kallattipura - Lalbag Road MDR from Km 0.00 to km 20.00 (In Selected reaches) in Tarikere Taluk of Chikmagalur District. | TRK-5 | 5.09 | 5.09 |  |  | 5.09 |  | 5.09 |  | 0 | 0 |  | 0
|  | E | Improvements to Channapura-Giribhomanahalli Road Via Giriyapura Yagati -Maravanji MDR from Km 0.00 to Km 45.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District | KDR-201 | 8.35 | 8.95 |  |  | 8.95 |  | 8.95 |  | 0 | 0 |  | -0.7
|  | F | Improvements to Road joining Jodilingadalli to SH-152 from Km 0.00 to Km 9.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | KDR- New | 3.41 | 9.56 |  |  | 9.56 |  | 9.56 |  | 0 | 0 |  | -1.8
|  | G | Improvements to Panchanahalli - Timmlapura Road Via Timmalapura Panchanahalli Hoskerehalligate Niduvalli Garagadahalli Anandpuragate Kankanadu Vanabogihalli Honnenhalli Sannenhalli MDR from Km 0.00 to Km 21.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | KDR-223 | 7 | 7 |  |  | 7 |  | 7 |  | 0 | 0 |  | -0.3
|  | H | Improvements to Belgur-Panchanalli Road joining SH-152 from Km 0.00 to Km 5.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District | MDR | 2.5 | 3.2 |  |  | 3.2 |  | 3.2 |  | 0 | 0 |  | -15.107
|  | I | Improvements to Road joining SH-152 to NH-206 from Km 0.00 to Km 12.00 (In Selected Reaches) in Kadur Taluk of Chikmagalur District. | MDR | 3.56 | 5.36 |  |  | 5.36 |  | 5.36 |  | 0 | 0 |  | -3.515
|  | J | Improvements to Road joining SH-152 to Singatgere-Panchanalli Road from Km 0.00 to Km 5.5.00 (In Selected Reaches) in Kadur Taluk of Chickmagalur District. | MDR | 1.8 | 2.1 |  |  | 2.1 |  | 2.1 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 95.383 | 110.49 | 0 | 7 | 103.49 | 0 | 110.49 |  | 0 | 0 |  | 0
|  |  | Shivamogga Circle Total |  | 389.398 | 413.75 | 7.68 | 141.168 | 228.085 | 15.98 | 392.913 |  | 0 | 0 |  | 0
Mangalore Circle | [12 empty] | 0 | 0 |  | 0.2 |  | 0 | 0 | 1.753 | 0 | 1.753
Udupi Division | [12 empty] | 0 | 0 |  | -0.17
116 | 534 | A | Improvements to Padubidre-Chikkalagudda Road (SH-01) from km 50.00 to 52.050 km in (selected reaches) Hebri Taluk of Udupi District. | SH-1 | 1.428 | 1.43 |  | 1.428 |  |  | 1.428 |  | 0 | 0 |  | -0.16
|  | B | Improvements to Mangalore - Athradi SH-67 from Km 47.28 Km to Km 48.28 in (selected reaches) Karkala Taluka of Udupi Dist.. | SH-67 | 1 | 0.8 |  | 0.8 |  |  | 0.8 |  | 0 | 0 |  | -0.4
|  | C | Improvements to Kalyanpura - Mudaru SH from Ch Km 27.50 to Km 32.00 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 1.7 | 1.87 |  | 1.87 |  |  | 1.87 |  | 0 | 0 |  | 2.766
|  | D | Improvement to Subramanya-Udupi SH-37 from Km 119.50 to Km 126.10 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | SH-37 | 3 | 3.16 |  | 3.16 |  |  | 3.16 |  | 0 | 0 |  | 1.326
|  | E | Improvements to Kalyanpura - Mudaru SH from Ch Km 41.00 to Km 48.00 (selected reaches) from single lane to intermediate lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 5.64 | 6.04 |  |  | 6.04 |  | 6.04 |  | 0 | 0 |  | 0
117 | 535 | A | Improvements to Subramanya -Udupi road SH37 from Ch Km 139.40 to Km 153.30 (selceted reaches) in Kapu Taluk of Udupi District.(Via palli Kattigeri, belle, manipura, Kasaba) | SH-37 | 9.466 | 6.7 |  | 6.7 |  |  | 6.7 |  | 0 | 0 |  | 0.17
|  | B | Improvements to Mangalore- Atharadi road SH67 from Ch Km 49.98 to Km 71.74 (selected reaches) in Kapu Taluk of Udupi District. | SH-67 | 6.696 | 5.37 |  | 5.37 |  |  | 5.37 |  | 0 | 0 |  | 1.31
118 | 536 | A | Improvements to Mudradi-Seethanadi- Bhramavara road Development of 4Lane from Ch Km 14.90 to Km 27.70 (selceted reaches) in Bhramavara Taluk of Udupi District.(Via. Havanji, Kolalagiri, Kukkehalli and Perdoor) | Newly Upgraded SH | 5.485 | 5.485 |  |  |  | 5.485 | 5.485 |  | 0 | 0 |  | -0.15
|  | B | Improvements to Koteshwara-Kodi- Kundapura road from Ch Km 0.00 to Km 2.50 MDR in Kundapura Taluk of Udupi District. ( Via :Koteshwara-Kodi- Kundapura ) | KDP204 | 2 | 1.83 |  |  | 1.83 |  | 1.83 |  | 0 | 0 |  | -0.089
|  | C | Improvements to Brahmavara-Jannadi- Biddalkatte-Sauda-Shankaranarayana- Siddapura road from Ch 2.50 Km to 12.00 Km(selceted reaches)MDR in Brahmavara Taluk of Udupi District. ( Via : Koteshwara-Kodi- Kundapura ) | KDP5 | 6.14 | 5.01 |  | 4.83 |  |  | 4.83 |  | 0 | 0 |  | -0.26
|  | D | Improvements to Kota-Goliyangadi road from Ch Km14.80 to Km 20.20 Major District road in Kundapura Taluk of Udupi District. ( Via: Koteshwara-Kodi- Kundapura ) | UDP4 | 5 | 5.15 |  | 5.15 |  |  | 5.15 |  | 0 | 0 |  | -0.15
|  | E | Improvements to Someshwara- Koteshwara road MDR from Ch Km 34.00 to 41.50 Km (selected reaches) in Kundapura Taluk of Udupi District. ( Via. Haladi-Bidkalakatte) | KDP9 | 4.1 | 4.189 |  | 4.189 |  |  | 4.189 |  | 0 | 0 |  | 4.393
119 | 537 | A | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 339.50 to Km 346.20 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 4.876 | 5.136 |  | 5.136 |  |  | 5.136 |  | 0 | 0 |  | 0
|  | B | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 346.20 to 356.45 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 9.291 | 9.471 |  | 9.441 |  |  | 9.441 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 65.822 | 61.641 | 0 | 48.074 | 7.87 | 5.485 | 61.429 |  | 0 | 0 |  | 0
Mangalore Division | [12 empty] | 0 | 0 |  | 2.72
120 | 538 | A | Improvements to Subramanya - Udupi State Highway 37 from Ch Km 3.50 to Km 14.00 (Selected reaches) in Kadaba Taluk of Dakshina Kannada District. | SH37 | 7.08 | 7.08 |  | 7.08 |  |  | 7.08 |  | 0 | 0 |  | 0
|  | B | Improvements to Bangalore-Jalsoor State Highway -85 from Ch Km 291.51 toKm 337.91 (Selected reaches) from single lane to intermediate Lane in Sullia Taluk of Dakshina Kannada District. | SH85 | 10.21 | 10.21 |  |  | 10.21 |  | 10.21 |  | 0 | 0 |  | 0.35
121 | 539 | A | Improvements to Subramanya- Udupi State Highway -37 from Km 72.75 to Km 94.65 in (Selected reaches) Belthangady Taluk of Dakshina KannadaDistrict. | SH37 | 12.02 | 9.3 |  | 9.3 |  |  | 9.3 |  | 0 | 0 |  | 1.68
|  | B | Improvements to Dharmasthala- Thottataddy-Chibidre MDR from Ch Km 0.00 to Km 10.80 (selected reaches) and Puduvettu Kayarthadka Nidle MDR from Ch Km 0.00 to Km 8.00 (selected reaches) in Belthangady Taluk of Dakshina Kannada District. | BEL26 | 3.03 | 3.03 |  |  | 3.03 |  | 3.03 |  | 0 | 0 |  | 0
122 | 540 |  | Improvements to Mani-Ullala road from Ch Km 18.68 to Km 21.00 (4 Lane ) (selected reaches) in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 1.81 | 1.46 | 1.46 |  |  |  | 1.46 |  | 0 | 0 |  | 0
123 | 541 | A | Improvements to Mangalore- Athradi State Highway-67 from Ch Km 32.00 to Km 36.50 to (2 lane) road in Mangalore Taluk of DakshinaKannada District. | SH-67 | 3.7 | 2.02 | 2.02 |  |  |  | 2.02 |  | 0 | 0 |  | -0.15
|  | B | Improvements to Gantalkatte- Mudukonaje- Anegudde-Ammanottu-Marnadu Major District Road from Ch Km 7.70 to Km 10.30 from single lane to intermediate Lane in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 2.02 | 2.02 |  |  | 2.02 |  | 2.02 |  | 0 | 0 |  | 0.46
|  | C | Improvements to Kandandale- Moodbidre- Bantwala road MDR from Ch Km 21.00 to Km 26.00 (2 lane) (selected reaches) in Mangalore Taluk of Dakshina Kannada District. | Newly Upgraded SH | 5.18 | 5.18 |  | 5.18 |  |  | 5.18 |  | 0 | 0 |  | 0
|  | D | Improvements to Kallamundkuru-Paaladkka Mithabailu road Kanthawa High school MDR from Ch Km 0.00 to Km 4.50 (selected reaches) in Mangalore Taluk of Dakshina KannadaDistrict. | Newly Upgraded MDR | 1.82 | 1.97 |  | 1.97 |  |  | 1.97 |  | 0 | 0 |  | 0
|  | E | Improvements to Mangalpette- Taalipadi road MDR from Ch Km 1.80 to 5.00 Km (in selected reaches) in Mangalore Taluk of Dakshina Kannada District | MNG19 | 1.36 | 0.9 |  |  | 0.9 |  | 0.9 |  | 0 | 0 |  | 1.45
|  | F | Improvements to Halleangadi-Pakshikere road MDRfrom Ch Km 0.60 to 3.00 Km in Mangalore Taluk of Dakshina Kannada District (via: Indiranagar to Pakshikere church) | MNG36 | 1.8 | 1.8 |  |  | 1.8 |  | 1.8 |  | 0 | 0 |  | 0
124 | 542 | A | Improvements to Puttur- Uppinangadi- Guruvayanakere development of 4Lane from Ch Km 1.40 to Km 11.60 to (selected reaches) in Puttur Taluk of DakshinaKannada District | PUT8 | 2.3 | 2.3 | 2.3 |  |  |  | 2.3 |  | 0 | 0 |  | 0.85
|  | B | Improvements to Saradka Periyaltada MDR road from Ch Km 0.00 to 9.00 Km (selected reaches) in Bantwala Taluk of Dakshina Kannada District | PUT10 | 6.6 | 5.15 |  |  | 5.15 |  | 5.15 |  | 0 | 0 |  | 0
|  | C | Improvements to Subramanya- Manjeshwara SH-100 road from Ch Km 48.000 to Km 50.00 in Puttur Taluk of Dakshina KannadaDistrict | SH100 | 1.78 | 1.78 |  |  | 1.78 |  | 1.78 |  | 0 | 0 |  | 0
125 | 543 | A | Improvements to Marvuru - Adyapadi - Unele- Kandavara MDR Ch road from Km 0.00 to Km 2.00 (selected reaches) and Maddya Peddiyangadi MDR from Km 0.00 to Km 2.00 (selected reaches) in Mangalore Taluk of Dakshina KannadaDistrict. | MNG105 MNG202 | 3.67 | 2.82 |  |  | 2.82 |  | 2.82 |  | 0 | 0 |  | -0.13
|  | B | Improvements to Parari-Ulayaibettu-Mallur MDR From Ch 2.40 km to 4.40 km in Mangalore Taluk of Dakshina Kannada District | MNG82 | 0.85 | 0.85 |  |  | 0.85 |  | 0.85 |  | 0 | 0 |  | 1.13
|  | C | Improvements to Bhatrakere - Katlasar - Kukkudakatte - Nirakere - Todar -Mastikatte - Road MDR from Ch 0.00 to 5.00 Km (selected reaches) in Mangalore Taluk of Dakshina Kannada District | Newly Upgraded MDR | 3.72 | 3.72 |  |  | 3.72 |  | 3.72 |  | 0 | 0 |  | 0
|  | D | Improvement to Surthakal- Kabaka SH 101 development of 4lane from Km 1.60 to Km 4.80 ( in selected reaches) in Mangalore Taluka of Dakishna Kannada District. | SH-101 | 1.7 | 1.83 | 1.83 |  |  |  | 1.83 |  | 0 | 0 |  | 0
126 | 544 | A | Improvements to Moodabidre-Bantwal, Moodabidre-Kadandale MDR from Ch 40.80 Km to 42.80 Km (in selected reaches) in Bantwal taluk of Dakshina Kannada district. (via: Poochmooguru- Bantwal) | Newly Upgraded SH | 1.13 | 1.13 |  |  |  |  | 0 |  | 0 | 0 |  | 0
|  | B | Improvements to Mani -Ullala MDR from Ch 0.00 Km to 2.50 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 1.83 | 1.83 |  | 1.83 |  |  | 1.83 |  | 0 | 0 |  | 0
|  | C | Improvements to Ganjimata Niddodi road via Yedapadavu Kuppepadavu-Arla Soranadu Road Rayi Moorje road from Ch 20.00 Km to 25.85 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 5.74 | 5.74 |  |  | 5.74 |  | 5.74 |  | 0 | 0 |  | 8.36
|  | D | Improvements to Manihalla-Agilamogaru road from Ch 0.00 Km to 15.50 Km MDR (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 6.75 | 6.75 |  |  | 6.75 |  | 6.75 |  | 0 | 0 |  | 12.753
|  | E | Improvements to Vogga Ulli road from Ch 6.00 Km to 14.20 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district.(Via Maninalkaru kakkepadvu Ulli). | BNT19 | 4.28 | 4.28 |  |  | 4.28 |  | 4.28 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 90.38 | 83.15 | 7.61 | 25.36 | 49.05 | 0 | 82.02 |  | 0 | 0 |  | 0
|  |  | MANGALORE Circle Total |  | 156.202 | 144.791 | 7.61 | 73.434 | 56.92 | 5.485 | 143.449 |  | 0 | 0 |  | -0.05
Bangalore Circle | [12 empty] | 0 | 0 |  | -0.2
Bangalore Rural Division | [12 empty] | 0 | 0 |  | 1.038
127 | 545 | A | Improvements to Bangalore-Anekal-Bannerghatta Road (SH-87) from Km 16.80 to Km 20.00 & Km 26.25 to Km 28.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | ANK52 | 3.2 | 3.25 | 3.25 |  |  |  | 3.25 |  | 0 | 0 |  | -1.332
|  | B | Improvements to MDR From NH-7 to SH-87 Via Hulimangala, Jigani from Km 6.50 to Km 9.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 2.2 | 2.4 |  |  | 2.4 |  | 2.4 |  | 0 | 0 |  | -6.2
|  | C | Improvements to MDR From Bagganadoddi to Amani Bidarakere via Mysuruammanadoddi, Shavayanadoddi, Yellamanadoddi, Pujaganahapalaya, Krishnaiahndoddi, Mahntalingapura, Kallubalu,Bukkasagara, Harapanahalli, Koppagate Connecting from Km 0.00 to Km 14.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | SH-87 | 4.805 | 3.767 |  |  | 3.767 |  | 3.767 |  | 0 | 0 |  | 0.13
|  | D | Improvements to New SH From Magadi Road (SH-85) to Gunjuru (SH-35) via Hamahappanahalli cross-Chandrappa Circle- Doddaaladamara-Ramohalli-Kumbalgodu-Agara-Thataguni- Kaggalipura-Bannerughatta-Hommadevanahalli-Bettadasapura-Vipro Junction-Hosuru Road (NH-7) Konnapana Agragara-Sarjapura Main Road-(Kodathi gate) Kachamaranahalli from Km 6.00 to Km 13.60 & Km 17.80 to Km 29.40 (in selected reaches) in Bangalore SouthTaluk of Bangalore Rural District | New SH | 6.08 | 7.412 |  | 7.412 |  |  | 7.412 |  | 0 | 0 |  | -0.51
|  | E | Improvements to MDR From Bylalu to Lakshmipura Ondane Mailikallu from Km 6.20 to Km 8.50 (in selected reaches) in Bangalore South Taluk of Bangalore Rural District | BNS210 | 2.3 | 8.5 |  | 8.5 |  |  | 8.5 |  | 0 | 0 |  | 0
|  | F | Improvements to MDR Connecting BM Road to Karubele via H Gollahalli from Km 2.50 to Km 5.00 (in selected reaches) inBangalore South Taluk of Bangalore Rural District | BNS214 | 2 | 1.87 |  | 0.65 | 1.22 |  | 1.87 |  | 0 | 0 |  | 0.282
|  | G | Improvements to MDR from NH-75 (Makali) to Bettahalsuru connecting SH-104 via Honnasandra Cross, Aluru, APMC Yard,Basaveshwara Temple, Kodipalaya, Madhure, Kakolu,Rajanakunte, Thimmasandra, Betta Halasuru, NH-7, Muthagada Halli, Begur, Chikkanahalli and mylanahalli from Km 0.00 to Km 7.65 (Change to Ch:19.00) (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | SH | 6.05 | 6.56 |  | 0.612 | 5.948 |  | 6.56 |  | 0 | 0 |  | -2.047
|  | H | Improvements to MDR from Singanayakanahalli to Madappanahalli via Shyanubhoganahalli Ch: 0.50 KM to 2.35 KM(in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 1.85 | 1.85 |  | 1.85 |  |  | 1.85 |  | 0 | 0 |  | 0.04
|  | I | Improvements to MDR from Gollahalli To Hesarghatta CH 8.20 KM to CH : 9.60 KM in Bangalore North Taluk, of Bangalore District | MDR | 1.4 | 1.118 |  | 1.118 |  |  | 1.118 |  | 0 | 0 |  | 0
|  | J | Improvements to Road from Channapattana Kavanapura- SRS Betta- Avverahalli-Kailancha-Nagohalli-Hunasanhalli-Uragahalli-Bidadi-Ganakallu-Nelamangala from Ch;65.70 to70.00 Km ( Mallasandra to Sondekoppa) in Bangalore North Taluk, of Bangalore District | MDR | 4.3 | 6.347 |  | 6.347 |  |  | 6.347 |  | 0 | 0 |  | 0.62
128 | 546 | A | Improvements to Chandapura -Dommasandra MDR from Km 1.50 to Km 6.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 4 | 3.96 |  | 3.96 |  |  | 3.96 |  | 0 | 0 |  | 1.38
|  | B | Improvements to Iggaluru to Gumlapura MDR from Km 29.25 to Km 30.56 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 1.2 | 1.2 | 1.2 |  |  |  | 1.2 |  | 0 | 0 |  | 0.247
|  | C | Improvements to MDR FromVenkateshwara circle, Shanimahathama Temple via to Ragavendra Circle, Srirama Temple, Tilaknagara & Shanimahathama Temple MDR from Km 34.00 to Km 36.00 in Anekal Taluk of Bangalore Rural District | MDR | 1.56 | 0.94 | 0.94 |  |  |  | 0.94 |  | 0 | 0 |  | 8.5
129 | 547 | A | Improvements to MDR from Dommasandra (Bangalore) to Sulikunte Colony via Shantigiri Asharama, Kodathi, JHC, Wipro, NEZ, Mulluru from Km 0.00 to Km 10.50 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District | BNE18 | 6.46 | 5.18 |  | 2.68 | 2.4 |  | 5.08 |  | 0 | 0 | 2.63 | 0.215
|  | B | Improvements to MDR from Bendiganahalli (NH-04) to Bommenahalli Budigere via Raghumenahalli, Hancharahalli, Jyothipura, Thirumenhalli from Km 0.00 to Km 13.00 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District. | MDR | 7.9 | 7.653 |  |  | 6 | 1.653 | 7.653 |  | 0 | 0 |  | 0.61
130 | 548 |  | Improvements to Bangalore Nandi MDR Connecting SH-104 to Bandikodigehalli MDR via Hosuru Bande, Bagaluru from Km 12.60 to Km 23.50 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 9.2 | 4.5 | 0 |  | 0.7 |  | 0.7 |  | 0 | 0 |  | 0
131 | 549 | A | Improvements to Hesarughatta Tank bund road (SH-39)from Km 4.00 to Km 7.00 in Bangalore North Taluk of Bangalore Rural District | SH-39 | 2.9 | 2.69 | 0.97 | 1.715 |  |  | 2.685 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR from Lakshmipura Cross to Golhalli Hesrughatta Road SH-39 via Lakshmipura, Abbigere, Chikkabanavara, Pipe line Road, Ganegarahalli, Somashettyhalli from Km 0.00 to Km 10.20 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 5.3 | 4.69 |  | 2.05 | 2.64 |  | 4.69 |  | 0 | 0 |  | 0
132 | 550 | A | Improvements to MDR from Muthkuru to NH-207 via Bylahalli, Muthgadahalli-Thottanuru-Thiruvaranga from Km 0.00 to Km 8.10 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS9 | 4.9 | 4.9 |  |  | 4.9 |  | 4.9 |  | 0 | 0 |  | 0.7
|  | B | Improvements to Siddalagatta - Anekal SH 35 road road MDR from Km 25.64 to Km 34.84 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS25 | 4.604 | 4.604 |  | 4.604 |  |  | 4.604 |  | 0 | 0 |  | 2.1
|  | C | Improvements to MDR from NGD (SH 74) to Thayagadahalli (BTS Road) via Byrashettyhalli-Bolamarahalli from Km 0.00 to Km 5.10 in Nelamangala Taluk of Bangalore Rural District | NLM10 | 5.1 | 5.1 |  |  | 5.1 |  | 5.1 |  | 0 | 0 |  | -0.22
|  | D | Improvements to MDR from NH-04 to Sompura via Devarahosahalli-Kamalapura Agalakuppe from Km 7.00 to Km 12.00 (in selected reaches) in Nelamangala Taluk of Bangalore Rural District | MDR | 2.66 | 1.96 |  | 1.96 |  |  | 1.96 |  | 0 | 0 |  | 1.47
|  | E | Improvements to Kodigehalli-Kanakenahalli road MDR from Km 0.00 to Km 19.00 (in selected reaches) in DoddaballapuraTaluk of Bangalore Rural District | DOD7 | 9.25 | 7.15 |  |  | 7.15 |  | 7.15 |  | 0 | 0 |  | 6.773
|  | F | Improvements to Devanahalli-Kempapura road (SH-96) from Km10.00 to Km 12.25 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | SH-96 | 1.4 | 1.62 | 1.62 |  |  |  | 1.62 |  | 0 | 0 |  | 0
|  | G | Improvements to MDR from Devanahalli town to NH-44 from Kempegowda Circle to Road to rani Circle from Km 0.00 to Km 3.60 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | DVN9 | 1.47 | 0 |  |  |  |  | 0 |  | 0 | 0 |  | -0.125
|  |  | Division Total |  | 102.089 | 99.221 | 7.98 | 43.458 | 42.225 | 1.653 | 95.316 |  | 0 | 0 |  | -1.77
Ramanagara Special Division | [12 empty] | 0 | 0 |  | 2.4
133 | 551 | A | Improvements to Road from Channapattana Kavanapura- SRS Betta- Avverahalli-Kailancha-Nagohalli-Hunasanhalli-Uragahalli-Bidadi- Ganakallu-Nelamangala from Ch;3.00 to 5.20 Km( in selected Reaaches) in Channapattana Taluk of Ramanagara District | MDR | 1.875 | 2 |  |  | 2 |  | 2 |  | 0 | 0 |  | 0
|  | B | Improvements to Road joining SH-33 from Harohalli- Maralvadi-hunasanhalli- Bannimukkodlu- Aalnatha kodihalli- Sathanur- Muttatti-kabbalu- channapattana- thittamaranahalli- bevoor from CH: 98.80 K M to 105 KM(in selected reaches) | SH-33 | 6.2 | 7.97 |  | 7.97 |  |  | 7.97 |  | 0 | 0 |  | 8
|  | C | Improvements to MDR From Channapatna to Ramanagara Border Via Kannamangala, Angarahalli, Gollahallidoddi from Km 7.35 to Km 16.00 (In selected reaches) in Channapatna Taluk of Ramanagara District. | MDR | 6.45 | 4.05 |  |  | 4.05 |  | 4.05 |  | 0 | 0 |  | 8.505
|  | D | Improvements to New SH Connecting From NH- 275 to Krishnapura Via Byrapattana, Chikkalooru, V.V.Halli, Ankushanahalli from Km 5.30 to 11.30 Km (In selected reaches) in Channapatna Taluk of Ramanagara District. | New SH | 6 | 6 |  |  | 6 |  | 6 |  | 0 | 0 |  | 0
134 | 552 |  | Improvements toNew SH From Kodihalli to Sathanuru Via Doddalahalli from Km 0.00 to Km 25.30 (In selected reaches) in Kanakapura Taluk of Ramanagara District. | New SH | 20 | 13.25 | 0.75 | 11.25 |  |  | 12 |  | 0 | 0 |  | -0.24
|  |  | Division Total |  | 40.525 | 33.27 | 0.75 | 19.22 | 12.05 | 0 | 32.02 |  | 0 | 0
Ramanagara Division | [12 empty] | 0 | 0 |  | 0.34
135 | 553 | A | Improvements to Hunasanahalli – Chikkanahalli( SH-3 Via Kanakapura, Ramanagara) , Magadi from Ch: km 82.67 to 94.40 km in Magadi Taluk of Ramanagara District. | SH-3 | 12 | 12.24 |  | 12.24 |  |  | 12.24 |  | 0 | 0 |  | -2.52
|  | B1 | Improvements to Hunasanahalli Chikkahalli Road SH -3 Via Kanakapura, Ramanagara, Magadi from Km 48.40 to Km 82.67 (In selected reaches) in Ramanagara Taluk of Ramanagara District. |  | 9.2 | 2.65 |  | 2.62 |  |  | 2.62 |  | 0 | 0 |  | 0
|  | B2 | Improvements to NH 275-Channapatna to Nelamangala via kavanapura S.R.S betta, Avverahalli, Kailancha, Nagohalli, Hunasanahalli, Urgalli, Bidadi, Ch:5.20 to 35.70km (Change of road) | SH-3 |  | 8.86 |  |  | 8.86 |  | 8.86 |  | 0 | 0 |  | -0.37
|  |  | Division Total |  | 21.2 | 23.75 | 0 | 14.86 | 8.86 | 0 | 23.72 |  | 0 | 0 |  | 0
Tumkur Division | [12 empty] | 0 | 0 |  | 0
136 | 554 | A | Improvements to Doddagangavadi Gate - Chowdanakuppe Road SH 111 from Km 12.00 to Km 15.25 (in selected reaches) in Kunigal Taluk of Tumakuru District | SH 111 | 1.89 | 2.26 |  | 2.26 |  |  | 2.26 |  | 0 | 0 |  | 0
|  | B | Improvements to MDR (old NH48) Road in Kunigal Town from Km 71.40 to Km 71.65 (in selected reaches) in Kunigal Taluk of Tumakuru District | KNL227 | 0 | 0 |  |  |  |  | 0 |  | 0 | 0 |  | -1.78
|  | C | Improvements to MDR connecting from NH48-Join Anchepalya - yelagalavdi Road via mallagatta,Begur,Kundur, Rajgere, Boregowdanapallya from Km 0.00 to Km 10.00 (in selected reaches) & bridge at Ch 2.25 Km in Kunigal Taluk of Tumakuru District | KNL27 | 1.125 | 1.125 |  |  | 1.125 |  | 1.125 |  | 0 | 0 |  | 0
137 | 555 | A | Improvements to Bagepalli- Halaguru Road SH 94 from Km 140.00 to Km 141.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | SH 94 | 0.63 | 0.63 |  |  | 0.63 |  | 0.63 |  | 0 | 0 |  | 0.03
|  | B | Improvements to New SH road connecting from NH 206 to NH 4 Via Tumkur Chelur Bukkapatna from Km 0.00 to Km 13.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | NEW SH | 5.95 | 7.73 |  |  | 7.73 |  | 7.73 |  | 0 | 0 |  | 0.354
|  | C | Improvements to K K Road to Kalyanapura Road Via Lakkenahalli, Tavrakere, Honnenahalli MDR from Km 0.00 to Km 1.75 & Km 6.90 to Km 15.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | MDR | 3.78 | 3.78 |  |  | 3.78 |  | 3.78 |  | 0 | 0 |  | 0
138 | 556 | A | Improvements to MDR from NH-4 to join Aregujjanahalli Road Via Maidala from Km 0.00 to Km 9.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-219 | 1.35 | 1.32 |  | 1.22 | 0.1 |  | 1.32 |  | 0 | 0 |  | -0.009
|  | B | Improvements to SH 33 from Km 23.70 to Km 26.40 in selected reaches in Tumakuru Taluk of Tumakuru District | SH-33 | 1.7 | 1.346 | 1.346 |  |  |  | 1.346 |  | 0 | 0 |  | -0.07
|  | C | Improvements to Hillstation road MDR from Km 0.00 to Km 5.20 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-16 | 2.19 | 2.19 |  | 2.19 |  |  | 2.19 |  | 0 | 0 |  | 0
|  | D | Improvements to K.B Road to AJ Road Via Amruthagiri Bittanakurike MDR from Km 0.00 to Km 10.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-203 | 2 | 2.009 |  |  | 2.009 |  | 2.009 |  | 0 | 0 |  | 0
|  | E | Improvements to Tumkur - Urdigere Road MDR from Km 0.00 to Km 6.00 (in selected reaches) in Tumakuru Taluk of Tumakuru District | TMK-9 | 0.66 | 0.73 | 0.73 |  |  |  | 0.73 |  | 0 | 0 |  | -2.026
139 | 557 | A | Improvements to Tumkur Chelur Bukkapatna Road MDR from Km 22.00 to Km 30.00 (in selected reaches) in Gubbi Taluk of Tumakuru District | GBB3 | 1.45 | 1.45 |  | 1.45 |  |  | 1.45 |  | 0 | 0 |  | 0
|  | B | Improvements to Gubbi Hebbur Road MDR from Km 3.00 to Km 7.725 (in selected reaches) in Gubbi Taluk of Tumakuru District | GBB12 | 4.67 | 4.67 |  |  | 4.67 |  | 4.67 |  | 0 | 0 |  | -0.765
140 | 558 | A | Improvements to Bochihalli-Turuvekere-Dabbegataa Road MDR from Km 0.00 to Km 1.20, Km 4.39 to Km 4.58, Km 14.70 to Km 15.40, Km 19.00 to Km 20.00, Km 20.70 to Km 30.00, Km 32.00 to Km 35.80 (in selected reaches) in Turuvekere Taluk of Tumakuru District | NEW SH | 10.43 | 12.456 |  |  | 12.456 |  | 12.456 |  | 0 | 0 |  | 0
|  | B | Improvements to Hirisave - Nonavinakere Road MDR from Km 65.80 to Km 78.80 (in selected reaches) in Turuvekere Taluk of Tumakuru District | TVK24 | 4.44 | 4.44 |  |  | 4.44 |  | 4.44 |  | 0 | 0 |  | -0.15
141 | 559 | A | Improvements to Mandya Hadagali Road SH 47 from Km 128.80 to Km 142.72 & Km 146.72 to Km 164.54 (in selected reaches) in Tiptur Taluk of Tumakuru District | SH 47 | 7.63 | 8.395 | 0.765 | 7.63 |  |  | 8.395 |  | 0 | 0 |  | -4.786
|  | B | Improvements to New SH Road connecting from NH-275 to join SH-47 via Dasavara, Makali, Ujjani, hittalapura, Huliyurdurga, K Honnamachanahalli, Kilara, Paduvagere, Hanumapura, Kodavatti, Yediyur, Mayasandra, Turuvekere, Nonavinakere, Hedgarahalli from Km 85.86 to Km 100.26 (in selected reaches) in Tiptur Taluk of Tumakuru District (Yediyur Tiptur Road MDR from Km 37.20 to Km 51.00 in selected reaches in Tiptur Taluk of Tumakuru District) | TPT8 | 7.57 | 7.57 |  | 7.57 |  |  | 7.57 |  | 0 | 0 |  | 0
142 | 560 |  | Improvements to Mandya Hadagali Road SH 47 from Km 164.54 to Km 195.05 (in selected reaches) in Chiknayakanahalli Taluk of Tumakuru District | SH 47 | 12.45 | 12.6 |  | 12.6 |  |  | 12.6 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 69.915 | 74.701 | 2.841 | 34.92 | 36.94 | 0 | 74.701 |  | 0 | 0 |  | -1.2
Madhugiri Division | [12 empty] | 0 | 0 |  | 0
143 | 561 |  | Improvements to Sira- Amarapura Road MDR from Km 0.00 to Km 42.20 (in selected reaches) in Sira Taluk of Tumakuru District | SRA3 | 12.25 | 12.25 |  | 12.25 |  |  | 12.25 |  | 0 | 0 |  | -0.925
144 | 562 |  | Improvements to Midigeshi-Chandanadur Road MDR from Km 38.00 to Km 47.70 (in selected reaches) in Madhugiri Taluk of Tumakuru District | MDG -9 | 7.12 | 8.32 |  |  | 8.32 |  | 8.32 |  | 0 | 0 |  | 1.14
145 | 563 | A | Improvements to Bagepalli- Halaguru Road SH 94 from Km 94.57 to Km 103.87 (in selected reaches) in Koratagere Taluk of Tumakuru District | SH 94 | 3.33 | 3.33 |  | 3.33 |  |  | 3.33 |  | 0 | 0 |  | -0.505
|  | B | Improvements to New SH road connecting from NH 48 (Nelahalu) to SH 158 (Chikkamaluru) Road Via Koratagere, Byrenahalli from Km 20.00 to Km 25.00 (in selected reaches) in Koratagere Taluk of Tumakuru District | NEW SH | 1.9 | 2.825 |  | 2.825 |  |  | 2.825 |  | 0 | 0 |  | -0.148
|  | C | Improvements to Byrenahalli - Thondebavi Road MDR from Km 0.00 to Km 13.10 (in selected reaches) in Koratagere Taluk of Tumakuru District | KTG -8 | 4.67 | 3.53 |  | 3.53 |  |  | 3.53 |  | 0 | 0 |  | -1.638
146 | 564 | A | Improvements to Kumta-Kadamadagi Road SH 48 from Km 352.00 to Km 392.16 (in selected reaches) in Pavagada-Taluk of Tumakuru District | SH 48 | 4.145 | 4.65 |  | 4.65 |  |  | 4.65 |  | 0 | 0 |  | 0
|  | B | Improvements to Pavagada Hindpur MDR from Km 0.00 to Km 29.60 (in selected reaches) in Pavagada Taluk of Tumakuru District | PVG-4 | 1.235 | 1.383 |  |  | 1.383 |  | 1.383 |  | 0 | 0 |  | -3
|  |  | Division Total |  | 34.65 | 36.288 | 0 | 26.585 | 9.703 | 0 | 36.288 |  | 0 | 0 |  | 0.375
Chikballapura Division | [12 empty] | 0 | 0 |  | 0
147 | 565 | A | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 87.70 to Km 106.80 (in selected reaches) in Bagepalli Taluk of Chikballapura District | SH 05 | 5.9 | 8.9 | 0.15 | 8.75 |  |  | 8.9 |  | 0 | 0 |  | -0.375
|  | B | Improvements to Chinthamani- K.Y Road Via Bikkanahalli, N.Kotturu, Kotagal, Sujjanahalli, Nandhanahosalli, Paapatimmanahalli New MDR from Km 3.20 to Km 13.00 (in selected reaches) in Chinthamani Taluk of Chikballapura District | NEW MDR | 8.6 | 8.225 |  |  | 8.225 |  | 8.225 |  | 0 | 0 |  | -0.001
|  | C | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 78.00 to Km 86.50 (in selected reaches) in Sidlagatta Taluk of Chikballapura District | SH 05 | 5.65 | 5.65 |  | 5.65 |  |  | 5.65 |  | 0 | 0 |  | 0
148 | 566 |  | Improvements to Chinthamani (SH 82) to Gauribidanuru connecting Road Via Cheluru, Bagepalli, Yallodu, Mallenahalli Cross, Vatadahosahalli Road New SH from Km 80.40 to Km 90.30 & Km 95.80 to Km 103.90 (in selected reaches) in Gauribidanuru Taluk of Chikballapura District | NEW SH | 8.1 | 8.475 |  | 8.475 |  |  | 8.475 |  | 0 | 0 |  | 0.2
149 | 567 | A | Improvements to Vijayapura- Nandhi Road New SH from Km 0.00 to Km 5.40 (in selected reaches) in Chikballapura Taluk of Chikballapura District | NEW SH | 5.05 | 5.051 |  | 5.051 |  |  | 5.051 |  | 0 | 0 |  | -0.185
|  | B | Improvements to Melur- Chadalapura Road MDR from Km 7.00 to Km 13.00 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR17 | 4.2 | 4.2 |  |  | 4.2 |  | 4.2 |  | 0 | 0 |  | -2.986
|  | C | Improvements to SH-58 to Chickballapur connecting Road via Namagondlu and Kethenahally Road MDR from Km 33.30 to Km 35.50 & Km 41.10 to Km 44.00 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR15 | 4.1 | 3.9 |  |  | 3.9 |  | 3.9 |  | 0 | 0 |  | 0
|  | D | Improvements to Gudibanda to join SH-58 and on to state border Via Ramapatna, Mandikal, Nallakadirenahally, Venkatapura, D.Palya and Melya MDR from Km 6.40 to Km 11.40 Km & Km 18.00 to Km 20.20 (in selected reaches) in Chikballapura Taluk of Chikballapura District | CBR21 | 3.5 | 3.685 |  |  | 3.685 |  | 3.685 |  | 0 | 0 |  | -1.455
|  |  | Division Total |  | 45.1 | 48.086 | 0.15 | 27.926 | 20.01 | 0 | 48.086 |  | 0 | 0 |  | 0
Kolar Division | [12 empty] | 0 | 0 |  | -0.42
150 | 568 | A | Improvements to Bangarapete - Kamasamudram Road MDR from Km 0.90 to Km 3.45, Km 4.695 to Km 9.50 & Km 10.00 to Km 11.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT11 | 5.16 | 6.615 |  |  | 6.615 |  | 6.615 |  | 0 | 0 |  | 0
|  | B | Improvements to Budhikote Kanamanahalli Road Via Balamande MDR from Km 0.00 to Km 3.00 & Km 16.25 to Km 20.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT 10 | 1.87 | 1.87 |  |  | 1.87 |  | 1.87 |  | 0 | 0 |  | -0.09
|  | C | Improvements to Devanahalli-Kempapura Road SH-96 from Km 83.00 to Km 95.51 (in selected reaches) in K G F Taluk of Kolar District | SH 96 | 2.98 | 3.4 | 3.4 |  |  |  | 3.4 |  | 0 | 0 |  | -0.19
|  | D | Improvements to Station Road MDR from Km 0.20 to Km 1.80 (in selected reaches) in K G F Taluk of Kolar District | BGT26 | 1.6 | 1.6 | 1.6 |  |  |  | 1.6 |  | 0 | 0 |  | 0
|  | E | Improvements to K G F State fund Road MDR from Km 2.92 to Km 4.20 (in selected reaches) in K G F Taluk of Kolar District | BGT5 | 1.1 | 1.19 | 1.19 |  |  |  | 1.19 |  | 0 | 0 |  | -0.135
|  | F | Improvements to Kolar- Malur- Hosur Road New SH from Km 12.60 to Km 22.50 (in selected reaches) in Malur Taluk of Kolar District | NEW SH | 6.57 | 6.76 |  | 6.76 |  |  | 6.76 |  | 0 | 0 |  | 0.55
151 | 569 |  | Improvements to Kolar- Malur- Hosur Road New SH from Km 0.00 to Km 12.60 (in selected reaches) in Kolar Taluk of Kolar District | NEW SH | 6.55 | 6.55 |  | 6.55 |  |  | 6.55 |  | 0 | 0 |  | 0.342
152 | 570 | A | Improvements to Andhra Border K Bayyapalli to Andhra Border Road Via Rayalamana dinne, Mulabagal, Vammasandra, Gukunte, Shankarapura New SH from Km 3.20 to Km 14.60 & Km 33.35 to Km 33.80 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW SH | 5.7 | 5.835 | 1.3 |  | 4.535 |  | 5.835 |  | 0 | 0 |  | -0.15
|  | B | Improvements to Mudavadi Kothamangal Road MDR from Km 14.32 to Km 21.04 (in selected reaches) in Mulabagal Taluk of Kolar District | MUL9 | 5.9 | 5.35 |  |  | 5.35 |  | 5.35 |  | 0 | 0 |  | 0.085
|  | C | Improvements to Mulabagal Punganur Road to Mulabagal Ramasandra connecting Road Via Byrakuru, Chikura Hosahalli, Rajendrahalli, Gudipalli, Nachahalli, Gukunte New MDR from Km 0.00 to Km 5.00 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW MDR | 2.45 | 2.108 |  |  |  | 2.108 | 2.108 |  | 0 | 0 |  | -1.463
|  | D | Improvements to Kothapalli- Masthi Road SH 99 from Km 9.00 to Km 18.60 (in selected reaches) in Srinivaspura Taluk of Kolar District | SH 99 | 7.45 | 7.6 |  | 7.6 |  |  | 7.6 |  | 0 | 0 |  | 1.885
|  | E | Improvements to Bayyapalli- Bandapalli Road MDR from Km 0.00 to Km 10.20 (in selected reaches) in Srinivaspura Taluk of Kolar District | SRI 9 | 10.2 | 10.115 |  |  | 10.115 |  | 10.115 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 57.53 | 58.993 | 7.49 | 20.91 | 28.485 | 2.108 | 58.993 |  | 0 | 0 |  | 0
|  |  | Bangalore Circle Total |  | 371.009 | 374.309 | 19.211 | 187.879 | 158.273 | 3.761 | 369.124 |  | 0 | 0 |  | -2.12
Mysore Circle | [12 empty] | 0 | 0 |  | -0.04
Mandya Division | [12 empty] | 0 | 0 |  | 0
153 | 571 | A | Improvements to Road from 142 Km of Sira-Najangudu to join 40th km of NH-48 Dudda road (MDR) from 0.00 km to 11.02 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 3.63 | 5.75 |  | 0.26 | 5.49 |  | 5.75 |  | 0 | 0 |  | -0.75
|  | B | Improvements to Road from MN road to join BN road Via M K Road, Hulivana, Chamalapura, Keelara, Dodda Banasawadi, Chikka Banasawadi & Hodaghatta (MDR) from 3.80 km to 11.28 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 2.62 | 2.66 |  |  | 2.66 |  | 2.66 |  | 0 | 0 |  | 0
|  | C | Improvements to Chinnayakanahalli- Tubinakere Road (MDR) from 1.10 km to 12.40 (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 1.55 | 1.55 |  |  | 1.55 |  | 1.55 |  | 0 | 0 |  | -0.025
|  | D | Improvements to BN Road to TM Hosur-Alagudu-Molenahalli-Koppalu Via Kodiyala-Yaliyur Road (Via T.M.Hosur) (MDR) from 9.00 km to 11.50 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 1.71 | 2.46 |  |  | 2.46 |  | 2.46 |  | 0 | 0 |  | 0.5
|  | E | Improvements to Srirangapatna chanarayapatna road darasaguppe road to join nelamane village (MDR) from 0.00 km to 2.60 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 1.167 | 1.167 |  |  | 1.167 |  | 1.167 |  | 0 | 0 |  | 0.06
|  | F | Improvements to Road joning Mandya - Madduru Taluk border Via Cheeranahalli (MDR) from km 1.20 km to 8.85 km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 1.695 | 1.72 |  |  | 1.72 |  | 1.72 |  | 0 | 0 |  | -0.164
|  | G | Improvements to Arakere - Mandya- Bannur road to Bannahally-Bettahally Road (MDR) from 0.00 km to 4.32 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 1.78 | 1.28 |  |  | 1.28 |  | 1.28 |  | 0 | 0 |  | 0
154 | 572 | A | Improvements to Road from M G M Road to Join K B Road Via K Shettihalli, Yadaganahalli, Sabbana Halli, Hebbakavadi Nala, Bheemana Halli, Bidara Hosahalli (MDR) from 0.00 km to 14.75 km (In Selected Reaches) in Madduru Taluk of Mandya District. | MDR | 4.1 | 4.04 |  |  | 4.04 |  | 4.04 |  | 0 | 0 |  | 0
|  | B | Improvements to Road from Hebberelu Village to join Lingasandra Cross Via Byalada kere, Navile, Bettada Rangaswami Temple, Lingasandra (MDR) from 0.00 km to 12.50 km (In Selected Reaches) in Madduru Taluk of Mandya District. | MDR | 4.086 | 4.25 |  |  | 4.25 |  | 4.25 |  | 0 | 0 |  | 0
155 | 573 | A | Improvements to Bindiganavile -Kadabahalli Road to join Bindiganavile -Kadabahalli Road via Mangaravally, Bydarahalli, Acharyapura & Vaddarahatti (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 2.655 | 2.655 |  |  | 2.655 |  | 2.655 |  | 0 | 0 |  | 0
|  | B | Improvements to Bindiganavile-ayyarahalli road via garudanahalli road (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 2.512 | 2.512 |  |  | 2.512 |  | 2.512 |  | 0 | 0 |  | 0
|  | C | Improvements to Mylarpatna to join NH 48 near Kalinganahalli gate (MDR) from 0.00 km to 7.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 3.458 | 4.6 |  |  | 3.458 |  | 3.458 |  | 0 | 0 |  | -1.9
156 | 574 | A | Improvements to Road from 2/15Mile of S.A road to join Hariharapura-Lingapura (MDR) from 6.00 km to 36.50 km(In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 3.125 | 3.125 |  |  | 3.125 |  | 3.125 |  | 0 | 0 |  | 0.075
|  | B | Improvements to Road from K.R.Pet-Bandihole road to join Kikkeri-Mandagere road via Heggadahalli, Hoddarahalli, ICL Factory, Ramenahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 2.415 | 2.415 |  |  | 2.415 |  | 2.415 |  | 0 | 0 |  | 0
|  | C | Improvements to Road from G.Boppanahalli – Halekothamaranahalli - Nayakanahalli, Malgur, Singapura. (MDR) from 4.50 km to 12.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 1.7 | 3.6 |  |  | 2.32 | 1.28 | 3.6 |  | 0 | 0 |  | 0
|  | D | Improvements to Road to Join Somanahalli to Somanathapura Via Mamballi (MDR) from km 0.00 to km 1.90 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 1.115 | 1.04 |  |  | 1.04 |  | 1.04 |  | 0 | 0 |  | 0
|  | E | Improvements to Road from S.A road to join Gondihalli via Madapura (MDR) from km 6.00 to km 9.40 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 1.95 | 2.16 |  |  | 1.95 |  | 1.95 |  | 0 | 0 |  | -0.73
|  | F | Improvements to Road from Nargonahalli to join Vitalapura via Giddanakoppalu, Gavimata, Kapanahalli (MDR) from km 0.00 to km 1.00 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 0.7 | 0.85 |  |  | 0.7 |  | 0.7 |  | 0 | 0 |  | 0
|  | G | Improvements to Hosaholalu-Ballekere-Natanahalli road (MDR) from 7.50 km to 8.50 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 0.774 | 0.774 |  |  | 0.774 |  | 0.774 |  | 0 | 0 |  | -0.222
|  | H | Improvements to Road from Bookinakere to join Bommalapura via Chokanahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 2.3 | 3.03 |  |  | 3.03 |  | 3.03 |  | 0 | 0 |  | -2.673
|  | I | Improvements to Road from Shrirangapatna - Arasikere Road (SH-07) to join Goodehosahalli Via Anegola, Bolamaranahalli & Kadahemmige (MDR) from 3.00 km to 6.71 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 1.344 | 1.344 |  |  | 1.344 |  | 1.344 |  | 0 | 0 |  | -0.84
157 | 575 | A | Improvements to Mandya- Thendekere from 17.00 km to 19.50 km (In Selected Reaches) in Pandavapura Taluk of Mandya District. | MDR | 1.413 | 1.635 |  |  | 1.635 |  | 1.635 |  | 0 | 0 |  | -0.205
|  | B | Improvements to Mundalakoppalu-Chikanahalli-Halebidu-Neelanahalli Road on the Kerettonnur-Melukote road due to Mandya- Thendekere from 0.00 km to 7.40 km (In Selected Reaches) in Pandavapura Taluk of Mandya District. | MDR | 1.827 | 4.5 |  |  | 4.5 |  | 4.5 |  | 0 | 0 |  | -0.056
|  | C | Improvements to road from 7th KM of Mandya-Hadagali Road to join 15th Km Mandya-Hadagali Road via Mallamanayakkattu – Gadadar – Modacakkanahalli - Kannatti from 0.00 km to 5.00 km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 3.36 | 4.2 |  |  | 2.5 | 1.7 | 4.2 |  | 0 | 0 |  | -0.45
158 | 598 | A | Road joining NH-209 to SH-84 Via Halaguru, K. Belluru, Rudrakshipura, Madduru, Koppa & Kowdle (SH) | SH-84 | 1.085 | 1.29 |  | 0 | 1.29 |  | 1.29 |  | 0 | 0
|  | B | Improvements to NH-209 to join Pandithhalli-Shimsha (PS) road (MDR) | MDR | 3.134 | 3.19 |  |  | 3.19 |  | 3.19 |  | 0 | 0 |  | -8.785
|  | C | Improvements to Road from Malavalli to join 16th km of Mandya-Bannur road (Sulthan Road) (MDR) (In Selected Reaches) in Malavally Tq | MDR | 1.58 | 2.03 |  | 1.03 | 1 |  | 2.03 |  | 0 | 0 |  | 0
159 | 606 |  | Improvements to K R Pete-Sravanabelagola Road MDR from 0.00km to 2.30 km (in Selected reaches) in K R Pete taluk of Mandya District | MDR | 1.255 | 1.255 |  | 0.5 |  |  | 0.5 |  | 0 | 0 |  | 0.09
|  |  | Division Total |  | 60.04 | 71.082 | 0 | 1.79 | 64.055 | 2.98 | 68.825 |  | 0 | 0 |  | -0.02
Mysore Division | [12 empty] | 0 | 0 |  | 0
160 | 576 | A | Improvements to Koratagere-Bavali Road (SH-33) in Mysore Town | SH-33 | 2.5 | 2.41 | 2.41 |  |  |  | 2.41 |  | 0 | 0 |  | -0.03
|  | B | Improvements to Bagalakote-Biligiriranganabetta (SH-57) in Nanjanagudu Tq | SH-57 | 9.31 | 9.33 |  | 9.33 |  |  | 9.33 |  | 0 | 0 |  | 0
|  | C | Improvements to Ramanathapura - Therakanambi (SH-86) in Nanjanagudu Tq | SH-86 | 4.15 | 4.15 |  | 4.15 |  |  | 4.15 |  | 0 | 0 |  | 0
|  | D | Improvements to Hura road to Ramanathapura-Therakanambi SH via Hanchipura road (MDR) (In Selected Reaches) in Nanjanagudu Tq | MDR | 1.52 | 1.55 |  |  | 1.55 |  | 1.55 |  | 0 | 0 |  | 0
161 | 577 | A | Improvements to KRS to join Mysore Ring Road in Mysore Tq | SH | 4.13 | 4.13 |  |  | 4.13 |  | 4.13 |  | 0 | 0 |  | 0
|  | B | Improvements to Gungral Chathra to K Nagenahalli (MDR) in Mysore Tq | MDR | 2.13 | 2.13 |  |  | 2.13 |  | 2.13 |  | 0 | 0 |  | 0
|  | C | Improvements to Mysore Naguvanahalli Road (MDR) in Mysore Tq | MDR | 1.525 | 1.525 |  |  | 1.525 |  | 1.525 |  | 0 | 0 |  | 0
|  | D | Improvements to Shrirangapatna - MM Hills Road (SH-79) in TNPura Tq | SH | 1.35 | 1.35 |  | 1.35 |  |  | 1.35 |  | 0 | 0 |  | 0
|  | E | Improvements to B.M. Road to Beedanahalli-Hanumanalu-Maragowdanahalli to Sulthan road (MDR) in TN Pura Tq | MDR | 0.8 | 0.8 |  | 0.8 |  |  | 0.8 |  | 0 | 0 |  | 0.005
|  | F | Improvements to Mugur -Bannhalli hundi road (MDR) in TN Pura Tq | MDR | 6.5 | 6.5 |  |  |  | 6.5 | 6.5 |  | 0 | 0 |  | 0.045
162 | 595 | A | Improvements to Sira - Nanjangudu (SH-84) from 227.00 km to 227.75 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | SH | 0.75 | 0.75 |  | 0.75 |  |  | 0.75 |  | 0 | 0 |  | 0
|  | B | Improvements to Hanumapura to join Doddahomma via P.Marahalli-Avathalapura (MDR) from 1.00 km to 8.00 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | MDR | 5.98 | 5.98 |  |  | 5.975 |  | 5.975 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 40.645 | 40.605 | 2.41 | 16.38 | 15.31 | 6.5 | 40.6 |  | 0 | 0 |  | 0
Hunsur Division | [12 empty] | 0 | 0 |  | 0
163 | 578 | A | Improvements to Kattemalalavadi to Sannenahalli - Kothegala Road MB Road from 0.00 km to 3.60 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 2.425 | 2.425 |  |  | 2.425 |  | 2.425 |  | 0 | 0 |  | 0
|  | B | Improvements to Hunsur - Dharmapura Road (MDR) from 0.00 km to 14.40 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 1.82 | 1.82 |  | 0.75 | 1.07 |  | 1.82 |  | 0 | 0 |  | 0
|  | C | Improvements to Tarikallu - Singaramaranahally Road (Via Karimuddanahally) (MDR) from 10.00 km to 13.50 km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 1.85 | 1.85 |  |  | 1.85 |  | 1.85 |  | 0 | 0 |  | 0
|  | D | Improvements to Rathnapuri to Hosavaranchi Road Via Kuddinirumuddanahalli join road from 0.30 km to 9.50 Km (In Selected Reaches) in Hunsuru Taluk of Mysore District. |  | 1.88 | 1.88 |  |  | 1.88 |  | 1.88 |  | 0 | 0 |  | 0
|  | E | Improvements to KR Nagar-Kattemalavadi-Channamgere Road via Makodu Ravandur- Attigodu- Sangarashettihalli from 23.71 km to 27.71 km (In Selected Reaches) in Piriyapatna Taluk of Mysore District. |  | 2.7 | 2.7 |  |  | 2.7 |  | 2.7 |  | 0 | 0 |  | 0
|  | F | Improvements to Poonadahalli – Chikkaneru - Haranahalli from 9.20 km to 15.20 km (In Selected Reaches) in Piriyapatna Taluk of Mysore District. |  | 3.8 | 3.8 |  |  | 3.8 |  | 3.8 |  | 0 | 0 |  | 0
|  | G | Improvements to Koratagere - Bavali SH-33 from 213.37 km to 278.00 km (In Selected Reaches) in H D Kote Taluk of Mysore District. |  | 6.2 | 6.2 | 0.4 | 5.8 |  |  | 6.2 |  | 0 | 0 |  | 0
164 | 579 | A | Improvements to Holenarasipura – Saligrama - KR Nagara SH-108 from 19.50 km to 32.00 km (In Selected Reaches) in KR Nagar Taluk of Mysore District. |  | 2.7 | 2.7 |  | 2.7 |  |  | 2.7 |  | 0 | 0 |  | 0
|  | B | Improvements to Ramanathapura - Terakanambi Road to Mysore - Bhantwala Road Via- Chikkahanasoge- Channamgere (SH) from 0.00 km to 7.00 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. |  | 2.275 | 2.275 |  |  | 2.275 |  | 2.275 |  | 0 | 0 |  | 0
|  | C | Improvements to K R Nagar - Bettadapura road to join K R Nagar-Malali-Hosakote-Ravanduru Road (SH) from 8.00 km to 17.50 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. |  | 2.1 | 2.1 |  |  | 2.1 |  | 2.1 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 27.75 | 27.75 | 0.4 | 9.25 | 18.1 | 0 | 27.75 |  | 0 | 0 |  | 0
Chamarajanagar Division | [12 empty] | 0 | 0 |  | 0
165 | 580 | A | Improvements to Badanaguppe - Nanjedevanapura Road (MDR) from 3.80 km to 5.80 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 1.64 | 1.64 |  |  | 1.64 |  | 1.64 |  | 0 | 0 |  | 0
|  | B | Improvements to Kodimole Basavanapura Hebbasur Byadamudlu-Basavapura Road (MDR) from 1.60 km to 6.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 4.32 | 4.32 |  |  | 4.32 |  | 4.32 |  | 0 | 0 |  | 0
|  | C | Improvements to Santhemarahalli Hebbasur Road (MDR) from 6.95 km to 10.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 1.06 | 1.06 |  |  | 1.06 |  | 1.06 |  | 0 | 0 |  | -0.029
|  | D | Improvements to Udigala Kothalavadi V Swamy Hills Road (MDR) from 7.20 km to 8.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District | MDR | 0.98 | 0.98 |  |  | 0.98 |  | 0.98 |  | 0 | 0 |  | 0
166 | 581 | A | Improvements to Road joining T Narasipura (Muguru Cross) to Santhemaralli (SH) from 0.00 km to 8.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | SH | 3.49 | 3.49 |  | 3.49 |  |  | 3.49 |  | 0 | 0 |  | 0
|  | B | Improvements to Kuderu-Thoravalli-Kesthuru-Mariyala Road (MDR) from 1.50 km to 9.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 6.03 | 6.059 |  |  | 6.059 |  | 6.059 |  | 0 | 0 |  | 0
167 | 582 | A | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Tammadahalli, Kengaki, Sagade, Maliyuru, Kulagana, Kebbepura, Hemmaragala & Badanavalu (SH) from 15.45 km to 18.45 km & 22.450 km to 29.45 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | SH | 5.14 | 5.14 |  |  | 5.14 |  | 5.14 |  | 0 | 0 |  | 0
|  | B | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Veeranapura, Harave & Heggawadi (SH) from 15.16 km to 18.80 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 2.1 | 2.1 |  |  | 2.1 |  | 2.1 |  | 0 | 0 |  | 0
|  | C | Improvements to Road joining Kurubara Hundi Via Hasaguli, Manchahalli (MDR) from 3.00 km to 5.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 0.55 | 0.55 |  |  | 0.55 |  | 0.55 |  | 0 | 0 |  | 0.71
|  | D | Improvements to Road joining Taggaluru to Bettadamadalli (MDR) from 6.70 km to 9.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 0.865 | 0.865 |  |  | 0.865 |  | 0.865 |  | 0 | 0 |  | 0
|  | E | Improvements to Road joining Chirakanahalli road to Kurubara Hundi (MDR) from 0.00 km to 2.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 0.965 | 0.965 |  |  | 0.965 |  | 0.965 |  | 0 | 0 |  | 0
|  | F | Improvements to Road joining NH-766 to Shrikantapura road Via Chikkahundi (MDR) from 0.00 km to 8.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 6.15 | 6.15 |  |  | 5.44 |  | 5.44 |  | 0 | 0 |  | 0
|  | G | Improvements to Hullapura Kadbur Road (MDR) from 13.00 km to 17.00 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 1.535 | 1.535 |  |  | 1.535 |  | 1.535 |  | 0 | 0 |  | 0.681
168 | 583 | A | Improvements to Hanur to Ellemalla-Kodalli Via Tabetta from 0.00 km to 16.40 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. | MDR | 6 | 6 |  | 6 |  |  | 6 |  | 0 | 0 |  | -8.059
|  | B | Improvements to Shrirangapatna - MalaiMahadeshwara Betta Road (SH-79) from km 107.50 km to 128.60 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. | SH | 6.6 | 6.6 |  |  | 6.6 |  | 6.6 |  | 0 | 0 |  | 0
|  |  | Division Total |  | 47.425 | 47.454 | 0 | 9.49 | 37.254 | 0 | 46.744 |  | 0 | 0 |  | 0
|  |  | Mysore Circle Total |  | 175.86 | 186.891 | 2.81 | 36.91 | 134.719 | 9.48 | 183.919 |  | 0 | 0 |  | 0
Hassan Circle | [12 empty] | 0 | 0 |  | 0
Hassan Division | [12 empty] | 0 | 0 |  | 0
169 | 584 |  | Improvements to Huliyaru -Keralapura Road SH-102 from Km 15.00 to Km 70.88 (In Selected Reaches) in Arsikere Taluk of Hassan District. | SH-102 | 12.235 | 12.235 |  | 12.235 |  |  | 12.235 |  | 0 | 0 |  | 0
170 | 585 |  | Improvement to Arkalgudu -Kodagu Border Road from Km 0.00 to Km 28.80 (In Selected Reaches) in Arakalgud Taluk of Hassan District | ARK-34 | 16.86 | 16.86 |  |  | 16.86 |  | 16.86 |  | 0 | 0 |  | 0
171 | 586 | A | Improvement to Road from Siddapura to join TDH Road via Kithanakere Barekattahalli MDR from Km 0.00 to km 7.00 (In Selected reaches) in Hassan Taluk of Hassan District | HSS-247 | 5.04 | 5.04 |  |  | 3.38 | 1.66 | 5.04 |  | 0 | 0 |  | -0.9
|  | B | Improvement to Road from Heragu road to join Dudda Shanthigrama Road via Kommanahalli Handrangi S.Devalapura Chattanahalli and Alasinahalli MDR from Km 0.00 to Km 9.00 (In Selected Reachs) in Hassan Taluk of Hassan District | MDR | 5.428 | 5.428 |  |  | 0.65 | 4.778 | 5.428 |  | 0 | 0 |  | 0.35
|  | C | Improvements to road from Markuli cross to Athichowdenahall road via varasanahalli from 0.00 Km to 12.00 Km ( in Selected Reach ) in Holenarasipura taluk of Hassan District. | HNP-18 | 9.47 | 9.47 |  |  | 9.47 |  | 9.47 |  | 0 | 0 |  | 0
172 | 587 | A | Improvements to Hirisave- Kerisave from B.M.Road to join Kabbali Road MDR from Km 7.30 to Km 20.00 (In Selected Reaches) in Channarayapatna Taluk of Hassan District. | CRP-206 | 4.64 | 5.54 |  |  | 5.54 |  | 5.54 |  | 0 | 0 |  | 0
|  | B | Improvements to B.M.Road to Turuvekere Border Via M.Honnenahalli-Dodderi-Hebbalalu-Akkanahalli Cross - Shettihalli -Ungaragere-Kabbali Mundakanahalli-Didaga- D.Tumakuru-Bidarekere-Uggenahalli Road MDR from Km 24.00 to Km 30.00 (In Selected Reaches) in Channarayapatna Taluk of Hassan District | CRP-42 | 4.16 | 3.81 |  |  | 3.81 |  | 3.81 |  | 0 | 0 |  | 0
173 | 588 | A | Improvement to Road from Kandli -Bylahalli -Bikkodu Road to TDH Road via Kyathanahalli Ugane Marenahalli Chinnenahalli Shankadakoppalu Mudlapura, Kabbli, Krishnapura MDR from Km.0.00 to Km 18.00 (In Selected Reaches) in Hassan Taluk of Hassan District. | HSS-203 | 7.038 | 7.038 |  |  | 7.038 |  | 7.038 |  | 0 | 0 |  | 0
|  | B | Improvement to Road from Alur to join Thuruvekere Via Doddakanagal, Vertikere, Kadadaravally, Kondajji, Yalagunda, Nittur-Bageshpura, Chindenahalligadi, Dasrigatta from Km 0.00 to Km 124.00 (In Selected Reaches) in Hassan Taluk of Hassan District | New SH | 3.71 | 3.71 |  |  | 3.71 |  | 3.71 |  | 0 | 0 |  | -0.005
|  | C | Improvement to Road from Kandli - Bylahalli -Bikkodu Road to MSF Road from Km.4.30 to Km 7.00 (In Selected Reaches) in Hassan Taluk of Hassan District. | HSS 207 | 2.55 | 2.55 |  |  | 2.55 |  | 2.55 |  | 0 | 0 |  | 0
|  | D | Improvement to Road from Ring road to Adlimane road to Thamalapura - Chikkakondagula - Kopplu - Thejur - Shanka Cross to HHAPC road through Rachanahalli Road from Km 0.00 to Km 9.00(In Selected reaches) in Hassan Taluk of Hassan District | HSS2 & VR | 2.4 | 2.4 |  |  | 2.4 |  | 2.4 |  | 0 | 0 |  | 0
174 | 589 | A | Improvements to Adgoor Sankenahalli Road MDR from Km 0.00 to Km 12.00 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-12 | 3.995 | 3.995 |  |  | 4 |  | 4 |  | 0 | 0 |  | 0
|  | B | Improvements to Road from NH-75 to join NH-173 from Km 70.00 to Km 91.10 (In Selected Reaches) (Halebeedu Gangooru Road from Km 0.00 to Km 8.00) and C M Road to Rajanashiriyuru MDR from Km 0.00 to Km 4.90 (In Selected Reaches) in Belur Taluk of Hassan District. | New SH | 5.67 | 5.67 |  |  | 5.67 |  | 5.67 |  | 0 | 0 |  | 0
|  | C | Improvements to Road from B T Road to join KBPB MDR from Km 0.00 to Km 6.70 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-58 | 0.93 | 0.93 |  |  | 0.93 |  | 0.93 |  | 0 | 0 |  | 0
|  | D | Improvements to road from B.T Road to C.M Road Shivaladahalli MDR from 0.00km to 6.00km ( in selected reaches) in Belur Taluk of Hassan District. | BLR-307 | 1.5 | 1.5 |  |  | 1.5 |  | 1.5 |  | 0 | 0 |  | 0
|  | E | Imrovements to road to C.M road to Hanike K B Hall Road via Mallanahalli, Mukthganne Honnenahalli MDR from 0.00km to 6.30km (in Selected reaches) in Belur Taluk of Hassan District. | BLR-28 | 1.3 | 1.3 |  |  | 1.3 |  | 1.3 |  | 0 | 0 |  | -0.555
175 | 597 | A | Improvements to Hanbal -Devrunda Road MDR from km 0.00 to km 12.60 (in selected reaches) in Sakleshpura Taluk of Hassan District. |  | 5.62 | 5.62 |  |  | 5.62 |  | 5.62 |  | 0 | 0 |  | 0
|  | B | Improvement to Road from BM Road to Ningegowdana koppalu shattihalli MDR from 7.00 Km to 16.00 Km (In Selected Reaches) in Hassan Taluk of Hassan District. |  | 5.873 | 5.873 |  |  | 5.873 |  | 5.873 |  | 0 | 0 |  | -1.35
|  |  | Division Total |  | 98.419 | 98.969 | 0 | 12.235 | 80.301 | 6.438 | 98.974 |  | 0 | 0 |  | -0.288
Kodagu Division | [12 empty] | 0 | 0 |  | -2.4
176 | 590 | A | Improvements to Hunsur-Talakaveri Road SH-90 from Ch 21.60 km to 61.00 km (selected reaches) in VirajpeteTaluk of Kodagu District | SH-90 | 16 | 17.35 | 1.55 | 15.8 |  |  | 17.35 |  | 0 | 0 |  | 0
|  | B | Improvements to Konanur - Makutta SH-91 from Ch 50.26 to to 75.00 km (selected reaches) in Virajpete Taluk of Kodagu District. | SH-91 | 5.83 | 6.118 |  |  | 6.118 |  | 6.118 |  | 0 | 0 |  | -0.04
177 | 591 |  | Improvements to Virajapete-Byndoor State Highway-27 from Ch 82.00 Km to 104.00 Km(selected reaches) in Somwarpete Taluk of Kodagu district | SH27 | 14.37 | 16.77 | 2.4 | 0.83 | 13.54 |  | 16.77 |  | 0 | 0 |  | -0.46
178 | 592 | A | Improvements to Virajapete-Byndoor State Highway-27 road from Ch 53Km to 60.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | SH27 | 4.5 | 4.5 |  |  | 4.5 |  | 4.5 |  | 0 | 0 |  | -4.538
|  | B | Improvements to Gopalpur-Banavara-Hebbale road from 2.00 Km to 7.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | upgraded road | 3.3 | 3.34 |  |  | 3.34 |  | 3.34 |  | 0 | 0 |  | -5.093
|  | C | Improvements to Konanur - Makutta road State Highway 91 from 32.00 Km to 36.00 Km (selected reaches) in Somwarpete Taluk of Kodagu district | SH 91 | 2.85 | 3.31 |  | 3.31 |  |  | 3.31 |  | 0 | 0 |  | -2.029
|  |  | Division Total |  | 46.85 | 51.388 | 3.95 | 19.94 | 27.498 | 0 | 51.388 |  | 0 | 0 |  | -20.237
|  |  | Hassan Circle Total |  | 145.269 | 150.357 | 3.95 | 32.175 | 107.799 | 6.438 | 150.362 |  | 0 | 0 |  | -49.411
|  |  | South Total |  | 1237.738 | 1270.098 | 41.261 | 471.566 | 685.796 | 41.144 | 1239.767 |  | 0 | 0 |  | 0 | [5 empty] | 1644.886
|  |  | South & North Total |  | 2249.41 | 2319.058 | 77.957 | 771.626 | 1344.382 | 75.682 | 2269.647 |  | 0 | 0 |  | -0.165 |  | 5.5m nov 1265.871
[6 empty] | 49.411 | 50.096 |  |  |  | 49.411 |  |  |  |  | -73.514 | [6 empty] | 14 m Width | 7 m Width | 5.50 m Width | 3.75 m Width | TOTAL
[6 empty] | IV stage-I | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | -540.8 |  |  |  | V stage-I Nov | 0 | 23.83 | 21.223 | 0 | 45.053
[6 empty] | IV stage-II | 0.15 | 0 | 0.015 | 0 | 0.165 | 0.33 |  |  |  | 0 | [5 empty] | V stage-I OCT | 0 | 11.9 | 11.26 | 0 | 23.16 |  | 21.223
[6 empty] | V stage-I | 1.126 | 30.706 | 41.517 | 0 | 73.349 |  | FINAL | [8 empty] | V stage-DIFF | 0 | 11.93 | 9.963 | 0 | 21.893
[6 empty] | TOTAL | 1.276 | 30.706 | 41.532 | 0 | 73.514 |  |  |  | -3.806 | [8 empty] | 0 | 23.83 | 15.223 | 0 | 39.053
[16 empty] | 517.189 |  | 7.16
[10 empty] | 110.3 |  |  | 720.258
[7 empty] | 2.17 | 15.814 | 22.603 | 1.653 |  |  | 0.15
[10 empty] | Added 7.16km to it bcz of mistake in Bidar Division |  |  |  |  | 36.671 | 286.185 | 632.764 | 30.38 | 986
[7 empty] | 1.38 | 79.05 | 1054.832 | 72.382 | 204.22
1105.079
1108.139

## District wise
2026-02-28
Phase IV Stage-II Progress District Wise
Sl No | District | No Of Packages | No Of Packages Completed | Completed works | Improvement in Km | Financial Progress | Completed | Zone |  | Balance works
1 | Kalburgi | 8 |  | 29 | 68.655 | 12615.97 | 4 | 311.525 | NE | 5 | 433441593454456
2 | Bidar | 4 |  |  | 30.21 | 13763.22 | 2
3 | Yadgir | 4 |  |  | 45.72 | 8736.12 | 1
4 | Bellary | 7 |  |  | 74.444 | 15832.15 | 0 | [5 empty] | 34
5 | Raichur | 6 |  |  | 44.346 | 13854.09 | 1
6 | Koppal | 5 |  |  | 48.15 | 12162.15 | 1
7 | Dharwad | 7 |  | 56 | 76.124 | 9842.8 | 0 | 718.355 | N | 2
8 | Gadag | 4 |  |  | 77.84 | 6163.25 | 3 | [5 empty] | 58
9 | Haveri | 7 |  |  | 113.17 | 10413.23 | 2 |  |  |  | 475,495,
10 | Uttar Kannada | 7 |  |  | 134.971 | 10582.91 | 2
11 | Belgaum | 19 |  |  | 189.57 | 17561.66 | 12
12 | Vijayapura | 8 |  |  | 55.68 | 41467.11 | 1
13 | Bagalkote | 6 |  |  | 71 | 11122.08 | 3
14 | Davanagere | 5 |  | 31 | 74.538 | 11687.1 | 0 | 536.362 | Central | 3
15 | Chitradurga | 7 |  |  | 101.3 | 15298.04 | 4
16 | Shimoga | 7 |  |  | 106.585 | 12239.84 | 0 |  |  |  | 514515544 |  | 34
17 | Udupi | 4 |  |  | 61.429 | 11435.03 | 1
18 | Dakishna Kannada | 7 |  |  | 82.02 | 9605.64 | 3
19 | Chickmagaluru | 4 |  |  | 110.49 | 12011.04 | 3
20 | Bangalore | 6 |  | 46 | 95.316 | 8526.74 | 0 | 703.405 | South | 6
21 | C B pura | 3 |  |  | 48.086 | 11900.3 | 2 |  |  |  | 548552573574606
22 | Ramanagara | 3 |  |  | 55.74 | 15611.02 | 1 | [5 empty] | 52
23 | Kolar | 3 |  |  | 58.993 | 11594.3 | 0
24 | Tumkur | 11 |  |  | 110.989 | 27652.69 | 8
25 | Mandya | 7 |  |  | 68.825 | 25220.98 | 2
26 | Mysore | 5 |  |  | 68.35 | 21611.53 | 2
27 | Chamarajnagar | 4 |  |  | 46.744 | 6139.84 | 0
28 | Kodagu | 3 |  |  | 51.388 | 2441.14 | 3
29 | Hassan | 7 |  |  | 98.974 | 46455.14 | 4
TOTAL |  | 178 | 0 | 162 | 2269.647 | 433547.11 | 65 | 2269.647 |  | 16
178
0
|  |  |  | 16 | [5 empty] | 2253.647 |  | 6
V stage-I nov | 0 | 23.83 | 0 | 21.22 | 0 |  |  | 45.05 |  | 21.22
V stage-I dec | 0 | 23.83 | 8.77 | 29.99 | 11 |  |  | 64.82 |  | 29.99
diff | 0 | 0 | 8.77 | 8.77 | 11 | 0 | 0 | 19.77 |  | 8.77

## 2022-23 (6)
GOVERNMENT OF KARNATAKA, PIU - STATE HIGHWAY DEVELOPMENT PROJECT, K.R.CIRCLE, BANGALORE
Package wise Details of Phase-4 Stage-2
1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 8 | 9 | 10 |  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Sl No | PKG No |  | Name of Work | SH/ MDR | CER No | Administrative Approved Amount (Rs. in lakhs) | Total Package Cost (Rs. in lakhs) | Technical sanctioned Amount (Rs. in lakhs) | Contract Amount (in Lakhs) | Variation Amount (Rs. in lakhs) | Revised Contract Amount including VO (Rs. in lakhs) | Revised Contract Amount With GST | Revised Contract Amount +PMC cost With GST | Name of Agency | Stipulated Date |  |  | Length Proposed as per DPR in Km | Length Proposed as per VO in Km | Physical Progress |  | Balance Length ( Km ) | Financial Progress |  | Balance (Financial amount) Rs. In Lakhs | Remarks
[15 empty] | Commencement | Completion | Revised Completion Date |  |  | Total Length Completed (in km) | % Progress |  | Total Cost (Rs. In Lakhs) | % Progress
Kalaburagi Circle
Bidar Division
1 | 429 | A | Improvements to SH-122 Maharastra Border Murki-Aurad-Handarki from Km 0.00 to Km 62.40 (in selected reaches) in Aurad Taluka of Bidar District. | SH- 122 | 9 | 2300 | 3300 | 2847.57 | 3360.22 | 836.68 | 4196.9 |  |  | M/s JS Infra Private Ltd, | 30.5.2022 | 30.11.2023 |  | 9.7 | 11.4 | 11.15 | 97.81% | 0.25 | 2485.34 | 59.22% | 1711.56 | 0.25 Km GSB+WMM+DBM+BC & CC drain Pending
|  | B | Improvements to SH-34 Aurad - Sadashivagad, from Km 21.00 to Km 72.50 (in selected reaches) in Bhalki Taluka of Bidar District. | SH-34 | 18 | 1000 | [7 empty] | 15: 4.41; 16: 6.04; 17: 4.41; 18: 73.01%; 19: 1.63; 23: 1.63 Km BC Pending
2 | 602 |  | Improvements to SH-122 Maharastra Border -Murki-Aurad-Handarki from Km 117.80 to Km 123.31 (in selected reaches) in Chitaguppa Taluka of Bidar District | SH -122 | 30 | 950 | 950 | 818.33 | 965.64 |  | 965.64 |  |  | Kotarki Laxman Sangamesh ( M/S Kotarki Constructions Private Limited) | 2022-07-30 | 2023-06-29 |  | 4 | 4 | 0 | 0% | 4 | 0 | 0% | 965.64 | 4.00 Km SG+GSB+WMM+DBM+BC Pending, Instructed EE, PWD to submit resending proposal
|  |  | Division Total |  |  | 4250 | 4250 | 3665.9 | 4325.86 | 836.68 | 5162.54 | 0 | 0 | 15: 18.11; 16: 21.44; 17: 15.56; 18: 1.7082; 19: 5.88; 20: 2485.34; 22: 2677.2
Kalaburagi Division
3 | 603 |  | Improvements to MDR from NH-218, Kattisangavi to Yenkanchi (SH-16) via Madari-Yengunta- Naribol-Biral(B)-Ganvar-Chigralli-ijeri-alur-kadkol-manashivanagi from Km 40.00 to 50.00 Km (in selected reaches) ( from chigralli cross to yedrami )in Jevargi Taluka of Kalaburagi District. | JEW45 | 45 | 950 | 950 | 817.94 | 940.64 |  | 940.64 |  |  | Sri. Mohammed Sirajuddin, Kalaburagai | 2022-05-21 | 2023-04-20 |  | 5.2 | 5.2 | 0 | 0% | 5.2 | 115 | 12.23% | 825.64 | 0.77 Km Sub grade, 1.19 Km GSB, Km, 2.19 Km WMM, 3.087 Km DBM & 5.176 Km BC pending.
4 | 433 |  | Improvements to road from Kadagunchi-Bodana road (MDR) to Tonasalli (SH125), MDR from Km 0.00 to Km17.50 and Km 26.50 to Km 35.00 (in selected reaches) in Kalaburagi Taluka of Kalaburagi District. | New MDR | 50 | 2100 | 2100 | 1808.92 | 2261.15 |  | 2261.15 |  |  | Sri. Shivkant C Mahajan, Kalaburagi | 2022-06-15 | 2023-12-14 |  | 9.935 | 9.935 | 0 | 0% | 9.935 | 1158.66 | 51.24% | 1102.49 | 1.08 Km SG & 1.14 Km GSB, 0.75 Km WMM+BM & 9.275 Km BC & 0.39 Km CC Road & CC drain pending
|  |  | Division Total |  |  | 3050 | 3050 | 2626.86 | 3201.79 | 0 | 3201.79 | 0 | 0 | 15: 15.135; 16: 15.135; 17: 0; 19: 15.135; 20: 1273.66; 22: 1928.13
Sedam Division
5 | 435 |  | Improvements to SH-122 Maharastra Border - Murki-Aurad-Handarki, from Km 153.80 to Km 164.00 Km and Km 207.00 to Km 218.77 (in selected reaches) in Sedam/ Chincholi Taluka of Kalaburagi District | SH-122 | 66 | 2250 | 2250 | 1938.02 | 2238.42 | 217.96 | 2456.38 |  |  | Siddappagouda Patil | 31.5.2022 | 30.11.2023 |  | 11.81 | 11.81 | 7.62 | 64.52% | 4.19 | 452.91 | 18.44% | 2003.47 | 0.2 Km SG ,2.42 km GSB, 2.22 Km WMM+DBM, 3.35 Km BC & 0.2 Km DLC+PQC & CC drain pending
6 | 600 |  | Improvements to SH-32 Umarga border-Aland-VK Salagar-Mahagaon -Sulepet road, from Km 80.00 to Km 118.00 via Herur Cross - Sulepet (in selected reaches) in Chincholi Taluka of Kalaburagi District. | SH-32 | 72 | 2250 | 2250 | 1938.3 | 2289.8 | 209.42 | 2499.22 |  |  | M/s Sharada Construction Pvt Ltd | 2022-06-15 | 2023-12-14 |  | 13.83 | 13.83 | 0 | 0% | 13.83 | 923.33 | 36.94% | 1575.89 | 0.40 Km SG+GSB+WMM+DBM & 13.727 Km BC work pending
|  |  | Division Total |  |  | 4500 | 4500 | 3876.32 | 4528.22 | 427.38 | 4955.6 | 0 | 0 | 15: 25.64; 16: 25.64; 17: 7.62; 19: 18.02; 20: 1376.24; 22: 3579.36
Yadgir Division
7 | 437 | A | Improvements to road Maharastra Border to Raichur Border (Markel- Kollur-Bilihar) road, MDR from Km 3.00 Km 9.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | New SH | 88 | 860 | 2150 | 1851.53 | 2090.18 | 199.72 | 2289.9 |  |  | Shri.Siddappagouda Patil, Yadgir | 2022-06-15 | 2023-12-14 |  | 4.75 | 4.75 | 0 | 0% | 4.75 | 485.96 | 21.22% | 1803.94 | 0.8 Km GSB++DLC+PQC & 3.90 Km BC pending 1.35 Km GSB+WMM+DBM+BC work & CC drain pending
|  | B | Improvements to road NH-150A to SH-127 Sangam-Raichur Border, MDR from Km16.30 to Km 57.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | SHA35 | 90 | 860 | [7 empty] | 15: 4.95; 16: 5.31; 17: 4.95; 18: 93.22%; 19: 0.36; 23: 0.36 Km Road work is in Progress
|  | C | Improvements to road Kurakunda to Bilhar Via Hortur, Halgera, Godihal Kumanur, Arjunagi, Kandalli, MDR from Km 0.00 to Km 13.00 (in selected reaches) in Wadgera Taluka of Yadgir District. | MDR | 91 | 430 | [7 empty] | 15: 2.3; 16: 2.3; 17: 0; 18: 0%; 19: 2.3; 23: 2.30 Km WMM+DBM+BC pending road work
8 | 440 |  | Improvements to SH-155 from Pattan cross(SH-10) to Narayanapura dam Km110.00 to KM 167.30 (in selected reaches) in Shorapur Taluka of Yadgir District. | SH-155 | 94 | 2700 | 2700 | 2323.03 | 2760.38 | 595.48 | 3355.86 |  |  | Sri. Basangouda Allikoti, Yadgir | 2022-06-15 | 2023-12-14 |  | 48.52 | 16.534 | 4.35 | 26.31% | 12.184 | 265 | 7.897% | 3090.86 | 12.18 Km SG+GSB+WMM+DBM 15.23 Km BC & 0.108 Km CC & CC drain pending
|  |  | Division Total |  |  | 4850 | 4850 | 4174.56 | 4850.56 | 795.2 | 5645.76 | 0 | 0 | 15: 60.52; 16: 28.894; 17: 9.3; 19: 19.594; 20: 750.96; 22: 4894.8
|  |  | Kalburgi Circle Total |  |  | 13600 | 13600 | 11716.78 | 13704.64 | 2059.26 | 15763.9 | 0 | 0 | 15: 104.27; 16: 75.974; 17: 32.48; 19: 43.494; 20: 4612.54; 22: 11151.36
Ballary Circle
Ballary Division
9 | 441 | A | Improvements to MDR road of Ballary - Kalyanadurga Ch.0.80 km to 2.00 Km ( double road) in Ballary taluk, Ballary district. | MDRBER6 | 96/21-22 | 600 | 1400 | 1197.28 | 1292.96 |  | 1292.96 |  |  | Sri. T Ramanjaneya Reddy, Mysore | 2022-07-05 | 2023-10-04 |  | 1.08 | 1.08 | 0.275 | 25.46% | 0.805 | 320.79 | 24.81% | 972.17 | Sub Grade-0.525 kmGSB-0.525 kmWMM-0.525 km DBM-0.275 kmBC-0.275 km CC Drain-1.205 km completed
|  | B | Improvements MDR road from Kampli-Kurugodu-Kuduthini-Haraginidoni-Ballary-Aluru via Moka village Devalapura -Kamalapura from ch.88.99 km to 90.39 Km (in selected reaches) in Ballary taluk,Ballary district. | SH-132(BER19) | 97/21-22 | 800 | [7 empty] | 15: 1.06; 16: 1.06; 17: 0.35; 18: 33.02%; 19: 0.71; 23: Sub Grade-6.600 km GSB-0.600 km WMM-0.300 km DBM-0.300 km BC-0.300 km CC Drain-0.600 km completed Box Culvert work in progress 2x2,2v & 2x2,1v
10 | 443 | A | Improvements to road from maruthi camp somasandra Siddammanahalli to Yarangalli village road chainage 5.00 Km to 9.50 Km in kurugodu Taluk Bellary District. | MDR | 111/21-22 | 400 | 950 | 813.27 | 934.45 | 89.79 | 1024.24 |  |  | Sri. Kalkutiginahal Masididipura Praveen Kumar (Sri Siddarameswara Construction), Ballary | 2022-06-08 | 2023-05-07 |  | 2.05 | 2.05 | 2.05 | 100% | 0 | 555.41 | 54.23% | 468.83 | Road furniture work is in Progress
|  | B | Improvements to road from Kanivathimmalapura village to Ramasagara road Chainage 0.00 Km to 4.00 Km in Kampli Taluk Bellary District | MDR | 123/21-22 | 300 | [7 empty] | 15: 1.4; 16: 2; 17: 0; 18: 0%; 19: 2; 23: 1.90km WMM under progress
|  | C | Improvements to road from Kuduthini to orvaayi cross road chainage 15.00 Km to 18.50 Km in Kurgodu Taluk Bellary District. | MDR | 135/21-22 | 250 | [7 empty] | 15: 1.35; 16: 1.35; 17: 1.35; 18: 100%; 19: 0; 23: Road furniture work is in Progress
|  |  | Division total |  |  | 2350 | 2350 | 2010.55 | 2227.41 | 89.79 | 2317.2 | 0 | 0 | 15: 6.94; 16: 7.54; 17: 4.025; 19: 3.515; 20: 876.2; 22: 1441
Vijayanagara Division | bar: 23
11 | 442 | A | Improvements to MDR road from Nallapura to Hosachinnapura ch.6.00 km to 9.40 Km in Hospet taluk ,Ballary district. | MDR HSP-217 | 98/21-22 | 400 | 2300 | 1961.66 | 2315.76 | 156.75 | 2472.51 |  |  | Sri. Sali Basavaraj, Hosapete | 2022-06-17 | 2023-12-16 |  | 2.53 | 3.23 | 3.23 | 100% | 0 | 1131.66 | 45.77% | 1340.85 | Road furniture work is in Progress
|  | B | Improvements to MDR road Connecting Ingalagi village to NH -63 km0.00 to 3.00 Km in Hospet taluk, Ballary district | MDR HSP-221 | 99/21-22 | 500 | [7 empty] | 15: 1.93; 16: 1.949; 17: 1.949; 18: 100%; 19: 0; 23: Road furniture work is in Progress
|  | C | Improvements to MDR road from Devalapura -Kamalapura , ch.10.00 km to 18.00 Km (in selected reaches) in Hospet taluk, Ballary district. | MDR HSP-14 | 100/21-22 | 700 | [7 empty] | 15: 7.74; 16: 7.633; 17: 7.63; 18: 99.96%; 19: 0.003; 23: Road furniture work is in Progress
|  | D | Improvements to MDR Road from Kondanayakanahalii to Danapura via Nagenahalli Thanda, ch.0.00 km to 6.00 Km in Hosapete taluk, Ballary district | MDR HSP 213 | 108/21-22 | 700 | [7 empty] | 15: 2.78; 16: 5.7; 17: 0; 18: 0%; 19: 5.7; 23: C & G work completed and work stopped
12 | 445 | A | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommnahally from ch.131.00 to ch 137.00 km, ch.140.00 to Ch 141.15.00 km & ch.153.00 to Ch 156.15 km in Kudligi taluk , Ballary district. | SH-131(KDL44) | 171/21-22 | 1250 | 2250 | 1928.95 | 2276.15 | 210.5 | 2486.65 |  |  | Sri. Sali Basavarj , Hosapete | 2022-06-15 | 2023-12-14 |  | 7.1 | 8.31 | 6.1 | 73.41% | 2.21 | 1686.43 | 67.82% | 800.22 | GSB work under progress
|  | B | Improvements MDR road from Hosahalli to Kanamadagu via Hagaribommanahalli from ch.1.22 Km to ch .7.30 km & ch.7.70km to Ch 8.75 km in Kudligi taluk ,Ballary district. | MDR KDL 13 | 180/21-22 | 1000 | [7 empty] | 15: 6.7; 16: 6.605; 17: 6.605; 18: 100%; 19: 0; 23: Road furniture work is in Progress
13 | 593 |  | Improvements SH -151 road from Itagi to Kanchikere via Chitageri,Kadabageri, Arasikere from ch.7.80 km to ch 25.00 km in Harapanahalli taluk, Ballary district. | SH-151(HRP6) | 181/21-22 | 2150 | 2150 | 1841.5 | 2203.11 |  | 2203.11 |  |  | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi , | 2022-05-06 | 2023-11-05 |  | 10.25 | 10.25 | 3.05 | 29.76% | 7.2 | 0 | 0% | 2203.11 | 3.05km Sub Grade to SDBC completed, Sub Grade work under progress
14 | 446 | A | Improvements SH -45 road connecting Arabhavi and Challakere Via Gokak,Naragunda ch.217.80 km to ch 225.02 km in Hadagali taluk, Ballary district. | SH-45(HDG202) | 190/21-22 | 950 | 1900 | 1621.59 | 1908.21 | 189.91 | 2098.12 |  |  | Sri Savajji Rajendraprasad (Varavi malleswara Contract Company Private Limited), Ballary , | 2022-06-16 | 2023-12-15 |  | 6.63 | 6.63 | 1.8 | 27.15% | 4.83 | 495.63 | 23.62% | 1602.49 | 1.80km Sub Grade to BC completed, WMM work under progress
|  | B | Improvements SH -131 road from Hampi to Kamalapura via Hagaribommanahalli from ch.159.00 km to ch 169.30 in Kudalagi taluk,Ballary district. | SH-131(KDL44) | 200/21-22 | 950 | [7 empty] | 15: 5.41; 16: 5.41; 17: 2.015; 18: 37.25%; 19: 3.395; 23: Sub Grade-5.22km GSB-2.015km WMM-1.68km DBM-1.68km BC-1.68km CC Drain-0.510km CC - 0.335 km Culvert-01no
|  |  | Division total |  |  | 8600 | 8600 | 7353.7 | 8703.23 | 557.16 | 9260.39 | 0 | 0 | 15: 51.07; 16: 55.717; 17: 32.379; 19: 23.338; 20: 3313.72; 22: 5946.67
Koppal Divison | bar: 23
15 | 447 |  | Improvements MDR road from Hosahalli to Koppala via Hirekasawadi,Halavarthi ch.0.00 km to ch 19.00 in Koppal taluk Koppal district. | MDR 206(KOP206) | 222/21-22 | 950 | 950 | 815.76 | 941.78 |  | 941.78 |  |  | Sri. Mallikarjuna H Ammapur, Lingasuguru | 2022-07-15 | 2023-06-16 |  | 3.36 | 3.36 | 2.05 | 61.01% | 1.31 | 480.96 | 51.07% | 460.82 | 2.050 km GSB+DLC+PQC completed, 2nos Box culvert completed
16 | 599 |  | Improvement to SH-59 road from Kustagi- to Pattadakallu 0.00 km to 21.20 km ( in selected reaches) in Kushtagi taluk, Koppal district . | SH-59 | 250/21-22 | 1000 | 1000 | 861.31 | 1075.4 | 156.49 | 1231.89 |  |  | Sri. Basavaraj Gowda Ganekal , Vijayapur | 2022-06-06 | 2023-05-05 |  | 5.3 | 6 | 6 | 100% | 0 | 850.05 | 69% | 381.84 | Road furniture work is in Progress
17 | 448 | A | Improvements MDR road from Ginigera to Irkalagada ch.3.00 km to ch 13.00 (selected reaches) in Koppal taluk ,Koppal district. | MDR (KOP18) | 300/21-22 | 1000 | 2250 | 1935.72 | 2438.92 | 243.34 | 2682.26 |  |  | Sri. Sharana Gowda,Raichur | 2022-07-01 | 2024-01-01 |  | 5.28 | 8.81 | 5.28 | 59.93% | 3.53 | 852.44 | 31.78% | 1829.82 | Sub Grade - 5.28 km B/s GSB - 5.28 km WMM-5.28 km BM-5.28 km SDBC-5.28 km Culvrts - 09 no
|  | B | Improvements MDR road from Gaddi to Hampasadurga upto NH-13 Ch.13.10 km to ch.15.90 km in Koppal taluk ,Koppal district. | MDR KOP219 | 313/21-22 | 300 | [7 empty] | 15: 2.15; 16: 2.15; 17: 0; 18: 0%; 19: 2.15; 23: Dropped
|  | C | Improvements to SH-130 road from Yelburga-Kankagiri-Gangavathi-Munirabad , 70.00km to 74.00 and 79.00 km to 81.90 km in Gangavathi taluk Koppal District. | SH-130 | 333/21-22 | 950 | [7 empty] | 15: 3.79; 16: 2.9; 17: 0; 18: 0%; 19: 2.9; 23: Sub Grade - 1.40 km GSB - 1.00 km Culverts - 15 no
18 | 449 |  | Improvements to SH-63 road from Raravi-Beluru Ch. 58.22 km to ch.75.42 km ( in selected reaches) in Kanakagiri taluk,Koppal District. | SH-63(GAN94) | 345/21-22 | 2250 | 2250 | 1939.1 | 2288.14 | 225.65 | 2513.79 |  |  | Sri. G Srinivas Rao ( Karunamaya Construction Company),Koppala | 2022-05-07 | 2023-11-24 |  | 9.97 | 10.21 | 8 | 78.35% | 2.21 | 1510.28 | 60.08% | 1003.51 | Sub Grade-8.52 km GSB - 8.81 km WMM - 8.81 km DBM - 9.00 km BC - 8.00 km CC Drain - 0.425 km Culverts - 15 nos
|  |  | Division total |  |  | 6450 | 6450 | 5551.89 | 6744.24 | 625.48 | 7369.72 | 0 | 0 | 15: 29.85; 16: 33.43; 17: 21.33; 19: 12.1; 20: 3693.73; 22: 4193.73
Raichur Division | bar: 23
19 | 452 | A | Improvements to SH-14 road from Ramadurga - Manvi via Badami,Pattadakallu,Hulagunda Ch:227.80 km to 236.00 in Manvi taluk, Raichur district. | SH-14 | 226/21-22 | 500 | 2000 | 1722.03 | 1745.03 |  | 1745.03 |  |  | Sri. Amaravaram Channa reddy ( ACR Projects), Bangalore | 2022-07-13 | 2024-01-12 |  | 2 | 2 | 0 | 0% | 2 | 739.93 | 42.4% | 1005.1 | WMM andf CC drain work in progress
|  | B | Improvements to MDR road from Kavithala to Veerapura cross via Anwari village, Ch:4.00 km to 13.30 km road via Anvaari village,in Lingasuguru& Manvi Taluk, Raichur district. | MAN 33 | 227/21-22 | 500 | [7 empty] | 15: 1.82; 16: 1.82; 17: 0; 18: 0%; 19: 1.82; 23: WMM work under Progress, CC Drain & CC Road Work in Progress
|  | C | Improvements to road from sindanooru taluk bappuru kuduthini lingasooguru ch KM 0.00 to 16.00 in Raichur District | LIN 206 | 207/21-22 | 1000 | [7 empty] | 15: 5.22; 16: 5.22; 17: 0; 18: 0%; 19: 5.22; 23: BM work in progress @ Ch:0.00 to 2.50 Km
20 | 453 |  | Improvements to road from SH-23 to Mukunda-Singapura road via Channahalli,Sindrampura, Mavinamadaguch. 0.00 km to 15.70km ( In selected reaches) in Sindanooru taluk ,Raichur district. | MDR-SIN228 | 199/21-22 | 1000 | 1000 | 861.65 | 1059.83 | 263.64 | 1323.47 |  |  | Sri. Karabasappa Gouda S Patil, Vijayapur | 2022-07-13 | 2023-06-12 |  | 4.705 | 5.9 | 4.71 | 79.83% | 1.19 | 695 | 52.51% | 628.47 | Sub Grade work in progress @ Ch:14.00 to 15.00 Km
21 | 454 | A | Improvements to MDR road from Gannadala to Jalahalli via Kakkaladoodi Kamaladinne, Maykaladoodi, Ch:0.00 km to 20.00km ( in Selected reaches) in Devadurga taluk, Raichur district. | MDR DEV 209 | 101/21-22 | 2000 | 2300 | 1978.77 | 2360.9 | 233.46 | 2594.36 |  |  | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi | 2022-05-06 | 2023-11-05 |  | 7.89 | 9.77 | 6 | 61.41% | 3.77 | 1712.67 | 66.02% | 881.69 | BC Work is completed @ Ch: 6.00 to 7.80 Ch:8.00 to 9.45 Km and Ch:10.00 to 10.60 Km and Ch: 11.30 to 12.370KM,0.00 to 1.44 km WMM work in Progress
|  | B | Improvements to MDR road from Maladakallu cross Malledevaragoodda via karadigooda, Jagatagallu) Ch:0.00 km to 18.00 km ( In selected reaches) in Devadurga taluk ,Raichur district | MDR DEV 216 | 131/21-22 | 300 | [7 empty] | 15: 1.44; 16: 1.47; 17: 1.47; 18: 100%; 19: 0; 23: SDBC Work is completed @ Ch:3.61 to 4.04 Km and Ch:4.40 to 5.60 Km
22 | 455 | A | Improvements to SH-61 road from Managooli-Bechaali upto NH-167 Ch. km 239.23 km to 241.19 km ( in Selected reaches) upto NH-167 in Raichur Taluk , Raichur district. | SH-61 | 141/21-22 | 200 | 950 | 807.67 | 742.7 |  | 742.7 |  |  | Sri. Venkatesh Yadav, Manvi | 2022-05-20 | 2023-04-19 |  | 1.02 | 1.02 | 0 | 0% | 1.02 | 465.62 | 62.69% | 277.08 | BM work under Progress
|  | B | Improvements to road from SH-13 (NH-167) Yaragera Gillesooguru via Gannadala Ch KM 0.00 to 20.78 ( in Selected reaches) in Raichur Taluk ,Raichur district. | SH-13 | 151/21-22 | 500 | [7 empty] | 15: 2.7; 16: 2.7; 17: 0; 18: 0%; 19: 2.7; 23: BM work under Progress
|  | C | Improvements to road from NH-167 connecting H-127 via Ashapura Udumagal, Purathipli road CH KM 5.70 to 9.00 in Raicur Taluk, Raichur District. | MDR RA15 | 161/21-22 | 250 | [7 empty] | 15: 1.52; 16: 1.52; 17: 0; 18: 0%; 19: 1.52; 23: BM work under Progress
23 | 456 | A | Improvements to MDR road from Raichur-Buradipadha Ch:0.00 km to 6.00 km ( in Selected reaches) in Raichur Taluk ,Raichur district. | MDR RAI 6 | 212/21-22 | 700 | 2200 | 1875.75 | 2244.6 |  | 2244.6 |  |  | Sri. M Eranna (M/s MECO Construction & Infra Tech Pvt Ltd), Manvi | 2022-06-04 | 2023-12-05 |  | 1.78 | 1.78 | 1.78 | 100% | 0 | 283.06 | 12.61% | 1961.54 | PQC Work in Progress @ Ch 0.00 to 1.78 Km(RHS )
|  | B | Improvements to MDR road connecting Raichur and SH-127 via Ashapura, Purthipalli ch. 0.00 km to 5.00 km ( in Selected reaches) Raichur Taluk Raichur district | MDR RAI 5 | 242/21-22 | 700 | [7 empty] | 15: 1.85; 16: 1.85; 17: 0.77; 18: 41.62%; 19: 1.08; 23: Curing Work in Progress @ Ch 1.480 to 2.40 Km
|  | C | Improvements to MDR road from SH-167 ( Devasooguru Katagooda road) to Raichur -Yaklasapura via Ambavadi ch. 1.72 km to 3.10 km in Raichur taluk, Raichur District | MDR RAI 215 | 272/21-22 | 300 | [7 empty] | 15: 1.41; 16: 1.41; 17: 0; 18: 0%; 19: 1.41; 23: Work dropped
|  | D | Improvements to MDR road from Basavana bhavi circle of Raichur -Singanodi road to Vidhanasaba nagara Ricemill ,ch. 0.00 km to 8.00 km ( selected reaches) in Raichur taluk , Raichur District. | MDR RAI 206 | 228/21-22 | 500 | [7 empty] | 15: 1.11; 16: 1.11; 17: 0; 18: 0%; 19: 1.11; 23: Scarification work in Progress
|  |  | Division total |  |  | 8450 | 8450 | 7245.87 | 8153.06 | 497.1 | 8650.16 | 0 | 0 | 15: 34.465; 16: 37.57; 17: 14.73; 19: 22.84; 20: 3896.28; 22: 4753.88
|  |  | Ballary Circle Total |  |  | 25850 | 25850 | 22162.01 | 25827.94 | 1769.53 | 27597.47 | 0 | 0 | 15: 122.325; 16: 134.257; 17: 72.464; 19: 61.793; 20: 11779.93; 22: 16335.28
Dharwad Cricle
Dharwad Division
24 | 457 | A | Improvements to Padubidri-Chikkalagudda SH-01 from Ch: 340.30 to 356.97 Km (in selected reaches) in Kalaghatagi taluk of Dharwad District. | SH-01 | 39 | 1900 | 2250 | 1939.79 | 2164.61 | 407.97 | 2572.58 |  |  | Sri. Mallikarjun Siddaramappa Patil | 21.09.2022 | 20.03.2024 |  | 9.695 | 9.695 | 7.3 | 75.3% | 2.395 | 1327.41 | 51.6% | 1245.17 | 7.300 km BC Completed, Balance 2.395km WMM work in progress
|  | B | Improvements to Managundi-Tadasinakoppa from Ch: 0.00 Km to 5.00 Km (in selected reaches) in Dharwad taluk of Dharwad District. | MDR | 40 | 350 | [7 empty] | 15: 2.04; 16: 2.62; 17: 0; 18: 0%; 19: 2.62; 23: 1.874 Km WMM Completed, Balance work in Progress
25 | 458 | A | Improvements to Beedi-Belavanaki SH-56 from Ch: 62.40 to 69.28 Km (in selected reaches) in Navalagund taluk of Dharwad District. | SH-56 | 41 | 1020 | 2300 | 1980.05 | 2330.44 |  | 2330.44 |  |  | Sri. Mallikarjun B Kallur (M B Kallur Infrastructure Company) | 02-08-2022 | 2024-02-01 |  | 6.42 | 6.42 | 0 | 0% | 6.42 | 557.44 | 23.92% | 1773 | 6.42 km GSB,5.00km WMM & DBM 5.00km completed, Balance work in Progress
|  | B | Improvements to Supa-Annigeri SH-28 from Ch:108.77 to 114.77 Km (in selected reaches) in Navalagund taluk of Dharwad District. | SH-28 | 42 | 280 | [7 empty] | 15: 1.53; 16: 1.53; 17: 0; 18: 0%; 19: 1.53; 23: C & G is in progress
|  | C | Improvements to Supa-Annigeri SH-28 from Ch: 84.70 to 99.30 Km (in selected reaches) in Hubballi taluk of Dharwad District. | SH-28 | 43 | 1000 | [7 empty] | 15: 6.42; 16: 6.42; 17: 0; 18: 0%; 19: 6.42; 23: 6.42 km GSB completed, 5.90 km WMM & DBM completed. Balance work in progress
26 | 459 | A | Improvements to Samshi-Gudageri road from 0.0 to 11.0Km in Kundagol taluka | MDR | 48 | 850 | 2200 | 1890.89 | 2171.13 | 521.83 | 2692.96 |  |  | Sri.Chandrashekhar Appasaheb Biradar | 03-08-2022 | 2024-02-02 |  | 6.45 | 6.45 | 0 | 0% | 6.45 | 820 | 30.45% | 1872.96 | 6.45 km GSB, 2.4 km WMM Completed, Balance WMM work in Progrss
|  | B | Improvements to Pashupatihal-Rottigavad MDR road Ch 0.0km to 3.18Km, 3.9 to 9.3Km and 11.00 to 13.5Km in Kundagol tq. | MDR | 49 | 750 | [7 empty] | 15: 5.73; 16: 9.702; 17: 0; 18: 0%; 19: 9.702; 23: 9.00 km Subgrade completed, Balance work in Progress
|  | C | Improvements to Hireharakuni Shishuvinal road upto Kundagol tq limit (MDR) from Ch: 0.00 Km to 5.16 Km in Kundagol tq . | MDR | 58 | 450 | [7 empty] | 15: 3.75; 16: 3.75; 17: 0; 18: 0%; 19: 3.75; 23: 3.75 km BM completed. Balance work in Progress
|  | D | Improvements to Varur-Hindasageri via (NH-04) from Surashettikoppa road upto Hubballi city limit road (MDR) from Ch: 0.0 Km to 2.0Km (in selected reaches) in Hubballi tq of Dharwad District. | MDR | 71 | 150 | [7 empty] | 15: 1.6; 16: 1.72; 17: 0; 18: 0%; 19: 1.72; 23: 1.60 Km BM completed. Balance work in Progress
27 | 460 |  | Improvements to Veerapura Toll-Manturu MDR road from Ch: 0.40 to 3.00 Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 73 | 950 | 950 | 819.34 | 1005.17 | 99.02 | 1104.19 |  |  | Sri Chandrashekhar Appasaheb Biradar | 06-07-2022 | 05-06-2023 |  | 2.08 | 2.1 | 0.26 | 12.38% | 1.84 | 436.85 | 39.56% | 667.34 | 2.075 km GSB, 0.975 km DLC, 0.975 km PQC completed, Balance work in Progress
28 | 461 | A | Improvements from Anand Nagar Main Road to Gokul Main Road ( opposite RN Shetty Factory) in Hubballi taluk of Dharwad District. | MDR | 74 | 700 | 1700 | 1450.36 | 1562.04 | 155.47 | 1717.51 |  |  | Sri. Bhimshi Siddappa Biradar (B S Biradar) | 18-06-2022 | 17-12-2023 |  | 1.301 | 1.59 | 0 | 0% | 1.59 | 671.2 | 39.08% | 1046.31 | Subgrade work in progress
|  | B | Improvements to BRTS Road to Jakka Reddy Hospital, Lokappana Hakkala, Railway Underpass connecting to NH Division Office Adjoining to Vidyanagar Police Station, Lakshmi Temple in Hubballi Dharwad Mahanagar, Hubballi tq of Dharwad District. | MDR | 75 | 600 | [7 empty] | 15: 2.29; 16: 2.146; 17: 2.146; 18: 100%; 19: 0; 23: work Completed
|  | C | Improvements to Hubballi Basaveshwara Nagar Gokul Road to join Ravi Nagar Road in Hubballi taluk of Dharwad District. | MDR | 76 | 400 | [7 empty] | 15: 1.46; 16: 1.762; 17: 1.762; 18: 100%; 19: 0; 23: work Completed
29 | 462 |  | PKG-462 Improvements to Beedi-Belavanaki SH-56 from Ch: 33.42 to 48.83Km (in selected reaches) in Dharwad taluk of Dharwad District. | SH-56 | 78 | 2250 | 2250 | 1939.47 | 2115.98 | 437.24 | 2553.22 |  |  | M/s M B Kallur Infrastructure Company | 02-08-2022 | 01-02-2024 |  | 13.72 | 13.18 | 0 | 0% | 13.18 | 856.1 | 33.53% | 1697.12 | 4.71 km DBM completed, Balance work in Progress
30 | 463 | A | Improvements to Supa-Annigeri SH-28 from Ch: 67.0Km to 68.5 Km in Dharwad Tq. | SH-28 | 79 | 1210 | 2300 | 1967.98 | 2279.16 |  | 2279.16 |  |  | Sri. Beeranna Subray Gaonkar (BSG Infrastructure) | 06-07-2022 | 05-01-2024 |  | 1.55 | 1.55 | 0 | 0% | 1.55 | 335 | 14.7% | 1944.16 | Not Yet Strated
|  | B | Improvements to Gokul cross-Tarihala- Kanavi-Honnapur MDR from Ch: 4.2Km to 4.8Km and 6.2Km to 8.4Km in Hubballi tq. | MDR | 80 | 480 | [7 empty] | 15: 0.814; 16: 0.814; 17: 0.214; 18: 26.29%; 19: 0.6; 23: 0.214 km PQC Completed. Balance work in Progress
|  | C | Improvements to Ittigatti-Kanavihonnapur MDR from Ch: 0.0 to 2.0Km in Dharwad tq. | MDR | 86 | 220 | [7 empty] | 15: 1.485; 16: 1.485; 17: 0; 18: 0%; 19: 1.485; 23: 1.485 km DBM completed. Balance work in progress
|  | D | Improvements to Gokul-Revadihal-Tarihal MDR road from Ch: 0.0 to 6.2Km (in selected reaches) in Hubballi taluk of Dharwad District. | MDR | 87 | 390 | [7 empty] | 15: 3.24; 16: 3.24; 17: 3.24; 18: 100%; 19: 0; 23: 2.59Km BC, 0.65 PQC completed,Road Furnitures work in progress
|  |  | Division Total |  |  | 13950 | 13950 | 11987.88 | 13628.53 | 1621.53 | 15250.06 | 0 | 0 | 15: 71.575; 16: 76.174; 17: 14.922; 19: 61.252; 20: 5004; 22: 10246.06
Gadag Division
31 | 464 | A | Improvements to Kalasapur-Mahalingapura- Anganakatti road (MDR) from Ch: 21.00 Km to 29.00 Km ( in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 89 | 640 | 2000 | 1722.68 | 1944.89 | 479.42 | 2424.31 |  |  | Sri K.V Hanchinal, Mundargi | 18-06-2022 | 17-12-2023 |  | 4.81 | 7.33 | 4.81 | 65.62% | 2.52 | 995.42 | 41.06% | 1428.89 | 4.81km Road work Completed. 2.52 Km WMM work in Progress
|  | B | Improvements to Asundi-Kurtkoti-Mulagunda road (MDR) Ch: 2.20 Km to 8.00 Km and 8.60 Km to 10.00 Km (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 109 | 640 | [7 empty] | 15: 3.98; 16: 3.98; 17: 3.68; 18: 92.46%; 19: 0.3; 23: 0.300km WMM Completed
|  | C | Improvements to Kalasapur-Mahalingapura- Anganakatti road Ch:0.30 Km to 2.60 and Ch: 7.00 Km to 21.00 (in selected reaches) in Gadag taluk of Gadag Dist. | MDR | 116 | 720 | [7 empty] | 15: 4.09; 16: 4.09; 17: 3.79; 18: 92.67%; 19: 0.3; 23: 0.300km WMM Completed
32 | 467 | A | Improvements to Hallikeri-Shirahatti road (MDR) from Ch: 0.00 to 26.00 (in selected reaches) in Mundaragi taluk of Gadag Dist. | MDR | 139 | 1735 | 3100 | 2671.98 | 3331.77 |  | 3331.77 |  |  | Sri. H. P. Madhukar & Company, Hubli | 21-06-2022 | 20-12-2023 |  | 10.51 | 10.51 | 8.59 | 81.73% | 1.92 | 1185 | 35.57% | 2146.77 | 7.00 Km BC, 1.59Km PQC Completed, Balance 1.92 GSB Work in progress
|  | B | Improvements to Gajendragada-Soraba Sh-136 from Ch: 23.70 to 36.00 Km (in selected reaches) in Ron taluk of Gadag Dist. | SH-136 | 158 | 1365 | [7 empty] | 15: 8.96; 16: 8.96; 17: 0; 18: 0%; 19: 8.96; 23: 3.14km SG,3.14km GSB &0.400 Km WMM Completed
|  |  | Division Total |  |  | 5100 | 5100 | 4394.66 | 5276.66 | 479.42 | 5756.08 | 0 | 0 | 15: 32.35; 16: 34.87; 17: 20.87; 19: 14; 20: 2180.42; 22: 3575.66
Haveri Division
33 | 468 | A | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 284.51 Km to 294.51 Km (In Selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 159 | 1575 | 2775 | 2391.65 | 2846.55 | 676.41 | 3522.96 |  |  | Sri S B Dundigoudar (Bannur Infrastructures Private Limited) | 03-08-2022 | 02-02-2024 |  | 8.225 | 9.42 | 8.38 | 88.96% | 1.04 | 2460.93 | 69.85% | 1062.03 | 8.38 km BC Completed, Balance 1.04 km WMM work in Progress.
|  | B | Improvements to Kalmala Shiggoan Sh-23 road from Ch: 294.51 Km to 303.200 Km (in selected reaches) in Shiggoan taluk of Haveri District. | SH-23 | 169 | 1200 | [7 empty] | 15: 6.617; 16: 9.22; 17: 6.617; 18: 71.77%; 19: 2.603; 23: 6.617km BC Completed, Balance2.60 km GSB work in progress
34 | 605 | A | Improvements to Shiggoan-Savanur railway station road (MDR) from Ch: 8.10 Km to 13.10 Km (In Selected reaches) in Savanur taluk, Haveri District. | MDR | 160 | 500 | 2200 | 1895.22 | 2274.94 | 507.19 | 2782.13 |  |  | Sri S B Dundigoudar (Bannur Infrastructures Private Limited) | 03-08-2022 | 02-02-2024 |  | 2.785 | 2.785 | 2.785 | 100% | 0 | 2103.55 | 75.61% | 678.58 | Work Completed, Furniture work in progress
|  | B | Improvements to Kumta-Tadas SH-69 road from Ch-134.50 Km to 142.00 Km (In Selected Reaches) in Shiggoan taluk of Haveri District. | SH-69 | 170 | 900 | [7 empty] | 15: 4.08; 16: 6.48; 17: 6.48; 18: 100%; 19: 0; 23: 6.48 km Completed, Road furniture work in Progress
|  | C | Improvements to Savanur- Hurulikuppi road from Ch-0.00 Km to 5.65 Km (In Selected Reaches) in Savanur taluk of Haveri District. | MDR | 172 | 800 | [7 empty] | 15: 5.095; 16: 5.42; 17: 3.85; 18: 71.03%; 19: 1.57; 23: 3.85 km BC Completed, Balance 1.59 km box cutting work in progress
35 | 469 |  | Improvements to Birur-Sammasagi SH: 76 Ch: 189.00 Km to 201.60 Km in selected reaches and 203.82 Km to 217.19 Km In Selected Reaches of Hanagal taluk, Haveri District. | SH-76 | 173 | 2300 | 2300 | 1984.45 | 2233.28 | 177.04 | 2410.33 |  |  | Sri Chandrashekhar Shetty (UNIQUE Constructions) | 02-08-2022 | 01-02-2024 |  | 15.735 | 15.735 | 0 | 0% | 15.735 | 390.14 | 16.19% | 2020.19 | 2.500 km DBM,9.271 Km WMM & 9.271 Km GSB Completed. Balance work in Progress
36 | 470 | A | Improvements to Havanur-Choudadanayyapura road Ch: 1.25 Km to 9.00 Km of Haveri taluk Haveri District | MDR | 174 | 630 | 2300 | 1979.52 | 2392.11 | 238.44 | 2630.55 |  |  | M/s JYOTI (Deveeka Constructions), | 03-08-2022 | 02-02-2024 |  | 3.9 | 3.9 | 3.9 | 100% | 0 | 949.13 | 36.08% | 1681.42 | Work Completed, Furniture work in progress
|  | B | Improvements to Halagi-Balehosur road Ch: 0.00 Km to 2.50 Km of Haveri taluk, Haveri District. | MDR | 175 | 250 | [7 empty] | 15: 1.68; 16: 1.68; 17: 1.68; 18: 100%; 19: 0; 23: Work Completed, Furniture work in progress
|  | C | Improvements to Agadi-Devagiri road Ch: 4.50 Km to 6.00 Km and 11.00 Km to 12.50 Km of Haveri taluk, Haveri District. | MDR | 176 | 425 | [7 empty] | 15: 1.388; 16: 1.388; 17: 0.558; 18: 40.2%; 19: 0.83; 23: 0.558 Km BC completed, 0.558 km CC Road to be started
|  | D | Improvements to Totadayellapura-Masoor-Guttala road Ch: 18.00 Km to 24.50 Km of Haveri taluk, Haveri District. | MDR | 177 | 495 | [7 empty] | 15: 3.03; 16: 3.03; 17: 3.03; 18: 100%; 19: 0; 23: Work Completed, Furniture work in progress
|  | E | Improvements to Agadi-Katenahalli road Ch: 0.80 Km to 6.50 Km Haveri taluk, Haveri District. | MDR | 178 | 500 | [7 empty] | 15: 3.428; 16: 3.428; 17: 3.428; 18: 100%; 19: 0; 23: Work Completed, Furniture work in progress
37 | 471 | A | Improvements toTavargi - Tumminkatte road (MDR) from Ch: 0.00 Km to 22.50 Km (In Selected reaches) in Hirekerur taluk, Haveri District. | MDR | 179 | 1000 | 2300 | 1971.77 | 2266.4 | 328.51 | 2594.91 |  |  | Sri. Sachin Kollur (M/s Kollur Gurunath Construction Infra Private Limited), | 16-07-2022 | 15-01-2024 |  | 8.368 | 8.72 | 0 | 0% | 8.72 | 685 | 26.4% | 1909.91 | 5.440 km DBM Completed , Work in Progress
|  | B | Improvements to Road from Birur-Sammasagi SH: 76 to Join Halageri-Hulikal SH-26 Via Hirekerur-Masur-Kodamaggi- Hallur road Ch: 28.25 Km to 47.45 Km in selected reaches of Hirekerur taluk, Haveri District | SH-76 | 182 | 900 | [7 empty] | 15: 7.59; 16: 7.59; 17: 7.59; 18: 100%; 19: 0; 23: Road work Completed, Road Furniture in Progress
|  | C | Improvements to Road from Birur- Sammasagi SH: 76 to Join Byadagi - Rattihalli road Via Aladageri Ch: 0.00 Km to 7.10 Km in selected reaches of Hirekerur taluk, Haveri District. | SH-76 | 183 | 400 | [7 empty] | 15: 3.98; 16: 3.98; 17: 3.98; 18: 100%; 19: 0; 23: Road work Completed, Road Furniture in Progress
38 | 472 | A | Improvements to Sanguru - Tilavalli MDR Ch: 0.00 Km to 5.60 Km in Haveri taluk, Haveri District. | MDR | 184 | 590 | 2250 | 1938.94 | 2272.32 | 222.73 | 2495.05 |  |  | Sri. Santosh Veerayya Hiremath | 03-08-2022 | 02-02-2024 |  | 3.76 | 3.76 | 3.6 | 95.74% | 0.16 | 1912.42 | 76.65% | 582.63 | 3.60Km BC Completed, Balance 0.160 km WMM Work in progress
|  | B | Improvements to Honnalli - Hanagal SH Via Tumminakatti - Rattihalli - Byadagi Road Ch: 0.00 Km to 9.62 Km in Byadagi taluk, Haveri District. | MDR | 185 | 1230 | [7 empty] | 15: 6.69; 16: 7.89; 17: 6.39; 18: 80.99%; 19: 1.5; 23: 6.60Km BC completed, Balance 1.50km WMM work in Progress
|  | C | Improvements to Ranebennur - Anavatti SH Via Yarekuppi - Joisarahalli - Ukkunda - Saravanda - Belakeri - Bisahalli - Anoor - Hamsabhavi - Chikkerur MDR Ch: 15.60 Km to 19.00 Km in Byadagi taluk, Haveri District. | MDR | 186 | 430 | [7 empty] | 15: 2.98; 16: 2.98; 17: 2.98; 18: 100%; 19: 0; 23: Road work Completed, Road Furniture in Progress
|  |  | Division Total |  |  | 14125 | 14125 | 12161.55 | 14285.6 | 2150.32 | 16435.93 | 0 | 0 | 15: 89.331; 16: 97.406; 17: 65.248; 19: 32.158; 20: 8501.17
Karwar Division
39 | 473 | A | Improvements to Kumta - Kodamadagu Road SH-48 from km 9.00 to 12.20 Km & 16.20 to 19.90 Km (In Selected reaches) in Honnavara Taluk And Kumta - Kodamadagu road SH-48 from Km 19.90 to 30.00 Km (In Selected Reaches) in Kumta Taluk of Uttara Kannada District. | SH-48 | 191 | 1900 | 2250 | 1939.63 | 2308.77 | 555.75 | 2864.52 |  |  | Sri Babu Sannakusa Moger (B.S.M Construction Company | 18-07-2022 | 17-01-2024 |  | 12.4 | 12.8 | 9.55 | 74.61% | 3.25 | 929.03 | 32.43% | 1935.49 | GSB = 3.25 Km, WMM = 3.25 Km, DBM = 3.25 Km & BC =3.25 Km is balance
|  | B | Improvements to Aghanashini - Kumta road MDR from Km 0.00 to 6.00 Km in Kumta Taluk of Uttara Kannada District. | MDR | 192 | 350 | [7 empty] | 15: 3; 16: 4.946; 17: 4.946; 18: 100%; 19: 0; 23: Road furniture is pending
40 | 474 | A | Improvements to Gokarna - Vaddi road SH-143 Km 38.00 to 47.15 Km (In Selected Reaches) in Ankola Taluk of Uttara Kannada District | SH-143 | 193 | 1080 | 2300 | 1979.4 | 2474.25 | 615.64 | 3089.89 |  |  | Sri Shivakanth Mahajan (Mahajan Biz Ventures Pvt Ltd) | 2022-05-26 | 25-11-2023 |  | 7.5 | 5.4 | 5.4 | 100% | 0 | 2059.3 | 66.65% | 1030.59 | Road furniture is pending
|  | B | Improvements to Hyderabad to Shejwada road from 0.00 km to 2.00 km in Karwar taluk of Uttara Kannada district. | MDR | 194 | 120 | [7 empty] | 15: 1.32; 16: 0.48; 17: 0; 18: 0%; 19: 0.48; 23: Due to litigation
|  | C | Improvements to Agasur - Shiragutte - kodasane road from 0.00 to 12.60 Km (in selected reaches) in Ankola Taluk of Uttara Kannada District. | MDR | 195 | 310 | [7 empty] | 15: 1.81; 16: 2.3; 17: 1.9; 18: 82.61%; 19: 0.4; 23: DBM = 0.40 Km BC = 0.40 Km Balance
|  | D | Improvements to Belur-Karwar-Ilakal State Highway road from 0.00 km to 4.00 km in Karwar taluk of Uttara Kannada district. | MDR | 196 | 220 | [7 empty] | 15: 2.72; 16: 4; 17: 4; 18: 100%; 19: 0; 23: TOTAL ROAD COMPLETED Road Furniture
|  |  | Improvements to Karwar-Kaiga-Ilakal road from 27.35 km to 32.00 km in widening and Resurfacing Karwar taluk of Uttara Kannada district. | MDR |  | 330 | [7 empty] | 15: 2.72; 16: 4; 17: 4; 18: 100%; 19: 0; 23: TOTAL ROAD COMPLETED Road Furniture
|  | E | Improvements to Aurad - Sadhashivagad SH-34 Ambrai Cross to Ulaga road MDR from Km 0.00 to 3.30 Km (In Selected Reaches) in Karwar Taluk of Uttara Kannada District. | SH-34 | 197 | 240 | [7 empty] | 15: 3.3; 16: 3.3; 17: 3.3; 18: 100%; 19: 0; 23: TOTAL ROAD COMPLETED Road Furniture
41 | 475 | A | Improvements to Heggera - Magod - Nagarbhastikere road MDR from Km 3.40 to 20.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 198 | 1190 | 2250 | 1890.2 | 2264.76 | 529.68 | 2794.44 |  |  | Sri Ramesh Sannppa Naik (R.S Nayak & Co.,) | 2022-07-28 | 27-01-2024 |  | 10.3 | 8.915 | 2.94 | 32.98% | 5.975 |  | 0% | 2794.44 | WIDENING & STRENGTHENING (GSB & WMM) =7.06 Km DBM & BC = 7.06 Km COMPLETED GSB-7.06 Km
|  | B | Improvements to Magudu - Koodalagade road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Honnavar Taluk of Uttara Kannada District. | MDR | 201 | 530 | [7 empty] | 15: 2.7; 16: 2.807; 17: 0; 18: 0%; 19: 2.807; 23: GSB-2.70 km, 2.7 Km WMM, DBM BC 0.28 Pending
|  | C | Improvements to koppa panchayath hadala- kacchodi road MDR from Km 0.00 to 6.00 Km (In Selected Reaches) in Bhatkal Taluk of Uttara Kannada District. | MDR | 202 | 530 | [7 empty] | 15: 3.5; 16: 3.82; 17: 2.662; 18: 69.69%; 19: 1.158; 23: GSB COMPLETED WMM, DBM & BC = 0.84 Km Balance
|  |  | Division Total |  |  | 6800 | 6800 | 5809.23 | 7047.78 | 1701.07 | 8748.85 | 0 | 0 | 15: 51.27; 16: 52.768; 17: 38.698; 19: 14.07; 20: 2988.33; 22: 5760.52
Sirsi Division | bar: 23
42 | 478 | A | Improvements to Gokarna - Vaddi - Devanahalli road SH-143 from Km 65.20 to 73.15 Km in Sirsi Taluk of Uttara Kannada District. | SH-143 | 4 | 900 | 2300 | 1980.06 | 2450.03 | 244 | 2694.03 |  |  | Sri Shanmukappa R Ballary | 2022-06-02 | 2023-12-01 |  | 5.425 | 5.425 | 5.425 | 100% | 0 | 652.87 | 24.23% | 2041.16 | TOTAL ROAD COMPLETED, Road furniture work is pending
|  | B | Improvements to Khanapur - Taalaguppa road SH-93 from Km 170.00 to 200.50 Km (In Selected reaches) in Siddapura Taluk of Uttara Kannada District. | SH-93 | 5 | 900 | [7 empty] | 15: 1.59; 16: 1.07; 17: 0; 18: 0%; 19: 1.07; 23: EWE, GSB, WMM = 1.00 Km Balance
|  | C | Improvements to Bhatkal - Soraba road SH-50 from Km 85.90 to 86.70 Km, Km 87.20 to 93.965 Km, Km 96.50 to 96.90 Km, Km 97.30 to 98.80 Km & Km 99.55 to 100.90 in Siddapur Taluk of Uttara Kannada District. | SH-50 | 6 | 500 | [7 empty] | 15: 5.38; 16: 7.51; 17: 5.68; 18: 75.63%; 19: 1.83; 23: GSB = 1.82 Km WMM = 1.82 Km DBM = 1.82 Km BC = 1.82 Km Balance
43 | 479 |  | Improvements to Karwar - Kaiga - Ilkal road SH-06 in Mundgod Taluk from Km125.80 to 146.10 Km (in Selected Reaches) of Uttara Kannada District. | SH-06 | 7 | 2250 | 2250 | 1941.54 | 2335.94 | 580.22 | 2916.16 |  |  | Sri Shivakumar Policepatil (M/s S.S Policepatil Company) | 2022-05-31 | 2023-11-30 |  | 15.71 | 17.848 | 7.5 | 42.02% | 10.348 | 731.19 | 25.07% | 2184.97 | BC = 10.35 Km Balance
|  |  | Division Total |  |  | 4550 | 4550 | 3921.6 | 4785.97 | 824.22 | 5610.19 | 0 | 0 | 15: 28.105; 16: 31.853; 17: 18.605; 19: 13.248; 20: 1384.06; 22: 4226.13
|  |  | Dharwad Circle Total |  |  | 44525 | 44525 | 38274.92 | 45024.54 | 6776.56 | 51801.11 | 0 | 0 | 15: 272.631; 16: 293.071; 17: 158.343; 19: 134.728; 20: 20057.98; 22: 23808.37
Belagavi Circle
Vijayapura Division
44 | 480 | A | Improvements to road Shiradon Lingasur SH 41 from Ch: 71.43 Km to Ch: 82.00 Km and Ch: 93.50 Km to Ch: 100.23 Km (in selected reaches) in Sindagi Taluk in Vijayapur District. | SH 41 | 203 | 1100 | 2300 | 1965.37 | 2445.3 |  | 2668.01 |  |  | Sri Siddanagouda H Patil | 2022-07-12 | 2024-01-11 |  | 6.91 | 6.91 | 6.91 | 100% | 0 | 2366.09 | 96.76% | 79.21 | Road work Completed & Road Furniture work under progress
|  | B | Improvements to road Ukkalli Dindawar- Sasanur from Ch. 50.50 Km to Ch. 62.86 Km (in selected reaches) in Basavanabagewadi Taluk in Vijayapur District | Upgraded To SH | 204 | 1200 | [7 empty] | 15: 6.47; 16: 7.825; 17: 0; 18: 0%; 19: 7.825; 23: 6.50 Km BM completed & balance 1.325 Km work under progress
45 | 481 |  | Improvements to Road Ukkalli - Dindawar - Sasanur MDR from Km 15.10 to 31.00 Km (In Selected reaches) in Basavanbagewadi Taluk of Vijayapura District. | Upgraded To SH | 205 | 1000 | 1000 | 855.39 | 1053.83 |  | 1308.99 |  |  | Sri Ramesh Sharanappa Koulagi | 2022-07-15 | 2023-06-14 |  | 4 | 4 | 2.7 | 67.5% | 1.3 | 485 | 46.02% | 568.83 | 2.7 Km BC Completed & CC 0.69Km pending, 0.60Km WMM completed. 0.61Km all works pending
46 | 483 |  | Improvements to Kawadimatti - Donkamadu MDR from Ch 0.00 Km to Ch 19.60 Km (In Selected reaches) in Muddebihal Taluk of Vijayapura District. | MDR/MDD-208 | 208 | 2300 | 2300 | 1971.27 | 2444.37 |  | 2684.15 |  |  | Sri Siddanagoud H Patil | 2022-05-11 | 2023-11-10 |  | 9.61 | 10.365 | 8.37 | 80.75% | 1.995 | 2290.23 | 93.69% | 154.14 | 0.65Km CC completed (0.250KM GSB Under progress for CC road), 1.10Km work to be started(BT)
47 | 484 |  | Improvements to road Inchigeri Horti Roogi MDR from Ch: 13.00 Km to Ch: 33.60 Km (in selected reaches) in Indi Taluk in Vijayapur District. | MDR/IND-11 | 209 | 1000 | 1000 | 854.06 | 1007.79 |  | 1104.65 |  |  | Sri Hanamanth Rayappa Chinchali | 2022-08-03 | 2023-07-02 |  | 6.06 | 6.09 | 5.17 | 84.89% | 0.92 | 983.91 | 97.63% | 23.88 | BT, Road completed , 290M Drain completed. 370 Mtr CC Road Completed(560mtr CC road pending)
48 | 485 |  | Improvements to Minchanala - Atharga - Thamba - Koralli MDR from Ch.37.60 to 51.40 Km (In Selected reaches) in Sindagi Taluk of Vijayapura District. | MDR/SND-9 | 211 | 1000 | 1000 | 855.43 | 940.95 |  | 940.95 |  |  | Sri Babasaheb Bapusaheb Gunjate, Maharshtra | 2022-08-02 | 2023-07-01 |  | 6.02 | 6.02 | 3.5 | 58.14% | 2.52 | 225 | 23.91% | 715.95 | 2.52 Km BC pending,
49 | 486 |  | Improvements to road from Jorapur Water Tank to Connecting NH-50 in Vijayapura Taluk of Vijayapura District. | SH | 213 | 2000 | 2000 | 1714.14 | 2074.19 |  | 2589.9 |  |  | Sri Sunil M Ullagaddi | 2022-07-13 | 2024-01-12 |  | 3.69 | 3.53 | 0 | 0% | 3.53 | 953.06 | 45.95% | 1121.13 | 2.60KM DBM completed , 410mtr CC completed ,Median & Street light work in progress. 520Mtr Road work pending
|  |  | Division Total |  |  | 9600 | 9600 | 8215.66 | 9966.43 |  | 11296.65 | 0 | 0 | 15: 42.76; 16: 44.74; 17: 26.65; 19: 18.09; 20: 7303.29; 22: 2663.14
Bagalkot Division
50 | 488 |  | Improvements to Sureban Chitharagi Kudalasangama SH 133 from Ch.43.70 to 58.20 Km (In Selected reaches) in Badami Taluk of Bagalkote District. | SH-133 | 215 | 2000 | 2000 | 1709.03 | 2044.44 |  | 2044.44 |  |  | Sri Earanna Mamadapur | 2022-06-23 | 2023-12-22 |  | 8.33 | 8.33 | 3.5 | 42.02% | 4.83 |  | 0% | 2044.44 | 4.83 Km GSB under progress
51 | 489 | A | Improvements to Jamakhandi Galagali via Mudaganoor MDR from Ch.14.82 to 27.00 Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-3 | 216 | 800 | 2300 | 1966.72 | 2422.82 | 239.44 | 2662.26 |  |  | B N Naganagoudar Contractors | 2022-05-11 | 2023-11-10 |  | 9.61 | 6.78 | 1.7 | 25.07% | 5.08 | 1283.6 | 52.98% | 1139.22 | 5.00KM DBM completed , 1.58KM not started
|  | B | Improvements to Badagandi – Sangam MDR from Ch.5.00 to 6.72Km in Bilagi Taluk of Bagalkote District. | MDR/BLG-6 | 217 | 0 | [7 empty] | 17: 0; 18: 0%; 19: 0; 23: Work dropped
|  | C | Improvements to Sankeshwar – Sangam SH-44 from Ch.110.00 to 124.00 Km (In Selected reaches) (Nerbudihal village limit) in Badami Taluk of Bagalkote District | SH-44 | 218 | 500 | [7 empty] | 15: 1.803; 16: 1.803; 17: 1.803; 18: 100%; 19: 0; 23: Road Work Completed & Road Furniture work under progress
|  | D | Improvements to Constrution of Bridge/Box Culvert at CH:3.50km in Kanakatti Anavala Ge-mu-ra of Beelagi constituency at Badami taluk, Bagalkote Dist. |  |  | 300 | [7 empty] | 23: 5 vent-Box culvert, 3 Vent-Completed balance work in progress
|  | E | Improvements at Construction of bridge/box culvert at Ch:0.20Km in sulikere Kagalagomba Ge-mu-road of beelagi constituency at Badami taluk, Bagalakote Dist. |  |  | 200 | [7 empty] | 23: 3 vent Deck slab upto slab level, balance work in progress
|  | F | Improvements at Construction of Bridge/box culverts at SH-44 Ch:107.00 km in Sankeshwar Sangam near Kadarakoppa village of Bellary constituency at Badam taluk Bagalkote Dist. |  |  | 500 | [7 empty] | 23: 8 vent-Box culvert, 2 Vent-slab, slab laid, 6 vent -upto slab level Completed
52 | 492 | A | Improvements to Jambotti – Rabakavi SH-54 from Ch.130.47 to 131.13 Km, Ch.132.09 to Ch.133.70, CH.135.39 to 139.20 & CH.139.70 to 141.56 (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | SH-54 | 230 | 1650 | 3250 | 2774.06 | 3435.07 | 812.73 | 4247.8 |  |  | Sri Kashinath N Kankale (Kankale Constructions Private Limited) | 2022-07-29 | 2024-01-28 |  | 3.18 | 3.67 | 3.17 | 86.38% | 0.5 | 2408.41 | 70.11% | 1026.66 | work under progress
|  | B | Improvements to Road Madhurakhandi – Kallalli - Jagadala – Chimada MDR from Ch.0.00 to 10.80 Km (In Selected reaches) in Rabakavi - Banahatti Taluk of Bagalkote District. | MDR/JMK-9 | 231 | 650 | [7 empty] | 15: 4.05; 16: 4.04; 17: 4.04; 18: 100%; 19: 0; 23: Road Work Completed & Road Furniture work to be started
|  | C | Improvements to Bidari - Honawada Road via Thodalabagi - MDR from Ch.10.12 Km to 15.25 Km & Ch.25.60 Km to 31.00 Km in Jamkhandi Taluk of Bagalkote District. | MDR/JMK-24 | 229 | 950 | [7 empty] | 15: 4.74; 16: 5.72; 17: 1; 18: 17.48%; 19: 4.72; 23: 4.72 Km BC work balance
|  |  | Division Total |  |  | 7550 | 7550 | 6449.81 | 7902.33 | 1052.17 | 8954.5 | 0 | 0 | 15: 31.713; 16: 30.343; 17: 15.213; 19: 15.13; 20: 3692.01; 22: 4210.32
Belagavi Division
53 | 493 |  | Improvements to SH-20, Raichur-Bachi Roadfrom Ch. 333.00 Km to 393.53 Km (In Selected Reaches) in Belagavi Taluk Belagavi District. | SH-20 | 232 | 2150 | 2150 | 1849.43 | 2184.4 | 530.13 | 2712.53 |  |  | Sri Manjunath B Garag, | 2022-06-24 | 2023-12-23 |  | 5.39 | 5.39 | 0.7 | 12.99% | 4.69 | 759.77 | 34.78% | 1424.63 | Extended Carriageway under progress & Subgrade layer under progress
54 | 494 | A | Improvements to Yadiyurappa Margra (OLD PB Road) from Ch. 0.00 Km to 3.81 Km and from SPM Road to VRL Office Joining Road ( In slected Reaches) in Belagavi Taluk, Belagavi Districts. | MDR | 233 | 820 | 2300 | 1984.83 | 2483.21 | 118.85 | 2602.09 |  |  | M/s KKB Engineer Construction Private Limited | 2022-08-03 | 2024-02-02 |  | 1.61 | 1.61 | 1.61 | 100% | 0 | 460 | 18.52% | 2023.21 | Concrete Road Completed Extended CW paver block work under progress
|  | B | Improvements to SH-54, Jamboti-Rabakavi Road, Vajapeyee Marga ( Belagavi Panaji SH-4A, From Benco Cross to 3rd Gate) from Ch. 23.80 Km to 27.60 Km in Belagavi Taluk, Belagavi District. | SH-54 | 234 | 1480 | [7 empty] | 15: 1.64; 16: 1.966; 17: 1.2; 18: 61.04%; 19: 0.766; 23: 1.96 Km (RHS) & 1.20 km (LHS) Concrete road Completed. 0.76km (LHS) Balance Concrete road under progress
55 | 495 | A | Improvements to SH-93, Khanapur-Talugupppa Road, From Ch. 0.00 to 34.58 Km (in Selected Reach) in Khanapur Taluk, Belagavi District. | SH-93 | 236 | 500 | 1000 | 854.47 | 924.36 |  | 924.36 |  |  | Sri Jayadev Parugouda Biradar | 2022-08-03 | 2023-07-02 |  | 8 | 7.955 | 5.55 | 69.77% | 2.405 | 0 | 0% | 924.36 | BC 5.55 km completed, Balance is in progress
|  | B | Improvements to SH-138 Nagaragali-katakol road from Ch. 0.00 Km to 15.95 Km (Selected Reaches) in KhanapurTaluk, Belagavi District. | SH-138 | 237 | 500 | [7 empty] | 15: 5.43; 16: 5.43; 17: 0; 18: 0%; 19: 5.43; 23: Earthwork under progress
56 | 498 | A | Improvements to MDR-SAU89 SAVADATTI-SANGRESHKOPPA Road Via Mamani Kere from Ch. 0.00 Km to 8.00 Km in Savadatti Taluk, Belagavi District | MDR-SAU89 | 241 | 1000 | 2250 | 1934.43 | 2350.32 | 232.31 | 2582.64 |  |  | Sri Mallanagowda H Patil, Belagavi | 2022-08-02 | 2024-02-10 |  | 7.8 | 7.783 | 4.6 | 59.1% | 3.183 | 955.4 | 40.65% | 1394.92 | WMM Layer & Box culvert under progress GSB & BC work under progress
|  | B | Improvements to MDR SAU-4 Saundatti Hanchinal Road From Km Ch 0.00 to 6.00 Km (Selected Reaches) in Saundatti Taluka, Belagavi District | MDR SAU-4 | 267 | 740 | [7 empty] | 15: 4.04; 16: 4.04; 17: 4.04; 18: 100%; 19: 0; 23: Road Work Completed & Road Furniture work under progress
|  | C | Improvements to MDR from Yallamma Temple to SH-34 Joining Road, From Km Ch 0.00 to 2.00 Km in Savadatti Taluka, Belagavi District. | MDR | 268 | 510 | [7 empty] | 15: 2; 16: 2; 17: 2; 18: 100%; 19: 0; 23: Road Work Completed & Road Furniture work under progress
|  |  | Division Total |  |  | 7700 | 7700 | 6623.16 | 7942.29 | 881.29 | 8821.62 |  |  | 15: 35.91; 16: 36.174; 17: 19.7; 19: 16.474; 20: 2175.17; 22: 5767.12
Chikkodi Division
57 | 504 | A | Improvements to SH-31, JATH-JAMBOTI Road, from Ch. 106.82 Km to 115.05 Km and 121.18 Km to 121.78 Km in Gokak Taluka, Belagavi District | SH-31 | 16 | 1440 | 2300 | 1981.76 | 2362.27 | 565.88 | 2928.15 |  |  | Sri B B Dasanavar, Gokak | 2022-08-29 | 2024-02-28 |  | 6.325 | 6.325 | 0 | 0% | 6.325 | 654.22 | 27.69% | 1708.05 | 5.229 km DBM completed, GSB & WMM work under progress
|  | B | Improvements to Jamboti rabhakavi Road SH-54 From Km 62.08 to 66.70 (Akkatangerahal to Telaginahatti) From Km 83.00 to 84.20 (Hanamapur Cross) And From Km 54.28 to 55.755 Gokak Taluk Belagavi Districts. | SH-54 | 17 | 860 | [7 empty] | 15: 4.9; 16: 4.9; 17: 0; 18: 0%; 19: 4.9; 23: 2.37 Km DBM Completed
58 | 506 | A | Improvements to Kagawad-Kaladagi Sh-53 Road from Ch: 22.40 Km to 24.10 Km, Ch: 24.90 Km 29.60 Km, 32.55 Km to 35.00 km, 44.39 Km to 44.90 Km in Raibag Taluk, Belagavi District. | SH-53 | 21 | 1430 | 2250 | 1937.43 | 2380.35 | 576.37 | 2956.72 |  |  | M/s Tarade Brothers Constructions Pvt Ltd., | 2022-07-21 | 2024-01-20 |  | 9.6 | 11.25 | 11.21 | 99.64% | 0.04 | 2455.36 | 103.2% | -75.01 | Road furniture Under Progress
|  | B | Improvements to Chikkodi Railway Station-Mugalakod-Handigundi MDR from Ch: 10.03 Km to 14.00 Km, And Ch: 19.00 Km to 39.15 Km in (Selected Reaches) Raibag Taluk, Belagavi District. | MDR | 23 | 820 | [7 empty] | 15: 5.1; 16: 7.24; 17: 0; 18: 0%; 19: 7.24; 23: Side Shoulder under progress
59 | 509 |  | Improvements to Harugeri-Raibag-Nagaramunnolli MDR from Ch. 16.00 Km to 18.68 And Ch: 23.80 to 37.00 ( Selected Reaches) in Raibag Taluk, Belagavi District. | MDR | 26 | 1275 | 1275 | 1095.51 | 1343.7 | 241.83 | 1585.53 |  |  | Sri Mainuddin Mulla (S A Mulla) | 2022-07-21 | 2023-10-20 |  | 6.2 | 6.33 | 4.31 | 68.09% | 2.02 | 1376.34 | 102.4% | -32.64 | Drain & Road furniture work under progress
|  |  | Division Total |  |  | 5825 | 5825 | 5014.7 | 6086.32 | 1384.08 | 7470.4 | 0 | 0 | 15: 32.125; 16: 36.045; 17: 15.52; 19: 24.46; 20: 18011.77; 22: 4189.84
|  |  | Belagavi Circle Total |  |  | 30675 | 30675 | 26303.33 | 31897.37 | 3317.54 | 36543.17 | 0 | 0 | 15: 142.508; 16: 147.302; 17: 77.083; 19: 74.154; 20: 31182.24; 21: 0; 22: 21433.68
|  |  | North Circle Total |  |  | 114650 | 114650 | 98457.04 | 116454.49 | 13922.89 | 131705.65 | 0 | 0 | 15: 641.734; 16: 650.604; 17: 340.37; 19: 350.682; 20: 100504.35; 22: 77060.346
Shivamogga Circle
Davanagere Division
60 | 511 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:186.35 Km to 194.05Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | SH-65 | 29 | 1100 | 2300 | 1976.51 | 2323.26 |  | 2323.26 |  |  | Sri Paramesh Ramappa, Davanagere | 27.07.2022 | 26.01.2024 |  | 7.7 | 7.7 | 7.7 | 100% | 0 | 1129.97 | 48.64% | 1193.29 | Road Furniture work is in progress
|  | B | Improvements to Road From Nalluru -Devarahalli MDR From Ch:5.00 Km to 11.00 Km in Channagiri Taluk of Davanagere District | CNG12 | 31 | 650 | [7 empty] | 15: 4.97; 16: 4.97; 17: 4.97; 18: 100%; 19: 0; 23: Road Furniture work is in progress
|  | C | Improvements to Road From Pandomatti to Neethigere MDR From Ch:0.00 Km to 16.00 Km (In Selected Reaches) in Channagiri Taluk of Davanagere District | CNG27 | 32 | 550 | [7 empty] | 15: 3.92; 16: 3.92; 17: 3.33; 18: 84.95%; 19: 0.59; 23: CC road completed upto DLC Further PQC work is in progress
61 | 512 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:233.00Km to 242.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District. | SH-65 | 34 | 1000 | 3000 | 2579.78 | 2937.46 | 725.96 | 3663.42 |  |  | M/s Udayshivakumar Infra Private Limited, Davanagere | 21.07.2022 | 20.01.2024 |  | 8.78 | 5.9 | 0.35 | 5.932% | 5.55 | 1357.45 | 37.05% | 2305.97 | Currently Box cutting at Ch.240.34 to 240.84Km is in progress & 1.55Km PQC on LHS is in progress
|  | B | Improvements to Road From Davanagere Budihala Arasapura MDR From Ch:4.80Km to 12.75Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG9 | 35 | 800 | [7 empty] | 15: 3.3; 16: 3.3; 17: 3.3; 18: 100%; 19: 0; 23: Road Furniture work is in progress
|  | C | Improvements to Road From Bethur to Dhoddabathi MDR From Ch:0.00Km to 12.00Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 37 | 700 | [7 empty] | 15: 3.47; 16: 3.47; 17: 3.47; 18: 100%; 19: 0; 23: Road Furniture work is in progress
|  | D | Improvements to Road From Malpe-Molakalmuru SH-65 to Rampura MDR From Ch:0.00Km to 11.50Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | New MDR | 38 | 500 | [7 empty] | 15: 2.45; 16: 2.45; 17: 1.74; 18: 71.02%; 19: 0.71; 23: Balance 0.710 Km length DLC work is in progress, 5 Structures are completed out of 7
62 | 513 | A | Improvements to Road From Mandya - Hadagali SH-47 From Ch:261.25Km to 293.83Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | SH-47 | 46 | 1350 | 2250 | 1932.48 | 2162.65 |  | 2162.65 |  |  | M/s Udayshivakumar Infra Private Limited, Davanagere | 06.07.2022 | 05.01.2024 |  | 12.33 | 12.33 | 9.35 | 75.83% | 2.98 | 655.9 | 30.33% | 1506.75 | Balance 2.980Km DBM work is in progress 8 Structures are completed
|  | B | Improvements to Road From Aluruhatti -Anagodu MDR From Ch:0.00Km to 13.245Km (In Selected Reaches) in Davanagere Taluk of Davanagere District | DVG12 | 47 | 900 | [7 empty] | 15: 6.78; 16: 6.78; 17: 5.24; 18: 77.29%; 19: 1.54; 23: Balance 1.1Km WMM & 0.44Km DLC work is in progress
63 | 514 | A | Improvements to Road From Malpe to Molakalmuru SH-65 From Ch:302.60Km to 306.40Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District. (Four Lane road) | SH-65 | 298 | 700 | 2250 | 1935.87 | 2307.96 |  | 2307.96 |  |  | M/s S Narayana Reddy, Channarayapattana | 24.08.2022 | 23.02.2024 |  | 1.97 | 1.97 | 0 | 0% | 1.97 | 390.39 | 16.91% | 1917.57 | 0.667Km CC Drain on Both side & 0.440Km median work completed Further 1.970Km C&G work is in progress
|  | B | Improvements to Road From Rangapura Gadimakunte MDR From Ch:6.50Km to 12.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL208 | 51 | 650 | [7 empty] | 15: 6.5; 16: 6.5; 17: 0; 18: 0%; 19: 6.5; 23: 2.5Km GSB work is in progress
|  | C | Improvements to Road From Jagaluru Kadabanakatte MDR From Ch:9.00Km to 14.50Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL34 | 52 | 400 | [7 empty] | 15: 3.015; 16: 3.015; 17: 0.7; 18: 23.22%; 19: 2.315; 23: 1.5Km WMM work is in progress
|  | D | Improvements to Road From Baramasagara - Bilichodu -Basavanakote MDR From Ch:13.00Km to 37.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL3 | 53 | 200 | [7 empty] | 15: 1.21; 16: 1.21; 17: 1.21; 18: 100%; 19: 0; 23: Road Furniture work is in progress & Box culvert at Ch. 22.2Km is in progress | .
|  | E | Improvements to Road From Bilichodu-Sokke MDR From Ch:10.00Km to 16.00Km (In Selected Reaches) in Jagaluru Taluk of Davanagere District | JGL4 | 56 | 300 | [7 empty] | 15: 3.57; 16: 3.57; 17: 3.37; 18: 94.4%; 19: 0.2; 23: 0.2Km BM work is in progress
64 | 515 | A | Improvements to Road From Malebennuru - Ekegundhi - Nandhigudi Joining MDR From Ch-0.00Km to 6.00Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR11 | 57 | 475 | 3250 | 2789.13 | 3321.56 |  | 3321.56 |  |  | M/s Bale Constructions, Deodurga, Raichur | 21.09.2022 | 20.03.2024 |  | 3.21 | 3.21 | 0 | 0% | 3.21 | 684.09 | 20.6% | 2637.47 | Subgrade work is Completed for a length of 2.00Km further work in progress
|  | B | Improvements to Road From Palya-Mooginagundhi Joining MDR From Ch:0.00Km to 12.67Km (In Selected Reaches) in Harihara Taluk of Davanagere District | HRR12 | 59 | 475 | [7 empty] | 15: 3.7; 16: 3.7; 17: 0; 18: 0%; 19: 3.7; 23: HPC @ Ch 6.59Km is in progress 2 structure are completed out of 12
|  | C | Improvements to Road From Nalluru to Sasivehalli MDR From Ch:8.00Km to 16.63Km in Honnalli Taluk of Davanagere District | HNN15 | 60 | 1000 | [7 empty] | 15: 8.63; 16: 8.63; 17: 4; 18: 46.35%; 19: 4.63; 23: Balance 4.630km GSB work in progress 7 structures are completed out of 13
|  | D | Improvements to Road From Kurki to Kulambi MDR From Ch:16.40Km to 22.70Km in Honnalli Taluk of Davanagere District | HNN49 | 61 | 700 | [7 empty] | 15: 6.3; 16: 6.3; 17: 3.35; 18: 53.17%; 19: 2.95; 23: Balance 2.950km WMM work in progress 6 structures are completed out of 15
|  | E | Improvements to Road of Honnali -Katthige MDR From Ch:3.00Km to 13.20Km (In Selected Reaches) in Honnalli Taluk of Davanagere District | HNN21 | 62 | 600 | [7 empty] | 15: 4.32; 16: 4.32; 17: 3.55; 18: 82.18%; 19: 0.77; 23: Balance 0.770km GSB work in progress
|  |  | Division Total |  |  | 13050 | 13050 | 11213.77 | 13052.89 | 725.96 | 13778.85 | 0 | 0 | 15: 96.125; 16: 93.245; 17: 55.63; 19: 37.615; 20: 4217.8; 22: 9561.05
Chitradurga Division
65 | 517 | A | Improvements to SH-47- Kakanur MDR from KM 0.00 to 13.00 KM (In Selected Reaches) in Holalakere Taluk of Chitradurga District | HLK202 | 68 | 770 | 2300 | 1960.81 | 2322.26 | 478.09 | 2800.35 |  |  | Sri Rajasekharappa T, Chitradurga | 02.08.2022 | 01.02.2024 |  | 7.52 | 10.42 | 7.52 | 72.17% | 2.9 | 1034.2 | 36.93% | 1766.15 | 2.90 Km Work yet to be started
|  | B | Improvements to Sivaganga - Janakkal - Hosadurga Newly Upgraded State Highway from KM 0.00 to 16.55 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District | NEW SH | 69 | 650 | [7 empty] | 15: 6.53; 16: 7.02; 17: 4.64; 18: 66.1%; 19: 2.38; 23: 1.89Km GSB work in progress
|  | C | Improvements to State Highway-153-Singhenahalli- to join State Highway 48 Kasturiba Nagar via Talikatte- Malladihalli-Ramaghatta-Hirehemmiganur Newly Upgraded State Highway from KM 0.00 to 38.30 KM (In Selected Reaches) in Holalkere Taluk of Chitradurga District. | NEW SH | 70 | 880 | [7 empty] | 15: 7.56; 16: 7.56; 17: 6.23; 18: 82.41%; 19: 1.33; 23: 1.33km CCP work in progress & All structures are completed
66 | 518 | A | Improvements to Mandya -Hadagali Road State Highway - 47 from KM 183.00 to 212.00 KM (In Selected Reaches) in Hosadurga Taluk of Chitradurga District | SH-47 | 81 | 1700 | 2300 | 1976.39 | 2402.26 |  | 2402.26 |  |  | Sri C Halappa, Chowlahiriyuru, Kadur tq, Chikkamagaluru | 15.07.2022 | 14.01.2024 |  | 8.25 | 8.25 | 6.9 | 83.64% | 1.35 | 1180.19 | 49.13% | 1222.07 | Balance 1.350km DBMwork in progress 2 structures are completed out of 5
|  | B | Improvements to Sivaganga-Janakal Hosadurga Newly Upgraded State Highway from KM 24.00 to 29.2 KM (in Selected Reaches) in Hosadurga Taluk of Chitradurga District | NEW SH | 82 | 600 | [7 empty] | 15: 4.4; 16: 4.4; 17: 0; 18: 0%; 19: 4.4; 23: 3.8Km GSB completed
67 | 520 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 6.48 to 46.38 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 102 | 1400 | 2300 | 1979.02 | 2339.81 | 562.42 | 2902.23 |  |  | Sri Anwar Basha.K, Chitradurga | 29.07.2022 | 28.01.2024 |  | 10.97 | 10.97 | 9.77 | 89.06% | 1.2 | 990.49 | 42.33% | 1349.32 | Balance 1.203km DLC work in progress
|  | B | Improvements to Belagatta- Haikal, Nayakanhatti Suramanahalli -Chikkunti -Siddaiahkote - Rayapur -Molakalmooru Newly Upgraded State Highway Road from KM 39.80 km to 89.40 KM (in Selected Reaches) in Molakalmooru Taluk of Chitradurga District | NEW SH | 103 | 900 | [7 empty] | 15: 5.26; 16: 5.26; 17: 3.56; 18: 67.68%; 19: 1.7; 23: DBM for 1.0Km & 0.600km Earthwork is in progress.
68 | 521 | A | Improvements to Chalakkere-Mylanahalli-Obalapura Newly upgraded State Highway Road from KM 2.40 to 6.48 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 104 | 530 | 950 | 814.7 | 880.09 |  | 880.09 |  |  | M/s Balajikrupa Projects Private Limited, Bangalore | 20.06.2022 | 19.05.2023 |  | 3.88 | 3.88 | 3.8 | 97.94% | 0.08 | 397.9 | 45.21% | 482.19 | In balance 0.08 km work C&G work in progress
|  | B | Improvements to road from Pathappanagudi to Shira border via Jajur, Parashurampura, Dharmapura, Sakkara, Newly upgraded State Highway road From KM 0.00 to 46.10 KM (in Selected Reaches) in Challakere Taluk of Chitradurga District | NEW SH | 105 | 420 | [7 empty] | 15: 4; 16: 4; 17: 3.75; 18: 93.75%; 19: 0.25; 23: 0.250Km PQC work is in progress
69 | 522 |  | Improvements to Yalagodu-Turavanur Doddaghatta MDR from KM 0.00 to 22.20 KM (in Selected Reaches) in Chitradurga Taluk of Chitradurga District | CHD12 | 106 | 800 | 800 | 687.2 | 804.42 | 194.1 | 998.52 |  |  | M/s Subba Reddy & son’s Construction Private Limited | 29.07.2022 | 28.06.2023 |  | 9 | 10.5 | 8.4 | 80% | 2.1 | 925.47 | 115% | -121.05 | In balance 0.60km C&G work in progress
|  |  | Division Total |  |  | 8650 | 8650 | 7418.12 | 8748.84 | 1234.61 | 9983.45 | 0 | 0 | 15: 67.37; 16: 72.26; 17: 54.57; 19: 17.69; 20: 7999.84; 22: 5831.38
Shivamogga Special Division | bar: 15 to 17; 19 to 23
70 | 523 | A | Improvements to road from State Highway-148 to join State Highway-148 via Sirigere, Thamadihalli, Bilguni, Adagadi, Mandaghatta, Dhyavanakere, Ragihosahalli, Rechikoppa, Shettikere, Shantikere, Koragi, Horabilu, Tuppuru, Byadanal, Kattigehalli Newly upgraded MDR road from KM 0.00 to 23.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 107 | 700 | 2300 | 1958.93 | 2263.76 |  | 2263.76 |  |  | Sri Sharanappa Sangappa Alur (M/s S S Alur Construction Company), Vijayapura | 16.07.2022 | 15.01.2024 |  | 7.1 | 7.1 | 5 | 70.42% | 2.1 | 826.85 | 36.53% | 1436.91 | 2 km length yet to be started
|  | B | Improvements to State Highway 148 via Sirigare Manjerikoppa, Maleshankara Temple, Yerebisu, Koodi, Gammanagadde to join State Highway 148 newly upgraded MDR road from KM 0.00 to 20.00 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW MDR | 110 | 500 | [7 empty] | 15: 4.9; 16: 4.9; 17: 4.9; 18: 100%; 19: 0; 23: Road furniture work under progress
|  | C | Improvements to Koodligere-Kammaraghatta State Highway-115 road from KM 7.00 to 17.70 KM (in Selected Reaches) in Bhadravathi Taluk of Shivamogga District | SH-115 | 112 | 700 | [7 empty] | 15: 6; 16: 6; 17: 4.5; 18: 75%; 19: 1.5; 23: 1.5 km length work yet to be started
|  | D | Improvements to From Bhadravathi to Sasivehalli (Honnali Taluk Border) via Holehonnur, Sidlipura, Sanyasikodamge, Nagasamudra, Managotte, Anaveri, Nimbegundi, Saidarakallalli Newly upgraded State Highway road from KM 0.00 to 35.10 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | NEW SH | 113 | 400 | [7 empty] | 15: 3; 16: 3; 17: 0; 18: 0%; 19: 3; 23: Work yet to be Started
71 | 524 | A | Improvements to NH-26 near Hittur Cross from Umblebailu (SH-65) via Ganidalu-uralalli-Lakkinakoppa kadekal- Kuskur-Siddarahalli-Matturu Malalikoppa-Madaripalya, NH-13 & SH-57 to 100 feet road from Vinobhanagar Police Chowki to Sominakoppa, Gejjenahalli, Tyajavalli, Devabalu, Edavala Newly upgraded State Highway road from KM 0.00 to 46.60 KM (in Selected Reaches) in Shivamogga Taluk of Shivamogga District | NEW SH | 114 | 1800 | 2800 | 2406.91 | 2738.49 |  | 2738.49 |  |  | Sri Ibrahim Sharief, Thirthahalli | 21.06.2022 | 20.12.2023 |  | 13.9 | 13.9 | 9 | 64.75% | 4.9 | 1243.38 | 45.4% | 1495.11 | 1.10 km WMM work under progress for W & S Reach.
|  | B | Improvements to Tumkur - Honnavar State Highway-68 road from KM 6.20 to 9.50 KM (in Selected Reaches) in Bhadravathi Taluk of Shimoga District | SH-68 | 115 | 1000 | [7 empty] | 15: 1.26; 16: 1.26; 17: 1; 18: 79.37%; 19: 0.26; 23: 0.26Km work is under progress.
72 | 525 | A | Improvements to Begaru -Kalmane MDR road from KM 0.00 to 7.80 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | TRT 08 | 127 | 600 | 2300 | 1963.07 | 2447.18 |  | 2447.18 |  |  | Sri Abdul Kalam Azad, Thirthahalli | 21.06.2022 | 20.12.2023 |  | 6.85 | 6.85 | 6.85 | 100% | 0 | 1344.7 | 54.95% | 1102.48 | Road furniture work under progress
|  | B | Improvements to Padubidri - Chikkalagudda State Highway - 01 road from KM 113.00 to 131.00 KM (in Selected Reaches) in Tirthahalli Taluk of Shivamogga District | SH-01 | 128 | 860 | [7 empty] | 15: 6.65; 16: 6.65; 17: 6.65; 18: 100%; 19: 0; 23: Road furniture work under progress
|  | C | Improvements to Kuppalli- Kavisaila-Ayanur-Soodur-Gamma-Mallenahalli join to Hirekerur State Highway 148 road from KM 4.40 to 37.00 KM (in Selected Reaches) inTirthahalli Taluk of Shimoga District | SH-148 | 129 | 840 | [7 empty] | 15: 7.25; 16: 7.25; 17: 0; 18: 0%; 19: 7.25; 23: Culvert works completed, road work yet to be started.
|  |  | Division Total |  |  | 7400 | 7400 | 6328.91 | 7449.43 | 0 | 7449.43 | 0 | 0 | 15: 56.91; 16: 56.91; 17: 37.9; 19: 19.01; 20: 3414.93; 22: 4034.5
Shivamogga Division
73 | 526 |  | Improvements to Kuppalli- Kavishaila, via Ayanur, Soodur, Gama, Mallenahalli to join Hirekerur State Highway 148 road from KM 92.12 to 156.12 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-148 | 130 | 2300 | 2300 | 1980.33 | 2332.64 |  | 2332.64 |  |  | Sri Dayananda Shetty (M/s Manjushri construction Company), Kundapura | 21.06.2022 | 20.12.2023 |  | 11.6 | 11.6 | 9 | 77.59% | 2.6 | 1329.4 | 56.99% | 1003.24 | 2.6 km Scarifying work under progress.
74 | 527 |  | Improvements to Kumta Kadamadagi State Highway 48 road from KM 139.03 to 158.03 KM (in Selected Reaches) In Shikaripura Taluk of Shivamogga District | SH-48 | 132 | 2200 | 2200 | 1895.35 | 2209.37 |  | 2209.37 |  |  | Sri Vivekanand Karikal (V P Karikal) | 16.07.2022 | 15.01.2024 |  | 9.85 | 9.85 | 7.8 | 79.19% | 2.05 | 870.43 | 39.4% | 1338.94 | Remaining 2.05 km work under progress
75 | 528 | A | Improvements to Gajendragada to Soraba State Highway 136 road from KM 280.37 to 282.07 KM and KM 294.82 to 311.29 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-136 | 133 | 1210 | 2250 | 1927.75 | 2345.68 |  | 2345.68 |  |  | Sri Dayananda Shetty (M/s Manjushri construction Company), Kundapura | 21.06.2022 | 20.12.2023 |  | 8.2 | 8.2 | 7 | 85.37% | 1.2 |  | 0% | 2345.68 | 1.2 km earth work under progress for W & S.
|  | B | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 28.50 to 37.00 KM & KM 53.80 to 59.16 KM (in Selected Reaches) in Soraba Taluk of Shivamogga District. | SH-77 | 134 | 1040 | [7 empty] | 15: 8.9; 16: 8.9; 17: 7.6; 18: 85.39%; 19: 1.3; 23: 1.30 km EMB work under progress for reconstruction reach.
76 | 529 | A | Improvements to Haveri-Sagar State Highway 62 road from KM 99.01 to 109.87 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-62 | 136 | 1140 | 2300 | 1975.47 | 2350.79 |  | 2350.79 |  |  | Sri B. Ramakrishna Sheregar (G D Thimmappa Sheregar), Udupi | 30.07.2022 | 29.01.2024 |  | 2.6 | 2.6 | 1.4 | 53.85% | 1.2 | 395.68 | 16.83% | 1955.11 | 1.20 Km work to be started
|  | B | Improvements to Padubidri-Chikkalagudda State Highway- 01 road from KM 158.00 to 160.00 KM (in Selected Reaches) in Hosnagar Taluk of Shivamogga District. | SH-01 | 137 | 550 | [7 empty] | 15: 1.2; 16: 1.2; 17: 0; 18: 0%; 19: 1.2; 23: Total 1.2 km Drainage work-0.70 km & cover slab-0.400 m at LHS. Tree cutting under progress
|  | C | Improvements to Sirsi-Hosanagar State Highway 77 road from KM 66.00 to 74.00 KM and KM 76.27 to 87.20 KM (in Selected Reaches) in Sagar Taluk of Shivamogga District. | SH-77 | 138 | 610 | [7 empty] | 15: 6; 16: 6; 17: 5.6; 18: 93.33%; 19: 0.4; 23: 400 m work yet to be started.
|  |  | Division Total |  |  | 9050 | 9050 | 7778.9 | 9238.48 | 0 | 9238.48 | 0 | 0 | 15: 48.35; 16: 48.35; 17: 38.4; 19: 9.95; 20: 2595.51; 22: 6642.97
Chikkamangalore Division
77 | 531 | A | Improvements to Kuduregundi - Muttinarajya Road MDR from Km 0.00 to Km 29.00 (In Selected Reaches) in Narasimharajpura Taluk of Chickmagalur District. | NRP3 | 337 | 450 | 900 | 759.69 | 797.27 |  | 797.27 |  |  | Sri B. M R Rushyashringa Hegde, Chikkamangalore | 21.07.2022 | 20.06.2023 |  | 4.5 | 4.5 | 2.75 | 61.11% | 1.75 | 291.09 | 36.51% | 506.18 | further balance work is under progress
|  | B | Improvements to Masage - Halanduru Road MDR from Km 0.00 to Km 15.00 (In Selected Reaches) in Sringeri Taluk of Chickmagalur District. | SNG8 | 338 | 450 | [7 empty] | 15: 4.04; 16: 4.04; 17: 3.5; 18: 86.63%; 19: 0.54; 23: 3.5 Km (Bm+Sdbc) Completed,Further Remaing Length WMM Laying Work Under Progress
|  |  | Division Total |  |  | 900 | 900 | 759.69 | 797.27 | 0 | 797.27 | 0 | 0 | 15: 8.54; 16: 8.54; 17: 6.25; 19: 2.29; 20: 9170.13; 22: 3099.57
|  |  | Shivamogga Circle Total |  |  | 39050 | 39050 | 33499.39 | 39286.91 | 1960.57 | 41247.48 | 0 | 0 | 15: 277.295; 16: 279.305; 17: 192.75; 19: 86.555; 20: 27398.21; 22: 29169.47
Mangalore Circle
Udupi Division
78 | 534 | A | Improvements to Padubidre-Chikkalagudda Road (SH-01) from km 50.00 to 52.050 km in (selected reaches) Hebri Taluk of Udupi District. | SH-1 | 140 | 700 | 2300 | 1957.76 | 2293.14 | 524.63 | 2817.77 |  |  | Sri Jeevan Shetty, Udupi | 29.07.2022 | 28.01.2024 |  | 1.43 | 1.428 | 0 | 0% | 1.428 | 911.39 | 32.34% | 1906.38 | 0.900 Km work under progress
|  | B | Improvements to Mangalore - Athradi SH-67 from Km 47.28 Km to Km 48.28 in (selected reaches) Karkala Taluka of Udupi Dist.. | SH-67 | 142 | 325 | [7 empty] | 15: 1; 16: 0.8; 17: 0.8; 18: 100%; 19: 0; 23: Work completed with Road furniture
|  | C | Improvements to Kalyanpura - Mudaru SH from Ch Km 27.50 to Km 32.00 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 144 | 225 | [7 empty] | 15: 1.7; 16: 1.87; 17: 1.87; 18: 100%; 19: 0; 23: Work completed with Road furniture
|  | D | Improvement to Subramanya-Udupi SH-37 from Km 119.50 to Km 126.10 (selected reaches) from intermediate lane to two lane in Karkala Taluk of Udupi District. | SH-37 | 145 | 450 | [7 empty] | 15: 3; 16: 3.16; 17: 2.97; 18: 93.99%; 19: 0.19; 23: 2.97 Km BC completed with road furniture.Balance 0.19 Km under progress.
|  | E | Improvements to Kalyanpura - Mudaru SH from Ch Km 41.00 to Km 48.00 (selected reaches) from single lane to intermediate lane in Karkala Taluk of Udupi District. | Newly Upgraded SH | 146 | 600 | [7 empty] | 15: 5.64; 16: 6.04; 17: 6.04; 18: 100%; 19: 0; 23: Work completed with Road furniture
79 | 536 | A | Improvements to Mudradi-Seethanadi- Bhramavara road Development of 4Lane from Ch Km 14.90 to Km 27.70 (selceted reaches) in Bhramavara Taluk of Udupi District.(Via. Havanji, Kolalagiri, Kukkehalli and Perdoor) | Newly Upgraded SH | 149 | 2250 | 4500 | 3844.3 | 4548.15 | 1131.04 | 5679.19 |  |  | Sri Uppinakudru Rajesh Karanth, Kundapura | 22.06.2022 | 21.12.2023 |  | 5.49 | 5.485 | 1.495 | 27.26% | 3.99 | 1958.19 | 34.48% | 3721 | 1.495 Km DBM completed.Further subgrade work under progress
|  | B | Improvements to Koteshwara-Kodi- Kundapura road from Ch Km 0.00 to Km 2.50 MDR in Kundapura Taluk of Udupi District. ( Via :Koteshwara-Kodi- Kundapura ) | KDP204 | 152 | 275 | [7 empty] | 15: 2; 16: 1.83; 17: 1.83; 18: 100%; 19: 0; 23: Work completed with Road furniture
|  | C | Improvements to Brahmavara-Jannadi- Biddalkatte-Sauda-Shankaranarayana- Siddapura road from Ch 2.50 Km to 12.00 Km(selceted reaches)MDR in Brahmavara Taluk of Udupi District. ( Via : Koteshwara-Kodi- Kundapura ) | KDP5 | 153 | 875 | [7 empty] | 15: 6.14; 16: 5.01; 17: 4.83; 18: 96.41%; 19: 0.18; 23: 4.83 Km work completed with road furniture
|  | D | Improvements to Kota-Goliyangadi road from Ch Km14.80 to Km 20.20 Major District road in Kundapura Taluk of Udupi District. ( Via: Koteshwara-Kodi- Kundapura ) | UDP4 | 154 | 650 | [7 empty] | 15: 5; 16: 5.15; 17: 4.17; 18: 80.97%; 19: 0.98; 23: 4.17Km BC complelted.0.98 KmTree cutting work under progress.
|  | E | Improvements to Someshwara- Koteshwara road MDR from Ch Km 34.00 to 41.50 Km (selected reaches) in Kundapura Taluk of Udupi District. ( Via. Haladi-Bidkalakatte) | KDP9 | 155 | 450 | [7 empty] | 15: 4.1; 16: 4.189; 17: 4.189; 18: 100%; 19: 0; 23: Work completed with Road furniture
80 | 537 | A | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 339.50 to Km 346.20 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 156 | 900 | 2250 | 1926.01 | 2265.8 |  | 2265.8 |  |  | Sri B.Ramakrishna Sheregar, M/s G.D. Thimmappa Sheregar, Udupi | 30.07.2022 | 29.01.2024 |  | 4.88 | 4.876 | 3.926 | 80.52% | 0.95 | 978.25 | 43.17% | 1287.55 | 0.876 BC Completed with road furniture
|  | B | Improvements to Virajapete Byndoor State Highway-27 from Ch Km 346.20 to 356.45 (selected reaches) in Kundapura Taluk of Udupi District. | SH 27 | 157 | 1350 | [7 empty] | 15: 9.291; 16: 9.291; 17: 5.62; 18: 60.49%; 19: 3.671; 23: 5.620 BC completed
|  |  | Division Total |  |  | 9050 | 9050 | 7728.07 | 9107.09 | 1655.67 | 10762.76 | 0 | 0 | 15: 49.671; 16: 49.129; 17: 37.74; 19: 11.389; 20: 3847.83; 22: 6771.16
Mangalore Division | bar: 23
81 | 538 | A | Improvements to Subramanya - Udupi State Highway 37 from Ch Km 3.50 to Km 14.00 (Selected reaches) in Kadaba Taluk of Dakshina Kannada District. | SH37 | 243 | 825 | 2200 | 1892.88 | 2109.97 |  | 2109.97 |  |  | Pavithra Engineering and Constructions, Mangalore | 04.08.2022 | 03.02.2024 |  | 7.08 | 7.08 | 7.08 | 100% | 0 | 933.38 | 44.24% | 1176.59 | Completed, Road furniture is under progress.
|  | B | Improvements to Bangalore-Jalsoor State Highway -85 from Ch Km 291.51 toKm 337.91 (Selected reaches) from single lane to intermediate Lane in Sullia Taluk of Dakshina Kannada District. | SH85 | 244 | 1375 | [7 empty] | 15: 10.21; 16: 10.21; 17: 5.68; 18: 55.63%; 19: 4.53; 23: 5.68km Completed, 4.53 is underprogress
82 | 542 | A | Improvements to Puttur- Uppinangadi- Guruvayanakere development of 4Lane from Ch Km 1.40 to Km 11.60 to (selected reaches) in Puttur Taluk of DakshinaKannada District | PUT8 | 255 | 1000 | 2250 | 1939.47 | 2202.45 | 544.59 | 2747.04 |  |  | Sri Dayananda Shetty, M/s Manjushri Construction Co., Udupi | 30.07.2022 | 29.01.2024 |  | 2.3 | 2.3 | 0 | 0% | 2.3 | 0 | 0% | 2202.45 | C & G completed
|  | B | Improvements to Saradka Periyaltada MDR road from Ch Km 0.00 to 9.00 Km (selected reaches) in Bantwala Taluk of Dakshina Kannada District | PUT10 | 256 | 975 | [7 empty] | 15: 6.6; 16: 5.15; 17: 5.15; 18: 100%; 19: 0; 23: completed, Road furniture is under progress.
|  | C | Improvements to Subramanya- Manjeshwara SH-100 road from Ch Km 48.000 to Km 50.00 in Puttur Taluk of Dakshina KannadaDistrict | SH100 | 257 | 275 | [7 empty] | 15: 1.78; 16: 1.78; 17: 0; 18: 0%; 19: 1.78; 23: C & G completed
83 | 543 | A | Improvements to Marvuru - Adyapadi - Unele- Kandavara MDR Ch road from Km 0.00 to Km 2.00 (selected reaches) and Maddya Peddiyangadi MDR from Km 0.00 to Km 2.00 (selected reaches) in Mangalore Taluk of Dakshina KannadaDistrict. | MNG105 MNG202 | 258 | 400 | 2100 | 1793.48 | 2410.19 |  | 2410.19 |  |  | Sri Udaya Shetty, M/s USK Construction Company DP, Udupi Ph No: 9480345814 | 30.05.2022 | 29.11.2023 |  | 3.67 | 3.67 | 0.87 | 23.71% | 2.8 | 1676.26 | 69.55% | 733.93 | 0.17 DLC Completed.
|  | B | Improvements to Parari-Ulayaibettu-Mallur MDR From Ch 2.40 km to 4.40 km in Mangalore Taluk of Dakshina Kannada District | MNG82 | 259 | 200 | [7 empty] | 15: 0.85; 16: 0.85; 17: 0; 18: 0%; 19: 0.85; 23: C & G completed
|  | C | Improvements to Bhatrakere - Katlasar - Kukkudakatte - Nirakere - Todar -Mastikatte - Road MDR from Ch 0.00 to 5.00 Km (selected reaches) in Mangalore Taluk of Dakshina Kannada District | Newly Upgraded MDR | 260 | 500 | [7 empty] | 15: 3.72; 16: 3.72; 17: 3.72; 18: 100%; 19: 0; 23: Completed, Road furniture is under progress.
|  | D | Improvement to Surthakal- Kabaka SH 101 development of 4lane from Km 1.60 to Km 4.80 ( in selected reaches) in Mangalore Taluka of Dakishna Kannada District. | SH-101 | 261 | 1000 | [7 empty] | 15: 1.7; 16: 1.7; 17: 1.6; 18: 94.12%; 19: 0.1; 23: Balance work under progress.
84 | 544 | A | Improvements to Moodabidre-Bantwal, Moodabidre-Kadandale MDR from Ch 40.80 Km to 42.80 Km (in selected reaches) in Bantwal taluk of Dakshina Kannada district. (via: Poochmooguru- Bantwal) | Newly Upgraded SH | 262 | 200 | 2250 | 1926.72 | 2372.16 |  | 2372.16 |  |  | Sri Jagdeep D Suvarna,Kumta | 04.08.2022 | 03.02.2024 |  | 1.13 | 1.13 | 0 | 0% | 1.13 | 627.45 | 26.45% | 1744.71 | Left with the Overlaying part
|  | B | Improvements to Mani -Ullala MDR from Ch 0.00 Km to 2.50 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 263 | 240 | [7 empty] | 15: 1.83; 16: 1.83; 17: 0; 18: 0%; 19: 1.83; 23: Left with the Overlaying part
|  | C | Improvements to Ganjimata Niddodi road via Yedapadavu Kuppepadavu-Arla Soranadu Road Rayi Moorje road from Ch 20.00 Km to 25.85 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 264 | 410 | [7 empty] | 15: 5.74; 16: 5.74; 17: 5.74; 18: 100%; 19: 0; 23: Completed , Road furniture is under progress.
|  | D | Improvements to Manihalla-Agilamogaru road from Ch 0.00 Km to 15.50 Km MDR (selected reaches) in Bantwal taluk of Dakshina Kannada district. | Newly Upgraded SH | 454 | 700 | [7 empty] | 15: 6.75; 16: 6.75; 17: 6.75; 18: 100%; 19: 0; 23: Completed, Road furniture is under progress.
|  | E | Improvements to Vogga Ulli road from Ch 6.00 Km to 14.20 Km (selected reaches) in Bantwal taluk of Dakshina Kannada district.(Via Maninalkaru kakkepadvu Ulli). | BNT19 | 266 | 700 | [7 empty] | 15: 4.28; 16: 4.28; 17: 2.28; 18: 53.27%; 19: 2; 23: Balance 2.00 km road under progress.
|  |  | Division Total |  |  | 8800 | 8800 | 7552.55 | 9094.77 | 544.59 | 9639.36 | 0 | 0 | 15: 57.64; 16: 56.19; 17: 38.87; 19: 17.32; 20: 3237.09; 22: 8359.98
|  |  | Mangalore Circle Total |  |  | 17850 | 17850 | 15280.62 | 18201.86 | 2200.26 | 20402.12 | 0 | 0 | 15: 107.311; 16: 105.319; 17: 76.61; 19: 28.709; 20: 7084.92; 22: 15131.14
Bangalore Circle
Bangalore Rural Division
85 | 545 | A | Improvements to Bangalore-Anekal-Bannerghatta Road (SH-87) from Km 16.80 to Km 20.00 & Km 26.25 to Km 28.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | ANK52 | 273 | 350 | 5800 | 4961.68 | 6005.718 |  | 6005.718 |  |  | RAMESH THAMMANNAGOWDA( GANAPATHI STONE CRUSHERS PVT LTD | 2022-10-21 | 2024-04-21 |  | 3.2 | 3.2 | 2.168 | 67.75% | 1.032 | 2094.13 | 34.87% | 3911.588 | 1. Asphalt Work of 2.45 kms completed and remaining work is in Progress.
|  | B | Improvements to MDR From NH-7 to SH-87 Via Hulimangala, Jigani from Km 6.50 to Km 9.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 274 | 450 | [7 empty] | 15: 2.2; 16: 2.2; 17: 0; 18: 0%; 19: 2.2; 23: Drain culvert work under progress road work to be started
|  | C | Improvements to MDR From Bagganadoddi to Amani Bidarakere via Mysuruammanadoddi, Shavayanadoddi, Yellamanadoddi, Pujaganahapalaya, Krishnaiahndoddi, Mahntalingapura, Kallubalu,Bukkasagara, Harapanahalli, Koppagate Connecting from Km 0.00 to Km 14.50 (in selected reaches) in Anekal Taluk of Bangalore Rural District | SH-87 | 275 | 1000 | [7 empty] | 15: 4.805; 16: 4.805; 17: 3.75; 18: 78.04%; 19: 1.055; 23: 3.750 Kms B.C completed. Remaning work is in progress
|  | D | Improvements to New SH From Magadi Road (SH-85) to Gunjuru (SH-35) via Hamahappanahalli cross-Chandrappa Circle- Doddaaladamara-Ramohalli-Kumbalgodu-Agara-Thataguni- Kaggalipura-Bannerughatta-Hommadevanahalli-Bettadasapura-Vipro Junction-Hosuru Road (NH-7) Konnapana Agragara-Sarjapura Main Road-(Kodathi gate) Kachamaranahalli from Km 6.00 to Km 13.60 & Km 17.80 to Km 29.40 (in selected reaches) in Bangalore SouthTaluk of Bangalore Rural District | New SH | 276 | 1300 | [7 empty] | 15: 6.08; 16: 6.08; 17: 4.21; 18: 69.24%; 19: 1.87; 23: 4.21 kms GSB, WMM,DBM & BC work Completed. Road furniture work in progress
|  | E | Improvements to MDR From Bylalu to Lakshmipura Ondane Mailikallu from Km 6.20 to Km 8.50 (in selected reaches) in Bangalore South Taluk of Bangalore Rural District | BNS210 | 277 | 300 | [7 empty] | 15: 2.3; 16: 2.3; 17: 2.3; 18: 100%; 19: 0; 23: Road Completed. Road furniture work in progress
|  | F | Improvements to MDR Connecting BM Road to Karubele via H Gollahalli from Km 2.50 to Km 5.00 (in selected reaches) inBangalore South Taluk of Bangalore Rural District | BNS214 | 278 | 300 | [7 empty] | 15: 2; 16: 2; 17: 1.72; 18: 86%; 19: 0.28; 23: Asphalt 1.72 km work completed. Road furniture work in progress
|  | G | Improvements to MDR from NH-75 (Makali) to Bettahalsuru connecting SH-104 via Honnasandra Cross, Aluru, APMC Yard,Basaveshwara Temple, Kodipalaya, Madhure, Kakolu,Rajanakunte, Thimmasandra, Betta Halasuru, NH-7, Muthagada Halli, Begur, Chikkanahalli and mylanahalli from Km 0.00 to Km 7.65 (Change to Ch:19.00) (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | SH | 279 | 800 | [7 empty] | 15: 6.05; 16: 6.05; 17: 5.645; 18: 93.31%; 19: 0.405; 23: Road Completed Road furniture work in progress
|  | H | Improvements to MDR from Singanayakanahalli to Madappanahalli via Shyanubhoganahalli Ch: 0.50 KM to 2.35 KM(in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 280 | 300 | [7 empty] | 15: 1.85; 16: 1.85; 17: 1.85; 18: 100%; 19: 0; 23: Asphalt work completed. Road furniture work in progress
|  | I | Improvements to MDR from Gollahalli To Hesarghatta CH 8.20 KM to CH : 9.60 KM in Bangalore North Taluk, of Bangalore District | MDR | 281 | 180 | [7 empty] | 15: 1.4; 16: 1.4; 17: 1.118; 18: 79.86%; 19: 0.282; 23: Asphalt work completed. Road furniture work in progress
|  | J | Improvements to Road from Channapattana Kavanapura- SRS Betta- Avverahalli-Kailancha-Nagohalli-Hunasanhalli-Uragahalli-Bidadi-Ganakallu-Nelamangala from Ch;65.70 to70.00 Km ( Mallasandra to Sondekoppa) in Bangalore North Taluk, of Bangalore District | MDR | 282 | 820 | [7 empty] | 15: 4.3; 16: 4.3; 17: 4.3; 18: 100%; 19: 0; 23: Asphalt work completed. Road furniture work in progress
86 | 546 | A | Improvements to Chandapura -Dommasandra MDR from Km 1.50 to Km 6.00 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 282 | 450 | 900 | 767.34 | 813.38 |  | 813.38 |  |  | GOVINDALLI HUCHEGOWDA NAGARAJU ( G.H NAGARAJU ) | 2022-12-02 | 2023-11-02 |  | 4 | 4 | 2.99 | 74.75% | 1.01 |  | 0% | 813.38 | 3.00km Asphalt work completed. Remaining work under progress
|  | B | Improvements to Iggaluru to Gumlapura MDR from Km 29.25 to Km 30.56 (in selected reaches) in Anekal Taluk of Bangalore Rural District | MDR | 283 | 250 | [7 empty] | 15: 1.2; 16: 1.2; 17: 0; 18: 0%; 19: 1.2; 23: WMM Work in Progress
|  | C | Improvements to MDR FromVenkateshwara circle, Shanimahathama Temple via to Ragavendra Circle, Srirama Temple, Tilaknagara & Shanimahathama Temple MDR from Km 34.00 to Km 36.00 in Anekal Taluk of Bangalore Rural District | MDR | 284 | 200 | [7 empty] | 15: 1.56; 16: 1.56; 17: 0.95; 18: 60.9%; 19: 0.61; 23: 0.95 kms Asphalt completed, remaining reach Asphalting in progress.
87 | 547 | A | Improvements to MDR from Dommasandra (Bangalore) to Sulikunte Colony via Shantigiri Asharama, Kodathi, JHC, Wipro, NEZ, Mulluru from Km 0.00 to Km 10.50 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District | BNE18 | 286 | 1100 | 2100 | 1706.8 | 1908.91 |  | 1908.91 |  |  | M S VENKATESH( M S V Construtions Company ) | 2022-09-16 | 2024-03-16 |  | 6.46 | 6.46 | 0 | 0% | 6.46 | 0.89 | 0.04662% | 1908.02 | drain culvert work completed road work to be started
|  | B | Improvements to MDR from Bendiganahalli (NH-04) to Bommenahalli Budigere via Raghumenahalli, Hancharahalli, Jyothipura, Thirumenhalli from Km 0.00 to Km 13.00 (in selected reaches) in Bangalore East Taluk of Bangalore Rural District. | MDR | 287 | 1000 | [7 empty] | 15: 7.9; 16: 7.9; 17: 0; 18: 0%; 19: 7.9; 23: 2.50 Km Rigid pavement work completed. 1.30 Km WMM Completed remaining work in progress
88 | 548 |  | Improvements to Bangalore Nandi MDR Connecting SH-104 to Bandikodigehalli MDR via Hosuru Bande, Bagaluru from Km 12.60 to Km 23.50 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 288 | 1500 | 1500 | 1303.47 | 1333.33 |  | 1333.33 |  |  | Sri C R Girish (Ram And Company), Bangalore | 2022-11-03 | 2024-02-03 |  | 9.2 | 9.2 | 0 | 0% | 9.2 |  | 0% | 1333.33 | drain & Road work in progress
89 | 549 | A | Improvements to Hesarughatta Tank bund road (SH-39)from Km 4.00 to Km 7.00 in Bangalore North Taluk of Bangalore Rural District | SH-39 | 288 | 400 | 950 | 823.82 | 897.96 |  | 897.96 |  |  | Govindalli Huchegowda Nagaraju (G.H Nagaraju) | 2022-12-02 | 2023-11-02 |  | 2.9 | 2.9 | 1.05 | 36.21% | 1.85 |  | 0% | 897.96 | Asphalt work 1.05 Km completed. drain & Remaining Road work Progress
|  | B | Improvements to MDR from Lakshmipura Cross to Golhalli Hesrughatta Road SH-39 via Lakshmipura, Abbigere, Chikkabanavara, Pipe line Road, Ganegarahalli, Somashettyhalli from Km 0.00 to Km 10.20 (in selected reaches) in Bangalore North Taluk of Bangalore Rural District | MDR | 289 | 550 | [7 empty] | 15: 5.3; 16: 5.3; 17: 2.82; 18: 53.21%; 19: 2.48; 23: Asphalt Work 2.82 Km completed. Remaining Work Progress
90 | 550 | A | Improvements to MDR from Muthkuru to NH-207 via Bylahalli, Muthgadahalli-Thottanuru-Thiruvaranga from Km 0.00 to Km 8.10 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS9 | 289 | 475 | 3800 | 3285.45 |  |  | 0 |  |  | M/s Munikrishnappa | 2023-03-24 | 2024-09-23 |  | 4.9 | 4.9 | 0 | 0% | 4.9 |  | 0% | 0 | Not Yet Started.
|  | B | Improvements to Siddalagatta - Anekal SH 35 road road MDR from Km 25.64 to Km 34.84 (in selected reaches) in Hosakote Taluk of Bangalore Rural District | HOS25 | 290 | 475 | [7 empty] | 15: 4.604; 16: 4.604; 17: 0; 18: 0%; 19: 4.604; 23: Scarification along 4.2km in Progress and 1.4 km GSB & WMM has been laid.
|  | C | Improvements to MDR from NGD (SH 74) to Thayagadahalli (BTS Road) via Byrashettyhalli-Bolamarahalli from Km 0.00 to Km 5.10 in Nelamangala Taluk of Bangalore Rural District | NLM10 | 291 | 450 | [7 empty] | 15: 5.1; 16: 5.1; 17: 0; 18: 0%; 19: 5.1; 23: Not Yet Started.
|  | D | Improvements to MDR from NH-04 to Sompura via Devarahosahalli-Kamalapura Agalakuppe from Km 7.00 to Km 12.00 (in selected reaches) in Nelamangala Taluk of Bangalore Rural District | MDR | 292 | 500 | [7 empty] | 15: 3.05; 16: 3.05; 17: 0; 18: 0%; 19: 3.05; 23: Not Yet Started.
|  | E | Improvements to Kodigehalli-Kanakenahalli road MDR from Km 0.00 to Km 19.00 (in selected reaches) in DoddaballapuraTaluk of Bangalore Rural District | DOD7 | 293 | 950 | [7 empty] | 15: 9.57; 16: 9.57; 17: 0; 18: 0%; 19: 9.57; 23: Not Yet Started.
|  | F | Improvements to Devanahalli-Kempapura road (SH-96) from Km10.00 to Km 12.25 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | SH-96 | 294 | 500 | [7 empty] | 15: 1.4; 16: 1.4; 17: 0; 18: 0%; 19: 1.4; 23: Not Yet Started.
|  | G | Improvements to MDR from Devanahalli town to NH-44 from Kempegowda Circle to Road to rani Circle from Km 0.00 to Km 3.60 (in selected reaches) in Devanahalli taluk of Bangalore Rural District | DVN9 | 295 | 450 | [7 empty] | 15: 1.47; 16: 1.47; 17: 0; 18: 0%; 19: 1.47; 23: Not Yet Started.
|  |  | Division Total |  |  | 15050 | 15050 | 12848.56 | 10959.298 | 0 | 10959.298 | 0 | 0 | 15: 102.799; 16: 102.799; 17: 34.871; 19: 67.928; 20: 2095.02; 22: 8864.278
Ramanagara Special Division
91 | 552 |  | Improvements toNew SH From Kodihalli to Sathanuru Via Doddalahalli from Km 0.00 to Km 25.30 (In selected reaches) in Kanakapura Taluk of Ramanagara District. | New SH | 331 | 2000 | 2000 | 1700.07 | 2018.18 | 503.91 | 2522.09 |  |  | M/s Sri Chowdeshwari Concrete India Private Limited Kudulur Prasad Dinesh kumar | 2022-06-27 | 2023-12-27 |  | 20 | 13.25 | 5.4 | 40.75% | 7.85 | 563.84 | 27.94% | 1454.34 | 1.) 5.4 Kms DBM & BC Completed. 2) WMM Work under Progress
|  |  | Division Total |  |  | 2000 | 2000 | 1700.07 | 2018.18 | 503.91 | 2522.09 | 0 | 0 | 15: 20; 16: 13.25; 17: 5.4; 19: 7.85; 20: 563.84; 22: 3083.7
Ramanagara Division | bar: 23
92 | 553 | A | Improvements to Hunasanahalli – Chikkanahalli( SH-3 Via Kanakapura, Ramanagara) , Magadi from Ch: km 82.67 to 94.40 km in Magadi Taluk of Ramanagara District. | SH-3 | 332 | 950 | 1950 | 1693.41 | 2045.15 | 508.45 | 2553.6 |  |  | .KADAIAH PRAKASH (KPJ CONSTRUCTIONS PRIVATE LIMITED ) | 2022-09-02 | 2024-03-02 |  | 12 | 12.243 | 11.923 | 97.39% | 0.32 | 816.54 | 39.93% | 1228.61 | 11.923 Work Completed. Balance Work under progress
|  | B1 | Improvements to Hunasanahalli Chikkahalli Road SH -3 Via Kanakapura, Ramanagara, Magadi from Km 48.40 to Km 82.67 (In selected reaches) in Ramanagara Taluk of Ramanagara District. | [10 empty] | 15: 9.2; 16: 2.65; 17: 1.85; 18: 69.81%; 23: 1.85 work completed. Balance Work under progress
|  | B2 | Improvements to NH 275-Channapatna to Nelamangala via kavanapura S.R.S betta, Avverahalli, Kailancha, Nagohalli, Hunasanahalli, Urgalli, Bidadi, Ch:5.20 to 35.70km (Change of road) | SH-3 | 334 | 1000 | [7 empty] | 16: 8.86; 17: 4.52; 18: 51.02%; 19: 4.34; 23: 4.52 Km work completed. Balance Work under progress
|  |  | Division Total |  |  | 1950 | 1950 | 1693.41 | 2045.15 | 508.45 | 2553.6 | 0 | 0 | 15: 21.2; 16: 23.753; 17: 18.293; 19: 4.66; 20: 816.54; 22: 1228.61
Tumkur Division
93 | 554 | A | Improvements to Doddagangavadi Gate - Chowdanakuppe Road SH 111 from Km 12.00 to Km 15.25 (in selected reaches) in Kunigal Taluk of Tumakuru District | SH 111 | 350 | 350 | 1000 | 850.31 | 858.74 |  | 858.74 |  |  | Sri Rakshith Kempeere Gowda K Gowda & Company, Bangalore | 30.07.2022 | 29.06.2023 |  | 1.89 | 1.89 | 1.89 | 100% | 0 | 355.81 | 41.43% | 502.93 | Road Furniture work to be started
|  | B | Improvements to MDR (old NH48) Road in Kunigal Town from Km 71.40 to Km 71.65 (in selected reaches) in Kunigal Taluk of Tumakuru District | KNL227 | 351 | 100 | [7 empty] | 15: 0.25; 16: 0.25; 17: 0; 18: 0%; 19: 0.25; 23: work under progress
|  | C | Improvements to MDR connecting from NH48-Join Anchepalya - yelagalavdi Road via mallagatta,Begur,Kundur, Rajgere, Boregowdanapallya from Km 0.00 to Km 10.00 (in selected reaches) & bridge at Ch 2.25 Km in Kunigal Taluk of Tumakuru District | KNL27 | 352 | 550 | [7 empty] | 15: 1.125; 16: 1.125; 17: 0.855; 18: 76%; 19: 0.27; 23: Balance Work under progress
|  |  | Division Total |  |  | 1000 | 1000 | 850.31 | 858.74 | 0 | 858.74 | 0 | 0 | 15: 3.265; 16: 3.265; 17: 2.745; 19: 0.52; 20: 5644.93; 22: 6280.88
Madhugiri Division
94 | 561 |  | Improvements to Sira- Amarapura Road MDR from Km 0.00 to Km 42.20 (in selected reaches) in Sira Taluk of Tumakuru District | SRA3 | 162 | 2000 | 2000 | 1715.76 | 1954.76 |  | 1954.76 |  |  | Sri Sachin Kollur (M/s Kollur Gurunath Construction Infra Private Limited), Bidar | 14.07.2022 | 13.01.2024 |  | 12.25 | 12.25 | 4.75 | 38.78% | 7.5 |  | 0% | 1954.76 | WMM Work under progress
95 | 564 | A | Improvements to Kumta-Kadamadagi Road SH 48 from Km 352.00 to Km 392.16 (in selected reaches) in Pavagada-Taluk of Tumakuru District | SH 48 | 167 | 750 | 1000 | 855.85 | 900.6 |  | 900.6 |  |  | Sri B B Umesha, Bangalore | 07.07.2022 | 06.06.2023 |  | 4.145 | 4.145 | 3 | 72.38% | 1.145 | 505 | 56.07% | 395.6 | BM work under progress
|  | B | Improvements to Pavagada Hindpur MDR from Km 0.00 to Km 29.60 (in selected reaches) in Pavagada Taluk of Tumakuru District | PVG-4 | 168 | 250 | [7 empty] | 15: 1.235; 16: 1.235; 17: 1; 18: 80.97%; 19: 0.235; 23: Balance work under progress
|  |  | Division Total |  |  | 3000 | 3000 | 2571.61 | 2855.36 | 0 | 2855.36 | 0 | 0 | 15: 17.63; 16: 17.63; 17: 8.75; 19: 8.88; 20: 2746; 22: 2624.8
Chikballapura Division
96 | 565 | A | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 87.70 to Km 106.80 (in selected reaches) in Bagepalli Taluk of Chikballapura District | SH 05 | 368 | 1000 | 3000 | 2572.17 | 3062.3 |  | 3062.3 |  |  | Sri C.R Girish Ram & Company Engineers and Contractors, Bangalore | 27.06.2022 | 26.12.2023 |  | 5.9 | 5.9 | 4.8 | 81.36% | 1.1 | 2594.58 | 84.73% | 467.72 | 0.3 km WMM Completed, further work under progress
|  | B | Improvements to Chinthamani- K.Y Road Via Bikkanahalli, N.Kotturu, Kotagal, Sujjanahalli, Nandhanahosalli, Paapatimmanahalli New MDR from Km 3.20 to Km 13.00 (in selected reaches) in Chinthamani Taluk of Chikballapura District | NEW MDR | 369 | 1000 | [7 empty] | 15: 8.6; 16: 8.6; 17: 8.4; 18: 97.67%; 19: 0.2; 23: Shoulder work under progress (200m will not be tackled as there is existing CC road)
|  | C | Improvements to Bangarapete - Bagepalli Road SH 05 from Km 78.00 to Km 86.50 (in selected reaches) in Sidlagatta Taluk of Chikballapura District | SH 05 | 370 | 1000 | [7 empty] | 15: 5.65; 16: 5.65; 17: 4.2; 18: 74.34%; 19: 1.45; 23: 1.45 km GSB work under progress
|  |  | Division Total |  |  | 6300 | 6300 | 5396.65 | 6100.85 | 0 | 6100.85 |  |  | 15: 45.1; 16: 45.1; 17: 42.35; 19: 2.75; 20: 4331.68; 22: 1769.17
Kolar Division
97 | 568 | A | Improvements to Bangarapete - Kamasamudram Road MDR from Km 0.90 to Km 3.45, Km 4.695 to Km 9.50 & Km 10.00 to Km 11.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT11 | 376 | 800 | 3000 | 2542.09 | 2643.8 |  | 2643.8 |  |  | Sri Amaravaram Channa Reddy (ACR projects), Bangalore | 30.07.2022 | 29.01.2024 |  | 5.16 | 5.16 | 0 | 0% | 5.16 | 572.14 | 21.64% | 2071.66 | 5.16km upto DBM Completed
|  | B | Improvements to Budhikote Kanamanahalli Road Via Balamande MDR from Km 0.00 to Km 3.00 & Km 16.25 to Km 20.50 (in selected reaches) in Bangarapete Taluk of Kolar District | BGT 10 | 377 | 200 | [7 empty] | 15: 1.87; 16: 1.87; 17: 0; 18: 0%; 19: 1.87; 23: GSB work under progress
|  | C | Improvements to Devanahalli-Kempapura Road SH-96 from Km 83.00 to Km 95.51 (in selected reaches) in K G F Taluk of Kolar District | SH 96 | 378 | 600 | [7 empty] | 15: 2.98; 16: 2.98; 17: 0; 18: 0%; 19: 2.98; 23: 2.98km DBM Completed, further work under progress
|  | D | Improvements to Station Road MDR from Km 0.20 to Km 1.80 (in selected reaches) in K G F Taluk of Kolar District | BGT26 | 379 | 200 | [7 empty] | 15: 1.6; 16: 1.6; 17: 0; 18: 0%; 19: 1.6; 23: 1.60 km DBM Completed, further work under progress
|  | E | Improvements to K G F State fund Road MDR from Km 2.92 to Km 4.20 (in selected reaches) in K G F Taluk of Kolar District | BGT5 | 380 | 200 | [7 empty] | 15: 1.1; 16: 1.1; 17: 0; 18: 0%; 19: 1.1; 23: 1.10 km DBM completed. further work under progress
|  | F | Improvements to Kolar- Malur- Hosur Road New SH from Km 12.60 to Km 22.50 (in selected reaches) in Malur Taluk of Kolar District | NEW SH | 381 | 1000 | [7 empty] | 15: 6.57; 16: 6.57; 17: 0; 18: 0%; 19: 6.57; 23: Balance work under progress
98 | 569 |  | Improvements to Kolar- Malur- Hosur Road New SH from Km 0.00 to Km 12.60 (in selected reaches) in Kolar Taluk of Kolar District | NEW SH | 382 | 1000 | 1000 | 858.84 | 793.65 |  | 793.65 |  |  | Sri C Narayanaswamy (CNS Constructions), Kolar | 2022-11-04 | 2023-10-03 |  | 6.55 | 6.55 | 0 | 0% | 6.55 | 386.02 | 48.64% | 407.63 | Balance work under progress
99 | 570 | A | Improvements to Andhra Border K Bayyapalli to Andhra Border Road Via Rayalamana dinne, Mulabagal, Vammasandra, Gukunte, Shankarapura New SH from Km 3.20 to Km 14.60 & Km 33.35 to Km 33.80 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW SH | 383 | 800 | 3800 | 3234.93 | 3889.97 |  | 3889.97 |  |  | Sri B Bhaskar Naidu (Seethal Constructions), Bangalore | 02.07.2022 | 01.01.2024 |  | 5.7 | 5.835 | 4.4 | 75.41% | 1.435 | 1360.66 | 34.98% | 2529.31 | 1.435 Road work under progress
|  | B | Improvements to Mudavadi Kothamangal Road MDR from Km 14.32 to Km 21.04 (in selected reaches) in Mulabagal Taluk of Kolar District | MUL9 | 384 | 700 | [7 empty] | 15: 5.9; 16: 5.35; 17: 5.27; 18: 98.5%; 19: 0.08; 23: Road furniture work under progress
|  | C | Improvements to Mulabagal Punganur Road to Mulabagal Ramasandra connecting Road Via Byrakuru, Chikura Hosahalli, Rajendrahalli, Gudipalli, Nachahalli, Gukunte New MDR from Km 0.00 to Km 5.00 (in selected reaches) in Mulabagal Taluk of Kolar District | NEW MDR | 385 | 300 | [7 empty] | 15: 2.45; 16: 2.108; 17: 2.108; 18: 100%; 19: 0; 23: Road furniture work under progress
|  | D | Improvements to Kothapalli- Masthi Road SH 99 from Km 9.00 to Km 18.60 (in selected reaches) in Srinivaspura Taluk of Kolar District | SH 99 | 386 | 1100 | [7 empty] | 15: 7.45; 16: 7.6; 17: 0; 18: 0%; 19: 7.6; 23: 3.5 Km DBM Completed. Balance work under progress
|  | E | Improvements to Bayyapalli- Bandapalli Road MDR from Km 0.00 to Km 10.20 (in selected reaches) in Srinivaspura Taluk of Kolar District | SRI 9 | 387 | 900 | [7 empty] | 15: 10.2; 16: 10.115; 17: 9.65; 18: 95.4%; 19: 0.465; 23: 0.465 km CC work under progress
|  |  | Division Total |  |  | 7800 | 7800 | 6635.86 | 7327.42 | 0 | 7327.42 | 0 | 0 | 15: 57.53; 16: 56.838; 17: 21.428; 19: 35.41; 20: 2318.82; 22: 5008.6
|  |  | Bangalore Circle Total |  |  | 32100 | 32100 | 27424.79 | 27291.458 | 508.45 | 27799.908 | 0 | 0 | 15: 229.894; 16: 231.755; 17: 119.687; 19: 111.268; 20: 15206.99; 22: 28860.038
Mysore Circle
Mandya Division
100 | 571 | A | Improvements to Road from 142 Km of Sira-Najangudu to join 40th km of NH-48 Dudda road (MDR) from 0.00 km to 11.02 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 398 | 500 | 2000 | 1713.37 | 1711.76 |  | 1711.76 |  |  | Sri Kari Gowda C (M/s C.K.G Constructions Pvt Ltd.)Mysore | 04--07-2022 | 03--01-2024 |  | 3.63 | 3.63 | 2.13 | 58.68% | 1.5 | 724.41 | 42.32% | 987.35 | 2.128Km SDBC Completed & Scarifying started at another reach
|  | B | Improvements to Road from MN road to join BN road Via M K Road, Hulivana, Chamalapura, Keelara, Dodda Banasawadi, Chikka Banasawadi & Hodaghatta (MDR) from 3.80 km to 11.28 Km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 399 | 500 | [7 empty] | 15: 2.62; 16: 2.62; 17: 2.1; 18: 80.15%; 19: 0.52; 23: Road work Completed, road furniture work balance
|  | C | Improvements to Chinnayakanahalli- Tubinakere Road (MDR) from 1.10 km to 12.40 (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 400 | 200 | [7 empty] | 15: 1.55; 16: 1.55; 17: 1.05; 18: 67.74%; 19: 0.5; 23: 1.050 km road work completed, village limit need to be tackled
|  | D | Improvements to BN Road to TM Hosur-Alagudu-Molenahalli-Koppalu Via Kodiyala-Yaliyur Road (Via T.M.Hosur) (MDR) from 9.00 km to 11.50 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 401 | 200 | [7 empty] | 15: 1.71; 16: 1.71; 17: 1.71; 18: 100%; 19: 0; 23: Road work Completed, road furniture work balance
|  | E | Improvements to Srirangapatna chanarayapatna road darasaguppe road to join nelamane village (MDR) from 0.00 km to 2.60 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 402 | 200 | [7 empty] | 15: 1.167; 16: 1.167; 17: 0; 18: 0%; 19: 1.167; 23: GSB Work completed
|  | F | Improvements to Road joning Mandya - Madduru Taluk border Via Cheeranahalli (MDR) from km 1.20 km to 8.85 km (In Selected Reaches) in Mandya Taluk of Mandya District. | MDR | 403 | 200 | [7 empty] | 15: 1.695; 16: 1.695; 17: 1.695; 18: 100%; 19: 0; 23: Work completed except road furniture
|  | G | Improvements to Arakere - Mandya- Bannur road to Bannahally-Bettahally Road (MDR) from 0.00 km to 4.32 km (In Selected Reaches) in Shrirangapatna Taluk of Mandya District. | MDR | 404 | 200 | [7 empty] | 15: 1.78; 16: 1.78; 17: 1.28; 18: 71.91%; 19: 0.5; 23: 0.50 km length of work completed in other PWD grants.
101 | 573 | A | Improvements to Bindiganavile -Kadabahalli Road to join Bindiganavile -Kadabahalli Road via Mangaravally, Bydarahalli, Acharyapura & Vaddarahatti (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 410 | 300 | 1000 | 855.98 | 844.3 |  | 844.3 |  |  | Sri K R Manjunatha (KRM Constructions) Mysore |  |  |  | 2.655 | 2.655 | 0 | 0% | 2.655 | 331.36 | 39.25% | 512.94 | GSB work under progress
|  | B | Improvements to Bindiganavile-ayyarahalli road via garudanahalli road (MDR) from 0.00 km to 4.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 411 | 300 | [7 empty] | 15: 2.512; 16: 2.512; 17: 0; 18: 0%; 19: 2.512; 23: WMM work under progress
|  | C | Improvements to Mylarpatna to join NH 48 near Kalinganahalli gate (MDR) from 0.00 km to 7.00 km (In Selected Reaches) in Nagamangala Taluk of Mandya District. | MDR | 412 | 400 | [7 empty] | 15: 3.458; 16: 3.458; 17: 0; 18: 0%; 19: 3.458; 23: BM work completed, SDBC work under progress
102 | 574 | A | Improvements to Road from 2/15Mile of S.A road to join Hariharapura-Lingapura (MDR) from 6.00 km to 36.50 km(In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 413 | 380 | 1750 | 1497.08 | 1497.21 |  | 1497.21 |  |  | Sri K R Manjunatha (KRM Constructions) Mysore |  |  |  | 3.125 | 3.125 | 3.125 | 100% | 0 | 1243.55 | 83.06% | 253.66 | Work completed except road furniture
|  | B | Improvements to Road from K.R.Pet-Bandihole road to join Kikkeri-Mandagere road via Heggadahalli, Hoddarahalli, ICL Factory, Ramenahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 414 | 250 | [7 empty] | 15: 2.415; 16: 2.415; 17: 2.415; 18: 100%; 19: 0; 23: Work completed except road furniture
|  | C | Improvements to Road from G.Boppanahalli – Halekothamaranahalli - Nayakanahalli, Malgur, Singapura. (MDR) from 4.50 km to 12.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 415 | 200 | [7 empty] | 15: 1.7; 16: 1.7; 17: 0.4; 18: 23.53%; 19: 1.3; 23: CC road Work completed, Subgrade work under progress
|  | D | Improvements to Road to Join Somanahalli to Somanathapura Via Mamballi (MDR) from km 0.00 to km 1.90 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 416 | 150 | [7 empty] | 15: 1.115; 16: 1.115; 17: 1.04; 18: 93.27%; 19: 0.075; 23: Work completed except road furniture
|  | E | Improvements to Road from S.A road to join Gondihalli via Madapura (MDR) from km 6.00 to km 9.40 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 417 | 190 | [7 empty] | 15: 1.95; 16: 1.95; 17: 1.95; 18: 100%; 19: 0; 23: Work completed except road furniture
|  | F | Improvements to Road from Nargonahalli to join Vitalapura via Giddanakoppalu, Gavimata, Kapanahalli (MDR) from km 0.00 to km 1.00 (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 418 | 100 | [7 empty] | 15: 0.7; 16: 0.7; 17: 0; 18: 0%; 19: 0.7; 23: Not yet Started
|  | G | Improvements to Hosaholalu-Ballekere-Natanahalli road (MDR) from 7.50 km to 8.50 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 419 | 100 | [7 empty] | 15: 0.774; 16: 0.774; 17: 0.77; 18: 99.48%; 19: 0.004; 23: Work completed except road furniture
|  | H | Improvements to Road from Bookinakere to join Bommalapura via Chokanahalli (MDR) from 0.00 km to 3.00 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | MDR | 420 | 240 | [7 empty] | 15: 2.3; 16: 2.3; 17: 1.79; 18: 77.83%; 19: 0.51; 23: Work completed except road furniture
|  | I | Improvements to Road from Shrirangapatna - Arasikere Road (SH-07) to join Goodehosahalli Via Anegola, Bolamaranahalli & Kadahemmige (MDR) from 3.00 km to 6.71 km (In Selected Reaches) in K R Pete Taluk of Mandya District. | SH | 421 | 140 | [7 empty] | 15: 1.344; 16: 1.344; 17: 1.34; 18: 99.7%; 19: 0.004; 23: Work completed except road furniture
103 | 598 | A | Road joining NH-209 to SH-84 Via Halaguru, K. Belluru, Rudrakshipura, Madduru, Koppa & Kowdle (SH) | NH/SH | 407 | 100 | 1000 | 856.29 | 865.04 |  | 865.04 |  |  | Sri Chikkaboregowda Karigowda (CKG Constructions Private Limited), Mysore | 04--07--2022 | 03--06-2023 |  | 1.085 | 1.085 | 1.085 | 100% | 0 | 0 | 0% | 865.04 | Road furniture work under progress
|  | B | Improvements to NH-209 to join Pandithhalli-Shimsha (PS) road (MDR) | MDR | 408 | 400 | [7 empty] | 15: 3.134; 16: 3.134; 17: 3.134; 18: 100%; 19: 0; 23: Road furniture work under progress
|  | C | Improvements to Road from Malavalli to join 16th km of Mandya-Bannur road (Sulthan Road) (MDR) (In Selected Reaches) in Malavally Tq | MDR | 409 | 500 | [7 empty] | 15: 1.58; 16: 1.58; 17: 0; 18: 0%; 19: 1.58; 23: Work Under Progress
104 | 606 |  | Improvements to K R Pete-Sravanabelagola Road MDR from 0.00km to 2.30 km (in Selected reaches) in K R Pete taluk of Mandya District | MDR |  | 457.79 | 550 | 550 | 475.8 |  | 475.8 |  |  | Sri R.P. Revanna, K.R Pete | 13.03.2023 | 12.02.2024 |  | 1.255 | 1.255 | 0 | 0% | 1.255 |  |  |  | Work not yet started due to land acqisition Problem
|  |  | Division Total |  |  | 6207.79 | 6300 | 5472.72 | 5394.11 | 0 | 5394.11 | 0 | 0 | 15: 45.254; 16: 45.254; 17: 27.014; 19: 18.24; 20: 2299.32; 22: 3476.37
Mysore Division
105 | 577 | A | Improvements to KRS to join Mysore Ring Road in Mysore Tq |  | 430 | 500 | 2000 | 1716.13 | 1866.97 |  | 1866.97 |  |  | Sri Aravindkumar (Aravindakumar P B), Mandya |  |  |  | 4.13 | 4.13 | 3.76 | 91.04% | 0.37 | 1181.91 | 63.31% | 685.06 | Road Furniture work under progress.
|  | B | Improvements to Gungral Chathra to K Nagenahalli (MDR) in Mysore Tq | MDR | 431 | 250 | [7 empty] | 15: 2.13; 16: 2.13; 17: 2.13; 18: 100%; 19: 0; 23: Road Furniture work under progress.
|  | C | Improvements to Mysore Naguvanahalli Road (MDR) in Mysore Tq | MDR | 432 | 250 | [7 empty] | 15: 1.525; 16: 1.525; 17: 1.525; 18: 100%; 19: 0; 23: Road Furniture work under progress.
|  | D | Improvements to Shrirangapatna - MM Hills Road (SH-79) in TNPura Tq | SH | 433 | 500 | [7 empty] | 15: 1.35; 16: 1.35; 17: 0; 18: 0%; 19: 1.35; 23: work under progress
|  | E | Improvements to B.M. Road to Beedanahalli-Hanumanalu-Maragowdanahalli to Sulthan road (MDR) in TN Pura Tq | MDR | 434 | 200 | [7 empty] | 15: 0.8; 16: 0.8; 17: 0; 18: 0%; 19: 0.8; 23: work under progress
|  | F | Improvements to Mugur -Bannhalli hundi road (MDR) in TN Pura Tq | MDR | 435 | 300 | [7 empty] | 15: 6.5; 16: 6.5; 17: 6.5; 18: 100%; 19: 0; 23: Road Furniture work under progress.
106 | 595 | A | Improvements to Sira - Nanjangudu (SH-84) from 227.00 km to 227.75 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | SH | 422 | 200 | 1000 | 859.94 | 854.48 |  | 854.48 |  |  | Sri Chikkaboregowda Karigowda (CKG Constructions Private Limited), Mysore | 27.06.2022 | 26.05.2023 |  | 0.75 | 0.75 | 0 | 0% | 0.75 | 785.42 | 91.92% | 69.06 | work under progress
|  | B | Improvements to Hanumapura to join Doddahomma via P.Marahalli-Avathalapura (MDR) from 1.00 km to 8.00 km (In Selected Reaches) in Nanjanagudu Taluk of Mysore District. | MDR | 451 | 800 | [7 empty] | 15: 5.98; 16: 5.98; 17: 5.975; 18: 99.92%; 19: 0.005; 23: Road Furniture work under progress.
|  |  | Division Total |  |  | 3000 | 3000 | 2576.07 | 2721.45 | 0 | 2721.45 | 0 | 0 | 15: 23.165; 16: 23.165; 17: 19.89; 19: 3.275; 20: 1967.33; 22: 1785.79
Hunsur Division
107 | 579 | A | Improvements to Holenarasipura – Saligrama - KR Nagara SH-108 from 19.50 km to 32.00 km (In Selected Reaches) in KR Nagar Taluk of Mysore District. | SH | 395 | 400 | 1000 | 858.04 | 766.1 |  | 766.1 |  |  | Sri K .R Santhosh Mysore | 30.07.2022 | 29.06.2023 |  | 2.7 | 2.7 | 0 | 0% | 2.7 | 223.84 | 29.22% | 542.26 | WMM Work under Progress
|  | B | Improvements to Ramanathapura - Terakanambi Road to Mysore - Bhantwala Road Via- Chikkahanasoge- Channamgere (SH) from 0.00 km to 7.00 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. | SH | 396 | 300 | [7 empty] | 15: 2.275; 16: 2.275; 17: 0; 18: 0%; 19: 2.275; 23: Work under Progress
|  | C | Improvements to K R Nagar - Bettadapura road to join K R Nagar-Malali-Hosakote-Ravanduru Road (SH) from 8.00 km to 17.50 km (In Selected Reaches) in K R Nagar Taluk of Mysore District. | SH | 397 | 300 | [7 empty] | 15: 2.1; 16: 2.1; 17: 2.1; 18: 100%; 19: 0; 23: Work to be Started
|  |  | Division Total |  |  | 1000 | 1000 | 858.04 | 766.1 | 0 | 766.1 | 0 | 0 | 15: 7.075; 16: 7.075; 17: 2.1; 19: 4.975; 20: 223.84; 22: 2630.08
Chamarajanagar Division
108 | 580 | A | Improvements to Badanaguppe - Nanjedevanapura Road (MDR) from 3.80 km to 5.80 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. |  | 440 | 200 | 1000 | 858.22 | 931.12 |  | 931.12 |  |  | Sri Budanoor Thammaiah Sidappa ( M/s B T SIDDAPPA AND CO ) Mandya | 15 .07.2022 | 14.06.2023 |  | 1.64 | 1.64 | 1.64 | 100% | 0 | 435.82 | 46.81% | 495.3 | Road Furniture work to be started
|  | B | Improvements to Kodimole Basavanapura Hebbasur Byadamudlu-Basavapura Road (MDR) from 1.60 km to 6.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 436 | 450 | [7 empty] | 15: 4.32; 16: 4.32; 17: 0; 18: 0%; 19: 4.32; 23: 2.00 km WMM completed , Balance Work under Progress
|  | C | Improvements to Santhemarahalli Hebbasur Road (MDR) from 6.95 km to 10.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 437 | 200 | [7 empty] | 15: 1.06; 16: 1.06; 17: 1.06; 18: 100%; 19: 0; 23: Road Furniture work to be started
|  | D | Improvements to Udigala Kothalavadi V Swamy Hills Road (MDR) from 7.20 km to 8.50 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District |  | 438 &439 | 150 | [7 empty] | 15: 0.98; 16: 0.98; 17: 0.98; 18: 100%; 19: 0; 23: Road Furniture work Yet to be start
109 | 581 | A | Improvements to Road joining T Narasipura (Muguru Cross) to Santhemaralli (SH) from 0.00 km to 8.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | SH | 440 | 1000 | 1800 | 1551.14 | 1824.5 | 181.04 | 2005.54 |  |  | Sri Chandrashekar, (M/s KRCM Buildcon Private Limited) Chamarajnagar | 27.06.2022 | 26.12.2023 |  | 3.49 | 3.49 | 0 | 0% | 3.49 | 452.69 | 24.81% | 1371.81 | GSB Work under Progress
|  | B | Improvements to Kuderu-Thoravalli-Kesthuru-Mariyala Road (MDR) from 1.50 km to 9.00 km (In Selected Reaches) in Chamarajanagar Taluk of Chamarajanagar District. | MDR | 441 | 800 | [7 empty] | 15: 6.03; 16: 6.059; 17: 5.23; 18: 86.32%; 19: 0.829; 23: village limit pending
110 | 582 | A | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Tammadahalli, Kengaki, Sagade, Maliyuru, Kulagana, Kebbepura, Hemmaragala & Badanavalu (SH) from 15.45 km to 18.45 km & 22.450 km to 29.45 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | SH | 442 | 670 | 2250 | 1935.38 | 2400.54 |  | 2400.54 |  |  | Sri Nayan Reddy | 2022-08-30 | 2024-02-29 |  | 5.14 | 5.14 | 2.3 | 44.75% | 2.84 | 100 | 4.166% | 2300.54 | Work completed
|  | B | Improvements to Road Joing SH-81 to NH-150A Via Udigala, Veeranapura, Harave & Heggawadi (SH) from 15.16 km to 18.80 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | SH/NH | 443 | 240 | [7 empty] | 15: 2.1; 16: 2.1; 17: 0; 18: 0%; 19: 2.1; 23: Work completed
|  | C | Improvements to Road joining Kurubara Hundi Via Hasaguli, Manchahalli (MDR) from 3.00 km to 5.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 444 | 100 | [7 empty] | 15: 0.55; 16: 0.55; 17: 0; 18: 0%; 19: 0.55; 23: Work completed
|  | D | Improvements to Road joining Taggaluru to Bettadamadalli (MDR) from 6.70 km to 9.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 445 | 100 | [7 empty] | 15: 0.865; 16: 0.865; 17: 0; 18: 0%; 19: 0.865; 23: Work completed
|  | E | Improvements to Road joining Chirakanahalli road to Kurubara Hundi (MDR) from 0.00 km to 2.50 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 446 | 130 | [7 empty] | 15: 0.965; 16: 0.965; 17: 0; 18: 0%; 19: 0.965; 23: Work completed
|  | F | Improvements to Road joining NH-766 to Shrikantapura road Via Chikkahundi (MDR) from 0.00 km to 8.20 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 447 | 810 | [7 empty] | 15: 6.13; 16: 6.13; 17: 3.42; 18: 55.79%; 19: 2.71; 23: Work completed except 700m, due to huge pipe line shifting and land litigations.
|  | G | Improvements to Hullapura Kadbur Road (MDR) from 13.00 km to 17.00 km (In Selected Reaches) in Gundlupete Taluk of Chamarajanagar District. | MDR | 448 | 200 | [7 empty] | 15: 1.535; 16: 1.535; 17: 0; 18: 0%; 19: 1.535; 23: Work completed
111 | 583 | A | Improvements to Hanur to Ellemalla-Kodalli Via Tabetta from 0.00 km to 16.40 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. |  | 449 | 1000 | 2000 | 1721.42 | 1623.13 |  | 1623.13 |  |  | Sri K .R Santhosh Mysore | 30.07.2022 | 29.01.2024 |  | 6 | 6 | 0 | 0% | 6 | 452.42 | 27.87% | 1170.71 | Work under Progress
|  | B | Improvements to Shrirangapatna - MalaiMahadeshwara Betta Road (SH-79) from km 107.50 km to 128.60 km (In Selected Reaches) in Hanur Taluk of Chamarajanagar District. | SH | 450 | 1000 | [7 empty] | 15: 6.6; 16: 6.55; 17: 6.546; 18: 99.94%; 19: 0.004; 23: Road Furniture Work under Progress
|  |  | Division Total |  |  | 7050 | 7050 | 6066.16 | 6779.29 | 181.04 | 6960.33 | 0 | 0 | 15: 47.405; 16: 47.384; 17: 21.176; 19: 26.208; 20: 1440.93; 22: 5338.36
|  |  | Mysore Circle Total |  |  | 17257.79 | 17350 | 14972.99 | 15660.95 | 181.04 | 15841.99 | 0 | 0 | 15: 122.899; 16: 122.878; 17: 70.18; 19: 52.698; 20: 5931.42; 22: 13230.6
Hassan Circle
Hassan Division
112 | 585 |  | Improvement to Arkalgudu -Kodagu Border Road from Km 0.00 to Km 28.80 (In Selected Reaches) in Arakalgud Taluk of Hassan District | ARK-34 | 302 | 2000 | 2000 | 1714.84 | 2026.59 |  | 2026.59 |  |  | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 16.86 | 16.86 | 15.41 | 91.4% | 1.45 | 793.03 | 39.13% | 1233.56 | Balance Work under Progress
113 | 586 | A | Improvement to Road from Siddapura to join TDH Road via Kithanakere Barekattahalli MDR from Km 0.00 to km 7.00 (In Selected reaches) in Hassan Taluk of Hassan District | HSS-247 | 303 | 600 | 2150 | 1824.94 | 2224.07 |  | 2224.07 |  |  | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 5.036 | 5.036 | 0 | 0% | 5.036 | 1236.2 | 55.58% | 987.87 | Work under progress,
|  | B | Improvement to Road from Heragu road to join Dudda Shanthigrama Road via Kommanahalli Handrangi S.Devalapura Chattanahalli and Alasinahalli MDR from Km 0.00 to Km 9.00 (In Selected Reachs) in Hassan Taluk of Hassan District | MDR | 304 | 600 | [7 empty] | 15: 5.428; 16: 5.428; 17: 0; 18: 0%; 19: 5.428; 23: Work under Progress
|  | C | Improvements to road from Markuli cross to Athichowdenahall road via varasanahalli from 0.00 Km to 12.00 Km ( in Selected Reach ) in Holenarasipura taluk of Hassan District. | HNP-18 | 305 | 950 | [7 empty] | 15: 9.47; 16: 9.47; 17: 9.47; 18: 100%; 19: 0; 23: Road Furniture work under progress.
114 | 589 | A | Improvements to Adgoor Sankenahalli Road MDR from Km 0.00 to Km 12.00 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-12 | 315 | 600 | 1800 | 1533.36 | 1868.7 |  | 1868.7 |  |  | Sri K.S. Ashwathnarayan Gowda, (M/s YNG Construction India Private Limited) Hassan | 14.07.2022 | 13.01.2024 |  | 3.995 | 3.995 | 0 | 0% | 3.995 | 101.65 | 5.44% | 1767.05 | WMM work under progress
|  | B | Improvements to Road from NH-75 to join NH-173 from Km 70.00 to Km 91.10 (In Selected Reaches) (Halebeedu Gangooru Road from Km 0.00 to Km 8.00) and C M Road to Rajanashiriyuru MDR from Km 0.00 to Km 4.90 (In Selected Reaches) in Belur Taluk of Hassan District. | New SH | 316 | 800 | [7 empty] | 15: 5.67; 16: 5.67; 17: 5.67; 18: 100%; 19: 0; 23: Road Furniture Work under progress.
|  | C | Improvements to Road from B T Road to join KBPB MDR from Km 0.00 to Km 6.70 (In Selected Reaches) in Belur Taluk of Hassan District. | BLR-58 | 317 | 100 | [7 empty] | 15: 0.93; 16: 0.93; 17: 0.93; 18: 100%; 19: 0; 23: Road Furniture Work under progress.
|  | D | Improvements to road from B.T Road to C.M Road Shivaladahalli MDR from 0.00km to 6.00km ( in selected reaches) in Belur Taluk of Hassan District. | BLR-307 | 318 | 150 | [7 empty] | 15: 1.5; 16: 1.5; 17: 1.5; 18: 100%; 19: 0; 23: Road Furniture Work under progress.
|  | E | Imrovements to road to C.M road to Hanike K B Hall Road via Mallanahalli, Mukthganne Honnenahalli MDR from 0.00km to 6.30km (in Selected reaches) in Belur Taluk of Hassan District. | BLR-28 | 319 | 150 | [7 empty] | 15: 1.3; 16: 1.3; 17: 1.3; 18: 100%; 19: 0; 23: Road Furniture Work under progress.
|  |  | Division Total |  |  | 5950 | 5950 | 5073.14 | 6119.36 | 0 | 6119.36 | 0 | 0 | 15: 50.189; 16: 50.189; 17: 34.28; 19: 15.909; 20: 2130.88; 22: 8556.75
|  |  | Hassan Circle Total |  |  | 5950 | 5950 | 5073.14 | 6119.36 | 0 | 6119.36 | 0 | 0 | 15: 50.189; 16: 50.189; 17: 34.28; 19: 15.91; 20: 5819.8; 22: 11991.96
|  |  | South Total |  |  | 112207.79 | 112300 | 96250.93 | 106560.538 | 4850.32 | 111410.858 | 0 | 0 | 15: 787.588; 16: 789.446; 17: 493.507; 19: 305.14; 20: 61441.34; 22: 98383.208
|  |  | South & North Total |  |  | 226857.79 | 226950 | 194707.97 | 223015.028 | 18773.21 | 243116.508 | 0 | 0 | 0 | 0 | 0 | 0 | 1429.322 | 1440.05 | 833.877 |  | 653.82 | 161945.69 |  | 175443.554
[9 empty] | 475.79 |  |  |  |  | 15: 2252.788; 16: 2293.65
[6 empty] | 345490 |  |  | 349294.654 |  |  |  |  | 17: 1548.193; 20: -4153.3; 21: 172070.0978
[14 empty] | 455366.5241 | [8 empty] | 66335.6039
|  |  |  | -653.819 |  | 3442.79 | [7 empty] | 15: -41.55; 18: 653.819; 20: 109887.7961; 21: 4153.3022
[5 empty] | -0.009 | [8 empty] | 19: 606.173
[9 empty] | 69858.9308 |  |  |  |  | 16: 653.819; 20: 655.822
[5 empty] | 714.602 |  |  |  | 419153.5848 |  |  |  |  | 15: -4.36
[5 empty] | 350009.256 |  | 1.698 | [6 empty] | 16: 612.269; 18: 57849.4703; 19: 612.269; 20: 653.819
118373.9297
35.58
[19 empty] | 612.269 |  |  | 608.99

## Sheet1
3403.88
3136.16 |  | 3403.88
3829.49 |  | 3136.16
3391.67 |  | 3829.49
1697.15 |  | 3444.526
15458.35 |  | 2021.336
15835.392
3403.88
3136.16
3829.49
3444.526
2071.593
[7 empty] | 15885.649 | 15885.653
| V stage-I Nov | 0 | 23.83 | 15.223 | 0 | 39.053
| V stage-I October | 0 | 11.9 | 11.26 | 0 | 23.16
| diff | 0 | 11.93 | 3.963 | 0 | 15.893
3403.88
3136.16
3829.49
3455.33
2191.97
480.62
16497.45
3403.88
3136.16
3829.49
3460.3
2248.93
819.65
16898.41
16898.41

## Sheet5
2022-23 |  |  | 2023-24
2933.83 |  |  | 3338.813 | 1387.52
3325.42 | 1190.76 |  | 3396.12 | 1728.85
391.59 | 1190.76 |  | 57.307 | 341.33 | 1980.987
4517 | 4944.41 | 4524.11
3468.75 | 3888.64 | 1857.71
7985.75 | 8833.05 | 6381.82
3403.88
3136.16
3829.49
3444.526
2055.842
3403.88
3136.16
3829.49
3460.3
2269.65
936.31
17035.79 | 17035.79